This refers to the recent discussions held individually with Mr. K. Sekhar Babu *(Vice President),* Mr. Magesh Kumaran *(General Manager),* andMr. Selvam.

During the discussion, we clarified that the PCC Bed (M7.5) quantity stands at 500 cubic meters in the BOQ (Bill of Quantities). We have already executed work exceeding this quantity, meaning that the allocated quantity has been fully utilized.

Similarly, we understand that the excavated earth from the ash pond will be used to raise the height of the Ash Dyke and to form internal partitions within the ash dyke area. It is crucial to note that the existing contract does not include an item specifically for embankment work.

These two items are significant for our monthly billing; they are projected to account for substantial value of our billing from November onwards. Without formal inclusion of these items in the contract, we will be unable to process the corresponding RA Bills, certainly impacting our invoicing and cash flow.

We request that this matter be prioritized with M/s. Vedanta to ensure a suitable amendment is concluded within this month. This will enable us to reflect quantities of these items in our November and future RA bills.

Additionally, we have identified the need for amendments for some more items of work to align with actual quantities and project requirements. These items are detailed in Annexure-01.

We trust that these points will receive your immediate attention and look forward to a timely resolution that ensures smooth project progression and uninterrupted billing and cash flow.

Thanking you for your urgent attention to these matters.