## DPR
DPR - PETLABURJ
S.No | Date | Nature of work | Description of work | Quantity of work in m^3 | Man Power |  |  | Material Used |  |  |  | Remarks
[5 empty] | Mason | Male Helper | Female Helper | Material Type | Quantity | Units
1 | 2023-06-19 | Civil | Dismantling of Walls in examination work | 6.64 | [6 empty] | Mallikarjun people
2 | 2023-06-20 | Civil | Dismantling of Walls in Auto clave room | 5.39 | [6 empty] | Mallikarjun people
3 | 2023-06-24 | Civil | Dismantling @ corridor | 1.963 | [6 empty] | Mallikarjun people
4 | 2023-06-25 | Civil | Debri Lifting | 1.473 |  | 4 | 1 |  |  |  | Mallikarjun people
5 | 2023-06-30 | Civil | Debri Lifting | 7.21 |  | 11
6 | 2023-07-01 | Civil | Debri Lifting | 6.23 |  | 10
7 | 2023-07-11 | Civil | Marking for tile cutting for constructing walls
8 | 2023-07-13 | Civil | Tile cutting for wall construction |  |  | 2 |  |  |  |  | Sandeep labour
9 | 2023-07-15 | Civil | Debri lifting of tile cuttings |  |  | 2
10 | 2023-07-29 | Civil | Bricks shifting to 3rd floor |  |  | 13 |  |  | 2000 | Nos | Sandeep labour
11 | 2023-07-30 | Civil | Bricks shifting to 3rd floor |  |  | 13 |  |  | 1000 | Nos | Sandeep labour
12 |  | Civil | V-Bond material shifting to 3rd floor | [5 empty] | 50 | Nos | Sandeep labour
13 | 2023-07-31 | Civil | Sand Lifting |  |  | 2
14 |  | Civil | Removing Tile mortor |  |  | 2 |  |  |  |  | Sandeep labour | Just completed in Minor OT & Andrology Lab
15 | 2023-08-01 | Civil | Brick work in Minor OT & Andrology lab | 1.32 | 2 |  | 2 | Bricks | 120 | Nos | Sandeep labour
[8 empty] | V-Bond | 1.5
[8 empty] | Cement | 1
sand
16 | 2023-08-02 | Civil | Removing Tile Mortor |  |  | 2 |  |  |  |  | Balaji Labour | 1 for chipping & 1 Helper
17 | 2023-08-02 | Electrical | Removing old Electrical Wiring |  |  | 2 |  |  |  |  | Santosh Labour
18 | 2023-08-03 | Civil | Brick Work In Embryology Lab & IVF-OT | 1.31 | 2 |  | 2 | Bricks | 130 | Nos | Sandeep Labour
[8 empty] | Cement | 1 | Nos
[8 empty] | V-Bond | 1.5 | Nos
sand
19 | 2023-08-03 | Electrical | Removing old Electrical Wiring | 0 | 0 | 2 | 0 |  |  |  | Santosh Labour
20 | 2023-08-04 | Civil | Brick work in Manifold room & Auto clave room | 1.48 | 2 | 0 | 2 | Bricks | 130 | Nos | Sandeep labour
[8 empty] | Cement | 2 | Nos
[8 empty] | V-Bond | 2 | Nos
sand
21 | 2023-08-05 | Civil | Brick Work in counselling rooms |  | 2 |  | 2

## Material Received
Material Received Petlaburj
S.No | Date | Nature of Material | Description of Material | Quantity (Vol) | Quantity (Nos) | Invoice Number | Trader Name | Remarks
1 | 2023-06-24 | Equipment | Trolly |  | 3 |  |  | From Gandhi
2 | 2023-06-24 | Equipment | Tarpaulin | 2mX2m | 2
3 | 2023-06-24 | Equipment | Floor Protector | 4.3 m | 1
4 | 2023-07-28 | Civil | AAC Bricks |  | 3300 |  | OPUS
5 | 29-07-202 | Civil | V-Bond |  | 50
6 | 29-07-203 | Civil | Sand | 30 Tonns
7 | 2023-07-31 | Equipment | 900 litre drum |  | 1
8 | 2023-07-31 | Equipment | Plastic Pan |  | 10
9 | 2023-07-31 | Equipment | 20 lit Bucket |  | 2
10 | 2023-07-31 | Equipment | Sweepers |  | 10
11 | 2023-07-31 | Equipment | Hoe |  | 2
12 | 2023-07-31 | Equipment | Water Pipe 20m |  | 1
13 | 2023-07-31 | Civil | Cement (Coramandel 53) |  | 5
14 | 2023-08-01 | Civil | Steel Rods 8mm |  | 26
15 | 2023-08-09 | Equipment | Iron Stools |  | 4
16 | 2023-08-09 | Equipment | Thadka |  | 1
17 | 2023-08-09 | Equipment | Blade -5 inch |  | 2
18 | 2023-08-09 | Equipment | Blade - 8 inch |  | 2
19 | 2023-08-09 | Civil | Corse Aggregate | 1 m3
20 | 2023-08-10 | Civil | Cement (Coramandel 53) |  | 5
21
22