## Final Measurements
DETAILED MEASUREMENTS
| Name of the work:Design, Fabriction, establishing and commissioning of In - Vitro ferility centers (IVFC) alongwith allied Services on Turnkey basis at Gandhi hospital secunderabad. | [8 empty] | Agency: M/s. Asta vardhman Consortium | [5 empty] | Agt.No: 344/A/TSMIDC/Spl.Proj/IVFCs/2022-23, Dt. 05.07.2023
| Discription Of Work etc., | Measurements Upto date | [5 empty] | Rate |  |  | Per | Total Volume |  | Deduct/previous Measurements |  | Since last measurement |  |  | Remarks
|  | No |  | L | B | D | Content | Units | Rs | Ps. |  | Rs. | Ps | P.No. | Qty. | Qty | Value
[17 empty] | Rs. | Ps.
49 | Dismantling, clearing away and carefully stacking useful materials for re-use and disposal of unserviceable materials with 100m lead as directed by Executive Engineer duly taking actual premeasurements before dismantling including all labour charges , overheads & contractor profit etc., complete (Brick Masonary)
| Supply Duct | 1 | 2 | 0.75 | 0.23 | 0.4 | 0.138
| Return Duct | 1 | 2 | 0.85 | 0.23 | 0.4 | 0.1564
| Access Control Door | 1 | 1 | 3 | 0.23 | 3 | 2.07
| Door Deduction(-) | -1 | 1 | 1.5 | 0.23 | 2.6 | -0.897
[7 empty] | 1.4674 | Cum
Sup | Core Cutting For VRV Copper Pipe 110mm Dia
| Out Door Unit Terrace | 1 | 1 |  |  |  | 1
| Minor OT | 1 | 1 |  |  |  | 1
| Manifold Corridoor | 1 | 2 |  |  |  | 2
| Sperm Collection Room | 1 | 2 |  |  |  | 2
| Andrology Lab | 1 | 4 |  |  |  | 4
| Infront Store Room | 1 | 1 |  |  |  | 1
| Counseling Room1 | 1 | 1 |  |  |  | 1
| Autoclave Room | 1 | 1 |  |  |  | 1
| Ultra Sound Room | 1 | 1 |  |  |  | 1
| UPS Room | 1 | 1 |  |  |  | 1
| Prepost Operative Wards | 1 | 2 |  |  |  | 2
| Change Room | 1 | 2 |  |  |  | 2
| Auto Clave Toom | 1 | 1 |  |  |  | 1
| Cryo Room | 1 | 1 |  |  |  | 1
[7 empty] | 21 | Nos
53 | Masonry work in CM (1:6) prop (cement: Screened sand) in super structure with Aerated (Cellular) Autoclaved Concrete Blocks conforming to IS:2185 (Part-3) - 1984 and IS:6441-1972 of Compressive strength 3 N/mm2 600x 230 x 200 mm from approved source having minimum crushing strength of 3 N/Sq.m including cost and conveyance of all materials like cement, sand, bricks, water etc., to site, including sales & other taxes on all materials, all operational, incidental and labour charges such as mixing cement mortar, constructing masonry, scaffolding charges, lift charges, curing, etc., complete but excluding seigniorage charges for finished item of work. (APSS No. 501 & 504).
| AHU Brick Pedastal | 1 | 1 | 4.2 | 1.4 | 0.3 | 5.88
| RO Brick Pedastal | 1 | 1 | 0.6 | 0.6 | 0.6 | 0.36
[7 empty] | 6.24 | Cum
56 | Plastering 20mm thick in two coats using screened sand with base coat of 8mm thick in CM (1:6) and top coat of 4mm thick in CM (1:4) with dubara sponge finishing including cost and conveyance of all materials like cement, sand, water etc., to site, including sales & other taxes on all materials, and all operational, incidental charges on materials and including cost of all labour charges for mixing mortar, finishing, scaffolding, lift charges, curing, including cutting grooves as directed by Engineer-in-charge etc., and overheads & contractors profit complete for finished item of work. (SS 901,903 & 904).
| AHU Brick Pedastal | 1 | 1 | 4.2 | 1.4 |  | 5.88
| do | 1 | 2 | 4.2 |  | 0.3 | 2.52
| do | 1 | 2 | 1.4 |  | 0.3 | 0.84
| RO Brick Pedastal | 1 | 1 | 0.6 | 0.6 |  | 0.36
| do | 1 | 2 | 0.6 |  | 0.6 | 0.72
| do | 1 | 2 | 0.6 |  | 0.6 | 0.72
[7 empty] | 11.04 | Sqm
77 | Supplying and fixing of SWR PVC pipes (Prince/Sudhakar/Kisan/Supreme or any ISI brand) 4 Kg/Sq.cm. and fixing all special such as plain bends, off sets, door bends, single junctions, double junctions as per site requirement, fixing with PVC clamps if necessary with required number of Bombay nails including cost and conveyance of all materials to site, labour charges, overheads & contractors profit complete for finished item of work at all floor levels. (APSS No. 1302 1319 & 1326)
110mm dia
| Prepost Operative wards | 1 | 1 | 4.5 |  |  | 4.5
| Toilet At Counseling Room2 | 1 | 1 | 4.8 |  |  | 4.8
| Dr. Toilet | 1 | 1 | 5.6 |  |  | 5.6
| Sperm Collection Room | 1 | 1 | 4.2 |  |  | 4.2
| Scrub Wastewater Line | 1 | 1 | 7.53 |  |  | 7.53
[7 empty] | 26.63 | Rmt
75 | Supply and fixing of Ashirvad/ Ajay/ Astral Flowguard or equivalent CPVC Pipes and Fittings SDR 13.5 to meet the requirement of ASTM-D 2846 and are produced in CTS (Copper Tube Sizes 1/2" to 2") for hot and cold water (IS 15778:2007) including cost and conveyance of all materials to site, labour charges for fixing, overheads & contractors profit complete for finished item of work at all floor levels.
22.20 mm OD pipe
| Prepost Operative wards | 1 | 1 | 6.8 |  |  | 6.8
| Toilet At Counseling Room2 | 1 | 1 | 5.4 |  |  | 5.4
| Dr. Toilet | 1 | 1 | 10.7 |  |  | 10.7
| Sperm Collection Room | 1 | 1 | 4.8 |  |  | 4.8
| Scrub Inlet Line | 1 | 1 | 7.9 |  |  | 7.9
| Ro Inlet | 1 | 1 | 3.9 |  |  | 3.9
| VRV Drain pipe Major OT to out Side | 1 | 1 | 5.2 |  |  | 5.2
| VRV Drain pipe Major OT to out Side | 1 | 1 | 4.9 |  |  | 4.9
| Prepost Operative 3.0 TR Drain | 1 | 1 | 20.3 |  |  | 20.3
| Andrology Lab, Cryo Room to Toilet | 1 | 1 | 11.4 |  |  | 11.4
| Sperm Collection Room To Toilet | 1 | 1 | 1.2 |  |  | 1.2
| Blood Colletin Room To Toilet | 1 | 1 | 6.2 |  |  | 6.2
| Counseling Room1 ,2 to Toilet | 1 | 1 | 8.2 |  |  | 8.2
| Ultra Sound Room to Toilet | 1 | 1 | 2.3 |  |  | 2.3
| Split AC 2.0 Tr Drain | 1 | 1 | 6.2 |  |  | 6.2
[7 empty] | 98.6 | Rmt
Sup | Supplying and fixing GI pipe Medium Grade properties & weight as per IS 1239 in ground or on wall with GI fittings such as elbows tees couplings, nipples, plugs including excavation for trenches and refilling the trenches ,chiselling masonry walls and making good the walls & floors to the original surface and fixing MS clamps on TW blocks on walls including cost and conveyance of all materials and labour charges , overheads & contractors profit complete for finished item of work except for GI bends union and GI connectors with checkout and socket Tata or Zenith make or equivalent.
| Autoclave Outline 40mm | 1 | 1 | 17.55 |  |  | 17.55
| Autoclave Outline 25mm | 1 | 1 | 17.55 |  |  | 17.55
[7 empty] | 35.1 | Rmt
81 | Supply, installation and commissioning approved make floor mounted Anglo Indian wash down EWC conforming to IS: 2556 part8-2004 suit with P or S trap with dual flush porcelain cistren fixed on wash down EWC with all intenal parts of dual flush cistren. ultra solid seat cover of approved make with rubber buffer and cap and 15mm angle stop cock and 450mm long PVC iner connection pipe wall flanges all of approved make etc. Complete for finished item of work
| Prepost Operative wards | 1 | 1 |  |  |  | 1
| Toilet At Counseling Room2 | 1 | 1 |  |  |  | 1
| Dr. Toilet | 1 | 1 |  |  |  | 1
| Sperm Collection Room | 1 | 1 |  |  |  | 1
[7 empty] | 4 | Nos
80 | Supplying and fixing Indian make Flat Back Wash Hand Basin 1st quality conforming to IS:2556-Part-4:1972 of size 550mm x 400mm with 32 mm nominal size C.P. Fitting with parallel pipe thread conforming to IS:2963-1979 and fitted with 15 mm nominal bore Chromium Plated Pillar Tap of 1st quality Indian make heavy duty complete with standard CI brackets including wooden blocks ,1 No.12.70mm PVC connection with brass union nuts CP coated , angle stop cock 12.70mm dia. first quality Indian make heavy duty, 30mm dia. PVC flexible waste pipe 914.4mm length of 1st quality including cost and conveyance of all materials to site, labour charges , overheads & contractors profit for finished item of work.
| Prepost Operative wards | 1 | 1 |  |  |  | 1
| Toilet At Counseling Room2 | 1 | 1 |  |  |  | 1
| Dr. Toilet | 1 | 1 |  |  |  | 1
| Sperm Collection Room | 1 | 1 |  |  |  | 1
[7 empty] | 4 | Nos
83 | Supplying and fixing CP finish brass soap dish of approved make ISI quality including cost and conveyance of all materials, labour charges for fixing, overheads & contractors profit for finished item of work
| Prepost Operative wards | 1 | 1 |  |  |  | 1
| Toilet At Counseling Room2 | 1 | 1 |  |  |  | 1
| Dr. Toilet | 1 | 1 |  |  |  | 1
| Sperm Collection Room | 1 | 1 |  |  |  | 1
[7 empty] | 4 | Nos
84 | Supplying and fixing TV shape mirror with plastic frame of size 609.6mm x 457.2mm , plywood back with NP screws 1st quality including cost and conveyance of all materials, labour charges , overheads & contractors profit for finished item of work
| Prepost Operative wards | 1 | 1 |  |  |  | 1
| Toilet At Counseling Room2 | 1 | 1 |  |  |  | 1
| Dr. Toilet | 1 | 1 |  |  |  | 1
| Sperm Collection Room | 1 | 1 |  |  |  | 1
[7 empty] | 4 | Nos
Sup | Supplying and fixing of CP finish steel towel rods 600mm long and 20mm dia with brackets and aluminium screws including cost and conveyance of all materials, labour charges , overheads & contractors profit for finished item of work.
| Prepost Operative wards | 1 | 1 |  |  |  | 1
| Toilet At Counseling Room2 | 1 | 1 |  |  |  | 1
| Dr. Toilet | 1 | 1 |  |  |  | 1
| Sperm Collection Room | 1 | 1 |  |  |  | 1
[7 empty] | 4 | Nos
86 | Supplying and fixing 15 mm Steel body CP finish self closing tap push type conforming to IS 1711 as approved by the Engineer-In-Charge including cost and conveyance of all materials, labour charges, overheads & contractors profit complete for finished item of work in all floors.
| Prepost Operative wards | 1 | 1 |  |  |  | 1
| Toilet At Counseling Room2 | 1 | 1 |  |  |  | 1
| Dr. Toilet | 1 | 1 |  |  |  | 1
| Sperm Collection Room | 1 | 1 |  |  |  | 1
[7 empty] | 4 | Nos
82 | Supplying and fixing Chromium plated finish brass body quarter turn Bibcock cum Health Faucet with 1m long tube and wall hook with necessary fittings etc., complete including cost and conveyance of all materials, labour charges, complete for finished item of work in all floors. at Gandhi Hospital
| Prepost Operative wards | 1 | 1 |  |  |  | 1
| Toilet At Counseling Room2 | 1 | 1 |  |  |  | 1
| Dr. Toilet | 1 | 1 |  |  |  | 1
| Sperm Collection Room | 1 | 1 |  |  |  | 1
[7 empty] | 4 | Nos
73 | Supplying and fixing 15 mm brass body CP finish bib tap of not less than 300 grams weight screw type full turn with internal/external threaded connection conforming to IS 8931 as approved by the Engineer-In-Charge including cost and conveyance of all materials, labour charges, overheads and contractors profit complete for finished item of work in all floors. at Gandhi Hospital
| Dr. Toilet | 1 | 1 |  |  |  | 1
[7 empty] | 1 | Nos
79 | Supply and fixing of 4 inches 101.6mm multi floor trap with jali -UPVC/SWR pipe fittings as per site requirements with standard practice for all floor including cost and conveyance of all materials to site ,labour charges ,etc,. Complete for finshed item of work at handhi hospital
| Prepost Operative wards | 1 | 1 |  |  |  | 1
| Toilet At Counseling Room2 | 1 | 1 |  |  |  | 1
| Dr. Toilet | 1 | 1 |  |  |  | 1
| Sperm Collection Room | 1 | 1 |  |  |  | 1
| Scrub Wastewater Line | 1 | 1 |  |  |  | 1
[7 empty] | 5 | Nos
Sup | Supplying and fixing of 3" (75mm) Nahany trap with jali - UPVC/SWR pipe fittings as per site requirements with standard practice for all floors including cost and conveyance of all materials to site, labour charges , overheads & contractors profit etc., complete for finished item of work.
| Prepost Operative wards | 1 | 1 |  |  |  | 1
| Toilet At Counseling Room2 | 1 | 1 |  |  |  | 1
| Dr. Toilet | 1 | 1 |  |  |  | 1
| Sperm Collection Room | 1 | 1 |  |  |  | 1
| Scrub Wastewater Line | 1 | 1 |  |  |  | 1
[7 empty] | 5 | Nos
58 | Supply and Installation change room Cubicles at Gandhi Hospital GENERAL SPECIFICATIONS: Thickness of compact Laminate:12mm Thick Colour OF HPL Boards,In Single Colour,Size of Cubicle As per DWG, Door Size For Normal Cubicles AS per DWG Overall Height of Cubicle,2105mm Including bottom gap of 100mm,Accessories , Manufacturers standard makes of aluminium , SS Accessories .a Aluminium H Top Rail b. SS Hinges c. SS privacy Thumb turn occupancy indicator d.SS coat hook e. SS Door knob f. Aluminium U Channel g.Aluminium Door Stopper Channel h. Runner lining i.SS Screw And PVC Wall Plugs
| Dr. Change Room | 1 | 1 | 1.46 |  | 2.2 | 3.212
| do | 1 | 1 | 1.42 |  | 2.2 | 3.124
| Patient Change Room | 1 | 1 | 1.5 |  | 2.2 | 3.3
| Staff Change Room 1 | 1 | 1 | 1.62 |  | 2.2 | 3.564
| Staff Change Room 2 | 1 | 1 | 1.65 |  | 2.2 | 3.63
[7 empty] | 16.83 | Sqm
Sup | V-Board Partition
| Dr. Change Room | 2 | 2 | 1.43 |  | 3.35 | 19.162
| do | 1 | 2 | 0.075 |  | 3.35 | 0.5025
| Store Room | 1 | 2 | 3 |  | 3.35 | 20.1
| do | 1 | 2 | 2.26 |  | 3.35 | 15.142
| Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
| Patient and Staff Change Room | 2 | 2 | 1.87 |  | 3.45 | 25.806
| Window Closings Embryology Lab And UPS Room | 1 | 4 | 1.5 |  | 1.5 | 9
| Sperm Collection Toilet | 1 | 1 | 1 |  | 1.5 | 1.5
[7 empty] | 89.1125 | Sqm
Sup | Supply & application of one coat water based cement primer of interior grade I and two coats of acrylic emulsion paint having VOC (Volatile Organic Compound) content less than 50 grams/litre for internal walls including cost and conveyance of all materials to site, sales & other taxes, incidental, operational and all labour charges etc., and overheads & contractors profit complete for finished item of work in all floors.
| Step Down Room Door Replacing | 1 | 2 | 1.5 |  | 2.6 | 7.8
| do | 1 | 2 | 1.7 |  | 0.4 | 1.36
| Door Jam | 1 | 1 | 6.635 | 0.23 |  | 1.526
| Prepost operative room Door Replace | 1 | 2 | 1 |  | 2.6 | 5.2
| Embryology Lab Door Replacing | 1 | 2 | 1.16 |  | 2.9 | 6.728
| do | 1 | 2 | 1.7 |  | 0.4 | 1.36
| Door Jam | 1 | 1 | 6.7 | 0.23 |  | 1.541
| Major OT Door | 1 | 2 | 1.7 |  | 0.4 | 1.36
| Door Jam | 1 | 1 | 6.7 | 0.23 |  | 1.541
| OT Room Window Replacing | 3 | 2 | 1.5 |  | 1.5 | 13.5
| Toilet Room Window Replacing | 1 | 2 | 1.5 |  | 1.5 | 4.5
| Embrology Lab Windows Replacing | 3 | 2 | 1.5 |  | 1.5 | 13.5
| Access Control Door Wall | 2 | 2 | 3 |  | 3 | 36
| Door Deduction(-) | -2 | 2 | 1.5 |  | 2.6 | -15.6
| Door Jam | 1 | 2 | 6.7 | 0.23 |  | 3.082
| Prepost operative Window Closing | 1 | 2 | 1.1 |  | 1.9 | 4.18
| Record Room Wall | 1 | 2 | 3 |  | 3.45 | 20.7
| Door Deduction(-) | -1 | 2 | 1 |  | 2.1 | -4.2
| Door Jam | 1 | 1 | 5.2 | 0.15 |  | 0.78
| Partition Wall b/w Ultra Sound And Autoclave Room | 1 | 2 | 2.18 |  | 3.5 | 15.26
| Partition Wall b/w Counciling -2 And Counciling -1 | 1 | 2 | 2.452 |  | 3.5 | 17.164
| Doctors Toilet Room Wall | 1 | 2 | 4.7 |  | 3.5 | 32.9
| Door Deduction(-) | -1 | 2 | 1 |  | 2.1 | -4.2
| Door Jam | 1 | 1 | 5.2 | 0.15 |  | 0.78
| Partition Wall b/w Carridor and OT Room | 1 | 2 | 6.485 |  | 3.5 | 45.395
| Partition Wall b/w OT Rooms | 1 | 2 | 6.485 |  | 3.5 | 45.395
| P.Change Room Wall | 1 | 2 | 2.02 |  | 3.5 | 14.14
| Store Room | 1 | 2 | 2.582 |  | 3.5 | 18.074
| Door Jams | 1 | 1 | 5.2 | 0.15 |  | 0.78
| Door Deduction(-) | -1 | 2 | 1 |  | 2.1 | -4.2
| Partition Wall b/w Store And Blod Collection | 1 | 2 | 3.4 |  | 2.4 | 16.32
| Top | 1 | 2 | 3.4 | 0.15 |  | 1.02
| Blod Collection Room Wall | 1 | 2 | 2.582 |  | 3.5 | 18.074
| Door Jam | 1 | 1 | 5.2 | 0.15 |  | 0.78
| Door Deduction(-) | -1 | 2 | 1 |  | 2.1 | -4.2
| Partition Wall b/w Blood Collection And Sperm Collection | 1 | 2 | 3.3 |  | 2.4 | 15.84
| Top | 1 | 1 | 3.4 | 0.15 |  | 0.51
| do | 1 | 2 | 1 |  | 1.2 | 2.4
| partition Wall b/w Sperm Collection Room And Toilet Room | 1 | 2 | 3.3 |  | 3.5 | 23.1
| Door Jam | 1 | 1 | 5 | 0.15 |  | 0.75
| Door Deduction(-) | -1 | 2 | 0.8 |  | 2.1 | -3.36
| Sperm Collection Toilet Wall | 1 | 2 | 2.05 |  | 3.5 | 14.35
| Partition Wall b/w Toilet And Cryo Room | 1 | 2 | 1.7 |  | 3.5 | 11.9
| Cryo Room Wall | 1 | 2 | 3 |  | 3.5 | 21
| Door Jams | 1 | 1 | 5.2 | 0.15 |  | 0.78
| Door Deduction | -1 | 2 | 1 |  | 2.1 | -4.2
| Manifold Room | 1 | 2 | 3.185 |  | 3.5 | 22.295
| do | 1 | 2 | 1.385 |  | 3 | 8.31
| do | 1 | 2 | 2.23 |  | 3.5 | 15.61
| do | 1 | 2 | 1.33 |  | 3 | 7.98
| Andrology Lab Scrub Area | 1 | 2 | 2.585 |  | 3.45 | 17.8365
| Doctors Corridor Door Jam | 1 | 1 | 8.1 | 0.23 |  | 1.863
| Corridor Change Room | 1 | 1 | 8.1 | 0.23 |  | 1.863
| Prepost Operative Room Wall Area | 1 | 1 | 12.6 | 0.23 |  | 2.898
| Toilet Wall | 1 | 1 | 4.65 | 0.15 |  | 0.6975
| Counseling Rooms Partition Wall Area | 1 | 1 | 9.3 | 0.15 |  | 1.395
| Andrology Lab Main Door wall area | 1 | 1 | 11.2 | 0.23 |  | 2.576
| Toilet Wall | 1 | 1 | 5.25 | 0.15 |  | 0.7875
| do | 1 | 1 | 6.45 | 0.15 |  | 0.9675
| partition Wall | 1 | 1 | 1.8 | 0.15 |  | 0.27
| Toilet Wall Major OT | 1 | 1 | 5.25 | 0.15 |  | 0.7875
| do | 1 | 1 | 6.45 | 0.15 |  | 0.9675
| partition Wall | 1 | 1 | 1.8 | 0.15 |  | 0.27
| Andrlogy Lab Wall plastring | 1 | 1 | 3.2 |  | 1.5 | 4.8
| Reciption Platform Wall | 1 | 2 | 1.5 |  | 0.9 | 2.7
| do | 3 | 2 | 0.5 |  | 0.9 | 2.7
| Toilet Inside Prepost Operative Room | 1 | 1 | 3 |  | 1.5 | 4.5
| do | 1 | 1 | 0.8 |  | 1.5 | 1.2
| Andrlogy Lab Toilet Wall | 1 | 1 | 1.8 |  | 1.5 | 2.7
| do | 1 | 1 | 3 |  | 1.5 | 4.5
| do | 1 | 1 | 1.8 |  | 1.5 | 2.7
| Andrology lab Partition wall | 1 | 1 | 5.2 |  | 1.5 | 7.8
| Door Deduction(-) | -1 | 1 | 1.5 |  | 1.5 | -2.25
| Major OT Toilet Wall | 1 | 1 | 1.8 |  | 1.5 | 2.7
| Major OT | 1 | 1 | 4.05 |  | 1.5 | 6.075
| do | 1 | 1 | 3 |  | 1.5 | 4.5
| partiton wall | 1 | 1 | 1.8 |  | 1.5 | 2.7
[7 empty] | 536.1091 | Sqm
69 | Providing and applying Wall putty of White Cement or Polymer or Cement based of average 1 to 2 mm thickness over plastered surface to prepare the surface even and smooth after thoroughly brushing the surface to remove all dirt and remains of loose powdered materials, applying emery paper, Sand the surface, clean & wipe off loose dust, applying knifing paste filler by putty knife / muslin pad, air dry for 2 - 3 hrs, sand with 180 and 320 No., emery paper for the surface preparation including cost and conveyance of all materials to work site and all operational, incidental, labour charges, over heads and contractors profit etc., complete for finished item of work in all floors for Internal walls.
| Main Entry Corridor | 1 | 1 | 6.3 |  | 2 | 12.6
| main Entry Access Control Door | 1 | 1 | 3 |  | 2 | 6
| Door Deduction(-) | -1 | 1 | 1.5 |  | 2 | -3
| Corridor at Reception | 1 | 1 | 3 |  | 2 | 6
| Reception area | 1 | 2 | 3.4 |  | 2 | 13.6
| Record Room Main Door Wall | 1 | 1 | 3 |  | 2 | 6
| Door Jam | 1 | 1 | 5.2 | 0.15 |  | 0.78
| Door Deduction(-) | -1 | 1 | 1 |  | 2 | -2
| Record Room Inside | 1 | 2 | 3.2 |  | 2 | 12.8
| do | 1 | 1 | 3 |  | 2 | 6
| do | 1 | 1 | 3 |  | 3.5 | 10.5
| Door deductions(-) | -1 | 1 | 1 |  | 2.1 | -2.1
| Window Deduction(-) | 1 | 1 | 1.8 |  | 1.4 | 2.52
| Wndow Jam | 1 | 1 | 5.4 | 0.15 |  | 0.81
| Ultra Sound Room Inside Long Wall | 1 | 2 | 4.47 |  | 3.5 | 31.29
| Ultra Sound Room Inside Short Wall | 1 | 2 | 2.18 |  | 3.5 | 15.26
| Door Jam | 1 | 1 | 5.812 | 0.15 |  | 0.8718
| Door Deduction(-) | -1 | 1 | 1.215 |  | 2.3 | -2.7945
| Ventilator Deduction(-) | -1 | 1 | 0.45 |  | 0.45 | -0.2025
| Ventilator jam | 1 | 1 | 1.8 | 0.15 |  | 0.27
| Autoclave Room Inside Long Wall | 1 | 2 | 2.18 |  | 3.5 | 15.26
| Autoclave Room Inside Short Wall | 1 | 2 | 1.19 |  | 3.5 | 8.33
| Door deduction(-) | -1 | 1 | 1.21 |  | 2.37 | -2.8677
| Door Jam | 1 | 1 | 5.81 | 0.15 |  | 0.8715
| Toilet at Counseling Room 2 Inside Long Wall | 1 | 2 | 1.5 |  | 2 | 6
| Toilet at Counseling Room 2 Inside Short Wall Wall | 1 | 2 | 1.2 |  | 2 | 4.8
| Door Deduction(-) | -1 | 2 | 0.8 |  | 2 | -3.2
| Door Jam | 1 | 1 | 5 | 0.15 |  | 0.75
| Counseling Room 2 Inside Long Wall | 1 | 2 | 3.24 |  | 3.5 | 22.68
| Counseling Room 2 Inside Long Wall | 1 | 2 | 2.45 |  | 3.5 | 17.15
| Door jam | 1 | 1 | 5.47 | 0.15 |  | 0.8205
| Door Deduction(-) | -1 | 1 | 1.07 |  | 2.2 | -2.354
| Window Deduction(-) | -1 | 1 | 1.8 |  | 1.8 | -3.24
| Counseling Room 1 inside Long Wall | 1 | 2 | 3.24 |  | 3.5 | 22.68
| Counseling Room 1 inside Short Wall | 1 | 2 | 2.45 |  | 3.5 | 17.15
| Door Jam | 1 | 1 | 5.49 | 0.15 |  | 0.8235
| Door Deduction(-) | -1 | 1 | 1.09 |  | 2.2 | -2.398
| Corridor at Counseling Room 1 and 2 | 1 | 2 | 5.1 |  | 3.5 | 35.7
| do | 1 | 1 | 1.2 |  | 3.5 | 4.2
| Door Deductions(-) Counseling Room 2 | -1 | 1 | 1.09 |  | 2.2 | -2.398
| Door Deductions(-) Counseling Room 1 | -1 | 1 | 1.07 |  | 2.2 | -2.354
| Door Deductions(-) Auto Clave Room | -1 | 1 | 1.2 |  | 2.3 | -2.76
| Door Deductions(-) Altra Sound Room | -1 | 1 | 1.2 |  | 2.3 | -2.76
| Corridor at prepost Operative Wards | 1 | 2 | 6.3 |  | 2 | 25.2
| Door Deduction(-) | -1 | 1 | 1.49 |  | 2 | -2.98
| Corridor Deduction(-) | -1 | 1 | 1.2 |  | 2 | -2.4
| Prepost Operative Wards Inside Long Wall | 1 | 1 | 6.48 |  | 2 | 12.96
| Prepost Operative Wards Inside Long Wall | 1 | 1 | 4.38 |  | 2 | 8.76
| Prepost Operative Wards Inside Short Wall | 1 | 1 | 6 |  | 2 | 12
| Prepost Operative Wards Inside Short Wall | 1 | 1 | 4.8 |  | 2 | 9.6
| Door Deduction(-) | -1 | 1 | 1.49 |  | 2 | -2.98
| Door Jam | 1 | 1 | 6.49 | 0.23 |  | 1.4927
| Window Deduction(-) | -1 | 1 | 1.8 |  | 1.4 | -2.52
| Window Jam | 1 | 1 | 7.2 | 0.15 |  | 1.08
| Corridor At Semi Sterile Area | 1 | 2 | 6.45 |  | 2 | 25.8
| Corridor Opening Deductions(-) | -1 | 2 | 1.2 |  | 1.5 | -3.6
| Access Control Door at Semistearail Area | 1 | 2 | 3 |  | 3.5 | 21
| Door Deduction(-) | -1 | 2 | 1.5 |  | 2.6 | -7.8
| Door Jam | 1 | 1 | 6.7 | 0.23 |  | 1.541
| Corridor at Dr Change Room Long Wall | 1 | 2 | 4.7 |  | 3.5 | 32.9
| Corridor at Dr Change Room Short Wall | 1 | 2 | 4.68 |  | 3.5 | 32.76
| Corridor Opening Deductions(-) | 1 | 1 | 1.2 |  | 3 | 3.6
| Toilet Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
| Dr Toilet Inside | 1 | 2 | 4.68 |  | 2 | 18.72
| Dr Toilet Inside | 1 | 2 | 1.85 |  | 2 | 7.4
| Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
| Ventilator Deduction(-) | -1 | 1 | 0.45 |  | 0.45 | -0.2025
| Dr Change Room Partitions | 1 | 2 | 2.61 |  | 3.5 | 18.27
| Dr Change Room Partitions | 1 | 2 | 2.2 |  | 3.5 | 15.4
| Door Deductions(-) | -1 | 1 | 1 |  | 2.1 | -2.1
| Dr Change Room Partitions | 1 | 2 | 1.45 |  | 3.5 | 10.15
| Dr Change Room Partitions | 1 | 2 | 1.45 |  | 3.5 | 10.15
| Corridor at Manifold Room | 1 | 2 | 3.3 |  | 3.5 | 23.1
| Corridor at Manifold Room | 1 | 1 | 1.2 |  | 3.5 | 4.2
| Door Deductions(-) | -1 | 1 | 1.08 |  | 2.3 | -2.484
| Door Deductions(-) | -1 | 1 | 0.986 |  | 2.2 | -2.1692
| Manifold Room Inside Long Walls | 1 | 2 | 3.185 |  | 3.5 | 22.295
| Manifold Room Inside Short Walls | 1 | 2 | 2.13 |  | 3.5 | 14.91
| Door Deductions(-) | -1 | 1 | 1.01 |  | 2.3 | -2.323
| Door Jam | 1 | 1 | 5.61 | 0.15 |  | 0.8415
| Change Room walls | 3 | 2 | 1.87 |  | 3.5 | 39.27
| Change Room wall | 1 | 1 | 5.2 |  | 2 | 10.4
| Corridor at Blood Collection Room | 1 | 1 | 5.2 |  | 3.5 | 18.2
| Door Deductions(-) | -1 | 1 | 0.998 |  | 2.1 | -2.0958
| Door Deductions(-) | -1 | 1 | 0.999 |  | 2.1 | -2.0979
| Store Room Inside Long Wall | 1 | 1 | 3.3 |  | 3.5 | 11.55
| Store Room Inside Long Wall | 1 | 1 | 3.3 |  | 2.4 | 7.92
| Store Room Inside Short Wall | 1 | 2 | 2.5 |  | 3.5 | 17.5
| Door Deductions(-) | -1 | 1 | 1 |  | 2.1 | -2.1
| Partition Wall Top | 1 | 1 | 3.3 | 0.15 |  | 0.495
| Blood Collection Room Long Wall | 1 | 2 | 3.3 |  | 2.4 | 15.84
| Blood Collection Room Short Wall | 1 | 2 | 2.5 |  | 3.5 | 17.5
| Door Deductions(-) | -1 | 1 | 1 |  | 2.1 | -2.1
| Tartition Wall Top | 1 | 1 | 3.3 | 0.15 |  | 0.495
| Sperm Collection Inside Long Wall | 1 | 1 | 3.3 |  | 2.4 | 7.92
| Sperm Collection Inside Long Wall | 1 | 1 | 3.3 |  | 3.5 | 11.55
| Sperm Collection Inside Short Wall | 1 | 2 | 3.265 |  | 3.5 | 22.855
| Door Deductions(-) | -1 | 1 | 0.8 |  | 2.1 | -1.68
| Door Deductions(-) | -1 | 1 | 1 |  | 2.1 | -2.1
| Sperm Collection Toilet inside | 1 | 2 | 1.6 |  | 2 | 6.4
| Sperm Collection Toilet inside | 1 | 2 | 1.1 |  | 2 | 4.4
| Door Deductions(-) | -1 | 1 | 0.8 |  | 2.1 | -1.68
| Ventilator Deduction(-) | -1 | 1 | 0.45 |  | 0.45 | -0.2025
| Corridor at Sterile area | 1 | 2 | 6.3 |  | 2 | 25.2
| Corridor at Sterile area | 1 | 1 | 3 |  | 2 | 6
| Door Deductions(-) Minor OT | -1 | 1 | 1.5 |  | 2 | -3
| Door Deductions(-) Major OT | -1 | 1 | 1.5 |  | 2 | -3
| Door Deductions(-) Andrology Lab | -1 | 1 | 1.5 |  | 2 | -3
| Door Deductions(-) Emergency Exit | -1 | 1 | 1.8 |  | 2 | -3.6
| Minor OT Inside Long Walls | 1 | 2 | 6.4 |  | 3.5 | 44.8
| Minor OT Inside Short Walls | 1 | 2 | 4.2 |  | 3.5 | 29.4
| Door Deductions(-) | -1 | 1 | 1.5 |  | 2.6 | -3.9
| Pass box Opening (-) | -1 | 1 | 0.6 |  | 0.6 | -0.36
| Androlry Lab Long Walls Inside | 1 | 2 | 4.25 |  | 3.5 | 29.75
| Androlry Lab Short Walls Inside | 1 | 2 | 4.08 |  | 3.5 | 28.56
| Door Deductions(-) | -1 | 1 | 1.5 |  | 2.6 | -3.9
| Door Deductions(-) | -1 | 1 | 1 |  | 2.1 | -2.1
| Cryo Room Inside | 1 | 2 | 3 |  | 3.5 | 21
| do | 1 | 2 | 1.6 |  | 3.5 | 11.2
| Door Deductions | -1 | 1 | 1 |  | 2.1 | -2.1
| Staire Case area | 1 | 1 | 4.2 |  | 2 | 8.4
| Staire Case area | 1 | 2 | 4.2 |  | 2 | 16.8
| Window Deduction(-) | -1 | 1 | 1.8 |  | 1.8 | -3.24
| Dr. Change Room | 2 | 2 | 2.2 |  | 3.45 | 30.36
| Store Room | 1 | 2 | 3.18 |  | 3.45 | 21.942
| do | 1 | 2 | 2.18 |  | 3.45 | 15.042
| Door Deduction(-) | -1 | 2 | 0.8 |  | 2.1 | -3.36
| Change Rooms | 2 | 2 | 1.87 |  | 3.45 | 25.806
[7 empty] | 1007.3989 | Sqm
71 | Supply and application of one coat water based cement primer of interior grade I and two coats of water based PU paint having anti-bacterial applications content less than 50 grams/litre for internal walls including cost and conveyance of all materials to site, sales and other taxes, incidental, operational and all labour charges etc., and complete for finished item of work in 5th floor. at Gandhi Hospital
| Main Entry Corridor | 1 | 1 | 6.3 |  | 1.5 | 9.45
| main Entry Access Control Door | 1 | 1 | 3 |  | 1.5 | 4.5
| Door Deduction(-) | -1 | 1 | 1.5 |  | 2.6 | -3.9
| Corridor at Reception | 1 | 1 | 3 |  | 1.5 | 4.5
| Reception area | 1 | 2 | 3.4 |  | 1.5 | 10.2
| Record Room Main Door Wall | 1 | 2 | 3 |  | 3.05 | 18.3
| Door Jam | 1 | 1 | 5.2 | 0.15 |  | 0.78
| Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
| Record Room Inside | 1 | 2 | 3.2 |  | 1.5 | 9.6
| do | 1 | 1 | 3 |  | 1.5 | 4.5
| Window Deduction(-) | 1 | 1 | 1.8 |  | 1.4 | 2.52
| Wndow Jam | 1 | 1 | 5.4 | 0.15 |  | 0.81
| Ultra Sound Room Inside Long Wall | 1 | 2 | 4.505 |  | 3.05 | 27.4805
| Ultra Sound Room Inside Short Wall | 1 | 2 | 2.18 |  | 3.05 | 13.298
| Door Jam | 1 | 1 | 5.812 | 0.15 |  | 0.8718
| Door Deduction(-) | -1 | 1 | 1.215 |  | 2.3 | -2.7945
| Ventilator Deduction(-) | -1 | 1 | 0.45 |  | 0.45 | -0.2025
| Ventilator jam | 1 | 1 | 1.8 | 0.15 |  | 0.27
| Autoclave Room Inside Long Wall | 1 | 2 | 2.18 |  | 3.05 | 13.298
| Autoclave Room Inside Short Wall | 1 | 2 | 1.19 |  | 3.05 | 7.259
| Door deduction(-) | -1 | 1 | 1.21 |  | 2.37 | -2.8677
| Door Jam | 1 | 1 | 5.81 | 0.15 |  | 0.8715
| Toilet at Counseling Room 2 Inside Long Wall | 1 | 2 | 1.5 |  | 1.5 | 4.5
| Toilet at Counseling Room 2 Inside Short Wall Wall | 1 | 2 | 1.2 |  | 1.5 | 3.6
| Door Deduction(-) | 1 | 2 | 0.8 |  | 2.1 | 3.36
| Door Jam | 1 | 1 | 5 | 0.15 |  | 0.75
| Counseling Room 2 Inside Long Wall | 1 | 2 | 3.24 |  | 3.05 | 19.764
| Counseling Room 2 Inside Long Wall | 1 | 2 | 2.45 |  | 3.05 | 14.945
| Door jam | 1 | 1 | 5.47 | 0.15 |  | 0.8205
| Door Deduction(-) | -1 | 1 | 1.07 |  | 2.2 | -2.354
| Window Deduction(-) | -1 | 1 | 1.8 |  | 1.8 | -3.24
| Counseling Room 1 inside Long Wall | 1 | 2 | 3.24 |  | 3.05 | 19.764
| Counseling Room 1 inside Short Wall | 1 | 2 | 2.45 |  | 3.05 | 14.945
| Door Jam | 1 | 1 | 5.49 | 0.15 |  | 0.8235
| Door Deduction(-) | -1 | 1 | 1.09 |  | 2.2 | -2.398
| Corridor at Counseling Room 1 and 2 | 1 | 2 | 5.1 |  | 3.05 | 31.11
| do | 1 | 1 | 1.2 |  | 3.05 | 3.66
| Door Deductions(-) Counseling Room 2 | -1 | 1 | 1.09 |  | 2.2 | -2.398
| Door Deductions(-) Counseling Room 1 | -1 | 1 | 1.07 |  | 2.2 | -2.354
| Door Deductions(-) Auto Clave Room | -1 | 1 | 1.2 |  | 2.3 | -2.76
| Door Deductions(-) Altra Sound Room | -1 | 1 | 1.2 |  | 2.3 | -2.76
| Corridor at prepost Operative Wards | 1 | 2 | 6.3 |  | 1.5 | 18.9
| Door Deduction(-) | -1 | 1 | 1.49 |  | 1.5 | -2.235
| Corridor Deduction(-) | -1 | 1 | 1.2 |  | 2 | -2.4
| Prepost Operative Wards Inside Long Wall | 1 | 1 | 6.48 |  | 1.5 | 9.72
| Prepost Operative Wards Inside Long Wall | 1 | 1 | 4.38 |  | 1.5 | 6.57
| Prepost Operative Wards Inside Short Wall | 1 | 1 | 6 |  | 1.5 | 9
| Prepost Operative Wards Inside Short Wall | 1 | 1 | 4.8 |  | 1.5 | 7.2
| Door Deduction(-) | -1 | 1 | 1.49 |  | 2.5 | -3.725
| Door Jam | 1 | 1 | 6.49 | 0.23 |  | 1.4927
| Window Deduction(-) | -1 | 1 | 1.8 |  | 1.4 | -2.52
| Window Jam | 1 | 1 | 7.2 | 0.15 |  | 1.08
| Corridor At Semi Sterile Area | 1 | 2 | 6.45 |  | 2 | 25.8
| Corridor Opening Deductions(-) | -1 | 2 | 1.2 |  | 1.5 | -3.6
| Access Control Door at Semistearail Area | 1 | 2 | 3 |  | 3.05 | 18.3
| Door Deduction(-) | -1 | 2 | 1.5 |  | 2.6 | -7.8
| Door Jam | 1 | 1 | 6.7 | 0.23 |  | 1.541
| Corridor at Dr Change Room Long Wall | 1 | 2 | 4.7 |  | 3.05 | 28.67
| Corridor at Dr Change Room Short Wall | 1 | 2 | 4.68 |  | 3.05 | 28.548
| Corridor Opening Deductions(-) | 1 | 1 | 1.2 |  | 3 | 3.6
| Toilet Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
| Dr Toilet Inside | 1 | 2 | 4.68 |  | 1.5 | 14.04
| Dr Toilet Inside | 1 | 2 | 1.85 |  | 1.5 | 5.55
| Door Deduction(-) | -1 | 1 | 1 |  | 1.5 | -1.5
| Ventilator Deduction(-) | -1 | 1 | 0.45 |  | 0.45 | -0.2025
| Dr Change Room Partitions | 1 | 2 | 2.61 |  | 3.05 | 15.921
| Dr Change Room Partitions | 1 | 2 | 2.2 |  | 3.05 | 13.42
| Door Deductions(-) | -1 | 1 | 1 |  | 2.1 | -2.1
| Dr Change Room Partitions | 1 | 2 | 1.45 |  | 3.05 | 8.845
| Dr Change Room Partitions | 1 | 2 | 1.45 |  | 3.05 | 8.845
| Corridor at Manifold Room | 1 | 2 | 3.3 |  | 3.05 | 20.13
| Corridor at Manifold Room | 1 | 1 | 1.2 |  | 3.05 | 3.66
| Door Deductions(-) | -1 | 1 | 1.08 |  | 2.3 | -2.484
| Door Deductions(-) | -1 | 1 | 0.986 |  | 2.2 | -2.1692
| Manifold Room Inside Long Walls | 1 | 2 | 3.185 |  | 3.05 | 19.4285
| Manifold Room Inside Short Walls | 1 | 2 | 2.13 |  | 3.05 | 12.993
| Door Deductions(-) | -1 | 1 | 1.01 |  | 2.3 | -2.323
| Door Jam | 1 | 1 | 5.61 | 0.15 |  | 0.8415
| Change Room walls | 3 | 2 | 1.87 |  | 3.05 | 34.221
| Change Room wall | 1 | 1 | 5.2 |  | 1.5 | 7.8
| Corridor at Blood Collection Room | 1 | 1 | 5.2 |  | 3.05 | 15.86
| Door Deductions(-) | -1 | 1 | 0.998 |  | 2.1 | -2.0958
| Door Deductions(-) | -1 | 1 | 0.999 |  | 2.1 | -2.0979
| Store Room Inside Long Wall | 1 | 1 | 3.3 |  | 3.05 | 10.065
| Store Room Inside Long Wall | 1 | 1 | 3.3 |  | 2.4 | 7.92
| Store Room Inside Short Wall | 1 | 2 | 2.5 |  | 3.05 | 15.25
| Door Deductions(-) | -1 | 1 | 1 |  | 2.1 | -2.1
| Partition Wall Top | 1 | 1 | 3.3 | 0.15 |  | 0.495
| Blood Collection Room Long Wall | 1 | 2 | 3.3 |  | 2.4 | 15.84
| Blood Collection Room Short Wall | 1 | 2 | 2.5 |  | 3.05 | 15.25
| Door Deductions(-) | -1 | 1 | 1 |  | 2.1 | -2.1
| Tartition Wall Top | 1 | 1 | 3.3 | 0.15 |  | 0.495
| Sperm Collection Inside Long Wall | 1 | 1 | 3.3 |  | 2.4 | 7.92
| Sperm Collection Inside Long Wall | 1 | 1 | 3.3 |  | 3.05 | 10.065
| Sperm Collection Inside Short Wall | 1 | 2 | 3.265 |  | 3.05 | 19.9165
| Door Deductions(-) | -1 | 1 | 0.8 |  | 2.1 | -1.68
| Door Deductions(-) | -1 | 1 | 1 |  | 2.1 | -2.1
| Sperm Collection Toilet inside | 1 | 2 | 1.6 |  | 1.5 | 4.8
| Sperm Collection Toilet inside | 1 | 2 | 1.1 |  | 1.5 | 3.3
| Door Deductions(-) | -1 | 1 | 0.8 |  | 1.5 | -1.2
| Ventilator Deduction(-) | -1 | 1 | 0.45 |  | 0.45 | -0.2025
| Corridor at Sterile area | 1 | 2 | 6.3 |  | 1.5 | 18.9
| Corridor at Sterile area | 1 | 1 | 3 |  | 1.5 | 4.5
| Door Deductions(-) Minor OT | -1 | 1 | 1.5 |  | 1.5 | -2.25
| Door Deductions(-) Major OT | -1 | 1 | 1.5 |  | 1.5 | -2.25
| Door Deductions(-) Andrology Lab | -1 | 1 | 1.5 |  | 1.5 | -2.25
| Door Deductions(-) Emergency Exit | -1 | 1 | 1.8 |  | 1.5 | -2.7
| Minor OT Inside Long Walls | 1 | 2 | 6.4 |  | 3.05 | 39.04
| Minor OT Inside Short Walls | 1 | 2 | 4.2 |  | 3.05 | 25.62
| Door Deductions(-) | -1 | 1 | 1.5 |  | 2.6 | -3.9
| Pass box Opening (-) | -1 | 1 | 0.6 |  | 0.6 | -0.36
| Androlry Lab Long Walls Inside | 1 | 2 | 4.25 |  | 3.05 | 25.925
| Androlry Lab Short Walls Inside | 1 | 2 | 4.08 |  | 3.05 | 24.888
| Door Deductions(-) | -1 | 1 | 1.5 |  | 2.6 | -3.9
| Door Deductions(-) | -1 | 1 | 1 |  | 2.1 | -2.1
| Cryo Room Inside | 1 | 2 | 3 |  | 3.05 | 18.3
| do | 1 | 2 | 1.6 |  | 3.05 | 9.76
| Door Deductions | -1 | 1 | 1 |  | 2.1 | -2.1
| Staire Case area | 1 | 1 | 4.2 |  | 1.5 | 6.3
| Staire Case area | 1 | 2 | 4.2 |  | 1.5 | 12.6
| Window Deduction(-) | -1 | 1 | 1.8 |  | 1.5 | -2.7
| Dr. Change Room | 2 | 2 | 2.2 |  | 3.45 | 30.36
| Store Room | 1 | 2 | 3.18 |  | 3.45 | 21.942
| do | 1 | 2 | 2.18 |  | 3.45 | 15.042
| Door Deduction(-) | -1 | 2 | 0.8 |  | 2.1 | -3.36
| Change Rooms | 2 | 2 | 1.87 |  | 3.45 | 25.806
[7 empty] | 872.0934 | Sqm
67 | Providing and fixing in true horizontal level 14 mm - Mineral Fiber sheet 595 x 595 Square / Tegular Fissura fine model edge tiles with a Humidity Resistance of 90percentage RH, Average NRC 0.50, Light Reflectance greater than80percentage, Thermal Conductivity equal to 0.052 to 0.057 w/mk, Fire Performance Class 0/Class 1 using hot dipped Galvanized Steel section exposed surface with pre-coated capping, main Tee of size 24 x 32 mm at every 1200 mm c/c maximum and rotary stitched cross tee of size 24 x 27 mm at every 600 mm c/c and sub-cross tee of size 24 mm x 25 mm at 1200 mm c/c and wall angle of size 19 x 19 mm fixed to periphery of the wall and the above grid is suspended at every 1200 mm c/c in both directions using 2.0 mm thick pre-straightened GI Wire including cost and conveyance of all materials and labour charges such as cutting , fixing of standing of frame work exposing roof making etc., complete for finished item of work in 5th floor. at Gandhi Hospital
| Main Entry Corridor | 1 | 1 | 6.3 | 2.94 |  | 18.522
| Corridor at Reception | 1 | 1 | 3 | 3 |  | 9
| Reception | 1 | 1 | 3.4 | 3 |  | 10.2
| Record Room | 1 | 1 | 3.2 | 3 |  | 9.6
| Corridor at Prepost Operative Wards | 1 | 1 | 6.3 | 3 |  | 18.9
| Corridor at Counseling Room 1 and 2 | 1 | 1 | 5.1 | 1.2 |  | 6.12
| do | 1 | 1 | 0.4 | 0.1 |  | 0.04
| Toilet | 1 | 1 | 1.5 | 1.2 |  | 1.8
| Ultra Sound Room | 1 | 1 | 3.2 | 3 |  | 9.6
| Auto Clave Room | 1 | 1 | 2.18 | 1.9 |  | 4.142
| Counseling Room 2 | 1 | 1 | 3.24 | 2.4 |  | 7.776
| Counseling Room 1 | 1 | 1 | 3.2 | 2.45 |  | 7.84
| Prepost Operative Wards | 1 | 1 | 6.48 | 6 |  | 38.88
| Toilet Area Deduction(-) | -1 | 1 | 2 | 2.1 |  | -4.2
| Column Deduction(-) | -1 | 1 | 0.53 | 0.53 |  | -0.2809
| Toilet | 1 | 1 | 1.7 | 1.2 |  | 2.04
| Corridor At Semi Sterile Area | 1 | 1 | 6.45 | 3 |  | 19.35
| Dr Chganhe Room | 1 | 1 | 4.7 | 4.68 |  | 21.996
| do | 1 | 1 | 4.8 | 0.1 |  | 0.48
| Dr Toilet | 1 | 1 | 4.68 | 1.85 |  | 8.658
| Change Room Area | 1 | 1 | 6.45 | 3.07 |  | 19.8015
| Store Room | 1 | 1 | 3.3 | 2.58 |  | 8.514
| Blood Collection Room | 1 | 1 | 3.3 | 2.58 |  | 8.514
| Sperm Collection Room | 1 | 1 | 3.3 | 3.27 |  | 10.791
| Sterm Collection Toilet | 1 | 1 | 1.6 | 1.1 |  | 1.76
| Manifold Room | 1 | 1 | 3.185 | 2.13 |  | 6.784
| Deductions Column | -1 | 1 | 0.68 | 0.68 |  | -0.4624
| Minor OT | 1 | 1 | 6.4 | 4.2 |  | 26.88
| Corridor at Sterile area | 1 | 1 | 6.3 | 3 |  | 18.9
| Scrub Area | 1 | 1 | 3.53 | 0.68 |  | 2.4004
| Andrology Lab | 1 | 1 | 4.13 | 4.1 |  | 16.933
| Cryo room | 1 | 1 | 3 | 1.6 |  | 4.8
[7 empty] | 316.0786 | Sqm
93 | Providing Laying of scratch proof PVC/vinyl flooring of 2mm thickness with proper welded joints air tight along with leveling compound to match the existing flooring levels as per the engineer in charge instructions. Sub floor preparation with self leveling compound. After the sub floor preparation, it should be suitable for ESD Flooring.Rate inclusive of sifting of material and labour charges.at Gandhi Hospital
| Minor OT | 1 | 1 | 6.4 | 4.2 |  | 26.88
| Door Mat | 1 | 1 | 1.5 | 0.23 |  | 0.345
| Corridor at Sterile area | 1 | 1 | 6.3 | 3 |  | 18.9
| Deductions Air Shower(-) | -1 | 1 | 0.5 | 1.71 |  | -0.855
| Major OT | 1 | 1 | 6.48 | 4.05 |  | 26.244
| Door mat | 1 | 1 | 1.5 | 0.23 |  | 0.345
| do | 1 | 1 | 0.39 | 1.5 |  | 0.585
| Embrology Lab | 1 | 1 | 6.48 | 4.3 |  | 27.864
| Door mat | 1 | 1 | 1.5 | 0.1 |  | 0.15
| Scrub Area | 1 | 1 | 3.53 | 0.68 |  | 2.4004
| Andrology Lab | 1 | 1 | 4.13 | 4.1 |  | 16.933
| Door Mat | 1 | 1 | 1.5 | 0.1 |  | 0.15
| Cryo room | 1 | 1 | 3 | 1.6 |  | 4.8
| Door mat | 1 | 1 | 1 | 0.1 |  | 0.1
[7 empty] | 124.8414 | Sqm
52 | Conveyance of un- useful excavated earth to a distance of 21 km for disposal including hire charges of T and P, labour charges etc,. Complete for finished item of work Dismantled Brick Masonary at Gandhi Hospital
| Brick Dismatleting | 1 | 1 |  |  |  | 31.21
| Reinforcement Concrete | 1 | 1 |  |  |  | 0.7
| Un Reinforcement Concrete | 1 | 1 |  |  |  | 3.89
| Old cement Removal | 1 | 1 |  |  |  | 37.13
[7 empty] | 72.93 | Cum
160 | SITC of Factory fabricated and boxed ducting using Aluminium Sheets / coils, should be fabricated as per SMACNA, galvanised hardware and supports, silicon sealant at all longitudinal joints, Galvanized /GI Electroplated iron angle flanges for all the joints, bracing angles and minimum 5mm thick neoprene rubber gasket.- Duct pressure testing at 75mm to be carried oubefore insulatiting the duct. pressure testing to be done as per SMACNA. Procedure to be approved by consultant. 22G - 0.8 mm Thick at Gandhi Hospital
| Supply Duct 650 x 350 mm Terrace to Out side IVF OT | 1 | 6 | 1.23 | 2 |  | 14.76
| Elbow 650 x 350 mm | 1 | 1 | 0.95 | 2 |  | 1.9
| Straight 650 x 350 mm | 1 | 1 | 0.75 | 2 |  | 1.5
| Straight 650 x 350 mm | 1 | 8 | 1.23 | 2 |  | 19.68
| Elbow 650 x 350 mm OT Entry | 1 | 1 | 0.95 | 2 |  | 1.9
| Straight 650 x 350 mm OVF OT Inside | 1 | 7 | 1.23 | 2 |  | 17.22
| Straight 650 x 350 mm OVF OT Inside | 1 | 1 | 0.75 | 2 |  | 1.5
| Straight 650 x 350 mm OVF OT Inside | 1 | 1 | 1.05 | 2 |  | 2.1
| Straight 650 x 350 mm OVF OT Inside | 1 | 2 | 0.65 | 2 |  | 2.6
| Straight 200 x 350 mm OVF OT Inside | 1 | 1 | 0.65 | 1.1 |  | 0.715
| Dummy IVF OT 300 x 475mm | 1 | 1 | 0.3 |  | 0.45 | 0.135
| Embryology Supply 475 x 350 x 475 x 300 mm Tapper | 1 | 1 | 1.1 | 1.55 |  | 1.705
| Straight 475 x 300 mm Inside | 1 | 2 | 1.23 | 1.5 |  | 3.69
| Straight 475 x 300 mm Inside | 1 | 1 | 0.9 | 1.5 |  | 1.35
| Straight 650 x 300 mm Inside | 1 | 1 | 0.65 | 1.9 |  | 1.235
| Straight 250 x 300 mm Inside | 1 | 1 | 0.65 | 1.1 |  | 0.715
| Straight 300 x 300 x 300 x 175 mm Inside | 1 | 1 | 0.9 | 1.05 |  | 0.945
| Dummy 400 x 400 mm | 1 | 1 | 0.4 |  | 0.4 | 0.16
| Straight 350 x 300 mm | 1 | 1 | 1.23 | 1.3 |  | 1.599
| Straight 350 x 300 mm | 1 | 1 | 0.65 | 1.3 |  | 0.845
| Straight 350 x 300 mm | 1 | 1 | 1.43 | 1.3 |  | 1.859
| Dummy 475 x 400mm | 1 | 1 | 0.45 |  | 0.4 | 0.18
| Return Duct Terrace to IVF OT Out side 750 x 300 mm | 1 | 4 | 1.23 | 2.1 |  | 10.332
| Elbow 750 x 300 mm Out Side | 1 | 1 | 1.05 | 2.1 |  | 2.205
| Straight 750 x 300 mm Outside | 1 | 4 | 1.23 | 2.1 |  | 10.332
| Elbow 750 x 300 mm Out Side | 1 | 1 | 1.05 | 2.1 |  | 2.205
| Straight 750 x 300 mm Outside | 1 | 8 | 1.23 | 2.1 |  | 20.664
| Elbow 750 x 300 mm Out Side | 1 | 1 | 1.05 | 2.1 |  | 2.205
| Lab Entry Straight 750 x 300 mm | 1 | 9 | 1.23 | 2.1 |  | 23.247
| Straight 750 x 300 mm Embryology Inside | 1 | 1 | 0.7 | 2.1 |  | 1.47
| Tapper 750 x 300 x 525 x 300 mm | 1 | 1 | 0.9 | 1.85 |  | 1.665
| Straight 525 x 300 mm Embryology Inside | 1 | 4 | 1.23 | 1.6 |  | 7.872
| Straight 525 x 300 mm IVF OT Inside | 1 | 1 | 0.7 | 1.6 |  | 1.12
| Elbow 525 x 300 IVF OT Inside | 1 | 1 | 0.65 | 1.6 |  | 1.04
| Straight 525 x 300 mm IVF OT Inside | 1 | 4 | 1.23 | 1.6 |  | 7.872
| Straight 525 x 300 mm IVF OT Inside | 1 | 2 | 0.7 | 1.6 |  | 2.24
| Straight 625 x 175 mm IVF OT Inside | 1 | 6 | 2.67 | 1.5 |  | 24.03
| Modular Connections Embryology Lab 650 x 250 mm | 1 | 3 | 1.9 | 1.8 |  | 10.26
| Modular Connections IVF OT 650 x 250 mm | 1 | 3 | 1.9 | 1.8 |  | 10.26
| Riser Connection Embryology Lab 800 x 175 mm | 1 | 3 | 1.13 | 1.9 |  | 6.441
| Riser Connection IVF OT 800 x 175 mm | 1 | 3 | 1.13 | 1.9 |  | 6.441
[7 empty] | 230.194 | Sqm
156 | SITC of 20/21 G hard drawn copper refrigerant piping with all fittings, supports, insulation with 19 mm thk class O nitrile rubber insulation with factory laminated glass cloth for physical protection and UV protection etc. Quality of copper piping fittings shall be suitable for 18 G piping. Copper piping shall be clamped at every 1.5 mt. distance. copper piping shall be laid on inverted GI perforated cable trays and clamps as per specification inside the building. Copper piping on the terrace shall be laid with bottom and top cable tray. Thickness of the tray shall be 1.6 mm. Copper pipe size shall be as per OEM standards. Suction Line at Gandhi Hospital
| From AHU to Condensing Unit | 1 | 1 | 12 |  |  | 12
[7 empty] | 12 | Rmt
155 | SITC of 20/21 G hard drawn copper refrigerant piping with all fittings, supports, insulation with 19 mm thk class O nitrile rubber insulation with factory laminated glass cloth for physical protection and UV protection etc. Quality of copper piping fittings shall be suitable for 18 G piping. Copper piping shall be clamped at every 1.5 mt. distance. copper piping shall be laid on inverted GI perforated cable trays and clamps as per specification inside the building. Copper piping on the terrace shall be laid with bottom and top cable tray. Thickness of the tray shall be 1.6 mm. Copper pipe size shall be as per OEM standards. Liquid Line at Gandhi Hospital
| From AHU to Condensing Unit | 1 | 1 | 10 |  |  | 10
[7 empty] | 10 | Rmt
158 | SITC of CPVC drain ping with supports, clamps and 9 mm thk. Nitrile rubber tube insulation of the following sizes. Insulation shall have factory laminated glass cloth. 25mm Dia at Gandhi Hospital
| AHU Drain Outlet to Near Rain Water Pipe | 1 | 1 | 12 |  |  | 12
[7 empty] | 12 | Rmt
161 | Aluminium low leakage aerofoil design volume control dampers Suitable for manual and motorised operation At Gandhi Hospital
| AHU return 800 x 400 x 200 mm | 1 | 1 | 0.2 | 2.4 |  | 0.48
| AHU Supply 700 x 400 x 200 | 1 | 1 | 0.2 | 2.2 |  | 0.44
| AHU Fresh Air 400 x 400 x 200 mm | 1 | 1 | 0.2 | 1.6 |  | 0.32
[7 empty] | 1.24 | Sqm
162 | CBRI approved 16G GI Spring return actuated fire dampers rated for 90 minutes with limit switch. At Gandhi Hospital
| AHU Return Air Damper 750 x 350 x 200mm | 1 | 1 | 0.2 | 2.2 |  | 0.44
| AHU Supply 650 x 350 x 200 mm | 1 | 1 | 0.2 | 2 |  | 0.4
[7 empty] | 0.84 | Sqm
163 | SITC of SS perforated return raiser grilles with 10 microns filters with collar dampers At Gandhi Hospital
| IVF-OT SS Perforated 740 x 740 mm (Dummy) | 1 | 3 | 0.74 |  | 0.74 | 1.6428
| Embryology SS Perforated 740 x 740 mm (Dummy) | 1 | 3 | 0.74 |  | 0.74 | 1.6428
[7 empty] | 3.2856 | Sqm
164 | Extruded Al. powder coated EXHAUST / RETURN discrete grilles At Gandhi Hospital
| IVF-OT 630 x 330 mm (Dummy) | 1 | 3 | 0.63 |  | 0.33 | 0.6237
| Embryology 630 x 330 mm (Dummy) | 1 | 3 | 0.63 |  | 0.33 | 0.6237
[7 empty] | 1.2474 | Sqm
165 | SITC of Collar Dampers made of Al. extrusions with black powder coating for Grilles / Diffusers At Gandhi Hospital
| IVF-OT 800x 175 mm (Dummy) | 1 | 3 | 0.8 |  | 0.15 | 0.36
| Embryology 800 x 175 mm (Dummy) | 1 | 3 | 0.8 |  | 0.15 | 0.36
[7 empty] | 0.72 | Sqm
168 | SITC of Aluminium powder coated Fresh air and Exhaust Louvers of nonvision type with nylon mosquito net etc. At Gandhi Hospital
| Terrace Dresh Air Exhaust Louver 350 x 350 mm | 1 | 1 | 0.35 |  | 0.35 | 0.1225 | Sqm
169 | Supply, laying of Class O Nitrile rubber with factory laminated Glass cloth, all joints shall be covered with self-adhesive tapes 32mm Thick for Exposed Supply Air duct and finished with UV Protective Paint. at Gandhi Hospital
| Supply Duct 682 x 382 mm Terrace to Out side IVF OT | 1 | 6 | 1.43 | 2.252 |  | 19.3222
| Elbow 682 x 382 mm | 1 | 1 | 1.15 | 2.252 |  | 2.5898
| Straight 682 x 382 mm | 1 | 1 | 0.95 | 2.252 |  | 2.1394
| Straight 682 x 382 mm | 1 | 8 | 1.43 | 2.252 |  | 25.7629
| Elbow 682 x 382 mm OT Entry | 1 | 1 | 1.15 | 2.252 |  | 2.5898
| Straight 682 x 382 mm OVF OT Inside | 1 | 7 | 1.43 | 2.252 |  | 22.5425
| Straight 682 x 382 mm OVF OT Inside | 1 | 1 | 0.95 | 2.252 |  | 2.1394
| Straight 682 x 382 mm OVF OT Inside | 1 | 1 | 1.15 | 2.252 |  | 2.5898
| Straight 682 x 382 mm OVF OT Inside | 1 | 2 | 0.85 | 2.252 |  | 3.8284
| Straight 232 x 382 mm OVF OT Inside | 1 | 1 | 0.85 | 1.412 |  | 1.2002
| Modular Connections Embryology Lab 714 x 314 mm | 1 | 3 | 1.9 | 1.8 |  | 10.26
| Modular Connections IVF OT 714 x 314 mm | 1 | 3 | 1.9 | 1.8 |  | 10.26
| Riser Connection Embryology Lab 864 x 214 mm | 1 | 3 | 1.13 | 2.156 |  | 7.3088
| Riser Connection IVF OT 864 x 214 mm | 1 | 3 | 1.13 | 2.156 |  | 7.3088
[7 empty] | 119.842 | Sqm
170 | Supply, laying of Class O Nitrile rubber with factory laminated Glass cloth, all joints shall be covered with self-adhesive tapes 25mm Thick for Exposed Return Air Duct and finished with UV Protective Paint. at Gandhi Hospital
| Return Duct Terrace to IVF OT Out side 750 x 325 mm | 1 | 4 | 1.33 | 2.3 |  | 12.236
| Elbow 750 x 325 mm Out Side | 1 | 1 | 1.15 | 2.3 |  | 2.645
| Straight 750 x 325 mm Outside | 1 | 4 | 1.33 | 2.3 |  | 12.236
| Elbow 750 x 325 mm Out Side | 1 | 1 | 1.15 | 2.3 |  | 2.645
| Straight 750 x 325 mm Outside | 1 | 8 | 1.33 | 2.3 |  | 24.472
| Elbow 750 x 325 mm Out Side | 1 | 1 | 1.15 | 2.3 |  | 2.645
| Lab Entry Straight 750 x 325 mm | 1 | 9 | 1.33 | 2.3 |  | 27.531
[7 empty] | 84.41 | Sqm
171 | Supply, laying of Class O Nitrile rubber with factory laminated Glass cloth, all joints shall be covered with self-adhesive tapes 25mm Thick for Supply air duct running inside the building. at Gandhi Hospital
| Dummy IVF OT 325 x 475mm | 1 | 1 | 0.325 |  | 0.475 | 0.15437
| Embryology Supply 475 x 350 x 475 x 325 mm Tapper | 1 | 1 | 1.2 | 1.75 |  | 2.1
| Straight 475 x 325 mm Inside | 1 | 2 | 1.33 | 1.7 |  | 4.522
| Straight 475 x 325 mm Inside | 1 | 1 | 1 | 1.7 |  | 1.7
| Straight 650 x 325 mm Inside | 1 | 1 | 0.75 | 2.1 |  | 1.575
| Straight 250 x 325 mm Inside | 1 | 1 | 0.75 | 1.3 |  | 0.975
| Straight 325 x 325 x 325 x 175 mm Inside | 1 | 1 | 1 | 1.25 |  | 1.25
| Dummy 425 x 425 mm | 1 | 1 | 0.425 |  | 0.425 | 0.18062
| Straight 350 x 325 mm | 1 | 1 | 1.33 | 1.5 |  | 1.995
| Straight 350 x 325 mm | 1 | 1 | 0.75 | 1.5 |  | 1.125
| Straight 350 x 325 mm | 1 | 1 | 1.53 | 1.5 |  | 2.295
| Dummy 475 x 425mm | 1 | 1 | 0.475 |  | 0.425 | 0.20187
| Straight 750 x 325 mm Embryology Inside | 1 | 1 | 0.8 | 2.3 |  | 1.84
| Tapper 750 x 325 x 525 x 325 mm | 1 | 1 | 1 | 2.05 |  | 2.05
| Straight 525 x 325 mm Embryology Inside | 1 | 4 | 1.33 | 1.8 |  | 9.576
| Straight 525 x 325 mm IVF OT Inside | 1 | 1 | 0.8 | 1.8 |  | 1.44
| Elbow 525 x 325 IVF OT Inside | 1 | 1 | 0.75 | 1.8 |  | 1.35
| Straight 525 x 325 mm IVF OT Inside | 1 | 4 | 1.33 | 1.8 |  | 9.576
| Straight 525 x 325 mm IVF OT Inside | 1 | 2 | 0.8 | 1.8 |  | 2.88
| Straight 625 x 175 mm IVF OT Inside | 1 | 6 | 2.77 | 1.7 |  | 28.254
[7 empty] | 75.0399 | Sqm
172 | Supply, laying of Class O Nitrile rubber with factory laminated Glass cloth, all joints shall be covered with self-adhesive tapes 19mm Thick for Return air running inside the building. at Gandhi Hospital
| TDF Flange Insulation at Embryology Lab | 1 | 16 | 1.5 | 0.2 |  | 4.8 | Sqm
| TDF Flange Insulation at IVF-OT | 1 | 16 | 1.9 | 0.2 |  | 6.08 | Sqm
| TDF Flange Insulation at Exposed Area | 1 | 22 | 1.9 | 0.2 |  | 8.36 | Sqm
[7 empty] | 19.24 | Sqm
Sup | Supply & Installation of MS Angle for Duct Support, Cable Tray Support and Condensing Unit Stand of size 40 X 40 x 5 mm Thick.
| Condensing Unit-1 Supports Long Direction | 1 | 2 | 1.37 |  |  | 2.74
| Condensing Unit-1 Supports Short Direction | 1 | 2 | 0.33 |  |  | 0.66
| Legs | 1 | 4 | 0.32 |  |  | 1.28
| Square Plate 100 x 100 x 5mm Thick | 1 | 4 | 0.1 | 0.1 |  | 0.04
| Condensing Unit-2 Supports Long Direction | 1 | 2 | 1.37 |  |  | 2.74
| Condensing Unit-2 Supports Short Direction | 1 | 2 | 0.33 |  |  | 0.66
| Legs | 1 | 4 | 0.32 |  |  | 1.28
| Square Plate 100 x 100 x 5mm Thick | 1 | 4 | 0.1 | 0.1 |  | 0.04
| Cable Tray Supports Legs | 1 | 8 | 0.4 |  |  | 3.2
| Horizontals | 1 | 4 | 0.3 |  |  | 1.2
| Plate 75 mm Dia | 1 | 8 | 0.0044156 |  |  | 0.035325
| AHU Supply duct supports legs | 1 | 4 | 0.8 |  |  | 3.2
| AHU Supply duct supports legs | 1 | 2 | 0.9 |  |  | 1.8
| AHU Supply duct supports legs | 1 | 4 | 1.95 |  |  | 7.8
| Horizontals | 1 | 5 | 0.8 |  |  | 4
| Plate 75 mm Dia | 1 | 10 | 0.0044156 |  |  | 0.044156
[7 empty] | 30.7195 | 92.1584 | Kgs
Sup | Supply & Installation of MS Angle for Duct Support, Cable Tray Support and Condensing Unit Stand of size 25 X 25 x 5 mm Thick.
| AHU Return Duct Support Legs | 1 | 12 | 0.75 |  |  | 9
| Horizontals | 1 | 6 | 0.85 |  |  | 5.1
` | Plate 75 mm Dia | 1 | 12 | 0.0044156 |  |  | 0.052988
[7 empty] | 14.153 | 25.4754
Sup | Supply and installation of Canvas Connections For AHUS
| 750 x 350 Supply for AHU | 1 | 1 |  |  |  | 1
| 800 x 400 Return For AHU | 1 | 1 |  |  |  | 1
[7 empty] | 2 | Nos
Sup | 4C x 1.5 Sqmm Copper Flexible Cable For Condensing Unit to Electrical Panel
| Condensing unit to Electrical Panel | 1 | 1 | 22.4 |  |  | 22.4
| Electrical Panel to Heater | 1 | 1 | 21.5 |  |  | 21.5
| AHU to Electrical Panel | 1 | 1 | 30.2 |  |  | 30.2
[7 empty] | 74.1 | Rmt
Sup | Supply & installation of 50x6 GI flat for AHU Copper Pipe which is laid in 300mm cable tray
| AHU To Condensing Unit-1 | 1 | 1 | 2.3 |  |  | 2.3
| Condensing Unit-1 to Condensing Unit-2 | 1 | 1 | 1.65 |  |  | 1.65
[7 empty] | 3.95 | Rmt
87 | Supply and instalaion of Wall Panels 80mm thick double skin Modular wall panels made of .8mm Powder Coated GI on both sides, with 40 plus or minus 2 kg/cum demsity pUF as infill, GI profiles all along the periphery,flush on both sides with maximum allowable gap of 3-4mm filled with food grade silicon sealent and placed on cold rolled galvanised bottom tracks with a recess to provide floor to wall coving flush with the wall panel. This including all required hardware for completion panels to be covered with a protective film to avoid any damages during transpotation and installation at Gandhi Hispital
| IVF Ot Long Walls RHS | 1 | 1 | 6.17 |  | 2.55 | 15.7335
| Door Deduction(-) | -1 | 1 | 1.5 |  | 2.55 | -3.825
| Long Wall LHS | 1 | 1 | 6.17 |  | 2.55 | 15.7335
| Short Walls | 1 | 1 | 3.65 |  | 2.55 | 9.3075
| Short Wall Main Door Wall | 1 | 1 | 4.02 |  | 2.55 | 10.251
| Door Deduction(-) | -1 | 1 | 1.48 |  | 2.55 | -3.774
| Sides | 1 | 1 | 0.39 |  | 2.55 | 0.9945
| Door Sides | 1 | 2 | 0.32 |  | 2.55 | 1.632
| Embryology Lab Long Walls | 1 | 2 | 6.21 |  | 2.55 | 31.671
| Door Deduction(-) | -1 | 1 | 1.5 |  | 2.55 | -3.825
| Short Walls | 1 | 2 | 3.97 |  | 2.55 | 20.247
| Air Shower Sides | 1 | 2 | 0.5 |  | 2.6 | 2.6
[7 empty] | 96.746 | Sqm
88 | Supply and installtion of 50mm thick double skin cealing system made .8mm thich powder coated GI sheet on both sides, 40 plus or minus 2kg/cum density PUF ad infill, GI Profiles all along the periphery, panels flush towards room sides with maximum allowable gap of 3-4mm at panelto panel joints filled with silicon sealent ceiling panels are suspended from the RCC salb bu using concealed Aall ceiling grid with tie rod and adjestable turn bickle arrangement etc. This includes all required hardware for completition. panels to be covered with a protective film to avoid any damge during transpotation and installation at Gandhi Hospital.
| IVF OT | 1 | 1 | 6.17 | 3.65 |  | 22.5205
| do | 1 | 1 | 1.5 | 0.39 |  | 0.585
| do | 1 | 1 | 1.48 | 0.32 |  | 0.4736
| Columns Deduction(-) | -1 | 1 | 0.55 | 0.39 |  | -0.2145
| Embryology lab | 1 | 1 | 6.21 | 3.97 |  | 24.6537
[7 empty] | 48.0183 | Sqm
92 | Supply and installation of Extruded Aluminium Coving at Gndhi Hopital
| IVF Ot Long Walls RHS | 1 | 1 | 4.3 |  |  | 4.3
| do | 1 | 1 | 1.5 |  |  | 1.5
| do | 1 | 1 | 0.39 |  |  | 0.39
| Long Wall LHS | 1 | 1 | 6.16 |  |  | 6.16
| Sort Wall Main Door | 1 | 1 | 0.6 |  |  | 0.6
| do | 1 | 2 | 0.32 |  |  | 0.64
| do | 1 | 1 | 1 |  |  | 1
| do | 1 | 1 | 0.39 |  |  | 0.39
| do | 1 | 1 | 0.91 |  |  | 0.91
| Vertical Coving | 1 | 4 | 2.41 |  |  | 9.64
| Embryology Lab Long Walls | 1 | 2 | 6.21 |  |  | 12.42
| Short Walls | 1 | 2 | 3.97 |  |  | 7.94
| Vertical Coving | 1 | 4 | 2.42 |  |  | 9.68
| Pass Box Sides | 1 | 3 | 2.68 |  |  | 8.04
[7 empty] | 63.61 | Rmt
90 | Single leaf clean room door 46mm thick flush made of .8mm thick powedr coated GI sheet on both sides 90 pus or minus 2kg/cum density honeycomb with stand upto 220 deg.C temperature ,and compressible strength upto 400 kg/sqm,1.2mm thick GPSP door frames ,double glazed vision panel with necessary adhesive tapes and silicon swalent, necessary hardware like SS304 ball bearing butt hinges D- hnadles,push plates ,Dorma make door closer concealed tower bolt ,drop seals for the double leaf door and provision for fixing magnetic type door interlocking system and automatic door bottoms,BOth sides lock and key etc,. Complete .
| UPS Room (990 x 2280mm) | 1 | 1 |  |  |  | 1
| Cryo Room(1000 x 2250mm) | 1 | 1 |  |  |  | 1
| Auto Clave Room Single Shutter(980 x 2260mm) | 1 | 1 |  |  |  | 1
[7 empty] | 3 | Nos
89 | Double leaf clean room door 46mm thick flush made of .8mm thick powedr coated GI sheet on both sides 90 pus or minus 2kg/cum density honeycomb with stand upto 220 deg.C temperature ,and compressible strength upto 400 kg/sqm,1.2mm thick GPSP door frames ,double glazed vision panel with necessary adhesive tapes and silicon swalent, necessary hardware like SS304 ball bearing butt hinges D- hnadles,push plates ,Dorma make door closer concealed tower bolt ,drop seals for the double leaf door and provision for fixing magnetic type door interlocking system and automatic door bottoms,BOth sides lock and key etc,. Complete .
| Access Control Door (1490 x 2570mm) | 1 | 1 |  |  |  | 1
| Minor OT Door(1490 x 2570mm) | 1 | 1 |  |  |  | 1
| IVF OT Door (1450 x 2550mm) | 1 | 1 |  |  |  | 1
| Embryology lab Door(1500 x 2400mm) | 1 | 1 |  |  |  | 1
| Andrology Lab Door (1490 x 2580mm) | 1 | 1 |  |  |  | 1
[7 empty] | 5 | Nos
91 | Emergency Fire door 46mm thick flush made of .8mm thick powedr coated GI sheet on both sides 90 pus or minus 2kg/cum density honeycomb with stand upto 220 deg.C temperature ,and compressible strength upto 400 kg/sqm,1.2mm thick GPSP door frames ,double glazed vision panel with necessary adhesive tapes and silicon swalent, necessary hardware like SS304 ball bearing butt hinges D- hnadles,push plates ,Dorma make door closer concealed tower bolt ,drop seals for the double leaf door and provision for fixing magnetic type door interlocking system and automatic door bottoms,BOth sides lock and key etc,. Complete .
| Emergency Fire Door(1730 x 2610mm) | 1 | 1 |  |  |  | 1 | Nos
Sup | Providing of factory made prelaminated FPVC (Foamed Polyvinyl Chloride) Doors frame of the size 105 x 40 mm with a wall thickness of 10mm made out of extroded rigid FPVC profile mitre joined with 6 Nos. of 50mm long Screw. The Door frame shall be fixed to the wall by using 80mm long screws through the frame with the help of PVC fastners of 3 no's to be provuded for each vertical membr, GI Stiffenrs of ( "U" GI Channel of size 29 x 9 x 1 mm, 150mm long) - no's at hinge point, Frame reinforcement of ("U" GI Channel Of Size 46 x 22 .06mm), Bottom tie rod of ("U" GI Channel Size of 15 x15 1mm ) etc. complete as per the manufactures specification for finished item of work. Maximum door frame size :980 x 2070 including providing of 35mm thick factory made prelaminated ABS (Acrolynitrile Butadyne Styrene) Door shutter Moulded in Different designes,consisting of all round Frame made out of water proof solid foam PVC bar of size 20 x 32 mm, reinforced by 32 x 32 mm -2 no's for vertical made out of LVL (Laminated Veneer lumber) , core material of 32 mm thick high density craft paper honey comb board, sandwiched on both sides with prelaminated ABS sheet thickness of 1.5mm. PVC edge banding of size .45 mm on the vertcal sides. Hardware made out of steel coated butterfly hinges -3 No's. for each shutter and ISI make S.S round lock completes for finished item of work. maximum shutter of: 910 x 1030mm
| Prepost Oreraive Wards Double Shutter Door | 1 | 1 | 1.48 |  | 2.57 | 3.8036
| Store Room | 1 | 1 | 0.99 |  | 2.095 | 2.0741
| Manifold Room Single Shutter | 1 | 1 | 1.01 |  | 2.29 | 2.3129
| Sperm Collection Room Single Shutter | 1 | 1 | 0.978 |  | 2.27 | 2.2201
| Blood Collection Room Single Shutter | 1 | 1 | 0.991 |  | 2.26 | 2.2397
| Counseling Room1 | 1 | 1 | 1.08 |  | 2.25 | 2.43
| Counseling Room2 | 1 | 1 | 1.07 |  | 2.24 | 2.3968
| Ultra Sound Room Single Shutter Door | 1 | 1 | 1.2 |  | 2.37 | 2.844
| Record Room | 1 | 1 | 1.2 |  | 2.35 | 2.82
[7 empty] | 23.1411 | Sqm
Sup | WPC Doors
| Toilet At Counseling Room | 1 | 1 | 0.8 |  | 2.1 | 1.68
| Toilet at Wards | 1 | 1 | 0.8 |  | 2.1 | 1.68
| Sperm Collection Toilet | 1 | 1 | 0.8 |  | 2.1 | 1.68
| Dr. Toilet | 1 | 1 | 1 |  | 2.1 | 2.1
[7 empty] | 7.14 | Sqm
61 | Supplying and fixing of Unplasticised Poly Vinyl Chloride UPVC 3 track sliding windows with mesh shutter – 2-glass shutters and 1-mesh shutter duly manufactured using UPVC reinforced profiles Composition of profile shall consists a minimum of 5.5 PHR of TiO2 and not more than 12 PHR of CaCo3 for every 100 parts of PVC resin of 94mm x 45 mm/80 mm x 52 mm x 2.20 mm for outer frames, 58 mm x 39 mm/54 mm x 38 mm x 2.20mm for sliding shutter frames capable of mounting single glazing system structurally reinforced with hot dip galvanized up to 50 microns of minimum thickness of 1.0/1.2 mm prefabricated and welded through fusion welding. The window sash shall be fitted with 5 mm thick clear float glass of reputed make and mesh shutter frame shall be 42 mm x 25mm/52 mm x 21.5 mm x 2.0 mm fitted with Vinyl Coated Fiber mesh- on rollers/ pulley duly fixed with Grey colour TPV Gasket for sash and Glazing bead shall be co extruded with Grey colour soft PVC. System shall have single point locking with Touch Lock and the system is to be installed at the site using anchor fasteners, silicon rubber sealant, easy glazing/deglazing at site etc., including cost and conveyance of all materials, accessories, labour charges for transportation, erection at site includingetc., complete for finished item of work. at Gandhi Hospital
| UPS Room | 1 | 1 | 1.5 |  | 1.8 | 2.7
| Sperm Collection and Blood Collection | 1 | 1 | 3.05 |  | 0.4 | 1.22
| Blood Collection and Autoclave Room | 1 | 1 | 3.15 |  | 0.4 | 1.26
| Prepost Operative Wards | 1 | 1 | 1.5 |  | 1.8 | 2.7
[7 empty] | 7.88 | Sqm
62 | Providing, supplying and fixing of Fixed Louvered Ventilator made out of multi chambered uPVC sections with Glazing bead shall be co-extruded with Grey colour soft PVC. having isolated drainage and reinforced with Galvanized Iron profiles throughout the window. The outer frame having an overall size of 60 mm x 55 mm x 2.40 with reinforcement of 1 mm thickness and Mullion with overall size of 74 mm x 60 mm x 2.40 mm with reinforcement of 1 mm thickness. Composition of profile shall consists a minimum of 5.5 PHR of TiO2 and not more than 12 PHR of CaCo3 for every 100 parts of PVC resin. Ventilator shall be provided with 4.5 mm Pin Head glass, standard hardware. Wall thickness of frame and Mullion shall be 2.4 mm., including cost and conveyance of all materials, accessories, labour charges for transportation, erection at site etc., complete for finished item of work hinges IS:205 150mm long, 1 No. aldrop IS:2681 300mm long, 1 No. tower bolt IS:204 of 200 mm x 10 mm dia at top, 2 Nos. 150 mm at Gandhi Hospital
| Counseling Room | 1 | 1 | 0.585 |  | 0.5 | 0.2925
| Manifold Room | 1 | 1 | 0.585 |  | 0.505 | 0.29542
| Pre/post Operative Ward Toilet | 1 | 1 | 0.599 |  | 0.514 | 0.30789
| Dr. Toilet | 1 | 1 | 0.601 |  | 0.561 | 0.33716
| Cryo Room | 1 | 1 | 0.593 |  | 0.5 | 0.2965
[7 empty] | 1.5295 | Sqm
55 | Providing Mild steel MS steel bars Fe 250 grade as per IS 432 of different diameters including labour charges for straightening, cutting, bending to required sizes and shapes, placing in position with cover blocks of approved materials and size and tying and lap-splicing with binding wire of 18 SWG, forming grills for reinforcement work as per approved designs and drawings, including cost and conveyance of steel bars, including all wastages such as overlaps, couplings, chairs, spacer bars including cost and conveyance of binding wire, cover blocks and all incidental, operational, labour charges such as cutting, bending, placing in position, tying including sales and other taxes on all materials etc. , complete for finished item of work. TSSS No.126 For RBM walls 6mm dia: 5th Floor at Gandhi Hospital
| Prepost Opetative Wards | 1 | 1 | 1.5 |  | 1.8 | 2.7
| Counseling Room | 1 | 1 | 1.5 |  | 1.8 | 2.7
| Sperm Collection Room | 1 | 1 | 1 |  | 1.8 | 1.8
[7 empty] | 7.2 | Sqm