## Sheet1
DETAILED MEASUREMENTS
| Name of the work:Design, Fabriction, establishing and commissioning of In - Vitro ferility centers (IVFC) alongwith allied Services on Turnkey basis at Gandhi hospital secunderabad. | [8 empty] | Agency: M/s. Asta vardhman Consortium | [5 empty] | Agt.No: 344/A/TSMIDC/Spl.Proj/IVFCs/2022-23, Dt. 05.07.2023
S.No | Discription Of Work etc., | Measurements Upto date | [5 empty] | Rate |  |  | Per | Total Volume |  | Deduct/previous Measurements |  | Since last measurement |  |  | Remarks
|  | No |  | L | B | D | Content | Units | Rs | Ps. |  | Rs. | Ps | P.No. | Qty. | Qty | Value
[17 empty] | Rs. | Ps.
Floor Chipping
1 | Waiting area | 1 | 1 | 8 | 4.7 |  | 37.6
2 | Reception | 1 | 1 | 3.18 | 4.6
3 | Sample and Injection Room | 1 | 1 | 4.48 | 3.25
4 | Corridor @ Reception | 1 | 1 | 7.5 | 1.8
5 | Counselling Room 1,2 & Ultrasound Room | 1 | 1 | 10.4 | 6.5
6 | Patient Change Room | 1 | 1 | 3.5 | 1.8
7 | Toilet @ Electrical Room | 1 | 1 | 1.44 | 1.2
8 | Electrical Room | 1 | 1 | 3 | 3.4
9 | Pre/Post Operative Ward | 1 | 1 | 7.95 | 5
10 | Corridor @ Pre/Post Operative | 1 | 1 | 7.9 | 1.8
11 | Corridor from Embryology to Andrology | 1 | 1 | 21.3 | 1.7
12 | Embryologist Room | 1 | 1 | 4.77 | 4.5
13 | Change Rooms Toilets | 1 | 1 | 16.55 | 4.78
14 | Minor OT | 1 | 1 | 6.87 | 4.47
15 | Minor OT to Manifold corridor | 1 | 1 | 14.48 | 1.7
16 | IVF-OT | 1 | 1 | 7 | 4.45
17 | Embryology and Manifold | 1 | 1 | 7 | 4.45
Wall cladding removal
1 | Waiting area | 1 | 2 | 4.36 | 1.5
|  | 1 | 2 | 0.5 | 1.97
|  | 1 | 1 | 4.7 | 1.5
|  | 1 | 1 | 3.2 | 1.5
|  | 1 | 1 | 4.7 | 1.97
|  | 1 | 1 | 8 | 1.5
| wall top | 1 | 1 | 4.7 | 0.3
|  | 1 | 1 | 4.6 | 0.3
|  | 1 | 1 | 8 | 0.3
2 | Reception | 1 | 1 | 3.18 | 4.6
|  | 1 | 1 | 4.6 |  | 0.82
|  | 1 | 1 | 3.9 | 0.3
|  | 1 | 1 | 0.35 |  | 1.14
|  | 1 | 1 | 3.18 |  | 1.95
| Window Deduction (-) | -1 | 1 | 1.8 |  | 1.3
|  | -1 | 1 | 4.58 |  | 1.95
|  | -1 | 1 | 1.2 |  | 1.95
3 | Sample and Injection Room | 1 | 2 | 4.6 |  | 1.95
| Door Deduction (-) | -1 | 1 | 1.2 |  | 1.95
|  | 1 | 2 | 3.25 |  | 1.95
| Window Deduction (-) | -1 | 1 | 1.8 |  | 1.3
| Corridor @ Reception | 1 | 1 | 4 |  | 1.95
4 | Patient Change Room | 1 | 2 | 2.14 |  | 1.95
|  | 1 | 1 | 1.8 |  | 1.95
| Window Deduction (-) | -1 | 1 | 1.2 |  | 1.2
5 | Toilet @ Electrical Room | 1 | 2 | 1.44 |  | 1.47
|  | 1 | 2 | 1.2 |  | 1.47
| Door Deduction (-) | -1 | 1 | 0.8 |  | 1.47
|  | 1 | 2 | 1.17 |  | 1.95
| Door Deduction (-) | -1 | 1 | 0.8 |  | 1.95
|  | 1 | 2 | 1.82 |  | 1.95
| Door Deduction (-) | -1 | 1 | 1 |  | 1.95
|  | -1 | 1 | 1.18 |  | 1.95
|  | 1 | 2 | 0.3 |  | 1.95
6 | Electrical Room | 1 | 2 | 3.4 |  | 1.95
| Window Deduction (-) | -1 | 1 | 1.8 |  | 1.2
|  | 1 | 2 | 3 |  | 1.95
| Window Deduction (-) | -1 | 1 | 1.8 |  | 1.2
| Door Deduction (-) | -1 | 1 | 1 |  | 1.95
7 | Pre/Post Operative Ward | 1 | 2 | 5 |  | 1.95
| Door Deduction (-) | -1 | 1 | 1.2 |  | 1.95
|  | 1 | 1 | 7.95 |  | 1.95
| Window Deduction (-) | -1 | 2 | 1.8 |  | 1.2
|  | 1 | 2 | 0.3 |  | 1.95
8 | Corridor @ Pre/Post Operative | 1 | 1 | 7.9 |  | 1.8
|  | 1 | 1 | 0.4 |  | 1.95
|  | 1 | 1 | 0.1 |  | 1.95
9 | Corridor from Embryology to Andrology | 1 | 1 | 21.3 |  | 1.95
| Door Deduction (-) | -1 | 1 | 1 |  | 1.95
| Window Deduction (-) | -1 | 5 | 1.8 |  | 1.2
| Door Deduction (-) | -1 | 1 | 1.74 |  | 1.95
|  | 1 | 1 | 10.16 |  | 0.9
|  | 1 | 1 | 5.7 |  | 1.95
10 | Embryologist Room | 1 | 2 | 4.77 |  | 1.95
| Door Deduction (-) | -1 | 1 | 1 |  | 1.95
| Window Deduction (-) | -1 | 2 | 1.8 |  | 1.2
|  | 1 | 2 | 4.5 |  | 1.95
11 | Change Rooms Toilets | 1 | 2 | 16.55 |  | 1.95
| Window Deduction (-) | -1 | 8 | 1.8 |  | 1.2
|  | 1 | 6 | 4.78 |  | 1.95
|  | 1 | 8 | 0.46 |  | 1.95 | [12 empty] | columns
12 | Minor OT | 1 | 2 | 6.87 |  | 1.95
| Door Deduction (-) | -1 | 2 | 1 |  | 1.95
| Window Deduction (-) | -1 | 2 | 1.8 |  | 1.2
|  | 1 | 2 | 0.42 |  | 1.95 | [12 empty] | columns
|  | 1 | 2 | 4.47 |  | 1.95
| Window Deduction (-) | -1 | 1 | 1.8 |  | 1.2
13 | Minor OT to Manifold corridor | 1 | 1 | 9.16 |  | 1.95
| Door Deduction (-) | -1 | 2 | 1 |  | 1.95
|  | 1 | 1 | 7.6 |  | 0.9
14 | IVF-OT | 1 | 2 | 7 |  | 1.95
|  | -1 | 2 | 1 |  | 1.95
|  | -1 | 2 | 1.8 |  | 1.2
|  | 1 | 4 | 4.45 |  | 1.95
15 | Dead End | 1 | 4 | 1.8 |  | 1.95
16 | Embryology and Manifold | 1 | 1 | 7 |  | 1.95
|  | 1 | 1 | 3.67 |  | 1.95
| Window Deduction (-) | -1 | 2 | 1.8 |  | 1.2
|  | 1 | 2 | 4.45 |  | 1.95
| Window Deduction (-) | -1 | 1 | 1.8 |  | 1.2
|  | 1 | 2 | 0.5 |  | 1.95 | [12 empty] | columns
Granite Removal
1 | Waiting area | 1 | 1 | 3.5 | 0.5
|  | 1 | 1 | 4.3 | 0.5
|  | 1 | 1 | 7.57 | 0.5
|  | 1 | 1 | 4.22 | 0.5
2 | Pre/Post Operative Ward | 1 | 1 | 17 | 0.6
3 | Corridor @ Pre/Post Operative | 1 | 1 | 7.9 | 0.3
4 | Corridor from Embryology to Andrology | 1 | 1 | 10.16 | 0.3
5 | Minor OT to Manifold corridor | 1 | 1 | 7.6 | 0.3
Brick Demolition
1 | Waiting area | 1 | 1 | 1.6 | 0.23 | 1.5
|  | 1 | 17 | 0.5 | 0.15 | 0.45
|  | 1 | 3 | 0.45 | 0.45 | 0.45
2 | Sample and Injection Room | 1 | 1 | 1 | 0.1 | 2.3
3 | Corridor @ Reception | 1 | 1 | 1.8 | 0.23 | 2.5
4 | Toilet @ Electrical Room | 1 | 1 | 1.3 | 0.1 | 2.5
| Door Deduction (-) | -1 | 1 | 1 | 0.1 | 2.5
5 | Pre/Post Operative Ward | 1 | 17 | 0.5 | 0.15 | 0.5
6 | Corridor @ Pre/Post Operative | 1 | 1 | 1.8 | 0.23 | 2.5
| Door Deduction (-) | -1 | 1 | 1.2 | 0.23 | 2.5
7 | Embryologist Room | 1 | 1 | 1.4 | 0.23 | 2.5
|  | -1 | 1 | 1 | 0.23 | 2.5
8 | Change Rooms Toilets
| main door wall | 1 | 1 | 1.4 | 0.23 | 2.5
| Door Deduction (-) | -1 | 1 | 1 | 0.23 | 2.5
| partition wall | 1 | 1 | 4.3 | 0.1 | 3
| partition wall | 1 | 1 | 4.3 | 0.23 | 3
| Door Deduction (-) | -1 | 1 | 1.2 | 0.23 | 2.5
|  | 1 | 1 | 2.4 | 0.23 | 2.55
| Window Deduction (-) | -1 | 1 | 1.8 | 0.23 | 2
9 | Minor OT
| main door wall | 1 | 1 | 1.3 | 0.23 | 2.5
| Door Deduction (-) | -1 | 1 | 1 | 0.23 | 2.5
| partition wall | 1 | 1 | 3.1 | 0.23 | 2.3
| Door Deduction (-) | -1 | 1 | 1 | 0.23 | 2.3
10 | IVF-OT
| main door wall | 1 | 2 | 1.2 | 0.23 | 2.5
| Door Deduction (-) | -1 | 2 | 1 | 0.23 | 2.5
| partition wall | 1 | 1 | 4 | 0.1 | 3
|  | 1 | 1 | 2 | 0.23 | 3
|  | 1 | 1 | 1.25 | 0.23 | 0.8
11 | Embryology and Manifold
| door opening | 1 | 1 | 1.8 | 0.1 | 2.3
| door opening | 1 | 1 | 2.7 | 0.23 | 2.5
| Window Deduction (-) | -1 | 1 | 1.8 | 0.23 | 2
|  | 1 | 1 | 3 | 0.23 | 0.7
Door Removal
1 | Sample Collection & Injection room | 1 | 1
2 | Corridor @ Reception | 1 | 1
3 | Toilet @ Electrical Room | 1 | 2
4 | Corridor @ Pre/Post Operative | 1 | 1
5 | Embryologist Room | 1 | 1
6 | Change Rooms Toilets | 1 | 2
7 | Minor OT | 1 | 2
8 | IVF-OT | 1 | 2
Window Removal
1 | Reception
2 | Sample and Injection Room | 1 | 1
3 | Patient Change Room | 1 | 1
4 | Electrical Room | 1 | 2
5 | Pre/Post Operative Ward | 1 | 2
6 | Embryologist Room | 1 | 2
7 | Change Rooms Toilets | 1 | 8
8 | Minor OT | 1 | 3
9 | IVF-OT | 1 | 2
10 | Embryology and Manifold | 1 | 3
Skirting Removal
1 | Counselling Room 1,2 & Ultrasound Room | 1 | 2 | 10.4 |  | 0.16
|  | 1 | 2 | 6.5 |  | 0.16
| columns | 1 | 2 | 1.6 |  | 0.16
| columns | 1 | 2 | 0.46 |  | 0.16
| Door Deduction (-) | -1 | 2 | 1.8 |  | 0.16
| Door Deduction (-) | -1 | 2 | 1.8 |  | 0.16