## Sheet1
DETAILED MEASUREMENTS
| Name of the work:Design, Fabriction, establishing and commissioning of In - Vitro ferility centers (IVFC) alongwith allied Services on Turnkey basis at MGM Hospital, Warangal. | [8 empty] | Agency: M/s. Asta vardhman Consortium | [5 empty] | Agt.No: 344/A/TSMIDC/Spl.Proj/IVFCs/2022-23, Dt. 05.07.2023
| Discription Of Work etc., | Measurements Upto date | [5 empty] | Rate |  |  | Per | Total Volume |  | Deduct/previous Measurements |  | Since last measurement |  |  | Remarks
|  | No |  | L | B | D | Content | Units | Rs | Ps. |  | Rs. | Ps | P.No. | Qty. | Qty | Value
[17 empty] | Rs. | Ps.
Floor Chipping
1 | Waiting area | 1 | 1 | 8 | 4.7 |  | 37.6
2 | Reception | 1 | 1 | 3.18 | 4.6 |  | 14.628
3 | Sample and Injection Room | 1 | 1 | 4.48 | 3.25 |  | 14.56
4 | Corridor @ Reception | 1 | 1 | 7.5 | 1.8 |  | 13.5
5 | Counselling Room 1,2 & Ultrasound Room | 1 | 1 | 10.4 | 6.5 |  | 67.6
6 | Patient Change Room | 1 | 1 | 3.5 | 1.8 |  | 6.3
7 | Toilet @ Electrical Room | 1 | 1 | 1.44 | 1.2 |  | 1.728
8 | Electrical Room | 1 | 1 | 3 | 3.4 |  | 10.2
9 | Pre/Post Operative Ward | 1 | 1 | 7.95 | 5 |  | 39.75
10 | Corridor @ Pre/Post Operative | 1 | 1 | 7.9 | 1.8 |  | 14.22
11 | Corridor from Embryology to Andrology | 1 | 1 | 21.3 | 1.7 |  | 36.21
12 | Embryologist Room | 1 | 1 | 4.77 | 4.5 |  | 21.465
13 | Change Rooms Toilets | 1 | 1 | 16.55 | 4.78 |  | 79.109
14 | Minor OT | 1 | 1 | 6.87 | 4.47 |  | 30.7089
15 | Minor OT to Manifold corridor | 1 | 1 | 14.48 | 1.7 |  | 24.616
16 | IVF-OT | 1 | 1 | 7 | 4.45 |  | 31.15
17 | Embryology and Manifold | 1 | 1 | 7 | 4.45 |  | 31.15
474.4949
Wall cladding removal
1 | Waiting area | 1 | 2 | 4.36 | 1.5 |  | 13.08
|  | 1 | 2 | 0.5 | 1.97 |  | 1.97
|  | 1 | 1 | 4.7 | 1.5 |  | 7.05
|  | 1 | 1 | 3.2 | 1.5 |  | 4.8
|  | 1 | 1 | 4.7 | 1.97 |  | 9.259
|  | 1 | 1 | 8 | 1.5 |  | 12
| wall top | 1 | 1 | 4.7 | 0.3 |  | 1.41
|  | 1 | 1 | 4.6 | 0.3 |  | 1.38
|  | 1 | 1 | 8 | 0.3 |  | 2.4
2 | Reception | 1 | 1 | 3.18 | 4.6 |  | 14.628
|  | 1 | 1 | 4.6 |  | 0.82 | 3.772
|  | 1 | 1 | 3.9 | 0.3 |  | 1.17
|  | 1 | 1 | 0.35 |  | 1.14 | 0.399
|  | 1 | 1 | 3.18 |  | 1.95 | 6.201
| Window Deduction (-) | -1 | 1 | 1.8 |  | 1.3 | -2.34
|  | -1 | 1 | 4.58 |  | 1.95 | -8.931
|  | -1 | 1 | 1.2 |  | 1.95 | -2.34
3 | Sample and Injection Room | 1 | 2 | 4.6 |  | 1.95 | 17.94
| Door Deduction (-) | -1 | 1 | 1.2 |  | 1.95 | -2.34
|  | 1 | 2 | 3.25 |  | 1.95 | 12.675
| Window Deduction (-) | -1 | 1 | 1.8 |  | 1.3 | -2.34
| Corridor @ Reception | 1 | 1 | 4 |  | 1.95 | 7.8
4 | Patient Change Room | 1 | 2 | 2.14 |  | 1.95 | 8.346
|  | 1 | 1 | 1.8 |  | 1.95 | 3.51
| Window Deduction (-) | -1 | 1 | 1.2 |  | 1.2 | -1.44
5 | Toilet @ Electrical Room | 1 | 2 | 1.44 |  | 1.47 | 4.2336
|  | 1 | 2 | 1.2 |  | 1.47 | 3.528
| Door Deduction (-) | -1 | 1 | 0.8 |  | 1.47 | -1.176
|  | 1 | 2 | 1.17 |  | 1.95 | 4.563
| Door Deduction (-) | -1 | 1 | 0.8 |  | 1.95 | -1.56
|  | 1 | 2 | 1.82 |  | 1.95 | 7.098
| Door Deduction (-) | -1 | 1 | 1 |  | 1.95 | -1.95
|  | -1 | 1 | 1.18 |  | 1.95 | -2.301
|  | 1 | 2 | 0.3 |  | 1.95 | 1.17
6 | Electrical Room | 1 | 2 | 3.4 |  | 1.95 | 13.26
| Window Deduction (-) | -1 | 1 | 1.8 |  | 1.2 | -2.16
|  | 1 | 2 | 3 |  | 1.95 | 11.7
| Window Deduction (-) | -1 | 1 | 1.8 |  | 1.2 | -2.16
| Door Deduction (-) | -1 | 1 | 1 |  | 1.95 | -1.95
7 | Pre/Post Operative Ward | 1 | 2 | 5 |  | 1.95 | 19.5
| Door Deduction (-) | -1 | 1 | 1.2 |  | 1.95 | -2.34
|  | 1 | 1 | 7.95 |  | 1.95 | 15.5025
| Window Deduction (-) | -1 | 2 | 1.8 |  | 1.2 | -4.32
|  | 1 | 2 | 0.3 |  | 1.95 | 1.17
8 | Corridor @ Pre/Post Operative | 1 | 1 | 7.9 |  | 1.8 | 14.22
|  | 1 | 1 | 0.4 |  | 1.95 | 0.78
|  | 1 | 1 | 0.1 |  | 1.95 | 0.195
9 | Corridor from Embryology to Andrology | 1 | 1 | 21.3 |  | 1.95 | 41.535
| Door Deduction (-) | -1 | 1 | 1 |  | 1.95 | -1.95
| Window Deduction (-) | -1 | 5 | 1.8 |  | 1.2 | -10.8
| Door Deduction (-) | -1 | 1 | 1.74 |  | 1.95 | -3.393
|  | 1 | 1 | 10.16 |  | 0.9 | 9.144
|  | 1 | 1 | 5.7 |  | 1.95 | 11.115
10 | Embryologist Room | 1 | 2 | 4.77 |  | 1.95 | 18.603
| Door Deduction (-) | -1 | 1 | 1 |  | 1.95 | -1.95
| Window Deduction (-) | -1 | 2 | 1.8 |  | 1.2 | -4.32
|  | 1 | 2 | 4.5 |  | 1.95 | 17.55
11 | Change Rooms Toilets | 1 | 2 | 16.55 |  | 1.95 | 64.545
| Window Deduction (-) | -1 | 8 | 1.8 |  | 1.2 | -17.28
|  | 1 | 6 | 4.78 |  | 1.95 | 55.926
|  | 1 | 8 | 0.46 |  | 1.95 | 7.176
12 | Minor OT | 1 | 2 | 6.87 |  | 1.95 | 26.793
| Door Deduction (-) | -1 | 2 | 1 |  | 1.95 | -3.9
| Window Deduction (-) | -1 | 2 | 1.8 |  | 1.2 | -4.32
|  | 1 | 2 | 0.42 |  | 1.95 | 1.638
|  | 1 | 2 | 4.47 |  | 1.95 | 17.433
| Window Deduction (-) | -1 | 1 | 1.8 |  | 1.2 | -2.16
13 | Minor OT to Manifold corridor | 1 | 1 | 9.16 |  | 1.95 | 17.862
| Door Deduction (-) | -1 | 2 | 1 |  | 1.95 | -3.9
|  | 1 | 1 | 7.6 |  | 0.9 | 6.84
14 | IVF-OT | 1 | 2 | 7 |  | 1.95 | 27.3
|  | -1 | 2 | 1 |  | 1.95 | -3.9
|  | -1 | 2 | 1.8 |  | 1.2 | -4.32
|  | 1 | 4 | 4.45 |  | 1.95 | 34.71
15 | Dead End | 1 | 4 | 1.8 |  | 1.95 | 14.04
16 | Embryology and Manifold | 1 | 1 | 7 |  | 1.95 | 13.65
|  | 1 | 1 | 3.67 |  | 1.95 | 7.1565
| Window Deduction (-) | -1 | 2 | 1.8 |  | 1.2 | -4.32
|  | 1 | 2 | 4.45 |  | 1.95 | 17.355
| Window Deduction (-) | -1 | 1 | 1.8 |  | 1.2 | -2.16
|  | 1 | 2 | 0.5 |  | 1.95 | 1.95
530.7106
Granite Removal
1 | Waiting area | 1 | 1 | 3.5 | 0.5 |  | 1.75
|  | 1 | 1 | 4.3 | 0.5 |  | 2.15
|  | 1 | 1 | 7.57 | 0.5 |  | 3.785
|  | 1 | 1 | 4.22 | 0.5 |  | 2.11
2 | Pre/Post Operative Ward | 1 | 1 | 17 | 0.6 |  | 10.2
3 | Corridor @ Pre/Post Operative | 1 | 1 | 7.9 | 0.3 |  | 2.37
4 | Corridor from Embryology to Andrology | 1 | 1 | 10.16 | 0.3 |  | 3.048
5 | Minor OT to Manifold corridor | 1 | 1 | 7.6 | 0.3 |  | 2.28
27.693
Brick Demolition
1 | Waiting area | 1 | 1 | 1.6 | 0.23 | 1.5 | 0.552
|  | 1 | 17 | 0.5 | 0.15 | 0.45 | 0.57375
|  | 1 | 3 | 0.45 | 0.45 | 0.45 | 0.27338
2 | Sample and Injection Room | 1 | 1 | 1 | 0.1 | 2.3 | 0.23
3 | Corridor @ Reception | 1 | 1 | 1.8 | 0.23 | 2.5 | 1.035
4 | Toilet @ Electrical Room | 1 | 1 | 1.3 | 0.1 | 2.5 | 0.325
| Door Deduction (-) | -1 | 1 | 1 | 0.1 | 2.5 | -0.25
5 | Pre/Post Operative Ward | 1 | 17 | 0.5 | 0.15 | 0.5 | 0.6375
6 | Corridor @ Pre/Post Operative | 1 | 1 | 1.8 | 0.23 | 2.5 | 1.035
| Door Deduction (-) | -1 | 1 | 1.2 | 0.23 | 2.5 | -0.69
7 | Embryologist Room | 1 | 1 | 1.4 | 0.23 | 2.5 | 0.805
|  | -1 | 1 | 1 | 0.23 | 2.5 | -0.575
8 | Change Rooms Toilets
| main door wall | 1 | 1 | 1.4 | 0.23 | 2.5 | 0.805
| Door Deduction (-) | -1 | 1 | 1 | 0.23 | 2.5 | -0.575
| partition wall | 1 | 1 | 4.3 | 0.1 | 3 | 1.29
| partition wall | 1 | 1 | 4.3 | 0.23 | 3 | 2.967
| Door Deduction (-) | -1 | 1 | 1.2 | 0.23 | 2.5 | -0.69
|  | 1 | 1 | 2.4 | 0.23 | 2.55 | 1.4076
| Window Deduction (-) | -1 | 1 | 1.8 | 0.23 | 2 | -0.828
9 | Minor OT
| main door wall | 1 | 1 | 1.3 | 0.23 | 2.5 | 0.7475
| Door Deduction (-) | -1 | 1 | 1 | 0.23 | 2.5 | -0.575
| partition wall | 1 | 1 | 3.1 | 0.23 | 2.3 | 1.6399
| Door Deduction (-) | -1 | 1 | 1 | 0.23 | 2.3 | -0.529
10 | IVF-OT
| main door wall | 1 | 2 | 1.2 | 0.23 | 2.5 | 1.38
| Door Deduction (-) | -1 | 2 | 1 | 0.23 | 2.5 | -1.15
| partition wall | 1 | 1 | 4 | 0.1 | 3 | 1.2
|  | 1 | 1 | 2 | 0.23 | 3 | 1.38
|  | 1 | 1 | 1.25 | 0.23 | 0.8 | 0.23
11 | Embryology and Manifold
| door opening | 1 | 1 | 1.8 | 0.1 | 2.3 | 0.414
| door opening | 1 | 1 | 2.7 | 0.23 | 2.5 | 1.5525
| Window Deduction (-) | -1 | 1 | 1.8 | 0.23 | 2 | -0.828
|  | 1 | 1 | 3 | 0.23 | 0.7 | 0.483
14.2731
Door Removal
1 | Sample Collection & Injection room | 1 | 1 |  |  |  | 1
2 | Corridor @ Reception | 1 | 1 |  |  |  | 1
3 | Toilet @ Electrical Room | 1 | 2 |  |  |  | 2
4 | Corridor @ Pre/Post Operative | 1 | 1 |  |  |  | 1
5 | Embryologist Room | 1 | 1 |  |  |  | 1
6 | Change Rooms Toilets | 1 | 2 |  |  |  | 2
7 | Minor OT | 1 | 2 |  |  |  | 2
8 | IVF-OT | 1 | 2 |  |  |  | 2
12
Window Removal
1 | Reception
2 | Sample and Injection Room | 1 | 1 |  |  |  | 1
3 | Patient Change Room | 1 | 1 |  |  |  | 1
4 | Electrical Room | 1 | 2 |  |  |  | 2
5 | Pre/Post Operative Ward | 1 | 2 |  |  |  | 2
6 | Embryologist Room | 1 | 2 |  |  |  | 2
7 | Change Rooms Toilets | 1 | 8 |  |  |  | 8
8 | Minor OT | 1 | 3 |  |  |  | 3
9 | IVF-OT | 1 | 2 |  |  |  | 2
10 | Embryology and Manifold | 1 | 3 |  |  |  | 3
24
Skirting Removal
1 | Counselling Room 1,2 & Ultrasound Room | 1 | 2 | 10.4 |  | 0.16 | 3.328
|  | 1 | 2 | 6.5 |  | 0.16 | 2.08
| columns | 1 | 2 | 1.6 |  | 0.16 | 0.512
| columns | 1 | 2 | 0.46 |  | 0.16 | 0.1472
| Door Deduction (-) | -1 | 2 | 1.8 |  | 0.16 | -0.576
| Door Deduction (-) | -1 | 2 | 1.8 |  | 0.16 | -0.576
4.9152