## Sheet1
S.No | Type of Work | Supplier Name |  | Progress
1 | Wooden Doors |  |  | To be ordered by 16-08-2023
2 | Panels, Scientific doors | Ahlada | Approval & Coordination | Work In Progress
3 | HVAC | VJ Engineers |  | Work In Progress
4 | VRV & Split AC | Comfort Cool Care Services |  | Work In Progress
5 | Sanitary & CP Fittings | Hindware |  | Order to be placed
6 | Electrical | Santosh |  | Work In Progress
7 | ELV | Gopi |  | Work In Progress
8 | HPL Partitions for Change Rooms |  |  | Need to finalise the supplier
| PO |  | Amount
| Percentage of Payment to be made is to be completed by tomorrow |  | 6 Lakhs
SOTC
| Inauguration date 20-08-2023 |  | IVF
Pre works to be completed by 10-08-2023
Materials to be reached to the site by 10-08-2023