## Eq Biil-3
DETAILED MEASUREMENTS
Name of the work:Design, Fabriction, establishing and commissioning of In - Vitro ferility centers (IVFC) alongwith allied Services on Turnkey basis at petlaburz Hyderabad. | [10 empty] | Agency: M/s. Asta vardhman Consortium | [5 empty] | Agt.No: 344/A/TSMIDC/Spl.Proj/IVFCs/2022-23, Dt. 05.07.2023
S.No | Agreement S.No | Discription Of Work etc., | Measurements Upto date | [5 empty] | Rate |  |  | Per | Total Volume |  | Deduct/previous Measurements |  | Since last measurement |  |  | Remarks
|  |  | No |  | L | B | D | Content | Units | Rs | Ps. |  | Rs. | Ps | P.No. | Qty. | Qty | Value
[18 empty] | Rs. | Ps.
1 | 199 | Ovum Aspiration Pumps at Petlaburj Hospital
|  | Ovum Aspiration Pumps | 1 | 2 |  |  |  | 2
[6 empty] | Total |  | 2 | Nos |  | Qty C/O V.Pg.No. Of MB:-
2 | 205 | IVF Workstation with LAF at Petlaburj Hospital
|  | IVF Workstation | 1 | 1 |  |  |  | 1
[6 empty] | Total |  | 1 | Nos |  | Qty C/O V.Pg.No. Of MB:-
3 | 206 | IVF Ant vibration Table for procedure at Petlaburj Hospital
|  | Antivibration Table | 1 | 1 |  |  |  | 1
[6 empty] | Total |  | 1 | Nos |  | Qty C/O V.Pg.No. Of MB:-
4 | 208 | Trigas bench Top Incubators for Human Embryo culture at Petlaburj Hospital
|  | Trigas bench Top Incubators | 1 | 1 |  |  |  | 1
[6 empty] | Total |  | 1 | Nos |  | Qty C/O V.Pg.No. Of MB:-
5 | 209 | Trinocular Stereozoom Microscope at Petlaburj Hospital
|  | Trinocular Stereozoom Microscope | 1 | 1 |  |  |  | 1
[6 empty] | Total |  | 1 | Nos |  | Qty C/O V.Pg.No. Of MB:-
6 | 210 | ICSI Micro manipulator with Inverted Microscope at Petlaburj Hospital
|  | Micro Manipulator | 1 | 1 |  |  |  | 1
[6 empty] | Total |  | 1 | Nos |  | Qty C/O V.Pg.No. Of MB:-
7 | 211 | IVF Laser System at Petlaburj Hospital
|  | Laser System | 1 | 1 |  |  |  | 1
[6 empty] | Total |  | 1 | Nos |  | Qty C/O V.Pg.No. Of MB:-
8 | 216 | VOC Meter for ART Lab at Petlaburj Hospital
|  | VOC Meter | 1 | 1 |  |  |  | 1
[6 empty] | Total |  | 1 | Nos |  | Qty C/O V.Pg.No. Of MB:-
9 | 218 | Binocular Microscope for Semen Analysis at Petlaburj Hospital
|  | Binocular Microscope | 1 | 1 |  |  |  | 1
[6 empty] | Total |  | 1 | Nos |  | Qty C/O V.Pg.No. Of MB:-
10 | 219 | Laminar flow cabinet with Andrology Work station at Petlaburj Hospital
|  | Laminar flow cabinet | 1 | 1 |  |  |  | 1
[6 empty] | Total |  | 1 | Nos |  | Qty C/O V.Pg.No. Of MB:-
11 | 222 | Pipetter and Denudation system at Petlaburj Hospital
|  | Pipetter and Denudation system | 1 | 1 |  |  |  | 1
[6 empty] | Total |  | 1 | Nos |  | Qty C/O V.Pg.No. Of MB:-
12 | 229 | Autoclave at Petlaburj Hospital
|  | Autoclave | 1 | 1 |  |  |  | 1
[6 empty] | Total |  | 1 | Nos |  | Qty C/O V.Pg.No. Of MB:-
13 | 236 | Reception Table at Petlaburj Hospital
|  | Reception Table | 1 | 1 |  |  |  | 1
[6 empty] | Total |  | 1 | Nos |  | Qty C/O V.Pg.No. Of MB:-
14 | 238 | Filing Cabinet at Petlaburj Hospital
|  | Filing Cabinet | 1 | 2 |  |  |  | 2
[6 empty] | Total |  | 2 | Nos |  | Qty C/O V.Pg.No. Of MB:-
15 | 239 | Patient Seating 3 in 1 model at Petlaburj Hospital
|  | Patient Seating 3 in 1 model | 1 | 3 |  |  |  | 3
[6 empty] | Total |  | 3 | Nos |  | Qty C/O V.Pg.No. Of MB:-
16 | 244 | Wall Storage Cabinets at Petlaburj Hospital
|  |  | 1 | 8 |  |  |  | 8
[6 empty] | Total |  | 8 | Nos |  | Qty C/O V.Pg.No. Of MB:-
17 | 245 | Office Table at Petlaburj Hospital
|  |  | 1 | 3 |  |  |  | 3
[6 empty] | Total |  | 3 | Nos |  | Qty C/O V.Pg.No. Of MB:-

## ABS-3
ABSTRACT
Name of Work:- Design, Fabriction, establishing and commissioning of In - Vitro ferility centers (IVFC) alongwith allied Services on Turnkey basis at MGMH Petlaburj,Hyd. | [7 empty] | Agency: | M/s. Asta Vardhman Consortium | [5 empty] | Agt.No:344/A/TSMIDC/Spl.Proj/IVFCs /2022-23,Dt.05.07.2023
S.No | Date of measurement/ S.No. in Agt. | Description Of Work etc., | Measurements Upto date |  |  |  |  | Rate |  | Per | Total Value to date |  | Deduct/previous Measurements |  | Since last measurement |  |  | Remarks
|  |  | No | L | B | D | Content | Rs | Ps. |  | Rs. | Ps | P.No. | Qty. | Qty | Value
[16 empty] | Rs. | Ps.
1 | 247 | Dismantling, clearing away and carefully stacking useful materials for re-use and disposal of unserviceable materials with 100m lead as directed by Executive Engineer duly taking actual premeasurements before dismantling including all labour charges , overheads & contractor profit etc., complete Finished item of work | [16 empty] | Original Rate
a) Brick Masonry
|  | Qty V.Pg.No:-01 of MB:-04 |  |  |  | 20.38 | 20.38 | 398 | Cum |  | 8111.24 |  | 20.38 | 8111.24 | - | - |  |  | 398
| 248 | b) Tiles Dismantling
|  | Qty V.Pg.No:-01 of MB:-04 |  |  |  | 729.9325 | 400 | 20 | Sqm |  | 8000 |  | 400 | 8000 | - | - |  |  | 20
[6 empty] | AE | 329.9325
2 | 249 | Dismantling doors, windows and clear storey windows, Ventilators etc., (wood or steel) shutters including Chowkhats, architraves,hold fasts and other attachments etc., and stacking them within 100m lead including labour charge etc., and overheads & contractors profit complete for finished item of work.
a)Not Exceeding 3.00Sqm Area
|  | Qty V.Pg.No:-01 of MB:-04 |  |  |  | 32 | 16 | 350 | Each |  | 5600 |  | 16 | 5600 | - | - |  |  | 350
[6 empty] | AE | 16
3 | 252 | Brick Masonry for panel walls in SuperStructure with CM (1:8) prop (cement: Screened sand) with Aerated Cellular Autoclaved Concrete Blocks conforming to IS:2185 (Part-3) - 1984 and IS:6441-1972 of Compressive strength 3 N/mm2 600x 230 x 200 mm from approved source having minimum crushing strength of 3 N/Sq.m including cost and conveyance of all materials like cement, sand, bricks, water etc., to site, including sales & other taxes on all materials, all operational, incidental and labour charges such as mixing cement mortar, constructing masonry, scaffolding charges, lift charges, curing, etc., complete but excluding seigniorage charges for finished item of work. (APSS No. 501 & 504).
|  | Qty V.Pg.No:-01 of MB:-04 |  |  |  | 16.3192 | 10.5 | 14558 | cum |  | 152859 |  | 10.5 | 152859 | - | - |  |  | 14558
[6 empty] | AE | 5.82
4 | 253 | Reinforced Masonry for partiton walls 100 mm thick in CM (1:4) prop (cement: Screened sand) in super structure with Aerated Cellular Autoclaved Concrete Blocks conforming to IS:2185 (Part-3) - 1984 and IS:6441-1972 of Compressive strength 3 N/mm2 600x 200 x 100 mm from approved source having minimum crushing strength of 3 N/Sq.m including cost and conveyance of all materials like cement, sand, bricks, water etc., to site, including sales & other taxes on all materials, all operational, incidental and labour charges such as mixing cement mortar, constructing masonry, scaffolding charges, lift charges, curing, etc., complete but excluding seigniorage charges for finished item of work. (APSS No. 501 & 504).
|  | Qty V.Pg.No:-02 of MB:-04 |  |  |  | 219.7595 | 215 | 1716 | Sqm |  | 368940 |  | 215 | 368940 | - | - |  |  | 1716
[6 empty] | AE | 4.7595
5 | 256 | Plastering 12mm thick in two coats using screened sand with base coat of 8mm thick in CM (1:6) and top coat of 4mm thick in CM (1:4) with dubara sponge finishing including cost and conveyance of all materials like cement, sand, water etc., to site, including sales & other taxes on all materials, and all operational, incidental charges on materials and including cost of all labour charges for mixing mortar, finishing, scaffolding, lift charges, curing, including cutting grooves as directed by Engineer-in-charge etc., and overheads & contractors profit complete for finished item of work. (SS 901,903 & 904).
|  | Qty V.Pg.No:-02 of MB:-04 |  |  |  | 822.13 | 430 | 906 | Sqm |  | 389580 |  | 430 | 389580 | 0 | 0 |  |  | 906
[6 empty] | AE:- | 392.13
6 | 263 | Flooring with soluble salt porcelain vitrified tiles screen printed and polished of size 600 x 600 mm and thickness between 8 to 10mm 1st quality conforming to IS: 13711, IS: 13712, IS: 13630Parts 1 to 15 of any colour and finish in all shades and designs with borders and design as per the approved flooring pattern as directed by the Engineer-In -Charge, laying tiles using spacers of 2mm thick, set over a base coat of CM 1:8 prop. 12mm thick using screened sand over CC bed already laid or RCC roof slab, including neat cement slurry of honey like consistency spread at the rate 3.3 kgs per Sqm. and jointed neatly with white cement paste to full depth mixed with pigment of matching shade including cost and conveyance of all materials like cement, sand, water, tiles, white cement etc., to site excluding cost of C.C. bed including cost of base coat and all labour charges for mixing of cement mortar, laying tiles to required slope as directed by the Engineer- in- charge etc., and complete for finished item of work. TSSS No.701 and 707.
|  | Qty V.Pg.No:-02 of MB:-04 |  |  |  | 294.66 | 294.659 | 1593 | Sqm |  | 469391.787 |  | 294.66 | 469393.38 | - | - |  |  | 1593
7 | 266 | Providing dadooing to walls with glazed full body porcelain wall tiles of size 300 x 600 mm with any type of design texture such as marble finish, wooden, bamboo, stone finishes etc., scratch less, stain free and thickness between 6-8 mm 1st quality conforming to IS:13711, IS:13712, IS:13630 Parts 1 to 15 of any colour and finish in all shades and designs with borders as approved by Engineer-in-Charge set over base coat of CM1:5 12 mm thick using screened sand with cement slurry of honey like consistency spread at the rate of 3.30 kgs per sqm and jointing with white cement paste mixed with pigment of matching shade to full depth, including cost of all materials like tiles, cement, sand and water etc., complete for finished item of work. 3rd Floor at Petlaburj Hospital
|  | Qty V.Pg.No:-03 of MB:-04 |  |  |  | 153.0952 | 30 | 1391 | Sqm |  | 41730 |  | 30 | 41730 | - | - |  |  | 1391
[6 empty] | AE | 123.0952
[9 empty] | Civil Sub-Total:- |  | 1444212.027 |  |  | 1444213.62 |  | 0
Civil Supplemental Items
1 |  | Dismantling, clearing away and carefully stacking useful materials for re-use and disposal of unserviceable materials with 100m lead as directed by Executive Engineer duly taking actual premeasurements before dismantling including all labour charges , overheads & contractor profit etc., complete Finished item of work
a)Old Cement Mortar
|  | Qty V.Pg.No:-03 of MB:-04 |  |  |  | 251.59 | 251.5889
b)Reinforced Cement Concrete
|  | Qty V.Pg.No:-03 of MB:-04 |  |  |  | 0.43 | 0.4293
2 |  | Providing Thermo Mechanically Treated ( TMT) ( Fe-500/500D/550D from primery producer TATA, SAIL, VSP, JSW Steel, Goel steel, Jindal panther, X- Vega & balaji Shakthi as per IS 1786-2008) of Different Diameters RCC Works , including labour charges for straightening, cutting, bending to required sizes and shapes, placing in position with cover blocks of approved materials and sizes and typing and lap - spacing with binding wire of 18 SWG, Forming grills for reinforcement work as per approved design and drawings, including and conveyanace of steel bars, including all wastages such as overlaps, coupling, chairs, spacer bars including cost and conveyance of binding wire cover blocks and incidential, operational, labour charges such as cutting bending, placing in position, typing incliding sales and other taxes on all materials etc., and overheads & contractors profit completefor finished item of work
|  | Qty V.Pg.No:-03 of MB:-04 |  |  |  |  | 0.2956
3 |  | Supply and placing of the Design Mix Concrete M 25 grade corresponding to IS 456 with minimum cement content of 380 kgs per 1 cum of concrete using Weight Batcher / Concrete mixer with 20mm size graded machine crushed hard granite metal (coarse aggregate - as per IS 383 - 1970 and IS 2386 Part 1 to Part 8) from approved quarry including cost and conveyance of all materials like cement, fine aggregate (sand) coarse aggregate, water etc., to site and sales & other taxes on all materials, centering using Casurina Ballies, Bamboos, Wooden Reapers, Runners, Wood Posts, Steel Plates etc., including all operational, incidental and labour charges such as weigh batching, machine mixing, lifting of concrete manually, laying concrete, curing , overheads & contractors profit etc., complete but excluding cost of steel and its fabrication charges for finished item of work (APSS No. 402)
For Lintels
|  | Qty V.Pg.No:-04 of MB:-04 |  |  |  | 0.75 | 0.74952
4 |  | Providing skirting to internal walls to 10 cm height with Double charged / multi charged stain free fullbody porcelain vitrified tiles with double layer pigment of size 600 x 600 mm and thickness between 8-10 mm 1st quality conforming to IS:15622 - 2017, IS:13630 (Parts 1 to 15) of any colour and finish in all shades and designs, length equal to flooring tiles, set over base coat of CM(1:5) 12 mm thick using screened sand with cement slurry of honey like consistency spread at the rate of 3.30 kgs per sqm and jointing with white cement paste mixed with pigment of matching shade to full depth, including cost of all materials like tiles, cement, sand and water etc.,and overheads & contractors profit complete for finished item of work.(APSS No.701 &707)
|  | Qty V.Pg.No:-04 of MB:-04 |  |  |  | 174.5 | 174.5
[8 empty] | Civil Suppl. Sub-Total:- |  |  | 0 |  |  | 0 |  | 0
Equipment Items
1 | 200 | IVF Test tube Warmers at Petlaburz Hospital
|  | Qty V.Pg.No:-04 of MB:-04 |  |  |  | 2 | 2 | 34650 | Nos |  | 69300 |  | 2 | 69300 |  |  |  | 70% | 49500
2 | 201 | DICOM compatible fully digital, compact, portable, Ultrasound Scan Machine Colour Doppler at Petlaburz Hospital
|  | Qty V.Pg.No:-04 of MB:-04 |  |  |  | 2 | 2 | 955500 | Nos |  | 1911000 |  | 2 | 1911000 |  |  |  | 70% | 1365000
3 | 202 | Multipurpose Electro hydraulic with manual override mobile OT Table, with divided leg section suitable for all Gynaecological surgical procedures, complete with 5cm Mattress and corded handset at Petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 1 | 1 | 394625 | Nos |  | 394625 |  | 1 | 394625 |  |  |  | 70% | 563750
4 | 203 | LED procedure Lights Double dome at petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 1 | 1 | 218750 | Nos |  | 218750 |  | 1 | 218750 |  |  |  | 70% | 312500
5 | 204 | LED procedure Lights Single dome at petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 1 | 1 | 131250 | Nos |  | 131250 |  | 1 | 131250 |  |  |  | 70% | 187500
6 | 207 | CO2 Incubators at Petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 2 | 2 | 577500 | Nos |  | 1155000 |  | 2 | 1155000 |  |  |  | 70% | 825000
7 | 212 | IVF Thermometer at Petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 1 | 1 | 43313 | Nos |  | 43313 |  | 1 | 43313 |  |  |  | 70% | 61875
8 | 213 | CO2 Cylinder and Manifold at Petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 2 | 2 | 35000 | Nos |  | 70000 |  | 2 | 70000 |  |  |  | 70% | 50000
9 | 214 | CO2 and O2 Analyzer at Petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 2 | 1 | 264600 | Nos |  | 264600 |  | 1 | 264600 |  |  |  | 70% | 378000
10 | 215 | PH Meter at Petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 1 | 1 | 65625 | Nos |  | 65625 |  | 1 | 65625 |  |  |  | 70% | 93750
11 | 217 | Sperm Counting Markler Chamber at Petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 1 | 1 | 52938 | Nos |  | 52938 |  | 1 | 52938 |  |  |  | 70% | 75625
12 | 220 | Clinical Centrifuge machine for Andrology at Petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 1 | 1 | 24150 | Nos |  | 24150 |  | 1 | 24150 |  |  |  | 70% | 34500
13 | 221 | DRY Incubator at Petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 1 | 1 | 394625 | Nos |  | 394625 |  | 1 | 394625 |  |  |  | 70% | 563750
14 | 223 | Pharmaceutical Refrigerator at Petlaburz Hospital
|  | Qty V.Pg.No:-06 of MB:-04 |  |  |  | 1 | 1 | 157500 | Nos |  | 157500 |  | 1 | 157500 |  |  |  | 70% | 225000
15 | 224 | Cryocane (TA 26 Ltr) with wheels at Petlaburz Hospital
|  | Qty V.Pg.No:-06 of MB:-04 |  |  |  | 2 | 2 | 43313 | Nos |  | 86626 |  | 2 | 86626 |  |  |  | 70% | 61875
16 | 225 | Defibrillator at Petlaburz Hospital
|  | Qty V.Pg.No:-06 of MB:-04 |  |  |  | 1 | 1 | 218750 | Nos |  | 218750 |  | 1 | 218750 |  |  |  | 70% | 312500
17 | 226 | 7 Para Patient Monitor at Petlaburz Hospital
|  | Qty V.Pg.No:-06 of MB:-04 |  |  |  | 2 | 2 | 196000 | Nos |  | 392000 |  | 2 | 392000 |  |  |  | 70% | 280000
18 | 228 | Anaesthesia Work station at Petlaburz Hospital
|  | Qty V.Pg.No:-06 of MB:-04 |  |  |  | 1 | 1 | 656250 | Nos |  | 656250 |  | 1 | 656250 |  |  |  | 70% | 937500
19 | 232 | Mulitfunctional Printer at Petlaburz Hospital
|  | Qty V.Pg.No:-06 of MB:-04 |  |  |  | 1 | 1 | 30625 | Nos |  | 30625 |  | 1 | 30625 |  |  |  | 70% | 43750
20 | 233 | Ultrasound Examination Couch at Petlaburz Hospital
|  | Qty V.Pg.No:-06 of MB:-04 |  |  |  | 1 | 1 | 56875 | Nos |  | 56875 |  | 1 | 56875 |  |  |  | 70% | 81250
21 | 235 | Laptop For Office Usage at Petlaburz Hospital
|  | Qty V.Pg.No:-06 of MB:-04 |  |  |  | 2 | 2 | 80500 | Nos |  | 161000 |  | 2 | 161000 |  |  |  | 70% | 115000
22 | 320 | 20 KVA UPS: Supply and installation of 20KVA 3ph in and 3ph out on line UPS system IGBT based rectifier with input power factor correction 32 bit microprocessor based with isolation transformers double conversion, SNMP controls, LCD display, Pure sine wave output, with auto static switch three phase input / Three phase output and modular structure for better thermal technology / cooling facility, with warranty up to three years.Makes: APC / Numeric / Emerson / Fuji Electric At Petlaburz
|  | Qty V.Pg.No:-06 of MB:-04 |  |  |  | 1 | 1 | 213500 | Nos |  | 213500 |  | 1 | 213500 |  |  |  | 70% | 305000
23 | 322 | Supply and providing of UPS Cum battery rack for 20 batteries at MGMH Petlaburz
|  | Qty V.Pg.No:-06 of MB:-04 |  |  |  | 1 | 1 | 4735 | Nos |  | 4735 |  | 1 | 4735 |  |  |  | 70% | 6764
1 | 199 | Ovum Aspiration Pumps at Petlaburj Hospital
|  | Qty V.Pg.No:-01 of MB:-05 |  |  |  | 2 | 2 | 168000 | Nos |  | 336000 |  |  |  | 2 | 336000 |  | 70% | 240000
2 | 205 | IVF Workstation with LAF at Petlaburj Hospital
|  | Qty V.Pg.No:-01 of MB:-05 |  |  |  | 1 | 1 | 481250 | Nos |  | 481250 |  |  |  | 1 | 481250 |  | 70% | 687500
3 | 206 | IVF Ant vibration Table for procedure at Petlaburj Hospital
|  | Qty V.Pg.No:-01 of MB:-05 |  |  |  | 1 | 1 | 67375 | Nos |  | 67375 |  |  |  | 1 | 67375 |  | 70% | 96250
4 | 208 | Trigas bench Top Incubators for Human Embryo culture at Petlaburj Hospital
|  | Qty V.Pg.No:-01 of MB:-05 |  |  |  | 1 | 1 | 577500 | Nos |  | 577500 |  |  |  | 1 | 577500 |  | 70% | 825000
5 | 209 | Trinocular Stereozoom Microscope at Petlaburj Hospital
|  | Qty V.Pg.No:-01 of MB:-05 |  |  |  | 1 | 1 | 216300 | Nos |  | 216300 |  |  |  | 1 | 216300 |  | 70% | 309000
6 | 210 | ICSI Micro manipulator with Inverted Microscope at Petlaburj Hospital
|  | Qty V.Pg.No:-02 of MB:-05 |  |  |  | 1 | 1 | 1837500 | Nos |  | 1837500 |  |  |  | 1 | 1837500 |  | 70% | 2625000
7 | 211 | IVF Laser System at Petlaburj Hospital
|  | Qty V.Pg.No:-02 of MB:-05 |  |  |  | 1 | 1 | 1792000 | Nos |  | 1792000 |  |  |  | 1 | 1792000 |  | 70% | 2560000
8 | 216 | VOC Meter for ART Lab at Petlaburj Hospital
|  | Qty V.Pg.No:-02 of MB:-05 |  |  |  | 1 | 1 | 511875 | Nos |  | 511875 |  |  |  | 1 | 511875 |  | 70% | 731250
9 | 218 | Binocular Microscope for Semen Analysis at Petlaburj Hospital
|  | Qty V.Pg.No:-02 of MB:-05 |  |  |  | 1 | 1 | 28875 | Nos |  | 28875 |  |  |  | 1 | 28875 |  | 70% | 41250
10 | 219 | Laminar flow cabinet with Andrology Work station at Petlaburj Hospital
|  | Qty V.Pg.No:-02 of MB:-05 |  |  |  | 1 | 1 | 175000 | Nos |  | 175000 |  |  |  | 1 | 175000 |  | 70% | 250000
11 | 222 | Pipetter and Denudation system at Petlaburj Hospital
|  | Qty V.Pg.No:-02 of MB:-05 |  |  |  | 1 | 1 | 72188 | Nos |  | 72188 |  |  |  | 1 | 72188 |  | 70% | 103125
12 | 229 | Autoclave at Petlaburj Hospital
|  | Qty V.Pg.No:-02 of MB:-05 |  |  |  | 1 | 1 | 393750 | Nos |  | 393750 |  |  |  | 1 | 393750 |  | 70% | 562500
13 | 236 | Reception Table at Petlaburj Hospital
|  | Qty V.Pg.No:-03 of MB:-05 |  |  |  | 1 | 1 | 77000 | Nos |  | 77000 |  |  |  | 1 | 77000 |  | 70% | 110000
14 | 238 | Filing Cabinet at Petlaburj Hospital
|  | Qty V.Pg.No:-03 of MB:-05 |  |  |  | 2 | 2 | 24150 | Nos |  | 48300 |  |  |  | 2 | 48300 |  | 70% | 34500
15 | 239 | Patient Seating 3 in 1 model at Petlaburj Hospital
|  | Qty V.Pg.No:-03 of MB:-05 |  |  |  | 3 | 3 | 26950 | Nos |  | 80850 |  |  |  | 3 | 80850 |  | 70% | 38500
16 | 244 | Wall Storage Cabinets at Petlaburj Hospital
|  | Qty V.Pg.No:-03 of MB:-05 |  |  |  | 8 | 8 | 12250 | Nos |  | 98000 |  |  |  | 8 | 98000 |  | 70% | 17500
17 | 245 | Office Table at Petlaburj Hospital
|  | Qty V.Pg.No:-03 of MB:-05 |  |  |  | 3 | 3 | 14000 | Nos |  | 42000 |  |  |  | 3 | 42000 |  | 70% | 20000
[9 empty] | Sub-Total:- |  | 13608800 |  |  | 6773037 |  | 6835763
[8 empty] | Sub-Total(Civil+ Civil Suppl.+Equipment):- |  |  | 15053012.027 |  |  | 8217250.62 |  | 6835763
[9 empty] | Add GST 18% |  | 2709542.1649 |  |  | 1479105.1116 |  | 1230437.34
[9 empty] | GrandTotal:- |  | 17762554.1919 |  |  | 9696355.7316 |  | 8066200.34
Certificate
[7 empty] | 1) | The work is in progress in according with the specification drawing and terms and condition the agreement.
[7 empty] | 2) | No recoveries are due for recovery from the contractor other than those proposed in the bill
[7 empty] | 3) | There are no further dues to be recovery from the contractor
[7 empty] | 4) | The contractor has conveyneced the materieals for use on the work as per the lead statement approved the agreement.
[7 empty] | 5) | The leads and lifts are covered in the contractor.

## CC-3
CC 3rd & Part Bill
Name of Work:- |  | Design, Fabriction, establishing and commissioning of In - Vitro ferility centers (IVFC) alongwith allied Services on Turnkey basis at MGMH Petlaburj,Hyd. | [5 empty] | Agency: | M/s. Asta Vardhman Consortium | [5 empty] | Agt.No: 344/A/TSMIDC/Spl.Proj/IVFCs/2022-23,Dt.05.07.2023
S.No | Date of measurement/ S.No. in Agt. | Description Of Work etc., | Measurements Upto date |  |  |  |  | Rate |  | Per | Total Value to date |  | Deduct/previous Measurements |  | Since last measurement |  |  | Remarks
|  |  | No | L | B | D | Content | Rs | Ps. |  | Rs. | Ps | P.No. | Qty. | Qty | Value
[16 empty] | Rs. | Ps.
1 | 247 | Dismantling, clearing away and carefully stacking useful materials for re-use and disposal of unserviceable materials with 100m lead as directed by Executive Engineer duly taking actual premeasurements before dismantling including all labour charges , overheads & contractor profit etc., complete Finished item of work | [16 empty] | Original Rate
a) Brick Masonry
[6 empty] | 20.38 | 20.38 | 398 | Cum |  | 8111.24 |  | 20.38 | 8111.24 | - | - |  |  | 398
| 248 | b) Tiles Dismantling
[6 empty] | 729.9325 | 400 | 20 | Sqm |  | 8000 |  | 400 | 8000 | - | - |  |  | 20
[6 empty] | AE | 329.9325
2 | 249 | Dismantling doors, windows and clear storey windows, Ventilators etc., (wood or steel) shutters including Chowkhats, architraves,hold fasts and other attachments etc., and stacking them within 100m lead including labour charge etc., and overheads & contractors profit complete for finished item of work.
a)Not Exceeding 3.00Sqm Area
[6 empty] | 32 | 16 | 350 | Each |  | 5600 |  | 16 | 5600 | - | - |  |  | 350
[6 empty] | AE | 16
3 | 252 | Brick Masonry for panel walls in SuperStructure with CM (1:8) prop (cement: Screened sand) with Aerated Cellular Autoclaved Concrete Blocks conforming to IS:2185 (Part-3) - 1984 and IS:6441-1972 of Compressive strength 3 N/mm2 600x 230 x 200 mm from approved source having minimum crushing strength of 3 N/Sq.m including cost and conveyance of all materials like cement, sand, bricks, water etc., to site, including sales & other taxes on all materials, all operational, incidental and labour charges such as mixing cement mortar, constructing masonry, scaffolding charges, lift charges, curing, etc., complete but excluding seigniorage charges for finished item of work. (APSS No. 501 & 504).
[6 empty] | 16.3192 | 10.5 | 14558 | cum |  | 152859 |  | 10.5 | 152859 | - | - |  |  | 14558
[6 empty] | AE | 5.82
4 | 253 | Reinforced Masonry for partiton walls 100 mm thick in CM (1:4) prop (cement: Screened sand) in super structure with Aerated Cellular Autoclaved Concrete Blocks conforming to IS:2185 (Part-3) - 1984 and IS:6441-1972 of Compressive strength 3 N/mm2 600x 200 x 100 mm from approved source having minimum crushing strength of 3 N/Sq.m including cost and conveyance of all materials like cement, sand, bricks, water etc., to site, including sales & other taxes on all materials, all operational, incidental and labour charges such as mixing cement mortar, constructing masonry, scaffolding charges, lift charges, curing, etc., complete but excluding seigniorage charges for finished item of work. (APSS No. 501 & 504).
[6 empty] | 219.7595 | 215 | 1716 | Sqm |  | 368940 |  | 215 | 368940 | - | - |  |  | 1716
[6 empty] | AE | 4.7595
5 | 256 | Plastering 12mm thick in two coats using screened sand with base coat of 8mm thick in CM (1:6) and top coat of 4mm thick in CM (1:4) with dubara sponge finishing including cost and conveyance of all materials like cement, sand, water etc., to site, including sales & other taxes on all materials, and all operational, incidental charges on materials and including cost of all labour charges for mixing mortar, finishing, scaffolding, lift charges, curing, including cutting grooves as directed by Engineer-in-charge etc., and overheads & contractors profit complete for finished item of work. (SS 901,903 & 904).
[6 empty] | 822.13 | 430 | 906 | Sqm |  | 389580 |  | 430 | 389580 | 0 | 0 |  |  | 906
[6 empty] | AE:- | 392.13
6 | 263 | Flooring with soluble salt porcelain vitrified tiles screen printed and polished of size 600 x 600 mm and thickness between 8 to 10mm 1st quality conforming to IS: 13711, IS: 13712, IS: 13630Parts 1 to 15 of any colour and finish in all shades and designs with borders and design as per the approved flooring pattern as directed by the Engineer-In -Charge, laying tiles using spacers of 2mm thick, set over a base coat of CM 1:8 prop. 12mm thick using screened sand over CC bed already laid or RCC roof slab, including neat cement slurry of honey like consistency spread at the rate 3.3 kgs per Sqm. and jointed neatly with white cement paste to full depth mixed with pigment of matching shade including cost and conveyance of all materials like cement, sand, water, tiles, white cement etc., to site excluding cost of C.C. bed including cost of base coat and all labour charges for mixing of cement mortar, laying tiles to required slope as directed by the Engineer- in- charge etc., and complete for finished item of work. TSSS No.701 and 707.
[6 empty] | 294.66 | 294.659 | 1593 | Sqm |  | 469391.787 |  | 294.66 | 469393.38 | - | - |  |  | 1593
7 | 266 | Providing dadooing to walls with glazed full body porcelain wall tiles of size 300 x 600 mm with any type of design texture such as marble finish, wooden, bamboo, stone finishes etc., scratch less, stain free and thickness between 6-8 mm 1st quality conforming to IS:13711, IS:13712, IS:13630 Parts 1 to 15 of any colour and finish in all shades and designs with borders as approved by Engineer-in-Charge set over base coat of CM1:5 12 mm thick using screened sand with cement slurry of honey like consistency spread at the rate of 3.30 kgs per sqm and jointing with white cement paste mixed with pigment of matching shade to full depth, including cost of all materials like tiles, cement, sand and water etc., complete for finished item of work. 3rd Floor at Petlaburj Hospital
[6 empty] | 153.0952 | 30 | 1391 | Sqm |  | 41730 |  | 30 | 41730 | - | - |  |  | 1391
[6 empty] | AE | 123.0952
[9 empty] | Civil Sub-Total:- |  | 1444212.027 |  |  | 1444213.62 |  | 0
Civil Supplemental Items
1 |  | Dismantling, clearing away and carefully stacking useful materials for re-use and disposal of unserviceable materials with 100m lead as directed by Executive Engineer duly taking actual premeasurements before dismantling including all labour charges , overheads & contractor profit etc., complete Finished item of work
a)Old Cement Mortar
[6 empty] | 251.59 | 251.5889
b)Reinforced Cement Concrete
[6 empty] | 0.43 | 0.4293
2 |  | Providing Thermo Mechanically Treated ( TMT) ( Fe-500/500D/550D from primery producer TATA, SAIL, VSP, JSW Steel, Goel steel, Jindal panther, X- Vega & balaji Shakthi as per IS 1786-2008) of Different Diameters RCC Works , including labour charges for straightening, cutting, bending to required sizes and shapes, placing in position with cover blocks of approved materials and sizes and typing and lap - spacing with binding wire of 18 SWG, Forming grills for reinforcement work as per approved design and drawings, including and conveyanace of steel bars, including all wastages such as overlaps, coupling, chairs, spacer bars including cost and conveyance of binding wire cover blocks and incidential, operational, labour charges such as cutting bending, placing in position, typing incliding sales and other taxes on all materials etc., and overheads & contractors profit completefor finished item of work
0.2956
3 |  | Supply and placing of the Design Mix Concrete M 25 grade corresponding to IS 456 with minimum cement content of 380 kgs per 1 cum of concrete using Weight Batcher / Concrete mixer with 20mm size graded machine crushed hard granite metal (coarse aggregate - as per IS 383 - 1970 and IS 2386 Part 1 to Part 8) from approved quarry including cost and conveyance of all materials like cement, fine aggregate (sand) coarse aggregate, water etc., to site and sales & other taxes on all materials, centering using Casurina Ballies, Bamboos, Wooden Reapers, Runners, Wood Posts, Steel Plates etc., including all operational, incidental and labour charges such as weigh batching, machine mixing, lifting of concrete manually, laying concrete, curing , overheads & contractors profit etc., complete but excluding cost of steel and its fabrication charges for finished item of work (APSS No. 402)
For Lintels
[6 empty] | 0.75 | 0.74952
4 |  | Providing skirting to internal walls to 10 cm height with Double charged / multi charged stain free fullbody porcelain vitrified tiles with double layer pigment of size 600 x 600 mm and thickness between 8-10 mm 1st quality conforming to IS:15622 - 2017, IS:13630 (Parts 1 to 15) of any colour and finish in all shades and designs, length equal to flooring tiles, set over base coat of CM(1:5) 12 mm thick using screened sand with cement slurry of honey like consistency spread at the rate of 3.30 kgs per sqm and jointing with white cement paste mixed with pigment of matching shade to full depth, including cost of all materials like tiles, cement, sand and water etc.,and overheads & contractors profit complete for finished item of work.(APSS No.701 &707)
[6 empty] | 174.5 | 174.5
[8 empty] | Civil Suppl. Sub-Total:- |  |  | 0 |  |  | 0 |  | 0
Equipment Items
1 | 200 | IVF Test tube Warmers at Petlaburz Hospital
[6 empty] | 2 | 2 | 34650 | Nos |  | 69300 |  | 2 | 69300 |  |  |  | 70% | 49500
2 | 201 | DICOM compatible fully digital, compact, portable, Ultrasound Scan Machine Colour Doppler at Petlaburz Hospital
[6 empty] | 2 | 2 | 955500 | Nos |  | 1911000 |  | 2 | 1911000 |  |  |  | 70% | 1365000
3 | 202 | Multipurpose Electro hydraulic with manual override mobile OT Table, with divided leg section suitable for all Gynaecological surgical procedures, complete with 5cm Mattress and corded handset at Petlaburz Hospital
[6 empty] | 1 | 1 | 394625 | Nos |  | 394625 |  | 1 | 394625 |  |  |  | 70% | 563750
4 | 203 | LED procedure Lights Double dome at petlaburz Hospital
[6 empty] | 1 | 1 | 218750 | Nos |  | 218750 |  | 1 | 218750 |  |  |  | 70% | 312500
5 | 204 | LED procedure Lights Single dome at petlaburz Hospital
[6 empty] | 1 | 1 | 131250 | Nos |  | 131250 |  | 1 | 131250 |  |  |  | 70% | 187500
6 | 207 | CO2 Incubators at Petlaburz Hospital
[6 empty] | 2 | 2 | 577500 | Nos |  | 1155000 |  | 2 | 1155000 |  |  |  | 70% | 825000
7 | 212 | IVF Thermometer at Petlaburz Hospital
[6 empty] | 1 | 1 | 43313 | Nos |  | 43313 |  | 1 | 43313 |  |  |  | 70% | 61875
8 | 213 | CO2 Cylinder and Manifold at Petlaburz Hospital
[6 empty] | 2 | 2 | 35000 | Nos |  | 70000 |  | 2 | 70000 |  |  |  | 70% | 50000
9 | 214 | CO2 and O2 Analyzer at Petlaburz Hospital
[6 empty] | 2 | 1 | 264600 | Nos |  | 264600 |  | 1 | 264600 |  |  |  | 70% | 378000
10 | 215 | PH Meter at Petlaburz Hospital
[6 empty] | 1 | 1 | 65625 | Nos |  | 65625 |  | 1 | 65625 |  |  |  | 70% | 93750
11 | 217 | Sperm Counting Markler Chamber at Petlaburz Hospital
[6 empty] | 1 | 1 | 52938 | Nos |  | 52938 |  | 1 | 52938 |  |  |  | 70% | 75625
12 | 220 | Clinical Centrifuge machine for Andrology at Petlaburz Hospital
[6 empty] | 1 | 1 | 24150 | Nos |  | 24150 |  | 1 | 24150 |  |  |  | 70% | 34500
13 | 221 | DRY Incubator at Petlaburz Hospital
[6 empty] | 1 | 1 | 394625 | Nos |  | 394625 |  | 1 | 394625 |  |  |  | 70% | 563750
14 | 223 | Pharmaceutical Refrigerator at Petlaburz Hospital
[6 empty] | 1 | 1 | 157500 | Nos |  | 157500 |  | 1 | 157500 |  |  |  | 70% | 225000
15 | 224 | Cryocane (TA 26 Ltr) with wheels at Petlaburz Hospital
[6 empty] | 2 | 2 | 43313 | Nos |  | 86626 |  | 2 | 86626 |  |  |  | 70% | 61875
16 | 225 | Defibrillator at Petlaburz Hospital
[6 empty] | 1 | 1 | 218750 | Nos |  | 218750 |  | 1 | 218750 |  |  |  | 70% | 312500
17 | 226 | 7 Para Patient Monitor at Petlaburz Hospital
[6 empty] | 2 | 2 | 196000 | Nos |  | 392000 |  | 2 | 392000 |  |  |  | 70% | 280000
18 | 228 | Anaesthesia Work station at Petlaburz Hospital
[6 empty] | 1 | 1 | 656250 | Nos |  | 656250 |  | 1 | 656250 |  |  |  | 70% | 937500
19 | 232 | Mulitfunctional Printer at Petlaburz Hospital
[6 empty] | 1 | 1 | 30625 | Nos |  | 30625 |  | 1 | 30625 |  |  |  | 70% | 43750
20 | 233 | Ultrasound Examination Couch at Petlaburz Hospital
[6 empty] | 1 | 1 | 56875 | Nos |  | 56875 |  | 1 | 56875 |  |  |  | 70% | 81250
21 | 235 | Laptop For Office Usage at Petlaburz Hospital
[6 empty] | 2 | 2 | 80500 | Nos |  | 161000 |  | 2 | 161000 |  |  |  | 70% | 115000
22 | 320 | 20 KVA UPS: Supply and installation of 20KVA 3ph in and 3ph out on line UPS system IGBT based rectifier with input power factor correction 32 bit microprocessor based with isolation transformers double conversion, SNMP controls, LCD display, Pure sine wave output, with auto static switch three phase input / Three phase output and modular structure for better thermal technology / cooling facility, with warranty up to three years.Makes: APC / Numeric / Emerson / Fuji Electric At Petlaburz
[6 empty] | 1 | 1 | 213500 | Nos |  | 213500 |  | 1 | 213500 |  |  |  | 70% | 305000
23 | 322 | Supply and providing of UPS Cum battery rack for 20 batteries at MGMH Petlaburz
[6 empty] | 1 | 1 | 4735 | Nos |  | 4735 |  | 1 | 4735 |  |  |  | 70% | 6764
1 | 199 | Ovum Aspiration Pumps at Petlaburj Hospital
[6 empty] | 2 | 2 | 168000 | Nos |  | 336000 |  |  |  | 2 | 336000 |  | 70% | 240000
2 | 205 | IVF Workstation with LAF at Petlaburj Hospital
[6 empty] | 1 | 1 | 481250 | Nos |  | 481250 |  |  |  | 1 | 481250 |  | 70% | 687500
3 | 206 | IVF Ant vibration Table for procedure at Petlaburj Hospital
[6 empty] | 1 | 1 | 67375 | Nos |  | 67375 |  |  |  | 1 | 67375 |  | 70% | 96250
4 | 208 | Trigas bench Top Incubators for Human Embryo culture at Petlaburj Hospital
[6 empty] | 1 | 1 | 577500 | Nos |  | 577500 |  |  |  | 1 | 577500 |  | 70% | 825000
5 | 209 | Trinocular Stereozoom Microscope at Petlaburj Hospital
[6 empty] | 1 | 1 | 216300 | Nos |  | 216300 |  |  |  | 1 | 216300 |  | 70% | 309000
6 | 210 | ICSI Micro manipulator with Inverted Microscope at Petlaburj Hospital
[6 empty] | 1 | 1 | 1837500 | Nos |  | 1837500 |  |  |  | 1 | 1837500 |  | 70% | 2625000
7 | 211 | IVF Laser System at Petlaburj Hospital
[6 empty] | 1 | 1 | 1792000 | Nos |  | 1792000 |  |  |  | 1 | 1792000 |  | 70% | 2560000
8 | 216 | VOC Meter for ART Lab at Petlaburj Hospital
[6 empty] | 1 | 1 | 511875 | Nos |  | 511875 |  |  |  | 1 | 511875 |  | 70% | 731250
9 | 218 | Binocular Microscope for Semen Analysis at Petlaburj Hospital
[6 empty] | 1 | 1 | 28875 | Nos |  | 28875 |  |  |  | 1 | 28875 |  | 70% | 41250
10 | 219 | Laminar flow cabinet with Andrology Work station at Petlaburj Hospital
[6 empty] | 1 | 1 | 175000 | Nos |  | 175000 |  |  |  | 1 | 175000 |  | 70% | 250000
11 | 222 | Pipetter and Denudation system at Petlaburj Hospital
[6 empty] | 1 | 1 | 72188 | Nos |  | 72188 |  |  |  | 1 | 72188 |  | 70% | 103125
12 | 229 | Autoclave at Petlaburj Hospital
[6 empty] | 1 | 1 | 393750 | Nos |  | 393750 |  |  |  | 1 | 393750 |  | 70% | 562500
13 | 236 | Reception Table at Petlaburj Hospital
[6 empty] | 1 | 1 | 77000 | Nos |  | 77000 |  |  |  | 1 | 77000 |  | 70% | 110000
14 | 238 | Filing Cabinet at Petlaburj Hospital
[6 empty] | 2 | 2 | 24150 | Nos |  | 48300 |  |  |  | 2 | 48300 |  | 70% | 34500
15 | 239 | Patient Seating 3 in 1 model at Petlaburj Hospital
[6 empty] | 3 | 3 | 26950 | Nos |  | 80850 |  |  |  | 3 | 80850 |  | 70% | 38500
16 | 244 | Wall Storage Cabinets at Petlaburj Hospital
[6 empty] | 8 | 8 | 12250 | Nos |  | 98000 |  |  |  | 8 | 98000 |  | 70% | 17500
17 | 245 | Office Table at Petlaburj Hospital
[6 empty] | 3 | 3 | 14000 | Nos |  | 42000 |  |  |  | 3 | 42000 |  | 70% | 20000
[9 empty] | Sub-Total:- |  | 13608800 |  |  | 6773037 |  | 6835763
[8 empty] | Sub-Total(Civil+ Civil Suppl.+Equipment):- |  |  | 15053012.027 |  |  | 8217250.62 |  | 6835763
[9 empty] | Add GST 18% |  | 2709542.1649 |  |  | 1479105.1116 |  | 1230437.34
[9 empty] | GrandTotal:- |  | 17762554.1919 |  |  | 9696355.7316 |  | 8066200.34

## Ele-4 (hidden)
DETAILED MEASUREMENTS
Name of the work:Design, Fabriction, establishing and commissioning of In - Vitro ferility centers (IVFC) alongwith allied Services on Turnkey basis at petlaburz Hyderabad. | [10 empty] | Agency: M/s. Asta vardhman Consortium | [5 empty] | Agt.No: 344/A/TSMIDC/Spl.Proj/IVFCs/2022-23, Dt. 05.07.2023
S.No | Agreement S.No | Discription Of Work etc., | Measurements Upto date | [5 empty] | Rate |  |  | Per | Total Volume |  | Deduct/previous Measurements |  | Since last measurement |  |  | Remarks
|  |  | No |  | L | B | D | Content | Units | Rs | Ps. |  | Rs. | Ps | P.No. | Qty. | Qty | Value
[18 empty] | Rs. | Ps.
1 | 293 | Supply and laying of ISI 25mm outer dia medium grade with IS:9537-part 3 rigid PVC pipe concealed in wall with all required PVC / Metallic Junction Boxes including masonry work and labour charges etc., Makes: Sudhakar / Precision /Universal/ Modi / Million Plast. at MGMH Petlaburj
|  | Entance | 1 | 1 | 1.5 |  |  | 1.5
|  | Reception | 1 | 1 | 10.7 |  |  | 10.7
|  | Doctor Chancge room | 1 | 1 | 13.4 |  |  | 13.4
|  | Record room | 1 | 1 | 9.2 |  |  | 9.2
|  | Senior faculity | 1 | 1 | 17.4 |  |  | 17.4
|  | Passage / Tolet | 1 | 1 | 4.7 |  |  | 4.7
|  | Ultra sound | 1 | 1 | 25.1 |  |  | 25.1
|  | Sample collection | 1 | 1 | 13.3 |  |  | 13.3
|  | Store room | 1 | 1 | 7.6 |  |  | 7.6
|  | Passage | 1 | 1 | 1.9 |  |  | 1.9
|  | Pre Operative ward | 1 | 1 | 15.2 |  |  | 15.2
|  | Clean Store room | 1 | 1 | 3.8 |  |  | 3.8
|  | Auto clave room | 1 | 1 | 17.9 |  |  | 17.9
|  | Passage | 1 | 1 | 7.4 |  |  | 7.4
|  | Mainfold | 1 | 1 | 10.9 |  |  | 10.9
|  | Electrical / UPS room | 1 | 1 | 14.1 |  |  | 14.1
|  | Major OT | 1 | 1 | 28.4 |  |  | 28.4
|  | Androgoly Lab | 1 | 1 | 31.5 |  |  | 31.5
|  | Cryo room | 1 | 1 | 10.4 |  |  | 10.4
|  | Serum collection | 1 | 5 | 2.9 |  |  | 14.5
|  | Lighting line | 1 | 5 | 1.6 |  |  | 8
|  | Waiting PP line | 1 | 2 | 2.9 |  |  | 5.8
|  | Lighting line | 1 | 2 | 1.2 |  |  | 2.4
|  | Lighting line | 1 | 2 | 1.9 |  |  | 3.8
|  | Post Operative ward PP line | 1 | 4 | 2.9 |  |  | 11.6
|  | Lighting line | 1 | 6 | 1.7 |  |  | 10.2
|  | Embrogolist room PP line | 1 | 4 | 2.9 |  |  | 11.6
|  | Lighting line | 1 | 2 | 1.7 |  |  | 3.4
|  | AC | 1 | 1 | 1.2 |  |  | 1.2
|  | Anesthestist PP line | 1 | 2 | 2.9 |  |  | 5.8
|  | Lighting line | 1 | 2 | 1.7 |  |  | 3.4
|  | Ac | 1 | 1 | 1.4 |  |  | 1.4
|  | Passage/ Toilet | 1 | 2 | 1.8 |  |  | 3.6
|  | Patient Change room PP line | 1 | 1 | 2.9 |  |  | 2.9
|  | Lighting line | 1 | 2 | 1.7 |  |  | 3.4
|  | Passage/ Toilet | 1 | 2 | 1.7 |  |  | 3.4
|  | Counselling room-1 PP Line | 1 | 3 | 2.9 |  |  | 8.7
|  | Lighting line | 1 | 4 | 1.7 |  |  | 6.8
|  | AC | 1 | 1 | 1.5 |  |  | 1.5
|  | Counselling room-2 PP line | 1 | 4 | 2.9 |  |  | 11.6
|  | Lighting line | 1 | 2 | 1.9 |  |  | 3.8
|  | AC | 1 | 2 | 1.2 |  |  | 2.4
|  | Passage/ Toilet | 1 | 4 | 1.8 |  |  | 7.2
|  | Corridoor DB-1 | 1 | 5 | 1.5 |  |  | 7.5
|  | DB-2 | 1 | 5 | 1.5 |  |  | 7.5
|  | DB-3 | 1 | 5 | 1.5 |  |  | 7.5
|  | DB-4 | 1 | 5 | 1.5 |  |  | 7.5
|  | DB-5 | 1 | 5 | 1.5 |  |  | 7.5
|  | DB-6 | 1 | 5 | 1.5 |  |  | 7.5
|  | DB-7 | 1 | 5 | 1.5 |  |  | 7.5
|  | DB-8 | 1 | 5 | 1.5 |  |  | 7.5
|  | DB-9 | 1 | 5 | 1.5 |  |  | 7.5
|  | DB-10 | 1 | 5 | 1.5 |  |  | 7.5
|  | SB-1 | 1 | 1 | 1.9 |  |  | 1.9
|  | SB-2 | 1 | 1 | 1.9 |  |  | 1.9
|  | SB-3 | 1 | 1 | 1.9 |  |  | 1.9
[8 empty] | 463.5 |  | RMT | C/o to Pg No: of M.B.No:
2 | 294 | Supply and laying of ISI 25mm outer dia medium grade with IS:9537-part 3 rigid PVC pipe surface on wall with all required PVC / Metallic Junction Boxes including masonry work and labour charges etc., Makes: Sudhakar / Precision /Universal/ Modi / Million Plast. at MGMH Petlaburj
|  | Entrance | 1 | 1 | 12.2 |  |  | 12.2
|  | Reception | 1 | 1 | 8.5 |  |  | 8.5
|  | Curcuit line | 1 | 1 | 18.9 |  |  | 18.9
|  | Power line | 1 | 1 | 14.4 |  |  | 14.4
|  | AC/ power line | 1 | 1 | 20.7 |  |  | 20.7
|  | Curcuit line | 1 | 1 | 18.5 |  |  | 18.5
|  | Doctor change room | 1 | 1 | 6.2 |  |  | 6.2
|  | Record room | 1 | 1 | 9.4 |  |  | 9.4
|  | Senior facuilty | 1 | 1 | 15.2 |  |  | 15.2
|  | Passage/toilet | 1 | 1 | 12.4 |  |  | 12.4
|  | Ultra sound | 1 | 1 | 17.9 |  |  | 17.9
|  | Sample collection | 1 | 1 | 8.7 |  |  | 8.7
|  | Store room | 1 | 1 | 17.9 |  |  | 17.9
|  | Passage | 1 | 1 | 4 |  |  | 4
|  | Pre operative ward | 1 | 1 | 21.1 |  |  | 21.1
|  | Clean store room | 1 | 1 | 9.7 |  |  | 9.7
|  | Auto clave | 1 | 1 |  |  |  | 0
|  | Passage | 1 | 1 | 6.2 |  |  | 6.2
|  | IVF OT Power line | 1 | 1 | 23.9 |  |  | 23.9
|  | Lighting line | 1 | 1 | 15.6 |  |  | 15.6
|  | Embrology | 1 | 1 | 36.4 |  |  | 36.4
|  | Mainfold | 1 | 1 | 9.9 |  |  | 9.9
|  | Electrical / UPS Room | 1 | 1 | 10.2 |  |  | 10.2
|  | Lighting line | 1 | 1 | 5.2 |  |  | 5.2
|  | Major OT | 1 | 1 | 34.3 |  |  | 34.3
|  | Androgoly Lab | 1 | 1 | 53.6 |  |  | 53.6
|  | Cryo room | 1 | 1 | 8.8 |  |  | 8.8
|  | Serum collection | 1 | 1 | 21.9 |  |  | 21.9
|  | Waiting | 1 | 1 | 3.7 |  |  | 3.7
|  | Post operative ward | 1 | 1 | 17.1 |  |  | 17.1
|  | Embrologist room | 1 | 1 | 22.6 |  |  | 22.6
|  | Anesthestist | 1 | 1 | 6.8 |  |  | 6.8
|  | Passage/toilet | 1 | 1 | 6.6 |  |  | 6.6
|  | Pateint change room | 1 | 1 | 25.1 |  |  | 25.1
|  | Passage/toilet | 1 | 1 | 9.5 |  |  | 9.5
|  | Counselling room -1 LL line | 1 | 1 | 19.8 |  |  | 19.8
|  | PP-1 line | 1 | 1 | 17.8 |  |  | 17.8
|  | AC/ power line | 1 | 1 | 15.9 |  |  | 15.9
|  | Ups line | 1 | 1 | 15.1 |  |  | 15.1
|  | Counselling room-2 | 1 | 1 | 5.6 |  |  | 5.6
|  | Passage/toilet | 1 | 1 | 15.1 |  |  | 15.1
|  | Corridoor LL ling | 1 | 1 | 33.1 |  |  | 33.1
|  | Drops | 1 | 10 | 3.1 |  |  | 31
|  | Near senior Faculty Curcuit line-1 | 1 | 1 | 9.8 |  |  | 9.8
|  | Curcuit Line-2 | 1 | 2 | 7.8 |  |  | 15.6
|  | Curcuit line-4 | 1 | 1 | 6.1 |  |  | 6.1
|  | UPS Line-1 | 1 | 1 | 4.8 |  |  | 4.8
|  | UPS line-2 | 1 | 1 | 3.8 |  |  | 3.8
|  | Near Auto Clave Curcuit line-1 | 1 | 2 | 9.1 |  |  | 18.2
|  | Curcuit line-2 | 1 | 2 | 6.3 |  |  | 12.6
|  | Power line-1 | 1 | 2 | 6.3 |  |  | 12.6
|  | Power line-2 | 1 | 1 | 4.8 |  |  | 4.8
|  | Power line-3 | 1 | 1 | 4.3 |  |  | 4.3
|  | Near Counselling -1 Curcuit line-1 | 1 | 1 | 9.8 |  |  | 9.8
|  | Curcuit Line-2 | 1 | 2 | 7.8 |  |  | 15.6
|  | Curcuit line-4 | 1 | 1 | 6.1 |  |  | 6.1
|  | UPS Line-1 | 1 | 1 | 4.8 |  |  | 4.8
|  | UPS line-2 | 1 | 1 | 3.8 |  |  | 3.8
|  | Near Serum collection Curcuit line-1 | 1 | 2 | 9.1 |  |  | 18.2
|  | Curcuit line-2 | 1 | 2 | 6.3 |  |  | 12.6
|  | Power line-1 | 1 | 2 | 6.3 |  |  | 12.6
|  | Power line-2 | 1 | 1 | 4.8 |  |  | 4.8
|  | Power line-3 | 1 | 1 | 4.3 |  |  | 4.3
|  | Near Mainfold Power Line-1 | 1 | 1 | 10.1 |  |  | 10.1
|  | Power line-2 | 1 | 2 | 8.8 |  |  | 17.6
|  | Curcuit line-1 | 1 | 2 | 4.1 |  |  | 8.2
|  | Curcuit line-2 | 1 | 1 | 3.8 |  |  | 3.8
|  | Near Major OT PP line-1 | 1 | 1 | 7.8 |  |  | 7.8
|  | Curcuit line-1 | 1 | 1 | 6.2 |  |  | 6.2
|  | Curcuit line-3 | 1 | 1 | 3.8 |  |  | 3.8
|  | PP-2 | 1 | 1 | 7.4 |  |  | 7.4
|  | PP-3 | 1 | 1 | 5.6 |  |  | 5.6
|  | AC/ power line | 1 | 1 | 4.3 |  |  | 4.3
|  | Curcuit line-4 | 1 | 1 | 3.9 |  |  | 3.9
|  | Main line-1 | 1 | 1 | 35 |  |  | 35
|  | Main line-2 | 1 | 1 | 38 |  |  | 38
|  | Main line-3 | 1 | 1 | 39 |  |  | 39
|  | Main line-4 | 1 | 1 | 46 |  |  | 46
|  | Main line-5 | 1 | 1 | 43 |  |  | 43
|  | Main line-6 | 1 | 1 | 42 |  |  | 42
|  | Main line-7 | 1 | 1 | 33.1 |  |  | 33.1
|  | Main line-8 | 1 | 1 | 32.1 |  |  | 32.1
|  | Main line-9 | 1 | 1 | 30.1 |  |  | 30.1
|  | Main line-10 | 1 | 1 | 29.1 |  |  | 29.1
|  | Auto clave | 1 | 1 | 35 |  |  | 35
[8 empty] | 1352.8 |  | RMT | C/o to Pg No: of M.B.No:
3 | 295 | Wiring with 2 runs of 22/0.3mm 1.5 Sq.mm FRLS / HFFR P.V.C. insulated flexible copper cable ISI MARK in existing pipe with 6A Modular switch, Ceiling rose/BH/SBH Modular switches with cover plate and GI switch box including all labour charges etc., complete. for Non- Residential Building Makes of wires: Polycab Makes of switches: - /Honeywell Blenge Plus at MGMH Petlaburj
|  | Entrance | 1 | 4 |  |  |  | 4
|  | Reception | 1 | 7 |  |  |  | 7
|  | Doctors change room | 1 | 3 |  |  |  | 3
|  | Record room | 1 | 2 |  |  |  | 2
|  | Senior Faculty | 1 | 5 |  |  |  | 5
|  | Passage/ Toilet | 1 | 7 |  |  |  | 7
|  | Ultra sound | 1 | 5 |  |  |  | 5
|  | Sample collection | 1 | 3 |  |  |  | 3
|  | Store collection | 1 | 3 |  |  |  | 3
|  | Passage | 1 | 2 |  |  |  | 2
|  | IVF OT | 1 | 8 |  |  |  | 8
|  | Embrogoly | 1 | 8 |  |  |  | 8
|  | Mainfold | 1 | 4 |  |  |  | 4
|  | Electrical room | 1 | 5 |  |  |  | 5
|  | UPS room | 1 | 5 |  |  |  | 5
|  | Major OT | 1 | 8 |  |  |  | 8
|  | Androgoly Lab | 1 | 6 |  |  |  | 6
|  | Cryo room | 1 | 3 |  |  |  | 3
|  | Serum collection | 1 | 3 |  |  |  | 3
|  | Wating/ Passage | 1 | 4 |  |  |  | 4
|  | Post Operative ward | 1 | 8 |  |  |  | 8
|  | Embrologist room | 1 | 3 |  |  |  | 3
|  | Anesthestist | 1 | 3 |  |  |  | 3
|  | Passage/Toilet | 1 | 4 |  |  |  | 4
|  | Patient Change room | 1 | 3 |  |  |  | 3
|  | Staff change room 1&2 | 1 | 2 |  |  |  | 2
|  | Passage & Toilet | 1 | 4 |  |  |  | 4
|  | Councelling room-1 | 1 | 3 |  |  |  | 3
|  | Councelling room-2 | 1 | 3 |  |  |  | 3
|  | Passage & Toilet | 1 | 4 |  |  |  | 4
|  | Corridoor | 1 | 16 |  |  |  | 16
[8 empty] | 148 |  | No's | C/o to Pg No: of M.B.No:
4 | 300 | Supply and run of 1 of 22 /0.3mm 1.5 Sq.mm FRLS / HFFR P.V.C. insulated flexible copper cable in existing conduit pipe for earth continuity including all labour charges etc., complete. Makes of wires: Finolex/ RR Cable/ Havells/ Polycab/ HPL. at MGMH Petlaburj
|  | IVF OT | 1 | 8 | 9.6 |  |  | 76.8
|  | Embrogoly lab | 1 | 8 | 7.2 |  |  | 57.6
|  | Major OT | 1 | 8 | 9.9 |  |  | 79.2
|  | Androgoly Lab | 1 | 6 | 11.2 |  |  | 67.2
|  | Pre Operative ward | 1 | 8 | 4.9 |  |  | 39.2
|  | Post Operative ward | 1 | 8 | 5.5 |  |  | 44
|  | Auto Clave | 1 | 3 | 5.2 |  |  | 15.6
[8 empty] | 379.6 |  | Rmt | C/o to Pg No: of M.B.No:
5 | 301 | Supply and run of 3 of 2.5 sq.mm 36/0.mm phase neutral and earth FRLS / HFFR PVC insulated flexible copper cable in existing conduit pipe for individual lighting circuits including labour charges etc., complete as required for switch boards. Makes of wires: Finolex/ RR Cable/ Havells/ Polycab/ HPL. at MGMH Petlaburj
|  | Entrance | 1 | 1 | 30.4 |  |  | 30.4
|  | Reception | 1 | 2 | 23.2 |  |  | 46.4
|  | UPS Line | 1 | 2 | 26.4 |  |  | 52.8
|  | SB | 1 | 2 | 21.1 |  |  | 42.2
|  | Doctor change room | 1 | 2 | 19.5 |  |  | 39
|  | Record room | 1 | 1 | 27.5 |  |  | 27.5
|  | SB | 1 | 2 | 21.7 |  |  | 43.4
|  | Senior Faculty | 1 | 2 | 19.9 |  |  | 39.8
|  | Toilet | 1 | 1 | 23.4 |  |  | 23.4
|  | Passage | 1 | 1 | 20.3 |  |  | 20.3
|  | Ultra sound | 1 | 2 | 14.7 |  |  | 29.4
|  | Sample collection | 1 | 2 | 12.6 |  |  | 25.2
|  | Store room | 1 | 2 | 22.6 |  |  | 45.2
|  | Passage | 1 | 2 | 20.5 |  |  | 41
|  | Pre poerative ward | 1 | 2 | 18.5 |  |  | 37
|  | Clean store room | 1 | 2 | 24.6 |  |  | 49.2
|  | Auto clave | 1 | 2 | 30.6 |  |  | 61.2
|  | Passage | 1 | 1 | 24.1 |  |  | 24.1
|  | IVF OT | 1 | 2 | 15.5 |  |  | 31
|  | Embrogoly lab | 1 | 2 | 18.4 |  |  | 36.8
|  | Mainfold | 1 | 2 | 36.3 |  |  | 72.6
|  | Electrical room | 1 | 2 | 39.6 |  |  | 79.2
|  | UPS room | 1 | 2 | 45.4 |  |  | 90.8
|  | Major OT | 1 | 1 | 16.5 |  |  | 16.5
|  | Androgoly Lab | 1 | 2 | 18.2 |  |  | 36.4
|  | SB | 1 | 2 | 14.5 |  |  | 29
|  | Cryo room | 1 | 2 | 14.3 |  |  | 28.6
|  | Serum collection SB-1 | 1 | 1 | 24.2 |  |  | 24.2
|  | SB-2 | 1 | 1 | 22.1 |  |  | 22.1
|  | SB-3 | 1 | 2 | 21.7 |  |  | 43.4
|  | SPP-1 | 1 | 1 | 19.2 |  |  | 19.2
|  | Waiting | 1 | 2 | 20.3 |  |  | 40.6
|  | Post operative ward SB- | 1 | 2 | 16.4 |  |  | 32.8
|  | SPP-1 | 1 | 1 | 22.2 |  |  | 22.2
|  | Embrologist room | 1 | 2 | 18.9 |  |  | 37.8
|  | Anesthestist | 1 | 2 | 17.6 |  |  | 35.2
|  | Passage/toilet SB-1 | 1 | 1 | 22.2 |  |  | 22.2
|  | SB-2 | 1 | 1 | 19.7 |  |  | 19.7
|  | Pateint change room | 1 | 2 | 21.1 |  |  | 42.2
|  | Staff change room 1 & 2 SB-1 | 1 | 1 | 18.8 |  |  | 18.8
|  | SB-2 | 1 | 1 | 18.6 |  |  | 18.6
|  | SPP-1 | 1 | 1 | 15.8 |  |  | 15.8
|  | Passage/toilet SB-1 | 1 | 1 | 21.6 |  |  | 21.6
|  | Counselling room-1 | 1 | 2 | 23.4 |  |  | 46.8
|  | Counselling room-2 | 1 | 2 | 20.7 |  |  | 41.4
|  | Passage/toilet SB-1 | 1 | 1 | 24.1 |  |  | 24.1
|  | SB-2 | 1 | 1 | 21.9 |  |  | 21.9
|  | Corridoor SB-1 | 1 | 1 | 19.1 |  |  | 19.1
|  | SB-2 | 1 | 1 | 14.3 |  |  | 14.3
|  | SB-3 | 1 | 1 | 10.7 |  |  | 10.7
[8 empty] | 1713.1 |  | Rmt | C/o to Pg No: of M.B.No:
6 | 302 | Supply and 3 runs of 4.0 sq mm 56/0.3 mm phase neutral and earth FRLS / HFFR PVC insulated flexible copper cable in existing conduit pipe including labour charges etc., complete for 16A sockets. Makes of wires: Finolex/ RR Cable/ Havells/ Polycab/ HPL. at MGMH Petlaburj
|  | Reception AC-1 | 1 | 1 | 28.8 |  |  | 28.8
|  | AC-2 | 1 | 1 | 28.6 |  |  | 28.6
|  | Doctor change room PP-1 | 1 | 1 | 20.4 |  |  | 20.4
|  | PP-2 | 1 | 1 | 16.2 |  |  | 16.2
|  | Record room | 1 | 1 | 25.2 |  |  | 25.2
|  | Senior facluty PP-1 | 1 | 1 | 23.1 |  |  | 23.1
|  | PP-2 | 1 | 1 | 22.5 |  |  | 22.5
|  | PP-3 | 1 | 1 | 19.9 |  |  | 19.9
|  | AC | 1 | 2 | 19.5 |  |  | 39
|  | Ultra sound PP-1 | 1 | 1 | 19.2 |  |  | 19.2
|  | PP-2 | 1 | 1 | 17.4 |  |  | 17.4
|  | AC-1 | 1 | 1 | 14.9 |  |  | 14.9
|  | AC-2 | 1 | 1 | 15.5 |  |  | 15.5
|  | PP-3 | 1 | 1 | 16.8 |  |  | 16.8
|  | PP-4 | 1 | 1 | 15.8 |  |  | 15.8
|  | Sample collection PP-1 | 1 | 1 | 11.9 |  |  | 11.9
|  | PP-2 | 1 | 1 | 12.7 |  |  | 12.7
|  | PP-3 | 1 | 1 | 10.4 |  |  | 10.4
|  | AC | 1 | 1 | 13 |  |  | 13
|  | Store room PP-1 | 1 | 1 | 26.9 |  |  | 26.9
|  | PP-1 | 1 | 1 | 23.9 |  |  | 23.9
|  | Preoperative ward PP-1 | 1 | 2 | 26.2 |  |  | 52.4
|  | PP-2 | 1 | 1 | 23.2 |  |  | 23.2
|  | PP-3 | 1 | 1 | 20.2 |  |  | 20.2
|  | PP-4 | 1 | 1 | 22.1 |  |  | 22.1
|  | AC | 1 | 1 | 26 |  |  | 26
|  | Autoclave PP-1 | 1 | 1 | 28.7 |  |  | 28.7
|  | PP-2 | 1 | 1 | 27.7 |  |  | 27.7
|  | PP-3 | 1 | 1 | 30.7 |  |  | 30.7
|  | PP-4 | 1 | 1 | 29.4 |  |  | 29.4
|  | PP-5 | 1 | 1 | 29.7 |  |  | 29.7
|  | IVF OT PP1 | 1 | 1 | 23.4 |  |  | 23.4
|  | PP-2 | 1 | 1 | 21.3 |  |  | 21.3
|  | PP-3 | 1 | 1 | 18.7 |  |  | 18.7
|  | PP-4 | 1 | 1 | 21.6 |  |  | 21.6
|  | PP-5 | 1 | 1 | 19.7 |  |  | 19.7
|  | PP-6 | 1 | 1 | 18.3 |  |  | 18.3
|  | Emborgoly Lab PP-1 | 1 | 1 | 24.8 |  |  | 24.8
|  | PP-2 | 1 | 1 | 23.8 |  |  | 23.8
|  | PP-3 | 1 | 1 | 22.3 |  |  | 22.3
|  | PP-4 | 1 | 1 | 26.9 |  |  | 26.9
|  | PP-5 | 1 | 1 | 22.7 |  |  | 22.7
|  | PP-6 | 1 | 1 | 21.1 |  |  | 21.1
|  | PP-7 | 1 | 1 | 19.5 |  |  | 19.5
|  | Mainfold PP-1 | 1 | 1 | 38.9 |  |  | 38.9
|  | PP-2 | 1 | 1 | 36.2 |  |  | 36.2
|  | PP-3 | 1 | 1 | 40.9 |  |  | 40.9
|  | PP-4 | 1 | 1 | 39.9 |  |  | 39.9
|  | PP-5 | 1 | 1 | 37.4 |  |  | 37.4
|  | UPS room AC-1 | 1 | 1 | 40.3 |  |  | 40.3
|  | AC-2 | 1 | 1 | 39.8 |  |  | 39.8
|  | PP-1 | 1 | 1 | 15.6 |  |  | 15.6
|  | PP-2 | 1 | 1 | 14.5 |  |  | 14.5
|  | PP-3 | 1 | 1 | 13.6 |  |  | 13.6
|  | PP-4 | 1 | 1 | 12.4 |  |  | 12.4
|  | Major OT PP-1 | 1 | 1 | 32.7 |  |  | 32.7
|  | AC-1 | 1 | 1 | 29.2 |  |  | 29.2
|  | PP-2 | 1 | 1 | 30.3 |  |  | 30.3
|  | PP-3 | 1 | 1 | 43.1 |  |  | 43.1
|  | PP-4 | 1 | 1 | 37 |  |  | 37
|  | PP-5 | 1 | 1 | 38.1 |  |  | 38.1
|  | PP-6 | 1 | 1 | 27.6 |  |  | 27.6
|  | PP-7 | 1 | 1 | 37 |  |  | 37
|  | PP-8 | 1 | 1 | 35.4 |  |  | 35.4
|  | AC-2 | 1 | 1 | 38.2 |  |  | 38.2
|  | Androgoly Lab PP-1 | 1 | 1 | 23.8 |  |  | 23.8
|  | AC-1 | 1 | 1 | 21.8 |  |  | 21.8
|  | PP-2 | 1 | 1 | 20.6 |  |  | 20.6
|  | AC-2 | 1 | 1 | 18.6 |  |  | 18.6
|  | PP-3 | 1 | 1 | 17.2 |  |  | 17.2
|  | PP-4 | 1 | 1 | 16.8 |  |  | 16.8
|  | PP-5 | 1 | 1 | 15.7 |  |  | 15.7
|  | PP-6 | 1 | 1 | 21.9 |  |  | 21.9
|  | Cryo room PP-1 | 1 | 1 | 18.1 |  |  | 18.1
|  | PP-2 | 1 | 1 | 14.3 |  |  | 14.3
|  | Serum collection PP-1 | 1 | 1 | 19.6 |  |  | 19.6
|  | Pp-2 | 1 | 1 | 17.8 |  |  | 17.8
|  | AC | 1 | 1 | 21.8 |  |  | 21.8
|  | Waiting PP-1 | 1 | 1 | 16.3 |  |  | 16.3
|  | PP-2 | 1 | 1 | 18.9 |  |  | 18.9
|  | AC | 1 | 1 | 21 |  |  | 21
|  | Post Operative ward PP-1 | 1 | 1 | 20.2 |  |  | 20.2
|  | PP-2 | 1 | 1 | 17.6 |  |  | 17.6
|  | PP-3 | 1 | 2 | 18.8 |  |  | 37.6
|  | PP-4 | 1 | 1 | 15.6 |  |  | 15.6
|  | PP-5 | 1 | 1 | 23.2 |  |  | 23.2
|  | PP-6 | 1 | 1 | 20.9 |  |  | 20.9
|  | AC | 1 | 1 | 21 |  |  | 21
|  | Embrologist room PP-1 | 1 | 1 | 19.8 |  |  | 19.8
|  | PP-2 | 1 | 2 | 21.5 |  |  | 43
|  | Anesthestist PP-1 | 1 | 2 | 15.1 |  |  | 30.2
|  | PP-2 | 1 | 1 | 16.8 |  |  | 16.8
|  | Pateient change room | 1 | 1 | 20.6 |  |  | 20.6
|  | Counselling room -1 PP-1 | 1 | 2 | 24.3 |  |  | 48.6
|  | AC | 1 | 1 | 23.1 |  |  | 23.1
|  | Counselling room -2 PP-1 | 1 | 2 | 22.1 |  |  | 44.2
|  | AC-1 | 1 | 1 | 21.6 |  |  | 21.6
|  | AC-2 | 1 | 1 | 18.4 |  |  | 18.4
[8 empty] | 2421 |  | No's | C/o to Pg No: of M.B.No:
7 | 303 | Supply and run of 5 of 6.0 Sqmm 90/0.3 mm 3 phases, neutral and earth FRLS / HFFR PVC insulated flexible copper cable in the existing conduit pipe for run of mains from Power panel board to TPN DBs with pin type lugs and connections etc., complete. for LDBs Makes of wires: Finolex/ RR Cable/ Havells/ Polycab/ HPL. at MGMH Petlaburj
|  | Main line -1 | 1 | 1 | 45.7 |  |  | 45.7
|  | Main line-2 | 1 | 1 | 51.8 |  |  | 51.8
|  | Main Line -3 | 1 | 1 | 53.3 |  |  | 53.3
|  | Main line-4 | 1 | 1 | 50.6 |  |  | 50.6
|  | Main line-5 | 1 | 1 | 38.7 |  |  | 38.7
[8 empty] | 240.1 |  | RMT | C/o to Pg No: of M.B.No:
8 | 304 | Supply and run of 5 of 10.0 Sqmm 140/0.3 mm 3 phases, neutral and earth FRLS / HFFR PVC insulated flexible copper cable in the existing conduit pipe for run of mains from Power panel board to TPN DBs with pin type lugs and connections etc., complete. for PDBs Makes of wires: Finolex/ RR Cable/ Havells/ Polycab/ HPL. at MGMH Petlaburj
|  | Main line -1 | 1 | 1 | 45.7 |  |  | 45.7
|  | Main line-2 | 1 | 1 | 51.8 |  |  | 51.8
|  | Main Line -3 | 1 | 1 | 53.3 |  |  | 53.3
|  | Main line-4 | 1 | 1 | 50.6 |  |  | 50.6
|  | Main line-5 | 1 | 1 | 38.7 |  |  | 38.7
|  | Auto clave | 1 | 1 | 43.9 |  |  | 43.9
[8 empty] | 284 |  | Rmt | C/o to Pg No: of M.B.No:
9 | 306 | Supply and fixing of 4 Way TPN DB Horizontal with IP 43 Protection as per IS:13032 Makes: Legrand / Schneider and Supply and Fixing of 1 No., of 40A FP 30mA RCCB as incomer and 12 Nos 6-32 A 10kA SP MCBs Makes: Legrand-DX3 / Schneider-Acti9 as out goings including internal connections and labour charges for FLUSH Mounting etc., complete. For Lighting DBs at MGMH Petlaburj
|  | Main Corridoor Left side | 1 | 5 |  |  |  | 5
|  | Right side | 1 | 5 |  |  |  | 5
[8 empty] | 10 |  | Nos | C/o to Pg No: of M.B.No:
10 | 308 | Supply and fixing of 8 Way VTPN DB Horizontal with IP 43 Protection as per IS:13032 Makes: Legrand / Schneider and Supply and Fixing of 1 No., of 100A FP 10KA MCB as incomer and 4 Nos 63 A 10kA TP MCBs, 4 Nos 40 A 10kA TP MCBs Makes: Legrand-DX3 / Schneider-Acti9 as out goings including internal connections and labour charges for FLUSH Mounting etc., complete. For UPS MDB DBs at MGMH Petlaburj
|  | UPS room | 1 | 1 |  |  |  | 1
[8 empty] | 1 |  | Nos | C/o to Pg No: of M.B.No:
11 | 309 | Providing and fixing of 125A 25KA TPN Thermal Magnetic Release Based MCCB and Terminal Spreaders in Existing panel board with 1 No. and 1 Set of Indication Lamps, LED type, R,Y,B and breaker ON , OFF, TRIP and spring charged lamps. and replace with above Mentioned with required Drilling Holes, removing and Making Busbar connections etc, as required. Makes: Legrand / Schneider/ABB/LandT/CandS at MGMH Petlaburj
|  | UPS room | 1 | 1 |  |  |  | 1
[8 empty] | 1 |  | Nos | C/o to Pg No: of M.B.No:
12 | 318 | SITC of Hot dip galvanized perforated cable tray of 100 mm Wide sizes for to run the cable from DBs to SBs and sockets and AC panel to Units units. All necessary supports and accessories are included. Cable tray for cables alone shall be included here Thickness shall be 1.6 mm. at MGMH Petlaburj
|  | From Reception to Panel | 1 | 1 | 36 |  |  | 36
|  |  | 1 | 1 | 25 |  |  | 25
|  |  | 1 | 1 | 9.9 |  |  | 9.9
|  |  | 1 | 1 | 8.1 |  |  | 8.1
[8 empty] | 79 |  | Rmt | C/o to Pg No: of M.B.No:
13 | 319 | SITC of Hot dip galvanized perforated cable tray of 300 mm Wide sizes for to run the cable from Floor Panel to Lab Panel and electrical room to AC panel and AC panel to Units. All necessary supports and accessories are included. Cable tray for cables alone shall be included here Thickness shall be 1.6 mm. at MGMH Petlaburj
|  | From Reception to Panel | 1 | 1 | 8.8 |  |  | 8.8
|  |  | 1 | 2 | 37.1 |  |  | 74.2
|  |  | 1 | 1 | 9.5 |  |  | 9.5
|  |  | 1 | 2 | 2.5 |  |  | 5
|  |  | 1 | 2 | 2.5 |  |  | 5
[8 empty] | 102.5 |  | Rmt | C/o to Pg No: of M.B.No:
14 | 325 | Supply and installation of 50x6 GI flat for body earthing of electrical panel and AC Panel which is laid in 300mm cable tray at MGMH Petlaburj
|  | From Reception to Panel | 1 | 2 | 8.8 |  |  | 17.6
|  |  | 1 | 2 | 37.1 |  |  | 74.2
|  |  | 1 | 1 | 9.5 |  |  | 9.5
|  |  | 1 | 2 | 2.5 |  |  | 5
|  |  | 1 | 2 | 2.5 |  |  | 5
|  | Drops | 1 | 2 | 38 |  |  | 76
|  | Loops | 1 | 2 | 15 |  |  | 30
[8 empty] | 217.3 |  | Rmt | C/o to Pg No: of M.B.No:
15 | 323 | Providing and Fixing maintenance free earthing which consists of G.I. Earth station, with 600X600X3.15mm GI Plate at 2500mm Depth including construction of brick pedestal, providing meshed funnel, GI cover and other civil Engineering works, spreading a homogenous mixture of salt, charcoal around the pipe etc., completely as per IS 3043, 1987 or latest revision. Earthing testing should be done as per IE Rules like Earth valve test Etc. at MGMH Petlaburj
|  | Near generator room | 1 | 2 |  |  |  | 2
[8 empty] | 2 |  | Nos | C/o to Pg No: of M.B.No:
16 | 324 | Providing and Fixing maintenance free earthing which consists of copper. Earth station, with 600X600X3.15mm Copper Plate at 2500mm Depth including construction of brick pedestal, providing meshed funnel, GI cover and other civil Engineering works, spreading a homogenous mixture of salt, charcoal around the pipe etc., completely as per IS 3043, 1987 or latest revision. Earthing testing should be done as per IE Rules like Earth valve test Etc. at MGMH Petlaburj
|  | Near generator room | 1 | 4 |  |  |  | 4
[8 empty] | 4 |  | Nos | C/o to Pg No: of M.B.No:
17 | 327 | Supply and installation of 25x3 Copper flat for Neutral earthing of UPS and Equipment which is laid in 100mm cable tray at MGMH Petlaburj
|  |  | 1 | 2 | 8.8 |  |  | 17.6
|  |  | 1 | 2 | 37.1 |  |  | 74.2
|  |  | 1 | 1 | 9.5 |  |  | 9.5
|  | Drops | 1 | 2 | 38 |  |  | 76
|  | Loops | 1 | 2 | 15 |  |  | 30
[8 empty] | 207.3 |  | Rmt | C/o to Pg No: of M.B.No:
18 | 328 | Supply and installation of 4 sqmm Copper wire for Earthing of DBs Equipment at MGMH Petlaburj
|  | DB-1 | 1 | 1 | 45.7 |  |  | 45.7
|  | DB-2 | 1 | 1 | 51.8 |  |  | 51.8
|  | DB-3 | 1 | 1 | 50.1 |  |  | 50.1
|  | DB-4 | 1 | 1 | 53.3 |  |  | 53.3
|  | DB-5 | 1 | 1 | 50.6 |  |  | 50.6
|  | DB-6 | 1 | 1 | 49.9 |  |  | 49.9
|  | DB-7 | 1 | 1 | 38.7 |  |  | 38.7
|  | DB-8 | 1 | 1 | 37.9 |  |  | 37.9
|  | DB-9 | 1 | 1 | 36.7 |  |  | 36.7
|  | DB-10 | 1 | 1 | 35.9 |  |  | 35.9
[8 empty] | 450.6 |  | Rmt | C/o to Pg No: of M.B.No:
19 | 329 | Supply, Laying and testing of 3.5Cx95 sqmm XLPE Insulated Cable 1100V grade armoured aluminium cable with ISI mark as per specification confirming to IS:7098 Part - I with heavy duty type double compression weather proof type brass cable glands duly nickel plated as per BS 6121 and IP66 complete with brass checknut, outer sheath sealing gasket heavy duty long barrel aluminium lugs confirming to I.S specifications with complete nut, bolt and washer etc.. Make of Cable: Polycab/ KEI/Universal/Glostar/Finolex. Make of gland and Lungs: HMI/Commet/Dowell’s at MGMH Petlaburj
|  | From Main panel to Electrical room | 1 | 1 | 180 |  |  | 180
[8 empty] | 180 |  | Rmt | C/o to Pg No: of M.B.No:
20 | 330 | Supply, Lying and testing of 3.5CX50 sqmm XLPE Insulated Cable 1100V grade armoured aluminium cable with ISI mark as per specification confirming to IS:7098 Part - I with heavy duty type double compression weather proof type brass cable glands duly nickel plated as per BS 6121 and IP66 complete with brass checknut, outer sheath sealing gasket heavy duty long barrel aluminium lugs confirming to I.S specifications with complete nut, bolt and washer etc.. Make of Cable: Polycab Make of gland and Lungs: HMI at MGMH Petlaburj
|  | From main panel to Electrical room | 1 | 1 | 180 |  |  | 180
[8 empty] | 180 |  | RMT | C/o to Pg No: of M.B.No:
21 | 331 | Supply, Lying and testing of 4Cx16 sqmm PVC Insulated Cable 1100V grade armoured Copper cable with ISI mark as per specification confirming to IS:7098 Part - I with heavy duty type double compression weather proof type brass cable glands duly nickel plated as per BS 6121 and IP66 complete with brass checknut, outer sheath sealing gasket heavy duty long barrel aluminium lugs confirming to I.S specifications with complete nut, bolt and washer etc.. Make of Cable: Polycab/ KEI/Universal/Glostar/Finolex. Make of gland and Lungs: HMI/Commet/Dowell’s at MGMH Petlaburj
|  |  | 1 | 1 | 100 |  |  | 100
[8 empty] | 100 |  | RMT | C/o to Pg No: of M.B.No:
22 | 332 | Supply, Lying and testing of 4Cx6 sqmm PVC Insulated Cable 1100V grade armoured Copper cable with ISI mark as per specification confirming to IS:7098 Part - I with heavy duty type double compression weather proof type brass cable glands duly nickel plated as per BS 6121 and IP66 complete with brass checknut, outer sheath sealing gasket heavy duty long barrel aluminium lugs confirming to I.S specifications with complete nut, bolt and washer etc. Make of Cable: Polycab/ KEI/Universal/ Glostar/Finolex. Make of gland and Lungs: HMI/Commet/Dowell’s at MGMH Petlaburj
|  |  | 1 | 1 | 120 |  |  | 120
[8 empty] | 120 |  | RMT | C/o to Pg No: of M.B.No:
23 | 333 | Supply, Lying and testing of 4Cx4 sqmm PVC Insulated Cable 1100V grade armoured Copper cable with ISI mark as per specification confirming to IS:7098 Part - I with heavy duty type double compression weather proof type brass cable glands duly nickel plated as per BS 6121 and IP66 complete with brass checknut, outer sheath sealing gasket heavy duty long barrel aluminium lugs confirming to I.S specifications with complete nut, bolt and washer etc. Make of Cable:Polycab/ KEI/Universal/Glostar/Finolex. Make of gland and Lungs: HMI/Commet/Dowell’s at MGMH Petlaburj
|  | Entrance | 1 | 1 | 80 |  |  | 80
[8 empty] | 80 |  | Rmt | C/o to Pg No: of M.B.No:
24 | 334 | SITC of IVF Center Main Panel Indoor IP-42 wall/ free standing floor mounted dust and vermin proof compartmentalized cubical panel made out of CRCA sheet, required hardware, duly treated for de-rusting in 7 tank process with de-phosphate and with powder coating on both side of panel in desired shade. The panel having PU/ Neoprene rubber gasket of not less than 3mm thickness, separate detachable gland plate M.S. base channel, hinged door with locking arrangement for equipment/switchgear. Thickness of sheet shall not be less than 1.6 mm up to 600 mm length / width of any compartment and be of 2.0 mm above 600 mm. Load bearing structure shall be of 2.0 mm thick sheet supported by base M.S. channel if required. Side walls and cable alley compartments having bolted type doors with /without detachable extension type structure with all type of suitable switching accessories and bus-bar as per load requirement of respective IVF equipment’s. Which is including Lighting, power DBs and UPS at MGMH Petlaburj
|  | In Electrical room | 1 | 1 |  |  |  | 1
[8 empty] | 1 |  | No's | C/o to Pg No: of M.B.No:
s | 335 | SITC of IVF center AC Panel outdoor IP-54 wall/ free standing floor mounted dust and vermin proof compartmentalized cubical panel made out of CRCA sheet, required hardware, duly treated for de-rusting in 7 tank process with de-phosphate and with powder coating on both side of panel in desired shade. The panel having PU/ Neoprene rubber gasket of not less than 3mm thickness, separate detachable gland plate M.S. base channel, hinged door with locking arrangement for equipment/switchgear. Thickness of sheet shall not be less than 1.6 mm up to 600 mm length / width of any compartment and be of 2.0 mm above 600 mm. Load bearing structure shall be of 2.0 mm thick sheet supported by base M.S. channel if required. Side walls and cable alley compartments having bolted type doors with / without detachable extension type structure with all type of suitable switching accessories and bus-bar as per load requirement of respective AC equipment’s. Which is including 1nos AHU’s stater with VFD by pass, Heater, ODU and VRF system at MGMH Petlaburj
|  | In Electrical room | 1 | 1 |  |  |  | 1
[8 empty] | 1 |  | Nos | C/o to Pg No: of M.B.No:

## ABS-4 (hidden)
ABSTRACT
Name of Work:- Design, Fabriction, establishing and commissioning of In - Vitro ferility centers (IVFC) alongwith allied Services on Turnkey basis at MGMH Petlaburj,Hyd. | [7 empty] | Agency: | M/s. Asta Vardhman Consortium | [5 empty] | Agt.No:344/A/TSMIDC/Spl.Proj/IVFCs /2022-23,Dt.05.07.2023
S.No | Date of measurement/ S.No. in Agt. | Description Of Work etc., | Measurements Upto date |  |  |  |  | Rate |  | Per | Total Value to date |  | Deduct/previous Measurements |  | Since last measurement |  |  | Remarks
|  |  | No | L | B | D | Content | Rs | Ps. |  | Rs. | Ps | P.No. | Qty. | Qty | Value
[16 empty] | Rs. | Ps.
1 | 247 | Dismantling, clearing away and carefully stacking useful materials for re-use and disposal of unserviceable materials with 100m lead as directed by Executive Engineer duly taking actual premeasurements before dismantling including all labour charges , overheads & contractor profit etc., complete Finished item of work | [16 empty] | Original Rate
a) Brick Masonry
|  | Qty V.Pg.No:-01 of MB:-04 |  |  |  | 20.38 | 20.38 | 398 | Cum |  | 8111.24 |  | 20.38 | 8111.24 | - | - |  |  | 398
| 248 | b) Tiles Dismantling
|  | Qty V.Pg.No:-01 of MB:-04 |  |  |  | 729.9325 | 400 | 20 | Sqm |  | 8000 |  | 400 | 8000 | - | - |  |  | 20
[6 empty] | AE | 329.9325
2 | 249 | Dismantling doors, windows and clear storey windows, Ventilators etc., (wood or steel) shutters including Chowkhats, architraves,hold fasts and other attachments etc., and stacking them within 100m lead including labour charge etc., and overheads & contractors profit complete for finished item of work.
a)Not Exceeding 3.00Sqm Area
|  | Qty V.Pg.No:-01 of MB:-04 |  |  |  | 32 | 16 | 350 | Each |  | 5600 |  | 16 | 5600 | - | - |  |  | 350
[6 empty] | AE | 16
3 | 252 | Brick Masonry for panel walls in SuperStructure with CM (1:8) prop (cement: Screened sand) with Aerated Cellular Autoclaved Concrete Blocks conforming to IS:2185 (Part-3) - 1984 and IS:6441-1972 of Compressive strength 3 N/mm2 600x 230 x 200 mm from approved source having minimum crushing strength of 3 N/Sq.m including cost and conveyance of all materials like cement, sand, bricks, water etc., to site, including sales & other taxes on all materials, all operational, incidental and labour charges such as mixing cement mortar, constructing masonry, scaffolding charges, lift charges, curing, etc., complete but excluding seigniorage charges for finished item of work. (APSS No. 501 & 504).
|  | Qty V.Pg.No:-01 of MB:-04 |  |  |  | 16.3192 | 10.5 | 14558 | cum |  | 152859 |  | 10.5 | 152859 | - | - |  |  | 14558
[6 empty] | AE | 5.82
4 | 253 | Reinforced Masonry for partiton walls 100 mm thick in CM (1:4) prop (cement: Screened sand) in super structure with Aerated Cellular Autoclaved Concrete Blocks conforming to IS:2185 (Part-3) - 1984 and IS:6441-1972 of Compressive strength 3 N/mm2 600x 200 x 100 mm from approved source having minimum crushing strength of 3 N/Sq.m including cost and conveyance of all materials like cement, sand, bricks, water etc., to site, including sales & other taxes on all materials, all operational, incidental and labour charges such as mixing cement mortar, constructing masonry, scaffolding charges, lift charges, curing, etc., complete but excluding seigniorage charges for finished item of work. (APSS No. 501 & 504).
|  | Qty V.Pg.No:-02 of MB:-04 |  |  |  | 219.7595 | 215 | 1716 | Sqm |  | 368940 |  | 215 | 368940 | - | - |  |  | 1716
[6 empty] | AE | 4.7595
5 | 256 | Plastering 12mm thick in two coats using screened sand with base coat of 8mm thick in CM (1:6) and top coat of 4mm thick in CM (1:4) with dubara sponge finishing including cost and conveyance of all materials like cement, sand, water etc., to site, including sales & other taxes on all materials, and all operational, incidental charges on materials and including cost of all labour charges for mixing mortar, finishing, scaffolding, lift charges, curing, including cutting grooves as directed by Engineer-in-charge etc., and overheads & contractors profit complete for finished item of work. (SS 901,903 & 904).
|  | Qty V.Pg.No:-02 of MB:-04 |  |  |  | 822.13 | 430 | 906 | Sqm |  | 389580 |  | 430 | 389580 | 0 | 0 |  |  | 906
[6 empty] | AE:- | 392.13
6 | 263 | Flooring with soluble salt porcelain vitrified tiles screen printed and polished of size 600 x 600 mm and thickness between 8 to 10mm 1st quality conforming to IS: 13711, IS: 13712, IS: 13630Parts 1 to 15 of any colour and finish in all shades and designs with borders and design as per the approved flooring pattern as directed by the Engineer-In -Charge, laying tiles using spacers of 2mm thick, set over a base coat of CM 1:8 prop. 12mm thick using screened sand over CC bed already laid or RCC roof slab, including neat cement slurry of honey like consistency spread at the rate 3.3 kgs per Sqm. and jointed neatly with white cement paste to full depth mixed with pigment of matching shade including cost and conveyance of all materials like cement, sand, water, tiles, white cement etc., to site excluding cost of C.C. bed including cost of base coat and all labour charges for mixing of cement mortar, laying tiles to required slope as directed by the Engineer- in- charge etc., and complete for finished item of work. TSSS No.701 and 707.
|  | Qty V.Pg.No:-02 of MB:-04 |  |  |  | 294.66 | 294.659 | 1593 | Sqm |  | 469391.787 |  | 294.66 | 469393.38 | - | - |  |  | 1593
7 | 266 | Providing dadooing to walls with glazed full body porcelain wall tiles of size 300 x 600 mm with any type of design texture such as marble finish, wooden, bamboo, stone finishes etc., scratch less, stain free and thickness between 6-8 mm 1st quality conforming to IS:13711, IS:13712, IS:13630 Parts 1 to 15 of any colour and finish in all shades and designs with borders as approved by Engineer-in-Charge set over base coat of CM1:5 12 mm thick using screened sand with cement slurry of honey like consistency spread at the rate of 3.30 kgs per sqm and jointing with white cement paste mixed with pigment of matching shade to full depth, including cost of all materials like tiles, cement, sand and water etc., complete for finished item of work. 3rd Floor at Petlaburj Hospital
|  | Qty V.Pg.No:-03 of MB:-04 |  |  |  | 153.0952 | 30 | 1391 | Sqm |  | 41730 |  | 30 | 41730 | - | - |  |  | 1391
[6 empty] | AE | 123.0952
[9 empty] | Civil Sub-Total:- |  | 1444212.027 |  |  | 1444213.62 |  | 0
Civil Supplemental Items
1 |  | Dismantling, clearing away and carefully stacking useful materials for re-use and disposal of unserviceable materials with 100m lead as directed by Executive Engineer duly taking actual premeasurements before dismantling including all labour charges , overheads & contractor profit etc., complete Finished item of work
a)Old Cement Mortar
|  | Qty V.Pg.No:-03 of MB:-04 |  |  |  | 251.59 | 251.5889
b)Reinforced Cement Concrete
|  | Qty V.Pg.No:-03 of MB:-04 |  |  |  | 0.43 | 0.4293
2 |  | Providing Thermo Mechanically Treated ( TMT) ( Fe-500/500D/550D from primery producer TATA, SAIL, VSP, JSW Steel, Goel steel, Jindal panther, X- Vega & balaji Shakthi as per IS 1786-2008) of Different Diameters RCC Works , including labour charges for straightening, cutting, bending to required sizes and shapes, placing in position with cover blocks of approved materials and sizes and typing and lap - spacing with binding wire of 18 SWG, Forming grills for reinforcement work as per approved design and drawings, including and conveyanace of steel bars, including all wastages such as overlaps, coupling, chairs, spacer bars including cost and conveyance of binding wire cover blocks and incidential, operational, labour charges such as cutting bending, placing in position, typing incliding sales and other taxes on all materials etc., and overheads & contractors profit completefor finished item of work
|  | Qty V.Pg.No:-03 of MB:-04 |  |  |  |  | 0.2956
3 |  | Supply and placing of the Design Mix Concrete M 25 grade corresponding to IS 456 with minimum cement content of 380 kgs per 1 cum of concrete using Weight Batcher / Concrete mixer with 20mm size graded machine crushed hard granite metal (coarse aggregate - as per IS 383 - 1970 and IS 2386 Part 1 to Part 8) from approved quarry including cost and conveyance of all materials like cement, fine aggregate (sand) coarse aggregate, water etc., to site and sales & other taxes on all materials, centering using Casurina Ballies, Bamboos, Wooden Reapers, Runners, Wood Posts, Steel Plates etc., including all operational, incidental and labour charges such as weigh batching, machine mixing, lifting of concrete manually, laying concrete, curing , overheads & contractors profit etc., complete but excluding cost of steel and its fabrication charges for finished item of work (APSS No. 402)
For Lintels
|  | Qty V.Pg.No:-04 of MB:-04 |  |  |  | 0.75 | 0.74952
4 |  | Providing skirting to internal walls to 10 cm height with Double charged / multi charged stain free fullbody porcelain vitrified tiles with double layer pigment of size 600 x 600 mm and thickness between 8-10 mm 1st quality conforming to IS:15622 - 2017, IS:13630 (Parts 1 to 15) of any colour and finish in all shades and designs, length equal to flooring tiles, set over base coat of CM(1:5) 12 mm thick using screened sand with cement slurry of honey like consistency spread at the rate of 3.30 kgs per sqm and jointing with white cement paste mixed with pigment of matching shade to full depth, including cost of all materials like tiles, cement, sand and water etc.,and overheads & contractors profit complete for finished item of work.(APSS No.701 &707)
|  | Qty V.Pg.No:-04 of MB:-04 |  |  |  | 174.5 | 174.5
[8 empty] | Civil Suppl. Sub-Total:- |  |  | 0 |  |  | 0 |  | 0
Equipment Items
1 | 200 | IVF Test tube Warmers at Petlaburz Hospital
|  | Qty V.Pg.No:-04 of MB:-04 |  |  |  | 2 | 2 | 34650 | Nos |  | 69300 |  | 2 | 69300 |  |  |  | 70% | 49500
2 | 201 | DICOM compatible fully digital, compact, portable, Ultrasound Scan Machine Colour Doppler at Petlaburz Hospital
|  | Qty V.Pg.No:-04 of MB:-04 |  |  |  | 2 | 2 | 955500 | Nos |  | 1911000 |  | 2 | 1911000 |  |  |  | 70% | 1365000
3 | 202 | Multipurpose Electro hydraulic with manual override mobile OT Table, with divided leg section suitable for all Gynaecological surgical procedures, complete with 5cm Mattress and corded handset at Petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 1 | 1 | 394625 | Nos |  | 394625 |  | 1 | 394625 |  |  |  | 70% | 563750
4 | 203 | LED procedure Lights Double dome at petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 1 | 1 | 218750 | Nos |  | 218750 |  | 1 | 218750 |  |  |  | 70% | 312500
5 | 204 | LED procedure Lights Single dome at petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 1 | 1 | 131250 | Nos |  | 131250 |  | 1 | 131250 |  |  |  | 70% | 187500
6 | 207 | CO2 Incubators at Petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 2 | 2 | 577500 | Nos |  | 1155000 |  | 2 | 1155000 |  |  |  | 70% | 825000
7 | 212 | IVF Thermometer at Petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 1 | 1 | 43313 | Nos |  | 43313 |  | 1 | 43313 |  |  |  | 70% | 61875
8 | 213 | CO2 Cylinder and Manifold at Petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 2 | 2 | 35000 | Nos |  | 70000 |  | 2 | 70000 |  |  |  | 70% | 50000
9 | 214 | CO2 and O2 Analyzer at Petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 2 | 1 | 264600 | Nos |  | 264600 |  | 1 | 264600 |  |  |  | 70% | 378000
10 | 215 | PH Meter at Petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 1 | 1 | 65625 | Nos |  | 65625 |  | 1 | 65625 |  |  |  | 70% | 93750
11 | 217 | Sperm Counting Markler Chamber at Petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 1 | 1 | 52938 | Nos |  | 52938 |  | 1 | 52938 |  |  |  | 70% | 75625
12 | 220 | Clinical Centrifuge machine for Andrology at Petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 1 | 1 | 24150 | Nos |  | 24150 |  | 1 | 24150 |  |  |  | 70% | 34500
13 | 221 | DRY Incubator at Petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 1 | 1 | 394625 | Nos |  | 394625 |  | 1 | 394625 |  |  |  | 70% | 563750
14 | 223 | Pharmaceutical Refrigerator at Petlaburz Hospital
|  | Qty V.Pg.No:-06 of MB:-04 |  |  |  | 1 | 1 | 157500 | Nos |  | 157500 |  | 1 | 157500 |  |  |  | 70% | 225000
15 | 224 | Cryocane (TA 26 Ltr) with wheels at Petlaburz Hospital
|  | Qty V.Pg.No:-06 of MB:-04 |  |  |  | 2 | 2 | 43313 | Nos |  | 86626 |  | 2 | 86626 |  |  |  | 70% | 61875
16 | 225 | Defibrillator at Petlaburz Hospital
|  | Qty V.Pg.No:-06 of MB:-04 |  |  |  | 1 | 1 | 218750 | Nos |  | 218750 |  | 1 | 218750 |  |  |  | 70% | 312500
17 | 226 | 7 Para Patient Monitor at Petlaburz Hospital
|  | Qty V.Pg.No:-06 of MB:-04 |  |  |  | 2 | 2 | 196000 | Nos |  | 392000 |  | 2 | 392000 |  |  |  | 70% | 280000
18 | 228 | Anaesthesia Work station at Petlaburz Hospital
|  | Qty V.Pg.No:-06 of MB:-04 |  |  |  | 1 | 1 | 656250 | Nos |  | 656250 |  | 1 | 656250 |  |  |  | 70% | 937500
19 | 232 | Mulitfunctional Printer at Petlaburz Hospital
|  | Qty V.Pg.No:-06 of MB:-04 |  |  |  | 1 | 1 | 30625 | Nos |  | 30625 |  | 1 | 30625 |  |  |  | 70% | 43750
20 | 233 | Ultrasound Examination Couch at Petlaburz Hospital
|  | Qty V.Pg.No:-06 of MB:-04 |  |  |  | 1 | 1 | 56875 | Nos |  | 56875 |  | 1 | 56875 |  |  |  | 70% | 81250
21 | 235 | Laptop For Office Usage at Petlaburz Hospital
|  | Qty V.Pg.No:-06 of MB:-04 |  |  |  | 2 | 2 | 80500 | Nos |  | 161000 |  | 2 | 161000 |  |  |  | 70% | 115000
22 | 320 | 20 KVA UPS: Supply and installation of 20KVA 3ph in and 3ph out on line UPS system IGBT based rectifier with input power factor correction 32 bit microprocessor based with isolation transformers double conversion, SNMP controls, LCD display, Pure sine wave output, with auto static switch three phase input / Three phase output and modular structure for better thermal technology / cooling facility, with warranty up to three years.Makes: APC / Numeric / Emerson / Fuji Electric At Petlaburz
|  | Qty V.Pg.No:-06 of MB:-04 |  |  |  | 1 | 1 | 213500 | Nos |  | 213500 |  | 1 | 213500 |  |  |  | 70% | 305000
23 | 322 | Supply and providing of UPS Cum battery rack for 20 batteries at MGMH Petlaburz
|  | Qty V.Pg.No:-06 of MB:-04 |  |  |  | 1 | 1 | 4735 | Nos |  | 4735 |  | 1 | 4735 |  |  |  | 70% | 6764
1 | 199 | Ovum Aspiration Pumps at Petlaburj Hospital
|  | Qty V.Pg.No:-01 of MB:-05 |  |  |  | 2 | 2 | 168000 | Nos |  | 336000 |  | 2 | 336000 |  |  |  | 70% | 240000
2 | 205 | IVF Workstation with LAF at Petlaburj Hospital
|  | Qty V.Pg.No:-01 of MB:-05 |  |  |  | 1 | 1 | 481250 | Nos |  | 481250 |  | 1 | 481250 |  |  |  | 70% | 687500
3 | 206 | IVF Ant vibration Table for procedure at Petlaburj Hospital
|  | Qty V.Pg.No:-01 of MB:-05 |  |  |  | 1 | 1 | 67375 | Nos |  | 67375 |  | 1 | 67375 |  |  |  | 70% | 96250
4 | 208 | Trigas bench Top Incubators for Human Embryo culture at Petlaburj Hospital
|  | Qty V.Pg.No:-01 of MB:-05 |  |  |  | 1 | 1 | 577500 | Nos |  | 577500 |  | 1 | 577500 |  |  |  | 70% | 825000
5 | 209 | Trinocular Stereozoom Microscope at Petlaburj Hospital
|  | Qty V.Pg.No:-01 of MB:-05 |  |  |  | 1 | 1 | 216300 | Nos |  | 216300 |  | 1 | 216300 |  |  |  | 70% | 309000
6 | 210 | ICSI Micro manipulator with Inverted Microscope at Petlaburj Hospital
|  | Qty V.Pg.No:-02 of MB:-05 |  |  |  | 1 | 1 | 1837500 | Nos |  | 1837500 |  | 1 | 1837500 |  |  |  | 70% | 2625000
7 | 211 | IVF Laser System at Petlaburj Hospital
|  | Qty V.Pg.No:-02 of MB:-05 |  |  |  | 1 | 1 | 1792000 | Nos |  | 1792000 |  | 1 | 1792000 |  |  |  | 70% | 2560000
8 | 216 | VOC Meter for ART Lab at Petlaburj Hospital
|  | Qty V.Pg.No:-02 of MB:-05 |  |  |  | 1 | 1 | 511875 | Nos |  | 511875 |  | 1 | 511875 |  |  |  | 70% | 731250
9 | 218 | Binocular Microscope for Semen Analysis at Petlaburj Hospital
|  | Qty V.Pg.No:-02 of MB:-05 |  |  |  | 1 | 1 | 28875 | Nos |  | 28875 |  | 1 | 28875 |  |  |  | 70% | 41250
10 | 219 | Laminar flow cabinet with Andrology Work station at Petlaburj Hospital
|  | Qty V.Pg.No:-02 of MB:-05 |  |  |  | 1 | 1 | 175000 | Nos |  | 175000 |  | 1 | 175000 |  |  |  | 70% | 250000
11 | 222 | Pipetter and Denudation system at Petlaburj Hospital
|  | Qty V.Pg.No:-02 of MB:-05 |  |  |  | 1 | 1 | 72188 | Nos |  | 72188 |  | 1 | 72188 |  |  |  | 70% | 103125
12 | 229 | Autoclave at Petlaburj Hospital
|  | Qty V.Pg.No:-02 of MB:-05 |  |  |  | 1 | 1 | 393750 | Nos |  | 393750 |  | 1 | 393750 |  |  |  | 70% | 562500
13 | 236 | Reception Table at Petlaburj Hospital
|  | Qty V.Pg.No:-03 of MB:-05 |  |  |  | 1 | 1 | 77000 | Nos |  | 77000 |  | 1 | 77000 |  |  |  | 70% | 110000
14 | 238 | Filing Cabinet at Petlaburj Hospital
|  | Qty V.Pg.No:-03 of MB:-05 |  |  |  | 2 | 2 | 24150 | Nos |  | 48300 |  | 2 | 48300 |  |  |  | 70% | 34500
15 | 239 | Patient Seating 3 in 1 model at Petlaburj Hospital
|  | Qty V.Pg.No:-03 of MB:-05 |  |  |  | 3 | 3 | 26950 | Nos |  | 80850 |  | 3 | 80850 |  |  |  | 70% | 38500
16 | 244 | Wall Storage Cabinets at Petlaburj Hospital
|  | Qty V.Pg.No:-03 of MB:-05 |  |  |  | 8 | 8 | 12250 | Nos |  | 98000 |  | 8 | 98000 |  |  |  | 70% | 17500
17 | 245 | Office Table at Petlaburj Hospital
|  | Qty V.Pg.No:-03 of MB:-05 |  |  |  | 3 | 3 | 14000 | Nos |  | 42000 |  | 3 | 42000 |  |  |  | 70% | 20000
13608800
Electrical-1
1 | 294 | Supply and laying of ISI 25mm outer dia medium grade with IS:9537-part 3 rigid PVC pipe concealed in wall with all required PVC / Metallic Junction Boxes including masonry work and labour charges etc., Makes: Sudhakar / Precision /Universal/ Modi / Million Plast. at MGMH Petlaburj
[6 empty] | 463.5 | 200 | 93 | RMt |  | 18600 |  |  |  | 200 | 18600 |  | 80% | 116
[6 empty] | AE | 263.5
2 | 294 | Supply and laying of ISI 25mm outer dia medium grade with IS:9537-part 3 rigid PVC pipe surface on wall with all required PVC / Metallic Junction Boxes including masonry work and labour charges etc., Makes: Sudhakar / Precision /Universal/ Modi / Million Plast. at MGMH Petlaburj
[6 empty] | 1352.8 | 450 | 86 | Rmt |  | 38700 |  |  |  | 450 | 38700 |  | 80% | 107
[6 empty] | AE | 902.8
3 | 295 | Wiring with 2 runs of 22/0.3mm 1.5 Sq.mm FRLS / HFFR P.V.C. insulated flexible copper cable ISI MARK in existing pipe with 6A Modular switch, Ceiling rose/BH/SBH Modular switches with cover plate and GI switch box including all labour charges etc., complete. for Non- Residential Building Makes of wires: Polycab Makes of switches: - /Honeywell Blenge Plus at MGMH Petlaburj
[6 empty] | 148 | 100 | 756 | Nos |  | 75600 |  |  |  | 100 | 75600 |  | 80% | 945
[6 empty] | AE | 48
4 | 300 | Supply and run of 1 of 22 /0.3mm 1.5 Sq.mm FRLS / HFFR P.V.C. insulated flexible copper cable in existing conduit pipe for earth continuity including all labour charges etc., complete. Makes of wires: Finolex/ RR Cable/ Havells/ Polycab/ HPL. at MGMH Petlaburj
[6 empty] | 379.6 | 350 | 32 | Rmt |  | 11200 |  |  |  | 350 | 11200 |  | 80% | 40
[6 empty] | AE | 29.6
5 | 301 | Supply and run of 3 of 2.5 sq.mm 36/0.mm phase neutral and earth FRLS / HFFR PVC insulated flexible copper cable in existing conduit pipe for individual lighting circuits including labour charges etc., complete as required for switch boards. Makes of wires: Finolex/ RR Cable/ Havells/ Polycab/ HPL. at MGMH Petlaburj
[6 empty] | 1713.1 | 600 | 142 | Rmt |  | 85200 |  |  |  | 600 | 85200 |  | 80% | 177
[6 empty] | AE | 1113.1
6 | 302 | Supply and 3 runs of 4.0 sq mm 56/0.3 mm phase neutral and earth FRLS / HFFR PVC insulated flexible copper cable in existing conduit pipe including labour charges etc., complete for 16A sockets. Makes of wires: Finolex/ RR Cable/ Havells/ Polycab/ HPL. at MGMH Petlaburj
[6 empty] | 2421 | 1200 | 204 | Nos |  | 244800 |  |  |  | 1200 | 244800 |  | 80% | 255
[6 empty] | AE | 1221
7 | 303 | Supply and run of 5 of 6.0 Sqmm 90/0.3 mm 3 phases, neutral and earth FRLS / HFFR PVC insulated flexible copper cable in the existing conduit pipe for run of mains from Power panel board to TPN DBs with pin type lugs and connections etc., complete. for LDBs Makes of wires: Finolex/ RR Cable/ Havells/ Polycab/ HPL. at MGMH Petlaburj
[6 empty] | 240.1 | 60 | 485 | Rmt |  | 29100 |  |  |  | 60 | 29100 |  | 80% | 606
[6 empty] | AE | 180.1
8 | 304 | Supply and run of 5 of 10.0 Sqmm 140/0.3 mm 3 phases, neutral and earth FRLS / HFFR PVC insulated flexible copper cable in the existing conduit pipe for run of mains from Power panel board to TPN DBs with pin type lugs and connections etc., complete. for PDBs Makes of wires: Finolex/ RR Cable/ Havells/ Polycab/ HPL. at MGMH Petlaburj
[6 empty] | 284 | 40 | 774 | Rmt |  | 30960 |  |  |  | 40 | 30960 |  | 80% | 967
[6 empty] | AE | 244
9 | 306 | Supply and fixing of 4 Way TPN DB Horizontal with IP 43 Protection as per IS:13032 Makes: Legrand / Schneider and Supply and Fixing of 1 No., of 40A FP 30mA RCCB as incomer and 12 Nos 6-32 A 10kA SP MCBs Makes: Legrand-DX3 / Schneider-Acti9 as out goings including internal connections and labour charges for FLUSH Mounting etc., complete. For Lighting DBs at MGMH Petlaburj
[6 empty] | 10 | 3 | 14660 | Rmt |  | 43980 |  |  |  | 3 | 43980 |  | 80% | 18325
[6 empty] | AE | 7
10 | 308 | Supply and fixing of 8 Way VTPN DB Horizontal with IP 43 Protection as per IS:13032 Makes: Legrand / Schneider and Supply and Fixing of 1 No., of 100A FP 10KA MCB as incomer and 4 Nos 63 A 10kA TP MCBs, 4 Nos 40 A 10kA TP MCBs Makes: Legrand-DX3 / Schneider-Acti9 as out goings including internal connections and labour charges for FLUSH Mounting etc., complete. For UPS MDB DBs at MGMH Petlaburj
[7 empty] | 1 | 51254 | Nos |  | 51254 |  |  |  | 1 | 51254 |  | 80% | 64067
11 | 309 | Providing and fixing of 125A 25KA TPN Thermal Magnetic Release Based MCCB and Terminal Spreaders in Existing panel board with 1 No. and 1 Set of Indication Lamps, LED type, R,Y,B and breaker ON , OFF, TRIP and spring charged lamps. and replace with above Mentioned with required Drilling Holes, removing and Making Busbar connections etc, as required. Makes: Legrand / Schneider/ABB/LandT/CandS at MGMH Petlaburj
[7 empty] | 1 | 23106 | Nos |  | 23106 |  |  |  | 1 | 23106 |  | 80% | 28883
12 | 318 | SITC of Hot dip galvanized perforated cable tray of 100 mm Wide sizes for to run the cable from DBs to SBs and sockets and AC panel to Units units. All necessary supports and accessories are included. Cable tray for cables alone shall be included here Thickness shall be 1.6 mm. at MGMH Petlaburj
[6 empty] | 79 | 70 | 343 | Rmt |  | 24010 |  |  |  | 70 | 24010 |  | 80% | 429
[6 empty] | AE | 9
13 | 319 | SITC of Hot dip galvanized perforated cable tray of 300 mm Wide sizes for to run the cable from Floor Panel to Lab Panel and electrical room to AC panel and AC panel to Units. All necessary supports and accessories are included. Cable tray for cables alone shall be included here Thickness shall be 1.6 mm. at MGMH Petlaburj
[6 empty] | 102.5 | 80 | 1048 | Rmt |  | 83840 |  |  |  | 80 | 83840 |  | 80% | 1310
[6 empty] | AE | 22.5
14 | 325 | Supply and installation of 50x6 GI flat for body earthing of electrical panel and AC Panel which is laid in 300mm cable tray at MGMH Petlaburj
[6 empty] | 217.3 | 200 | 263 | Rmt |  | 52600 |  |  |  | 200 | 52600 |  | 80% | 329
[6 empty] | AE | 17.3
15 | 323 | Providing and Fixing maintenance free earthing which consists of G.I. Earth station, with 600X600X3.15mm GI Plate at 2500mm Depth including construction of brick pedestal, providing meshed funnel, GI cover and other civil Engineering works, spreading a homogenous mixture of salt, charcoal around the pipe etc., completely as per IS 3043, 1987 or latest revision. Earthing testing should be done as per IE Rules like Earth valve test Etc. at MGMH Petlaburj
[7 empty] | 2 | 6800 | Nos |  | 13600 |  |  |  | 2 | 13600 |  | 80% | 8500
16 | 324 | Providing and Fixing maintenance free earthing which consists of copper. Earth station, with 600X600X3.15mm Copper Plate at 2500mm Depth including construction of brick pedestal, providing meshed funnel, GI cover and other civil Engineering works, spreading a homogenous mixture of salt, charcoal around the pipe etc., completely as per IS 3043, 1987 or latest revision. Earthing testing should be done as per IE Rules like Earth valve test Etc. at MGMH Petlaburj
[6 empty] | 4 | 2 | 17826 | Nos |  | 35652 |  |  |  | 2 | 35652 |  | 80% | 22283
[6 empty] | AE | 2
17 | 327 | Supply and installation of 25x3 Copper flat for Neutral earthing of UPS and Equipment which is laid in 100mm cable tray at MGMH Petlaburj
[6 empty] | 207.3 | 200 | 722 | Rmt |  | 144400 |  |  |  | 200 | 144400 |  | 80% | 902
[6 empty] | AE | 7.3
18 | 328 | Supply and installation of 4 sqmm Copper wire for Earthing of DBs Equipment at MGMH Petlaburj
[6 empty] | 450.6 | 80 | 66 | Rmt |  | 5280 |  |  |  | 80 | 5280 |  | 80% | 83
[6 empty] | AE | 370.6
19 | 329 | Supply, Laying and testing of 3.5Cx95 sqmm XLPE Insulated Cable 1100V grade armoured aluminium cable with ISI mark as per specification confirming to IS:7098 Part - I with heavy duty type double compression weather proof type brass cable glands duly nickel plated as per BS 6121 and IP66 complete with brass checknut, outer sheath sealing gasket heavy duty long barrel aluminium lugs confirming to I.S specifications with complete nut, bolt and washer etc.. Make of Cable: Polycab/ KEI/Universal/Glostar/Finolex. Make of gland and Lungs: HMI/Commet/Dowell’s at MGMH Petlaburj
[6 empty] | 180 | 120 | 966 | Rmt |  | 115920 |  |  |  | 120 | 115920 |  | 80% | 1207
[6 empty] | AE | 60
20 | 330 | Supply, Lying and testing of 3.5CX50 sqmm XLPE Insulated Cable 1100V grade armoured aluminium cable with ISI mark as per specification confirming to IS:7098 Part - I with heavy duty type double compression weather proof type brass cable glands duly nickel plated as per BS 6121 and IP66 complete with brass checknut, outer sheath sealing gasket heavy duty long barrel aluminium lugs confirming to I.S specifications with complete nut, bolt and washer etc.. Make of Cable: Polycab Make of gland and Lungs: HMI at MGMH Petlaburj
[6 empty] | 180 | 70 | 578 | Rmt |  | 40460 |  |  |  | 70 | 40460 |  | 80% | 722
[6 empty] | AE | 110
21 | 331 | Supply, Lying and testing of 4Cx16 sqmm PVC Insulated Cable 1100V grade armoured Copper cable with ISI mark as per specification confirming to IS:7098 Part - I with heavy duty type double compression weather proof type brass cable glands duly nickel plated as per BS 6121 and IP66 complete with brass checknut, outer sheath sealing gasket heavy duty long barrel aluminium lugs confirming to I.S specifications with complete nut, bolt and washer etc.. Make of Cable: Polycab/ KEI/Universal/Glostar/Finolex. Make of gland and Lungs: HMI/Commet/Dowell’s at MGMH Petlaburj
[7 empty] | 100 | 1186 | Rmt |  | 118600 |  |  |  | 100 | 118600 |  | 80% | 1483
22 | 332 | Supply, Lying and testing of 4Cx6 sqmm PVC Insulated Cable 1100V grade armoured Copper cable with ISI mark as per specification confirming to IS:7098 Part - I with heavy duty type double compression weather proof type brass cable glands duly nickel plated as per BS 6121 and IP66 complete with brass checknut, outer sheath sealing gasket heavy duty long barrel aluminium lugs confirming to I.S specifications with complete nut, bolt and washer etc. Make of Cable: Polycab/ KEI/Universal/ Glostar/Finolex. Make of gland and Lungs: HMI/Commet/Dowell’s at MGMH Petlaburj
[7 empty] | 120 | 387 | Rmt |  | 46440 |  |  |  | 120 | 46440 |  | 80% | 484
23 | 333 | Supply, Lying and testing of 4Cx4 sqmm PVC Insulated Cable 1100V grade armoured Copper cable with ISI mark as per specification confirming to IS:7098 Part - I with heavy duty type double compression weather proof type brass cable glands duly nickel plated as per BS 6121 and IP66 complete with brass checknut, outer sheath sealing gasket heavy duty long barrel aluminium lugs confirming to I.S specifications with complete nut, bolt and washer etc. Make of Cable:Polycab/ KEI/Universal/Glostar/Finolex. Make of gland and Lungs: HMI/Commet/Dowell’s at MGMH Petlaburj
[7 empty] | 80 | 285 | Rmt |  | 22800 |  |  |  | 80 | 22800 |  | 80% | 356
24 | 334 | SITC of IVF Center Main Panel Indoor IP-42 wall/ free standing floor mounted dust and vermin proof compartmentalized cubical panel made out of CRCA sheet, required hardware, duly treated for de-rusting in 7 tank process with de-phosphate and with powder coating on both side of panel in desired shade. The panel having PU/ Neoprene rubber gasket of not less than 3mm thickness, separate detachable gland plate M.S. base channel, hinged door with locking arrangement for equipment/switchgear. Thickness of sheet shall not be less than 1.6 mm up to 600 mm length / width of any compartment and be of 2.0 mm above 600 mm. Load bearing structure shall be of 2.0 mm thick sheet supported by base M.S. channel if required. Side walls and cable alley compartments having bolted type doors with /without detachable extension type structure with all type of suitable switching accessories and bus-bar as per load requirement of respective IVF equipment’s. Which is including Lighting, power DBs and UPS at MGMH Petlaburj
[7 empty] | 1 | 284000 | Nos |  | 284000 |  |  |  | 1 | 284000 |  | 80% | 355000
25 | 335 | SITC of IVF center AC Panel outdoor IP-54 wall/ free standing floor mounted dust and vermin proof compartmentalized cubical panel made out of CRCA sheet, required hardware, duly treated for de-rusting in 7 tank process with de-phosphate and with powder coating on both side of panel in desired shade. The panel having PU/ Neoprene rubber gasket of not less than 3mm thickness, separate detachable gland plate M.S. base channel, hinged door with locking arrangement for equipment/switchgear. Thickness of sheet shall not be less than 1.6 mm up to 600 mm length / width of any compartment and be of 2.0 mm above 600 mm. Load bearing structure shall be of 2.0 mm thick sheet supported by base M.S. channel if required. Side walls and cable alley compartments having bolted type doors with / without detachable extension type structure with all type of suitable switching accessories and bus-bar as per load requirement of respective AC equipment’s. Which is including 1nos AHU’s stater with VFD by pass, Heater, ODU and VRF system at MGMH Petlaburj
[7 empty] | 1 | 216000 | Nos |  | 216000 |  |  |  | 1 | 216000 |  | 80% | 270000
[9 empty] | Sub-Total:- |  | 1856102 |  |  | 13608800 |  | 1856102
[8 empty] | Sub-Total(Civil+ Civil Suppl.+Equipment):- |  |  | 16909114.027 |  |  | 15053013.62 |  | 1837502
[9 empty] | Add GST 18% |  | 3043640.5249 |  |  | 2709542.4516 |  | 330750.36
[9 empty] | GrandTotal:- |  | 19952754.5519 |  |  | 17762556.0716 |  | 2168252.36
Certificate
[7 empty] | 1) | The work is in progress in according with the specification drawing and terms and condition the agreement.
[7 empty] | 2) | No recoveries are due for recovery from the contractor other than those proposed in the bill
[7 empty] | 3) | There are no further dues to be recovery from the contractor
[7 empty] | 4) | The contractor has conveyneced the materieals for use on the work as per the lead statement approved the agreement.
[7 empty] | 5) | The leads and lifts are covered in the contractor.

## BIll-5
DETAILED MEASUREMENTS
Name of the work:Design, Fabriction, establishing and commissioning of In - Vitro ferility centers (IVFC) alongwith allied Services on Turnkey basis at petlaburz Hyderabad. | [10 empty] | Agency: M/s. Asta vardhman Consortium | [5 empty] | Agt.No: 344/A/TSMIDC/Spl.Proj/IVFCs/2022-23, Dt. 05.07.2023
S.No | Agreement S.No | Discription Of Work etc., | Measurements Upto date | [5 empty] | Rate |  |  | Per | Total Volume |  | Deduct/previous Measurements |  | Since last measurement |  |  | Remarks
|  |  | No |  | L | B | D | Content | Units | Rs | Ps. |  | Rs. | Ps | P.No. | Qty. | Qty | Value
[18 empty] | Rs. | Ps.
1 | 346 | Supply, transportation and installation of split AC unit 1.5 TR inverter type 3 Star capable of delivering 18000 BTU/hr and above with high wall mounted indoor unit and outdoor condensing unit Hermetically sealed compressor suitable for operation on 230V, 50Hz, 1Phase AC supply capable of performing cooling dehumidifying air circulating and filtering with cooling and condensing units with 3.5 mts of copper piping, insulation kit and 4 mts of 3 core copper flexible chord , built-in stabilizer Voltage range 160- 264 volts and cordless remote control. Makes : Daikin / Thoshiba / O General at MGMH Petlaburj
|  | UPS Room | 1 | 1 |  |  |  | 1
|  | Andrology Lab | 1 | 1 |  |  |  | 1
|  | Reception | 1 | 1 |  |  |  | 1
[6 empty] | Total |  | 3 | Nos |  | C/o to Pg No: of M.B.No:
2 | Sup | Condensing units - VRF/VRV System : Supply, Installation, Nitrogen testing , Vacuuming and Commissioning of air cooled variable refrigerant flow modular type condensing units, each comprising of multiple scroll compressors all inverter driven, full charge of refrigerant gas R-410a including additional gas filling , lubricating oil and all accessories as per the specifications. The condensing units shall be suitable to work on cooling mode. The minimum Energy Efficiency Ratio shall be as per ASHRAE STANDARDS 90.1 -2001 table 6.2.1B . The COP of the system shall be greater than 4 under ARI conditions for 100percentage load . The condensing units shall be suitable for operation on 415 plus or minus 10percentage volts, 50Hz, 3 phase AC power supply and , outdoor units to be mounted on MS platform with suitable Vibration Isolation pads to avoid vibrations. All the supports and angle base frame structure to be duly black painted with synthetic epoxy paint. the condensing units shall be of following capacities: The VRF ODU should be capable of working with total capacity of connected indoor units ranging between 100percentage to 140percentage of ODU capacity . COP minimum 3.5. Make : Daikin / LG / O General / Toshiba at MGMH Petlaburj 24HP
|  | 24 HP Outdoor Unit | 1 | 1 |  |  |  | 1
[6 empty] | Total |  | 1 | Nos
3 | 371 | VRF Indoor Units : Hi wall Splits : Supply, Installation, Testing and Commissioning of variable refrigerant flow modular type indoor units wired/wireless remote suitable for R410a refrigerant comprising of all accessories as per the specifications. The indoor units shall be suitable to work on cooling.The minimum Energy Efficiency Ratio shall be as per ASHRAE STANDARDS 90.1 -2001 table 6.2.1B. The indoor units shall be suitable for operation on 220 plus or minus 6percentage volts, 50Hz, 1 phase AC power supply. 0.8 TR at MGMH Petlaburj
|  | Cryo Room | 1 | 1 |  |  |  | 1
|  | Waiting Room | 1 | 1 |  |  |  | 1
[6 empty] | Total |  | 2 | Nos |  | C/o to Pg No: of M.B.No:
4 | 372 | VRF Indoor Units : Hi wall Splits : Supply, Installation, Testing and Commissioning of variable refrigerant flow modular type indoor units wired/wireless remote suitable for R410a refrigerant comprising of all accessories as per the specifications. The indoor units shall be suitable to work on cooling.The minimum Energy Efficiency Ratio shall be as per ASHRAE STANDARDS 90.1 -2001 table 6.2.1B. The indoor units shall be suitable for operation on 220 plus or minus 6percentage volts, 50Hz, 1 phase AC power supply. 1.0 TR at MGMH Petlaburj
|  | Counseling Room 1,2 | 1 | 2 |  |  |  | 2
|  | Anesthetist Room | 1 | 1 |  |  |  | 1
|  | Embryologist Room | 1 | 1 |  |  |  | 1
|  | Seamen Collection Room | 1 | 1 |  |  |  | 1
|  | Sample Collection | 1 | 1 |  |  |  | 1
[6 empty] | Total |  | 6 | Nos |  | C/o to Pg No: of M.B.No:
5 | 373 | VRF Indoor Units : Hi wall Splits : Supply, Installation, Testing and Commissioning of variable refrigerant flow modular type indoor units wired/wireless remote suitable for R410a refrigerant comprising of all accessories as per the specifications. The indoor units shall be suitable to work on cooling.The minimum Energy Efficiency Ratio shall be as per ASHRAE STANDARDS 90.1 -2001 table 6.2.1B. The indoor units shall be suitable for operation on 220 plus or minus 6percentage volts, 50Hz, 1 phase AC power supply. 1.5 TR at MGMH Petlaburj
|  | Senior Faculty Room | 1 | 1 |  |  |  | 1
|  | Ultra Sound Room | 1 | 1 |  |  |  | 1
|  | Major OT | 1 | 2 |  |  |  | 2
|  | Andrology Lab | 1 | 1 |  |  |  | 1
|  | UPS Room | 1 | 1 |  |  |  | 1
[6 empty] | Total |  | 6 | Nos |  | C/o to Pg No: of M.B.No:
6 | Sup | Cassette Units : Supply, Installation, Testing and Commissioning of variable refrigerant flow modular type indoor units wired/wireless remote suitable for R410a refrigerant comprising of all accessories as per the specifications. The indoor units shall be suitable to work on cooling mode.The minimum Energy Efficiency Ratio shall be as per ASHRAE STANDARDS 90.1 -2001 table 6.2.1B. The indoor units shall be suitable for operation on 220 plus or minus 6percentage volts, 50Hz, 1 phase AC power supply. 3.0 TR – 4 way at MGMH Petlaburj
|  | Pre Operative Wards | 1 | 1 |  |  |  | 1
|  | Post Operative Ward | 1 | 1 |  |  |  | 1
[6 empty] | Total |  | 2 | Nos |  | C/o to Pg No: of M.B.No:
7 | 375 | Supply, Installation, Testing and Commissioning of Hard copper REFRIGERANT PIPING of 16swg various sizes with necessary supports, fittings, interconnecting the liquid and suction lines between the aircooled outdoor units and the indoor units. The piping shall be carried out of Hard drawn copper pipes of type K with soldered / brazed socket fittings. Isolating valves shall be provided to isolate each compressor, strainers, sight glass and any other component requiring proper operation and maintenance. Both the suction and liquid lines shall be insulated with 19mm thick closed cell insulation for above 25mm dia , 13mm thick for pipes below 25mm dia . The insulation finished with treated woven glass fiber reinforced covering for inside Piping and including making required holes in the wall and re finishing and water tight of holes after laying holes as per the specifications and approved drawings at MGMH Petlaburj
|  | Copper Peping | 1 | 1 |  |  |  | 1
[6 empty] | Total |  | 1 | Lot |  | C/o to Pg No: of M.B.No:
8 | 376 | Supply, Installation , Testing and Commissioning of Refnet joints to be provided in refrigerant pipe line. Material of construction for fittings shall be similar to refrigerant piping at MGMH Petlaburj
|  | Major OT | 1 | 1 |  |  |  | 1
|  | Cryo Room | 1 | 1 |  |  |  | 1
|  | Andrology Room | 1 | 1 |  |  |  | 1
|  | Semen Collection Room | 1 | 2 |  |  |  | 2
|  | Waiting Room Corridor | 1 | 2 |  |  |  | 2
|  | Post Operative Ward | 1 | 1 |  |  |  | 1
|  | Anesthetist Room | 1 | 2 |  |  |  | 2
|  | Counseling Room -1 | 1 | 1 |  |  |  | 1
|  | Ultra Sound Room | 1 | 1 |  |  |  | 1
|  | Sample Collection Room | 1 | 1 |  |  |  | 1
|  | Pre Operative Wards | 1 | 1 |  |  |  | 1
|  | Auto Clave Room | 1 | 1 |  |  |  | 1
[6 empty] | Total |  | 15 | Nos |  | C/o to Pg No: of M.B.No:
9 | 291 | Supply, installation, testing and commissioning of 16 G GI powder coated suitable single person entry air shower as per the Technical Specifications at MGMH Petlaburj
|  | Air Shower | 1 | 1 |  |  |  | 1
[6 empty] | Total |  | 1 | Nos |  | C/o to Pg No: of M.B.No:
10 | 287 | Double leaf clean room Doors : 46mm thick flush doors made of 0.8mm thick Powder coated GI sheets on both sides, 90 plus or minus 2 kg/m3 density Honeycomb with stand upto 220 Deg.C Temperature, and compressible strength upto 400 Kg/Sqm, 1.2 mm thick GPSP . door frames, double glazed vision panel with necessary adhesive tapes and silicon sealant, necessary hardware like SS304 ball bearing butt hinges, D- handles, push plates, Dorma make door closure, concealed tower bolt, drop seals for the double leaf door and provision for fixing magnetic type door interlocking system and automatic door bottoms, Both side lock and keys etc. complete. Size 1500 X 2100 mm with 300mm X 300mm double glazed view panels at MGMH Petlaburj
|  | Access Control Door(1485 x 2100) | 1 | 1 |  |  |  | 1
|  | IVF OT Door (1485 x 2105) | 1 | 1 |  |  |  | 1
|  | Andrology Lab (1250 x 2115) | 1 | 1 |  |  |  | 1
|  | Embryology Lab (1495 x 2105) | 1 | 1 |  |  |  | 1
|  | Major OT (1495 x 2100) | 1 | 1 |  |  |  | 1
[6 empty] | Total |  | 5 | Nos |  | C/o to Pg No: of M.B.No:
11 | Sup | Single leaf clean room Doors : 46mm thick flush doors made of 0.8mm thick Powder coated GI sheets on both sides, 90 plus or minus 2 kg/m3 density Honeycomb with stand upto 220 Deg.C Temperature, and compressible strength upto 400 Kg/Sqm, 1.2 mm thick GPSP . door frames, double glazed vision panel with necessary adhesive tapes and silicon sealant, necessary hardware like SS304 ball bearing butt hinges, D- handles, push plates, Dorma make door closure, concealed tower bolt, drop seals for the double leaf door and provision for fixing magnetic type door interlocking system and automatic door bottoms, Both side lock and keys etc. complete. Size 900 X 2100 mm with 300 mm x 300 mm View panelat MGMH Petlaburj
|  | Cryo Room (1000 x 2100) | 1 | 1 |  |  |  | 1
|  | Autoclave Room (1000 x 2100) | 1 | 1 |  |  |  | 1
|  | Access Control Door (1140 x 2100) | 1 | 1 |  |  |  | 1
[6 empty] | Total |  | 3 | Nos |  | C/o to Pg No: of M.B.No:
12 | Sup | Emergency Fire Doors : 46mm thick flush doors made of 0.8mm thick Powder coated GI sheets on both sides, 90 plus or minus 2 kg/m3 density Honeycomb with stand upto 220 Deg.C Temperature, and compressible strength upto 400 Kg/Sqm, 1.2 mm thick GPSP . door frames, double glazed vision panel with necessary adhesive tapes and silicon sealant, necessary hardware like SS304 ball bearing butt hinges, D- handles, push plates, Dorma make door closure, concealed tower bolt, drop seals for the double leaf door and provision for fixing magnetic type door interlocking system and automatic door bottoms, Both side lock and keys etc. complete. Size 1500 X 2100 mm with 2 hours fire rated and panic push bar and accessories etc. at Gandhi Hospital
|  | Emergency Exit Door (1500 x 2100) | 1 | 1 |  |  |  | 1
[6 empty] | Total |  | 1 | Nos
13 | Sup | Emergency Fire Doors : 46mm thick flush doors made of 0.8mm thick Powder coated GI sheets on both sides, 90 plus or minus 2 kg/m3 density Honeycomb with stand upto 220 Deg.C Temperature, and compressible strength upto 400 Kg/Sqm, 1.2 mm thick GPSP . door frames, double glazed vision panel with necessary adhesive tapes and silicon sealant, necessary hardware like SS304 ball bearing butt hinges, D- handles, push plates, Dorma make door closure, concealed tower bolt, drop seals for the double leaf door and provision for fixing magnetic type door interlocking system and automatic door bottoms, Both side lock and keys etc. complete. Size 1000 X 2100 mm with 2 hours fire rated and panic push bar and accessories etc. at Gandhi Hospital
|  | UPS Room (1000 x 2600) | 1 | 1 |  |  |  | 1
|  | Electrical Room (1000 x 2100) | 1 | 1 |  |  |  | 1
[6 empty] | Total |  | 2 | Nos
14 | 285 | Supply and installation of 80mm thick double skin modular wall Panels made of 0.8 mm thick powder coated GI on both the sides, with 40 plus or minus 2 kg/m3 density PUF as infill, GI profiles all along the periphery, flush on both sides with maximum allowable gap of 3- 4mm filled with food grade silicon sealant and placed on cold rolled galvanised bottom tracks with a recess to provide floor to wall coving flush with the wall panel. This includes all required harware for completion Panels to be covered with a protective film to avoid any damages during transportation and installation at MGMH Petlaburj
|  | AP-80WP-24 (IVF OT) | 1 | 1 | 1.105 |  | 2.8 | 3.094
|  | AP-80WP-23 (IVF OT) | 1 | 1 | 1.105 |  | 2.65 | 2.9282
|  | AP-80WP-22 (IVF OT) | 1 | 1 | 1.105 |  | 2.65 | 2.9282
|  | AP-80WP-21 (IVF OT) | 1 | 1 | 1.105 |  | 2.8 | 3.094
|  | AP-80WP-20 (IVF OT) | 1 | 1 | 1.105 |  | 2.65 | 2.9282
|  | AP-80WP-01 (IVF OT) | 1 | 1 | 1.014 |  | 2.65 | 2.6871
|  | AP-80WP-02 (IVF OT) | 1 | 1 | 1.105 |  | 2.65 | 2.9282
|  | AP-80WP-03 (IVF OT) | 1 | 1 | 1.105 |  | 2.65 | 2.9282
|  | AP-80WP-49 (IVF OT) | 1 | 1 | 0.33 |  | 2.65 | 0.8745
|  | AP-80WP-50 (IVF OT) | 1 | 1 | 0.43 |  | 2.65 | 1.1395
|  | AP-80WP-51 (IVF OT) | 1 | 1 | 0.33 |  | 2.65 | 0.8745
|  | AP-80WP-04 (IVF OT) | 1 | 1 | 1.105 |  | 2.65 | 2.9282
|  | AP-80WP-05 (IVF OT) | 1 | 1 | 0.84 |  | 2.65 | 2.226
|  | AP-80WP-26 (IVF OT) | 1 | 1 | 1.105 |  | 2.65 | 2.9282
|  | AP-80WP-27 (IVF OT) | 1 | 1 | 1.105 |  | 2.8 | 3.094
|  | AP-80WP-28 (IVF OT) | 1 | 1 | 1.105 |  | 2.65 | 2.9282
|  | AP-80WP-29 (IVF OT) | 1 | 1 | 1.105 |  | 2.65 | 2.9282
|  | AP-80WP-30 (IVF OT) | 1 | 1 | 1.5 |  | 0.54 | 0.81
|  | AP-80WP-31 (IVF OT) | 1 | 1 | 0.184 |  | 2.65 | 0.4876
|  | AP-80WP-15 (IVF OT) | 1 | 1 | 0.842 |  | 2.65 | 2.2313
|  | AP-80WP-14 (IVF OT) | 1 | 1 | 1.105 |  | 2.8 | 3.094
|  | AP-80WP-57 (IVF OT) | 1 | 1 | 0.363 |  | 2.65 | 0.96195
|  | AP-80WP-56 (IVF OT) | 1 | 1 | 0.43 |  | 2.65 | 1.1395
|  | AP-80WP-55 (IVF OT) | 1 | 1 | 0.363 |  | 2.65 | 0.96195
|  | AP-80WP-13 (IVF OT) | 1 | 1 | 0.16 |  | 2.65 | 0.424
|  | AP-80DTP-12 (IVF OT) | 1 | 1 | 1.49 |  | 0.542 | 0.80758
|  | AP-80WP-11 (IVF OT) | 1 | 1 | 0.36 |  | 2.65 | 0.954
|  | AP-80WP-10 (IVF OT) | 1 | 1 | 1.1 |  | 2.65 | 2.915
|  | AP-80WP-25 (IVF OT) | 1 | 1 | 0.695 |  | 2.65 | 1.8417
|  | AP-80DTP-37 (Embryology Lab) | 1 | 1 | 1.495 |  | 0.542 | 0.81029
|  | AP-80WP-36 (Embryology Lab) | 1 | 1 | 0.188 |  | 2.65 | 0.4982
|  | AP-80WP-35 (Embryology Lab) | 1 | 1 | 1.105 |  | 2.65 | 2.9282
|  | AP-80WP-34 (Embryology Lab) | 1 | 1 | 1.105 |  | 2.65 | 2.9282
|  | AP-80WP-33 (Embryology Lab) | 1 | 1 | 1.105 |  | 2.8 | 3.094
|  | AP-80WP-32 (Embryology Lab) | 1 | 1 | 1.105 |  | 2.65 | 2.9282
|  | AP-80WP-06 (Embryology Lab) | 1 | 1 | 0.83 |  | 2.65 | 2.1995
|  | AP-80WP-52 (Embryology Lab) | 1 | 1 | 0.33 |  | 2.65 | 0.8745
|  | AP-80WP-53 (Embryology Lab) | 1 | 1 | 0.405 |  | 2.65 | 1.0733
|  | AP-80WP-54 (Embryology Lab) | 1 | 1 | 0.33 |  | 2.65 | 0.8745
|  | AP-80WP-07 (Embryology Lab) | 1 | 1 | 1.105 |  | 2.65 | 2.9282
|  | AP-80WP-08 (Embryology Lab) | 1 | 1 | 1.105 |  | 2.65 | 2.9282
|  | AP-80WP-09 (Embryology Lab) | 1 | 1 | 0.92 |  | 2.65 | 2.438
|  | AP-80WP-39 (Embryology Lab) | 1 | 1 | 1.105 |  | 2.65 | 2.9282
|  | AP-80WP-40 (Embryology Lab) | 1 | 1 | 1.105 |  | 2.8 | 3.094
|  | AP-80WP-41 (Embryology Lab) | 1 | 1 | 1.105 |  | 2.65 | 2.9282
|  | AP-80WP-42 (Embryology Lab) | 1 | 1 | 1.105 |  | 2.8 | 3.094
|  | AP-80WP-43 (Embryology Lab) | 1 | 1 | 1.105 |  | 2.65 | 2.9282
|  | AP-80WP-44 (Embryology Lab) | 1 | 1 | 0.76 |  | 2.65 | 2.014
|  | AP-80WP-19 (Embryology Lab) | 1 | 1 | 0.9 |  | 2.65 | 2.385
|  | AP-80WP-18 (Embryology Lab) | 1 | 1 | 1.105 |  | 2.8 | 3.094
|  | AP-80WP-17 (Embryology Lab) | 1 | 1 | 1.105 |  | 2.65 | 2.9282
|  | AP-80WP-60 (Embryology Lab) | 1 | 1 | 0.33 |  | 2.65 | 0.8745
|  | AP-80WP-59 (Embryology Lab) | 1 | 1 | 0.415 |  | 2.65 | 1.0998
|  | AP-80WP-58 (Embryology Lab) | 1 | 1 | 0.33 |  | 2.65 | 0.8745
|  | AP-80WP-16 (Embryology Lab) | 1 | 1 | 0.84 |  | 2.65 | 2.226
|  | AP-80WP-38 (Embryology Lab) | 1 | 1 | 0.182 |  | 2.65 | 0.4823
|  | AP-80WP-45 ( Air Shower) | 1 | 1 | 0.84 |  | 0.6 | 0.504
|  | AP-80DTP-46 ( Air Shower) | 1 | 1 | 1.14 |  | 0.79 | 0.9006
|  | AP-80WP-47 ( Air Shower) | 1 | 1 | 1.76 |  | 0.6 | 1.056
|  | AP-80WP-48 ( Air Shower) | 1 | 1 | 1.76 |  | 0.6 | 1.056
[6 empty] | Total |  | 121.0376 | Sqm |  | C/o to Pg No: of M.B.No:
15 | 286 | Supply and installation of 50mm thick double skin ceiling system made of 0.8 mm thick Powder Coated GI sheets on both sides, 40 plus or minus 2 kg/m3 density PUF as infill, GI profiles all along the periphery, panels flush towards room side with maximum allowable gap of 3-4mm at panel to panel joints filled with silicon sealant. Ceiling panels are suspended from the RCC slab by using concealed AL ceiling grid with tie rod and adjustable turn buckle arrangement etc. This includes all required hardware for completion. Panels to be covered with a protective film to avoid any damages during transportation and installation at MGMH Petlaburj
|  | AP-50CP-61 (IVF OT) | 1 | 1 | 1.14 |  | 2.037 | 2.3222
|  | AP-50CP-62 (IVF OT) | 1 | 1 | 1.14 |  | 2.037 | 2.3222
|  | AP-50CP-63 (IVF OT) | 1 | 1 | 1.14 |  | 2.037 | 2.3222
|  | AP-50CP-64 (IVF OT) | 1 | 1 | 1.14 |  | 2.037 | 2.3222
|  | AP-50CP-65 (IVF OT) | 1 | 1 | 1.083 |  | 2.037 | 2.2061
|  | AP-50CP-66 (IVF OT) | 1 | 1 | 1.14 |  | 2.037 | 2.3222
|  | AP-50CP-67 (IVF OT) | 1 | 1 | 1.14 |  | 2.037 | 2.3222
|  | AP-50CP-68 (IVF OT) | 1 | 1 | 1.14 |  | 2.037 | 2.3222
|  | AP-50CP-69 (IVF OT) | 1 | 1 | 1.14 |  | 2.037 | 2.3222
|  | AP-50CP-70 (IVF OT) | 1 | 1 | 1.083 |  | 2.037 | 2.2061
|  | AP-50CP-71 (IVF OT) | 1 | 1 | 1.14 |  | 2.036 | 2.321
|  | AP-50CP-72 (IVF OT) | 1 | 1 | 1.14 |  | 2.036 | 2.321
|  | AP-50CP-73 (IVF OT) | 1 | 1 | 1.14 |  | 2.036 | 2.321
|  | AP-50CP-74 (IVF OT) | 1 | 1 | 1.14 |  | 2.036 | 2.321
|  | AP-50CP-75 (IVF OT) | 1 | 1 | 1.083 |  | 2.036 | 2.205
|  | AP-50CP-76 (IVF OT Door) | 1 | 1 | 0.34 |  | 1.5 | 0.51
|  | AP-50CP-77 (Embryology Lab Door) | 1 | 1 | 0.227 |  | 1.48 | 0.33596
|  | AP-50CP-78 (Embryology Lab) | 1 | 1 | 0.54 |  | 2.025 | 1.0935
|  | AP-50CP-79 (Embryology Lab) | 1 | 1 | 1.14 |  | 2.025 | 2.3085
|  | AP-50CP-80 (Embryology Lab) | 1 | 1 | 1.14 |  | 2.025 | 2.3085
|  | AP-50CP-81 (Embryology Lab) | 1 | 1 | 1.14 |  | 2.025 | 2.3085
|  | AP-50CP-82 (Embryology Lab) | 1 | 1 | 0.54 |  | 2.025 | 1.0935
|  | AP-50CP-83 (Embryology Lab) | 1 | 1 | 0.54 |  | 2.025 | 1.0935
|  | AP-50CP-84 (Embryology Lab) | 1 | 1 | 1.14 |  | 2.025 | 2.3085
|  | AP-50CP-85 (Embryology Lab) | 1 | 1 | 1.14 |  | 2.025 | 2.3085
|  | AP-50CP-86 (Embryology Lab) | 1 | 1 | 1.14 |  | 2.025 | 2.3085
|  | AP-50CP-87 (Embryology Lab) | 1 | 1 | 0.54 |  | 2.025 | 1.0935
|  | AP-50CP-88 (Embryology Lab) | 1 | 1 | 0.54 |  | 2.025 | 1.0935
|  | AP-50CP-89 (Embryology Lab) | 1 | 1 | 1.14 |  | 2.025 | 2.3085
|  | AP-50CP-90 (Embryology Lab) | 1 | 1 | 1.14 |  | 2.025 | 2.3085
|  | AP-50CP-91 (Embryology Lab) | 1 | 1 | 1.14 |  | 2.025 | 2.3085
|  | AP-50CP-92 (Embryology Lab) | 1 | 1 | 0.54 |  | 2.025 | 1.0935
[6 empty] | Total |  | 62.6622 | Sqm |  | C/o to Pg No: of M.B.No:
16 | 289 | Supply and installation of Extruded Aluminium Coving at MGMH Petlaburj
|  | Embryology Lab Long Wall | 1 | 1 | 6.12 |  |  | 6.12
|  | do | 1 | 1 | 6.1 |  |  | 6.1
|  | Short Wall | 1 | 1 | 4.55 |  |  | 4.55
|  | do | 1 | 1 | 4.56 |  |  | 4.56
|  | Columns Sides | 1 | 4 | 0.2 |  |  | 0.8
|  | Corners Verticals | 1 | 4 | 2.505 |  |  | 10.02
|  | do | 1 | 8 | 2.705 |  |  | 21.64
|  | IVF OT Long Wall | 1 | 1 | 6.07 |  |  | 6.07
|  | do | 1 | 1 | 6.13 |  |  | 6.13
|  | Short Wall | 1 | 1 | 5.76 |  |  | 5.76
|  | do | 1 | 1 | 5.66 |  |  | 5.66
|  | Columns Sides | 1 | 4 | 0.2 |  |  | 0.8
|  | Corners Verticals | 1 | 4 | 2.505 |  |  | 10.02
|  | do | 1 | 8 | 2.7 |  |  | 21.6
[6 empty] | Total |  | 109.83 | Rmt |  | C/o to Pg No: of M.B.No:
17 | 292 | Supply, installation, Testing and Commissioning of Static Pass Boxes of Size 450X450mm with 1.2mm thick SS 304 Mat finish , with interlock doors, UV light On when doors closed condition. As per clean room standard and requirement. at MGMH Petlaburj
|  | OVF OT to Embrology Lab | 1 | 1 |  |  |  | 1
|  | Seamen Collection to Andrology Lab | 1 | 1 |  |  |  | 1
[6 empty] | Total |  | 2 | Nos |  | C/o to Pg No: of M.B.No:
18 | 259 | Supplying and fixing of Unplasticised Poly Vinyl Chloride UPVC 3 track sliding windows with mesh shutter – 2-glass shutters and 1-mesh shutter duly manufactured using UPVC reinforced profiles Composition of profile shall consists a minimum of 5.5 PHR of TiO2 and not more than 12 PHR of CaCo3 for every 100 parts of PVC resin of 94mm x 45 mm/80 mm x 52 mm x 2.20 mm for outer frames, 58 mm x 39 mm/54 mm x 38 mm x 2.20mm for sliding shutter frames capable of mounting single glazing system structurally reinforced with hot dip galvanized up to 50 microns of minimum thickness of 1.0/1.2 mm prefabricated and welded through fusion welding. The window sash shall be fitted with 5 mm thick clear float glass of reputed make and mesh shutter frame shall be 42 mm x 25mm/52 mm x 21.5 mm x 2.0 mm fitted with Vinyl Coated Fiber mesh- on rollers/ pulley duly fixed with Grey colour TPV Gasket for sash and Glazing bead shall be co-extruded with Grey colour soft PVC. System shall have single point locking with Touch Lock and the system is to be installed at the site using anchor fasteners, silicon rubber sealant, easy glazing/deglazing at site etc., including cost and conveyance of all materials, accessories, labour charges for transportation, erection at site includingetc., complete for finished item of work. at MGMH Petlaburj
|  | Receotion | 1 | 1 | 1.82 |  | 1.698 | 3.0904
|  | Record Room | 1 | 1 | 1.803 |  | 1.701 | 3.0669
|  | Sr Faculty Room | 1 | 1 | 1.804 |  | 1.704 | 3.074
|  | Store Room | 1 | 1 | 1.798 |  | 1.7 | 3.0566
|  | Pre Operative Ward | 1 | 1 | 1.808 |  | 1.7 | 3.0736
|  | Autoclave Room | 1 | 1 | 1.796 |  | 1.701 | 3.055
|  | Semen Collection Room | 1 | 1 | 1.812 |  | 1.702 | 3.084
|  | Post Operative Ward | 1 | 1 | 1.8 |  | 1.702 | 3.0636
|  | Embryologist Room | 1 | 1 | 1.807 |  | 1.7 | 3.0719
|  | Patient Changing Room | 1 | 1 | 1.806 |  | 1.696 | 3.063
|  | Counselling Room-2 | 1 | 1 | 1.796 |  | 1.702 | 3.0568
|  | Manifold Room | 1 | 1 | 1.797 |  | 1.701 | 3.0567
|  | UPS Room | 1 | 1 | 1.81 |  | 1.682 | 3.0444
[6 empty] | Total |  | 39.8569 | Sqm |  | C/o to Pg No: of M.B.No:
19 | 260 | Providing, supplying and fixing of Fixed Louvered Ventilator made out of multi chambered uPVC sections with Glazing bead shall be co-extruded with Grey colour soft PVC. having isolated drainage and reinforced with Galvanized Iron profiles throughout the window. The outer frame having an overall size of 60 mm x 55 mm x 2.40 with reinforcement of 1 mm thickness and Mullion with overall size of 74 mm x 60 mm x 2.40 mm with reinforcement of 1 mm thickness. Composition of profile shall consists a minimum of 5.5 PHR of TiO2 and not more than 12 PHR of CaCo3 for every 100 parts of PVC resin. Ventilator shall be provided with 4.5 mm Pin Head glass, standard hardware. Wall thickness of frame and Mullion shall be 2.4 mm., including cost and conveyance of all materials, accessories, labour charges for transportation, erection at site etc., complete for finished item of work hinges IS:205 150mm long, 1 No. aldrop IS:2681 300mm long, 1 No. tower bolt IS:204 of 200 mm x 10 mm dia at top, 2 Nos. 150 mm at MGMH Petlaburj
|  | Record Room Toilet | 1 | 1 | 0.63 |  | 0.57 | 0.3591
|  | Counseling 1 Room Toilet | 1 | 1 | 0.6 |  | 0.49 | 0.294
|  | Post Operative Ward Toilet | 1 | 1 | 0.61 |  | 0.49 | 0.2989
|  | Semen Collection Room Toilet | 1 | 1 | 0.59 |  | 0.49 | 0.2891
|  | Patient Changing Room Toilet | 1 | 1 | 0.615 |  | 0.595 | 0.36593
|  | Embryologist Room Toilet | 1 | 1 | 0.635 |  | 0.565 | 0.35877
[6 empty] | Total |  | 1.9658 | Sqm |  | C/o to Pg No: of M.B.No:
20 | 227 | Suction machine Portable suction unit: size 38x17x28.5cm, weight 5.1kg Technical specifications: SUCTION MACHINE with pump: Power supply: 230-240V/50Hz Vacuum capacity: 18 litres/mim Maximum depression: -75kPa (-563mmHg) Vacuum is created by a plastic piston and cylinder system, with four vacuum-creating modules (QuatroFlex™ technology). The membrane vacuum regulator permits accurate vacuum settings. Double overflow-protection system (bottle and pump). Working temperature range: +5 to +40°C. at Petlaburj Hospital
|  | Suction Machine | 1 | 1 |  |  |  | 1
[6 empty] | Total |  | 1 | Nos |  | C/o to Pg No: of M.B.No:
21 | 230 | Operative Hysteroscopy and Resectoscope Set Machine 2.9 mm hysteroscope "Hysteroscope sheath for 2.9 mm telescope operative inner sheath "Hysteroscope sheath for 2.9 mm telescope operative outer sheath Accessories for hysteroscope — Hysteroscopy scissor Hysteroscopy grasper Hysteroscopy biopsy forceps Monopolar electrode Bipolar electrode Monopolar cable Bipolar cabl Hysteroscopy pressure bag - 1000ml Hysteromat Vasa Point at Petlaburj Hospital
|  | Hysteroscopy | 1 | 1 |  |  |  | 1
[6 empty] | Total |  | 1 | Nos |  | C/o to Pg No: of M.B.No:
22 | 231 | Operative Laparoscopy Set "3 Chip CMOS or 3chip CCD Full HD Camera with -Camera Head and ZOOM Coupler- RESIOLUTION 1920 *1080 PIXELS" LED LIGHT SOURCE 300W LED Light Source "FIBRE OPTIC CABLE 4.8MM 2.5 MTR or more "MEDICL MONITOR LED 26” WITH POWER ADOPTOR" "40 LTR CO2 INSUFFLATOR WITH INBUILT HEATER" CO2 REGULATORTelescope 10MM 30 DEG HD TELESCOPE 10MM 5 MM 30 DEG HD TELESCOPE 5 MM 30 10 MM 0 DEG HD TELESCOPE 10 MM 0 DEG at Petlaburj Hospital
|  | Laparoscopy | 1 | 1 |  |  |  | 1
[6 empty] | Total |  | 1 | Nos |  | C/o to Pg No: of M.B.No:

## Abs -5
ABSTRACT
Name of Work:- Design, Fabriction, establishing and commissioning of In - Vitro ferility centers (IVFC) alongwith allied Services on Turnkey basis at MGMH Petlaburj,Hyd. | [7 empty] | Agency: | M/s. Asta Vardhman Consortium | [5 empty] | Agt.No:344/A/TSMIDC/Spl.Proj/IVFCs /2022-23,Dt.05.07.2023
S.No | Date of measurement/ S.No. in Agt. | Description Of Work etc., | Measurements Upto date |  |  |  |  | Rate |  | Per | Total Value to date |  | Deduct/previous Measurements |  | Since last measurement |  |  | Remarks
|  |  | No | L | B | D | Content | Rs | Ps. |  | Rs. | Ps | P.No. | Qty. | Qty | Value
[16 empty] | Rs. | Ps.
1 | 247 | Dismantling, clearing away and carefully stacking useful materials for re-use and disposal of unserviceable materials with 100m lead as directed by Executive Engineer duly taking actual premeasurements before dismantling including all labour charges , overheads & contractor profit etc., complete Finished item of work | [16 empty] | Original Rate
a) Brick Masonry
|  | Qty V.Pg.No:-01 of MB:-04 |  |  |  | 20.38 | 20.38 | 398 | Cum |  | 8111.24 |  | 20.38 | 8111.24 | - | - |  |  | 398
| 248 | b) Tiles Dismantling
|  | Qty V.Pg.No:-01 of MB:-04 |  |  |  | 729.9325 | 400 | 20 | Sqm |  | 8000 |  | 400 | 8000 | - | - |  |  | 20
[6 empty] | AE | 329.9325
2 | 249 | Dismantling doors, windows and clear storey windows, Ventilators etc., (wood or steel) shutters including Chowkhats, architraves,hold fasts and other attachments etc., and stacking them within 100m lead including labour charge etc., and overheads & contractors profit complete for finished item of work.
a)Not Exceeding 3.00Sqm Area
|  | Qty V.Pg.No:-01 of MB:-04 |  |  |  | 32 | 16 | 350 | Each |  | 5600 |  | 16 | 5600 | - | - |  |  | 350
[6 empty] | AE | 16
3 | 252 | Brick Masonry for panel walls in SuperStructure with CM (1:8) prop (cement: Screened sand) with Aerated Cellular Autoclaved Concrete Blocks conforming to IS:2185 (Part-3) - 1984 and IS:6441-1972 of Compressive strength 3 N/mm2 600x 230 x 200 mm from approved source having minimum crushing strength of 3 N/Sq.m including cost and conveyance of all materials like cement, sand, bricks, water etc., to site, including sales & other taxes on all materials, all operational, incidental and labour charges such as mixing cement mortar, constructing masonry, scaffolding charges, lift charges, curing, etc., complete but excluding seigniorage charges for finished item of work. (APSS No. 501 & 504).
|  | Qty V.Pg.No:-01 of MB:-04 |  |  |  | 16.3192 | 10.5 | 14558 | cum |  | 152859 |  | 10.5 | 152859 | - | - |  |  | 14558
[6 empty] | AE | 5.82
4 | 253 | Reinforced Masonry for partiton walls 100 mm thick in CM (1:4) prop (cement: Screened sand) in super structure with Aerated Cellular Autoclaved Concrete Blocks conforming to IS:2185 (Part-3) - 1984 and IS:6441-1972 of Compressive strength 3 N/mm2 600x 200 x 100 mm from approved source having minimum crushing strength of 3 N/Sq.m including cost and conveyance of all materials like cement, sand, bricks, water etc., to site, including sales & other taxes on all materials, all operational, incidental and labour charges such as mixing cement mortar, constructing masonry, scaffolding charges, lift charges, curing, etc., complete but excluding seigniorage charges for finished item of work. (APSS No. 501 & 504).
|  | Qty V.Pg.No:-02 of MB:-04 |  |  |  | 219.7595 | 215 | 1716 | Sqm |  | 368940 |  | 215 | 368940 | - | - |  |  | 1716
[6 empty] | AE | 4.7595
5 | 256 | Plastering 12mm thick in two coats using screened sand with base coat of 8mm thick in CM (1:6) and top coat of 4mm thick in CM (1:4) with dubara sponge finishing including cost and conveyance of all materials like cement, sand, water etc., to site, including sales & other taxes on all materials, and all operational, incidental charges on materials and including cost of all labour charges for mixing mortar, finishing, scaffolding, lift charges, curing, including cutting grooves as directed by Engineer-in-charge etc., and overheads & contractors profit complete for finished item of work. (SS 901,903 & 904).
|  | Qty V.Pg.No:-02 of MB:-04 |  |  |  | 822.13 | 430 | 906 | Sqm |  | 389580 |  | 430 | 389580 | 0 | 0 |  |  | 906
[6 empty] | AE:- | 392.13
6 | 263 | Flooring with soluble salt porcelain vitrified tiles screen printed and polished of size 600 x 600 mm and thickness between 8 to 10mm 1st quality conforming to IS: 13711, IS: 13712, IS: 13630Parts 1 to 15 of any colour and finish in all shades and designs with borders and design as per the approved flooring pattern as directed by the Engineer-In -Charge, laying tiles using spacers of 2mm thick, set over a base coat of CM 1:8 prop. 12mm thick using screened sand over CC bed already laid or RCC roof slab, including neat cement slurry of honey like consistency spread at the rate 3.3 kgs per Sqm. and jointed neatly with white cement paste to full depth mixed with pigment of matching shade including cost and conveyance of all materials like cement, sand, water, tiles, white cement etc., to site excluding cost of C.C. bed including cost of base coat and all labour charges for mixing of cement mortar, laying tiles to required slope as directed by the Engineer- in- charge etc., and complete for finished item of work. TSSS No.701 and 707.
|  | Qty V.Pg.No:-02 of MB:-04 |  |  |  | 294.66 | 294.659 | 1593 | Sqm |  | 469391.787 |  | 294.66 | 469393.38 | - | - |  |  | 1593
7 | 266 | Providing dadooing to walls with glazed full body porcelain wall tiles of size 300 x 600 mm with any type of design texture such as marble finish, wooden, bamboo, stone finishes etc., scratch less, stain free and thickness between 6-8 mm 1st quality conforming to IS:13711, IS:13712, IS:13630 Parts 1 to 15 of any colour and finish in all shades and designs with borders as approved by Engineer-in-Charge set over base coat of CM1:5 12 mm thick using screened sand with cement slurry of honey like consistency spread at the rate of 3.30 kgs per sqm and jointing with white cement paste mixed with pigment of matching shade to full depth, including cost of all materials like tiles, cement, sand and water etc., complete for finished item of work. 3rd Floor at Petlaburj Hospital
|  | Qty V.Pg.No:-03 of MB:-04 |  |  |  | 153.0952 | 30 | 1391 | Sqm |  | 41730 |  | 30 | 41730 | - | - |  |  | 1391
[6 empty] | AE | 123.0952
[9 empty] | Civil Sub-Total:- |  | 1444212.027 |  |  | 1444213.62 |  | 0
Civil Supplemental Items
1 |  | Dismantling, clearing away and carefully stacking useful materials for re-use and disposal of unserviceable materials with 100m lead as directed by Executive Engineer duly taking actual premeasurements before dismantling including all labour charges , overheads & contractor profit etc., complete Finished item of work
a)Old Cement Mortar
|  | Qty V.Pg.No:-03 of MB:-04 |  |  |  | 251.59 | 251.5889
b)Reinforced Cement Concrete
|  | Qty V.Pg.No:-03 of MB:-04 |  |  |  | 0.43 | 0.4293
2 |  | Providing Thermo Mechanically Treated ( TMT) ( Fe-500/500D/550D from primery producer TATA, SAIL, VSP, JSW Steel, Goel steel, Jindal panther, X- Vega & balaji Shakthi as per IS 1786-2008) of Different Diameters RCC Works , including labour charges for straightening, cutting, bending to required sizes and shapes, placing in position with cover blocks of approved materials and sizes and typing and lap - spacing with binding wire of 18 SWG, Forming grills for reinforcement work as per approved design and drawings, including and conveyanace of steel bars, including all wastages such as overlaps, coupling, chairs, spacer bars including cost and conveyance of binding wire cover blocks and incidential, operational, labour charges such as cutting bending, placing in position, typing incliding sales and other taxes on all materials etc., and overheads & contractors profit completefor finished item of work
|  | Qty V.Pg.No:-03 of MB:-04 |  |  |  | 0.3 | 0.2956
3 |  | Supply and placing of the Design Mix Concrete M 25 grade corresponding to IS 456 with minimum cement content of 380 kgs per 1 cum of concrete using Weight Batcher / Concrete mixer with 20mm size graded machine crushed hard granite metal (coarse aggregate - as per IS 383 - 1970 and IS 2386 Part 1 to Part 8) from approved quarry including cost and conveyance of all materials like cement, fine aggregate (sand) coarse aggregate, water etc., to site and sales & other taxes on all materials, centering using Casurina Ballies, Bamboos, Wooden Reapers, Runners, Wood Posts, Steel Plates etc., including all operational, incidental and labour charges such as weigh batching, machine mixing, lifting of concrete manually, laying concrete, curing , overheads & contractors profit etc., complete but excluding cost of steel and its fabrication charges for finished item of work (APSS No. 402)
For Lintels
|  | Qty V.Pg.No:-04 of MB:-04 |  |  |  | 0.75 | 0.74952
4 |  | Providing skirting to internal walls to 10 cm height with Double charged / multi charged stain free fullbody porcelain vitrified tiles with double layer pigment of size 600 x 600 mm and thickness between 8-10 mm 1st quality conforming to IS:15622 - 2017, IS:13630 (Parts 1 to 15) of any colour and finish in all shades and designs, length equal to flooring tiles, set over base coat of CM(1:5) 12 mm thick using screened sand with cement slurry of honey like consistency spread at the rate of 3.30 kgs per sqm and jointing with white cement paste mixed with pigment of matching shade to full depth, including cost of all materials like tiles, cement, sand and water etc.,and overheads & contractors profit complete for finished item of work.(APSS No.701 &707)
|  | Qty V.Pg.No:-04 of MB:-04 |  |  |  | 174.5 | 174.5
[8 empty] | Civil Suppl. Sub-Total:- |  |  | 0 |  |  | 0 |  | 0
Equipment Items
1 | 200 | IVF Test tube Warmers at Petlaburz Hospital
|  | Qty V.Pg.No:-04 of MB:-04 |  |  |  | 2 | 2 | 34650 | Nos |  | 69300 |  | 2 | 69300 |  |  |  | 70% | 49500
2 | 201 | DICOM compatible fully digital, compact, portable, Ultrasound Scan Machine Colour Doppler at Petlaburz Hospital
|  | Qty V.Pg.No:-04 of MB:-04 |  |  |  | 2 | 2 | 955500 | Nos |  | 1911000 |  | 2 | 1911000 |  |  |  | 70% | 1365000
3 | 202 | Multipurpose Electro hydraulic with manual override mobile OT Table, with divided leg section suitable for all Gynaecological surgical procedures, complete with 5cm Mattress and corded handset at Petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 1 | 1 | 394625 | Nos |  | 394625 |  | 1 | 394625 |  |  |  | 70% | 563750
4 | 203 | LED procedure Lights Double dome at petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 1 | 1 | 218750 | Nos |  | 218750 |  | 1 | 218750 |  |  |  | 70% | 312500
5 | 204 | LED procedure Lights Single dome at petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 1 | 1 | 131250 | Nos |  | 131250 |  | 1 | 131250 |  |  |  | 70% | 187500
6 | 207 | CO2 Incubators at Petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 2 | 2 | 577500 | Nos |  | 1155000 |  | 2 | 1155000 |  |  |  | 70% | 825000
7 | 212 | IVF Thermometer at Petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 1 | 1 | 43313 | Nos |  | 43313 |  | 1 | 43313 |  |  |  | 70% | 61875
8 | 213 | CO2 Cylinder and Manifold at Petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 2 | 2 | 35000 | Nos |  | 70000 |  | 2 | 70000 |  |  |  | 70% | 50000
9 | 214 | CO2 and O2 Analyzer at Petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 2 | 1 | 264600 | Nos |  | 264600 |  | 1 | 264600 |  |  |  | 70% | 378000
10 | 215 | PH Meter at Petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 1 | 1 | 65625 | Nos |  | 65625 |  | 1 | 65625 |  |  |  | 70% | 93750
11 | 217 | Sperm Counting Markler Chamber at Petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 1 | 1 | 52938 | Nos |  | 52938 |  | 1 | 52938 |  |  |  | 70% | 75625
12 | 220 | Clinical Centrifuge machine for Andrology at Petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 1 | 1 | 24150 | Nos |  | 24150 |  | 1 | 24150 |  |  |  | 70% | 34500
13 | 221 | DRY Incubator at Petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 1 | 1 | 394625 | Nos |  | 394625 |  | 1 | 394625 |  |  |  | 70% | 563750
14 | 223 | Pharmaceutical Refrigerator at Petlaburz Hospital
|  | Qty V.Pg.No:-06 of MB:-04 |  |  |  | 1 | 1 | 157500 | Nos |  | 157500 |  | 1 | 157500 |  |  |  | 70% | 225000
15 | 224 | Cryocane (TA 26 Ltr) with wheels at Petlaburz Hospital
|  | Qty V.Pg.No:-06 of MB:-04 |  |  |  | 2 | 2 | 43313 | Nos |  | 86626 |  | 2 | 86626 |  |  |  | 70% | 61875
16 | 225 | Defibrillator at Petlaburz Hospital
|  | Qty V.Pg.No:-06 of MB:-04 |  |  |  | 1 | 1 | 218750 | Nos |  | 218750 |  | 1 | 218750 |  |  |  | 70% | 312500
17 | 226 | 7 Para Patient Monitor at Petlaburz Hospital
|  | Qty V.Pg.No:-06 of MB:-04 |  |  |  | 2 | 2 | 196000 | Nos |  | 392000 |  | 2 | 392000 |  |  |  | 70% | 280000
18 | 228 | Anaesthesia Work station at Petlaburz Hospital
|  | Qty V.Pg.No:-06 of MB:-04 |  |  |  | 1 | 1 | 656250 | Nos |  | 656250 |  | 1 | 656250 |  |  |  | 70% | 937500
19 | 232 | Mulitfunctional Printer at Petlaburz Hospital
|  | Qty V.Pg.No:-06 of MB:-04 |  |  |  | 1 | 1 | 30625 | Nos |  | 30625 |  | 1 | 30625 |  |  |  | 70% | 43750
20 | 233 | Ultrasound Examination Couch at Petlaburz Hospital
|  | Qty V.Pg.No:-06 of MB:-04 |  |  |  | 1 | 1 | 56875 | Nos |  | 56875 |  | 1 | 56875 |  |  |  | 70% | 81250
21 | 235 | Laptop For Office Usage at Petlaburz Hospital
|  | Qty V.Pg.No:-06 of MB:-04 |  |  |  | 2 | 2 | 80500 | Nos |  | 161000 |  | 2 | 161000 |  |  |  | 70% | 115000
22 | 320 | 20 KVA UPS: Supply and installation of 20KVA 3ph in and 3ph out on line UPS system IGBT based rectifier with input power factor correction 32 bit microprocessor based with isolation transformers double conversion, SNMP controls, LCD display, Pure sine wave output, with auto static switch three phase input / Three phase output and modular structure for better thermal technology / cooling facility, with warranty up to three years.Makes: APC / Numeric / Emerson / Fuji Electric At Petlaburz
|  | Qty V.Pg.No:-06 of MB:-04 |  |  |  | 1 | 1 | 213500 | Nos |  | 213500 |  | 1 | 213500 |  |  |  | 70% | 305000
23 | 322 | Supply and providing of UPS Cum battery rack for 20 batteries at MGMH Petlaburz
|  | Qty V.Pg.No:-06 of MB:-04 |  |  |  | 1 | 1 | 4735 | Nos |  | 4735 |  | 1 | 4735 |  |  |  | 70% | 6764
6773037
1 | 199 | Ovum Aspiration Pumps at Petlaburj Hospital
|  | Qty V.Pg.No:-01 of MB:-05 |  |  |  | 2 | 2 | 168000 | Nos |  | 336000 |  | 2 | 336000 |  |  |  | 70% | 240000
2 | 205 | IVF Workstation with LAF at Petlaburj Hospital
|  | Qty V.Pg.No:-01 of MB:-05 |  |  |  | 1 | 1 | 481250 | Nos |  | 481250 |  | 1 | 481250 |  |  |  | 70% | 687500
3 | 206 | IVF Ant vibration Table for procedure at Petlaburj Hospital
|  | Qty V.Pg.No:-01 of MB:-05 |  |  |  | 1 | 1 | 67375 | Nos |  | 67375 |  | 1 | 67375 |  |  |  | 70% | 96250
4 | 208 | Trigas bench Top Incubators for Human Embryo culture at Petlaburj Hospital
|  | Qty V.Pg.No:-01 of MB:-05 |  |  |  | 1 | 1 | 577500 | Nos |  | 577500 |  | 1 | 577500 |  |  |  | 70% | 825000
5 | 209 | Trinocular Stereozoom Microscope at Petlaburj Hospital
|  | Qty V.Pg.No:-01 of MB:-05 |  |  |  | 1 | 1 | 216300 | Nos |  | 216300 |  | 1 | 216300 |  |  |  | 70% | 309000
6 | 210 | ICSI Micro manipulator with Inverted Microscope at Petlaburj Hospital
|  | Qty V.Pg.No:-02 of MB:-05 |  |  |  | 1 | 1 | 1837500 | Nos |  | 1837500 |  | 1 | 1837500 |  |  |  | 70% | 2625000
7 | 211 | IVF Laser System at Petlaburj Hospital
|  | Qty V.Pg.No:-02 of MB:-05 |  |  |  | 1 | 1 | 1792000 | Nos |  | 1792000 |  | 1 | 1792000 |  |  |  | 70% | 2560000
8 | 216 | VOC Meter for ART Lab at Petlaburj Hospital
|  | Qty V.Pg.No:-02 of MB:-05 |  |  |  | 1 | 1 | 511875 | Nos |  | 511875 |  | 1 | 511875 |  |  |  | 70% | 731250
9 | 218 | Binocular Microscope for Semen Analysis at Petlaburj Hospital
|  | Qty V.Pg.No:-02 of MB:-05 |  |  |  | 1 | 1 | 28875 | Nos |  | 28875 |  | 1 | 28875 |  |  |  | 70% | 41250
10 | 219 | Laminar flow cabinet with Andrology Work station at Petlaburj Hospital
|  | Qty V.Pg.No:-02 of MB:-05 |  |  |  | 1 | 1 | 175000 | Nos |  | 175000 |  | 1 | 175000 |  |  |  | 70% | 250000
11 | 222 | Pipetter and Denudation system at Petlaburj Hospital
|  | Qty V.Pg.No:-02 of MB:-05 |  |  |  | 1 | 1 | 72188 | Nos |  | 72188 |  | 1 | 72188 |  |  |  | 70% | 103125
12 | 229 | Autoclave at Petlaburj Hospital
|  | Qty V.Pg.No:-02 of MB:-05 |  |  |  | 1 | 1 | 393750 | Nos |  | 393750 |  | 1 | 393750 |  |  |  | 70% | 562500
13 | 236 | Reception Table at Petlaburj Hospital
|  | Qty V.Pg.No:-03 of MB:-05 |  |  |  | 1 | 1 | 77000 | Nos |  | 77000 |  | 1 | 77000 |  |  |  | 70% | 110000
14 | 238 | Filing Cabinet at Petlaburj Hospital
|  | Qty V.Pg.No:-03 of MB:-05 |  |  |  | 2 | 2 | 24150 | Nos |  | 48300 |  | 2 | 48300 |  |  |  | 70% | 34500
15 | 239 | Patient Seating 3 in 1 model at Petlaburj Hospital
|  | Qty V.Pg.No:-03 of MB:-05 |  |  |  | 3 | 3 | 26950 | Nos |  | 80850 |  | 3 | 80850 |  |  |  | 70% | 38500
16 | 244 | Wall Storage Cabinets at Petlaburj Hospital
|  | Qty V.Pg.No:-03 of MB:-05 |  |  |  | 8 | 8 | 12250 | Nos |  | 98000 |  | 8 | 98000 |  |  |  | 70% | 17500
17 | 245 | Office Table at Petlaburj Hospital
|  | Qty V.Pg.No:-03 of MB:-05 |  |  |  | 3 | 3 | 14000 | Nos |  | 42000 |  | 3 | 42000 |  |  |  | 70% | 20000
[11 empty] | 13608800 |  |  | 6835763
Electrical-1
1 | 293 | Supply and laying of ISI 25mm outer dia medium grade with IS:9537-part 3 rigid PVC pipe concealed in wall with all required PVC / Metallic Junction Boxes including masonry work and labour charges etc., Makes: Sudhakar / Precision /Universal/ Modi / Million Plast. at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 463.5 | 200 | 93 | RMt |  | 18600 |  | 200 | 18600 |  |  |  | 80% | 116
[6 empty] | AE | 263.5
2 | 294 | Supply and laying of ISI 25mm outer dia medium grade with IS:9537-part 3 rigid PVC pipe surface on wall with all required PVC / Metallic Junction Boxes including masonry work and labour charges etc., Makes: Sudhakar / Precision /Universal/ Modi / Million Plast. at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 1352.8 | 450 | 86 | Rmt |  | 38700 |  | 450 | 38700 |  |  |  | 80% | 107
[6 empty] | AE | 902.8
3 | 295 | Wiring with 2 runs of 22/0.3mm 1.5 Sq.mm FRLS / HFFR P.V.C. insulated flexible copper cable ISI MARK in existing pipe with 6A Modular switch, Ceiling rose/BH/SBH Modular switches with cover plate and GI switch box including all labour charges etc., complete. for Non- Residential Building Makes of wires: Polycab Makes of switches: - /Honeywell Blenge Plus at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 148 | 100 | 756 | Nos |  | 75600 |  | 100 | 75600 |  |  |  | 80% | 945
[6 empty] | AE | 48
4 | 300 | Supply and run of 1 of 22 /0.3mm 1.5 Sq.mm FRLS / HFFR P.V.C. insulated flexible copper cable in existing conduit pipe for earth continuity including all labour charges etc., complete. Makes of wires: Finolex/ RR Cable/ Havells/ Polycab/ HPL. at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 379.6 | 350 | 32 | Rmt |  | 11200 |  | 350 | 11200 |  |  |  | 80% | 40
[6 empty] | AE | 29.6
5 | 301 | Supply and run of 3 of 2.5 sq.mm 36/0.mm phase neutral and earth FRLS / HFFR PVC insulated flexible copper cable in existing conduit pipe for individual lighting circuits including labour charges etc., complete as required for switch boards. Makes of wires: Finolex/ RR Cable/ Havells/ Polycab/ HPL. at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 1713.1 | 600 | 142 | Rmt |  | 85200 |  | 600 | 85200 |  |  |  | 80% | 177
[6 empty] | AE | 1113.1
6 | 302 | Supply and 3 runs of 4.0 sq mm 56/0.3 mm phase neutral and earth FRLS / HFFR PVC insulated flexible copper cable in existing conduit pipe including labour charges etc., complete for 16A sockets. Makes of wires: Finolex/ RR Cable/ Havells/ Polycab/ HPL. at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 2421 | 1200 | 204 | Nos |  | 244800 |  | 1200 | 244800 |  |  |  | 80% | 255
[6 empty] | AE | 1221
7 | 303 | Supply and run of 5 of 6.0 Sqmm 90/0.3 mm 3 phases, neutral and earth FRLS / HFFR PVC insulated flexible copper cable in the existing conduit pipe for run of mains from Power panel board to TPN DBs with pin type lugs and connections etc., complete. for LDBs Makes of wires: Finolex/ RR Cable/ Havells/ Polycab/ HPL. at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 240.1 | 60 | 485 | Rmt |  | 29100 |  | 60 | 29100 |  |  |  | 80% | 606
[6 empty] | AE | 180.1
8 | 304 | Supply and run of 5 of 10.0 Sqmm 140/0.3 mm 3 phases, neutral and earth FRLS / HFFR PVC insulated flexible copper cable in the existing conduit pipe for run of mains from Power panel board to TPN DBs with pin type lugs and connections etc., complete. for PDBs Makes of wires: Finolex/ RR Cable/ Havells/ Polycab/ HPL. at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 284 | 40 | 774 | Rmt |  | 30960 |  | 40 | 30960 |  |  |  | 80% | 967
[6 empty] | AE | 244
9 | 306 | Supply and fixing of 4 Way TPN DB Horizontal with IP 43 Protection as per IS:13032 Makes: Legrand / Schneider and Supply and Fixing of 1 No., of 40A FP 30mA RCCB as incomer and 12 Nos 6-32 A 10kA SP MCBs Makes: Legrand-DX3 / Schneider-Acti9 as out goings including internal connections and labour charges for FLUSH Mounting etc., complete. For Lighting DBs at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 10 | 3 | 14660 | Rmt |  | 43980 |  | 3 | 43980 |  |  |  | 80% | 18325
[6 empty] | AE | 7
10 | 308 | Supply and fixing of 8 Way VTPN DB Horizontal with IP 43 Protection as per IS:13032 Makes: Legrand / Schneider and Supply and Fixing of 1 No., of 100A FP 10KA MCB as incomer and 4 Nos 63 A 10kA TP MCBs, 4 Nos 40 A 10kA TP MCBs Makes: Legrand-DX3 / Schneider-Acti9 as out goings including internal connections and labour charges for FLUSH Mounting etc., complete. For UPS MDB DBs at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 1 | 1 | 51254 | Nos |  | 51254 |  | 1 | 51254 |  |  |  | 80% | 64067
11 | 309 | Providing and fixing of 125A 25KA TPN Thermal Magnetic Release Based MCCB and Terminal Spreaders in Existing panel board with 1 No. and 1 Set of Indication Lamps, LED type, R,Y,B and breaker ON , OFF, TRIP and spring charged lamps. and replace with above Mentioned with required Drilling Holes, removing and Making Busbar connections etc, as required. Makes: Legrand / Schneider/ABB/LandT/CandS at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 1 | 1 | 23106 | Nos |  | 23106 |  | 1 | 23106 |  |  |  | 80% | 28883
12 | 318 | SITC of Hot dip galvanized perforated cable tray of 100 mm Wide sizes for to run the cable from DBs to SBs and sockets and AC panel to Units units. All necessary supports and accessories are included. Cable tray for cables alone shall be included here Thickness shall be 1.6 mm. at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 79 | 70 | 343 | Rmt |  | 24010 |  | 70 | 24010 |  |  |  | 80% | 429
[6 empty] | AE | 9
13 | 319 | SITC of Hot dip galvanized perforated cable tray of 300 mm Wide sizes for to run the cable from Floor Panel to Lab Panel and electrical room to AC panel and AC panel to Units. All necessary supports and accessories are included. Cable tray for cables alone shall be included here Thickness shall be 1.6 mm. at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 102.5 | 80 | 1048 | Rmt |  | 83840 |  | 80 | 83840 |  |  |  | 80% | 1310
[6 empty] | AE | 22.5
14 | 325 | Supply and installation of 50x6 GI flat for body earthing of electrical panel and AC Panel which is laid in 300mm cable tray at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 217.3 | 200 | 263 | Rmt |  | 52600 |  | 200 | 52600 |  |  |  | 80% | 329
[6 empty] | AE | 17.3
15 | 323 | Providing and Fixing maintenance free earthing which consists of G.I. Earth station, with 600X600X3.15mm GI Plate at 2500mm Depth including construction of brick pedestal, providing meshed funnel, GI cover and other civil Engineering works, spreading a homogenous mixture of salt, charcoal around the pipe etc., completely as per IS 3043, 1987 or latest revision. Earthing testing should be done as per IE Rules like Earth valve test Etc. at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 2 | 2 | 6800 | Nos |  | 13600 |  | 2 | 13600 |  |  |  | 80% | 8500
16 | 324 | Providing and Fixing maintenance free earthing which consists of copper. Earth station, with 600X600X3.15mm Copper Plate at 2500mm Depth including construction of brick pedestal, providing meshed funnel, GI cover and other civil Engineering works, spreading a homogenous mixture of salt, charcoal around the pipe etc., completely as per IS 3043, 1987 or latest revision. Earthing testing should be done as per IE Rules like Earth valve test Etc. at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 4 | 2 | 17826 | Nos |  | 35652 |  | 2 | 35652 |  |  |  | 80% | 22283
[6 empty] | AE | 2
17 | 327 | Supply and installation of 25x3 Copper flat for Neutral earthing of UPS and Equipment which is laid in 100mm cable tray at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 207.3 | 200 | 722 | Rmt |  | 144400 |  | 200 | 144400 |  |  |  | 80% | 902
[6 empty] | AE | 7.3
18 | 328 | Supply and installation of 4 sqmm Copper wire for Earthing of DBs Equipment at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 450.6 | 80 | 66 | Rmt |  | 5280 |  | 80 | 5280 |  |  |  | 80% | 83
[6 empty] | AE | 370.6
19 | 329 | Supply, Laying and testing of 3.5Cx95 sqmm XLPE Insulated Cable 1100V grade armoured aluminium cable with ISI mark as per specification confirming to IS:7098 Part - I with heavy duty type double compression weather proof type brass cable glands duly nickel plated as per BS 6121 and IP66 complete with brass checknut, outer sheath sealing gasket heavy duty long barrel aluminium lugs confirming to I.S specifications with complete nut, bolt and washer etc.. Make of Cable: Polycab/ KEI/Universal/Glostar/Finolex. Make of gland and Lungs: HMI/Commet/Dowell’s at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 180 | 120 | 966 | Rmt |  | 115920 |  | 120 | 115920 |  |  |  | 80% | 1207
[6 empty] | AE | 60
20 | 330 | Supply, Lying and testing of 3.5CX50 sqmm XLPE Insulated Cable 1100V grade armoured aluminium cable with ISI mark as per specification confirming to IS:7098 Part - I with heavy duty type double compression weather proof type brass cable glands duly nickel plated as per BS 6121 and IP66 complete with brass checknut, outer sheath sealing gasket heavy duty long barrel aluminium lugs confirming to I.S specifications with complete nut, bolt and washer etc.. Make of Cable: Polycab Make of gland and Lungs: HMI at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 180 | 70 | 578 | Rmt |  | 40460 |  | 70 | 40460 |  |  |  | 80% | 722
[6 empty] | AE | 110
21 | 331 | Supply, Lying and testing of 4Cx16 sqmm PVC Insulated Cable 1100V grade armoured Copper cable with ISI mark as per specification confirming to IS:7098 Part - I with heavy duty type double compression weather proof type brass cable glands duly nickel plated as per BS 6121 and IP66 complete with brass checknut, outer sheath sealing gasket heavy duty long barrel aluminium lugs confirming to I.S specifications with complete nut, bolt and washer etc.. Make of Cable: Polycab/ KEI/Universal/Glostar/Finolex. Make of gland and Lungs: HMI/Commet/Dowell’s at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 100 | 100 | 1186 | Rmt |  | 118600 |  | 100 | 118600 |  |  |  | 80% | 1483
22 | 332 | Supply, Lying and testing of 4Cx6 sqmm PVC Insulated Cable 1100V grade armoured Copper cable with ISI mark as per specification confirming to IS:7098 Part - I with heavy duty type double compression weather proof type brass cable glands duly nickel plated as per BS 6121 and IP66 complete with brass checknut, outer sheath sealing gasket heavy duty long barrel aluminium lugs confirming to I.S specifications with complete nut, bolt and washer etc. Make of Cable: Polycab/ KEI/Universal/ Glostar/Finolex. Make of gland and Lungs: HMI/Commet/Dowell’s at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 120 | 120 | 387 | Rmt |  | 46440 |  | 120 | 46440 |  |  |  | 80% | 484
23 | 333 | Supply, Lying and testing of 4Cx4 sqmm PVC Insulated Cable 1100V grade armoured Copper cable with ISI mark as per specification confirming to IS:7098 Part - I with heavy duty type double compression weather proof type brass cable glands duly nickel plated as per BS 6121 and IP66 complete with brass checknut, outer sheath sealing gasket heavy duty long barrel aluminium lugs confirming to I.S specifications with complete nut, bolt and washer etc. Make of Cable:Polycab/ KEI/Universal/Glostar/Finolex. Make of gland and Lungs: HMI/Commet/Dowell’s at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 80 | 80 | 285 | Rmt |  | 22800 |  | 80 | 22800 |  |  |  | 80% | 356
24 | 334 | SITC of IVF Center Main Panel Indoor IP-42 wall/ free standing floor mounted dust and vermin proof compartmentalized cubical panel made out of CRCA sheet, required hardware, duly treated for de-rusting in 7 tank process with de-phosphate and with powder coating on both side of panel in desired shade. The panel having PU/ Neoprene rubber gasket of not less than 3mm thickness, separate detachable gland plate M.S. base channel, hinged door with locking arrangement for equipment/switchgear. Thickness of sheet shall not be less than 1.6 mm up to 600 mm length / width of any compartment and be of 2.0 mm above 600 mm. Load bearing structure shall be of 2.0 mm thick sheet supported by base M.S. channel if required. Side walls and cable alley compartments having bolted type doors with /without detachable extension type structure with all type of suitable switching accessories and bus-bar as per load requirement of respective IVF equipment’s. Which is including Lighting, power DBs and UPS at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 1 | 1 | 284000 | Nos |  | 284000 |  | 1 | 284000 |  |  |  | 80% | 355000
25 | 335 | SITC of IVF center AC Panel outdoor IP-54 wall/ free standing floor mounted dust and vermin proof compartmentalized cubical panel made out of CRCA sheet, required hardware, duly treated for de-rusting in 7 tank process with de-phosphate and with powder coating on both side of panel in desired shade. The panel having PU/ Neoprene rubber gasket of not less than 3mm thickness, separate detachable gland plate M.S. base channel, hinged door with locking arrangement for equipment/switchgear. Thickness of sheet shall not be less than 1.6 mm up to 600 mm length / width of any compartment and be of 2.0 mm above 600 mm. Load bearing structure shall be of 2.0 mm thick sheet supported by base M.S. channel if required. Side walls and cable alley compartments having bolted type doors with / without detachable extension type structure with all type of suitable switching accessories and bus-bar as per load requirement of respective AC equipment’s. Which is including 1nos AHU’s stater with VFD by pass, Heater, ODU and VRF system at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 1 | 1 | 216000 | Nos |  | 216000 |  | 1 | 216000 |  |  |  | 80% | 270000
1856102
1 | 346 | Supply, transportation and installation of split AC unit 1.5 TR inverter type 3 Star capable of delivering 18000 BTU/hr and above with high wall mounted indoor unit and outdoor condensing unit Hermetically sealed compressor suitable for operation on 230V, 50Hz, 1Phase AC supply capable of performing cooling dehumidifying air circulating and filtering with cooling and condensing units with 3.5 mts of copper piping, insulation kit and 4 mts of 3 core copper flexible chord , built-in stabilizer Voltage range 160- 264 volts and cordless remote control. Makes : Daikin / Thoshiba / O General at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 3 | 1 | 38400 | Nos |  | 38400 |  |  |  | 1 | 38400 |  | 80% | 48000
[6 empty] | AE | 2
2 | Sup | Condensing units - VRF/VRV System : Supply, Installation, Nitrogen testing , Vacuuming and Commissioning of air cooled variable refrigerant flow modular type condensing units, each comprising of multiple scroll compressors all inverter driven, full charge of refrigerant gas R-410a including additional gas filling , lubricating oil and all accessories as per the specifications. The condensing units shall be suitable to work on cooling mode. The minimum Energy Efficiency Ratio shall be as per ASHRAE STANDARDS 90.1 -2001 table 6.2.1B . The COP of the system shall be greater than 4 under ARI conditions for 100percentage load . The condensing units shall be suitable for operation on 415 plus or minus 10percentage volts, 50Hz, 3 phase AC power supply and , outdoor units to be mounted on MS platform with suitable Vibration Isolation pads to avoid vibrations. All the supports and angle base frame structure to be duly black painted with synthetic epoxy paint. the condensing units shall be of following capacities: The VRF ODU should be capable of working with total capacity of connected indoor units ranging between 100percentage to 140percentage of ODU capacity . COP minimum 3.5. Make : Daikin / LG / O General / Toshiba at MGMH Petlaburj 16 HP
|  | Qty V.Pg.No:- of MB:- |  |  |  | 1 | 1 | 0 | Nos |  | 0 |  |  |  | 1 | 0 |  | 80%
3 | 371 | VRF Indoor Units : Hi wall Splits : Supply, Installation, Testing and Commissioning of variable refrigerant flow modular type indoor units wired/wireless remote suitable for R410a refrigerant comprising of all accessories as per the specifications. The indoor units shall be suitable to work on cooling.The minimum Energy Efficiency Ratio shall be as per ASHRAE STANDARDS 90.1 -2001 table 6.2.1B. The indoor units shall be suitable for operation on 220 plus or minus 6percentage volts, 50Hz, 1 phase AC power supply. 0.8 TR at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 2 | 2 | 24560 | Nos |  | 49120 |  |  |  | 2 | 49120 |  | 80% | 30700
4 | 372 | VRF Indoor Units : Hi wall Splits : Supply, Installation, Testing and Commissioning of variable refrigerant flow modular type indoor units wired/wireless remote suitable for R410a refrigerant comprising of all accessories as per the specifications. The indoor units shall be suitable to work on cooling.The minimum Energy Efficiency Ratio shall be as per ASHRAE STANDARDS 90.1 -2001 table 6.2.1B. The indoor units shall be suitable for operation on 220 plus or minus 6percentage volts, 50Hz, 1 phase AC power supply. 1.0 TR at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 6 | 3 | 24560 | Nos |  | 73680 |  |  |  | 3 | 73680 |  | 80% | 30700
[6 empty] | AE | 3
5 | 373 | VRF Indoor Units : Hi wall Splits : Supply, Installation, Testing and Commissioning of variable refrigerant flow modular type indoor units wired/wireless remote suitable for R410a refrigerant comprising of all accessories as per the specifications. The indoor units shall be suitable to work on cooling.The minimum Energy Efficiency Ratio shall be as per ASHRAE STANDARDS 90.1 -2001 table 6.2.1B. The indoor units shall be suitable for operation on 220 plus or minus 6percentage volts, 50Hz, 1 phase AC power supply. 1.5 TR at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 6 | 4 | 28000 | Nos |  | 112000 |  |  |  | 4 | 112000 |  | 80% | 35000
[6 empty] | AE | 2
6 | Sup | Cassette Units : Supply, Installation, Testing and Commissioning of variable refrigerant flow modular type indoor units wired/wireless remote suitable for R410a refrigerant comprising of all accessories as per the specifications. The indoor units shall be suitable to work on cooling mode.The minimum Energy Efficiency Ratio shall be as per ASHRAE STANDARDS 90.1 -2001 table 6.2.1B. The indoor units shall be suitable for operation on 220 plus or minus 6percentage volts, 50Hz, 1 phase AC power supply. 3.0 TR – 4 way at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 2 | 2 | 0 | Nos |  | 0 |  |  |  | 2 | 0 |  | 80%
7 | 375 | Supply, Installation, Testing and Commissioning of Hard copper REFRIGERANT PIPING of 16swg various sizes with necessary supports, fittings, interconnecting the liquid and suction lines between the aircooled outdoor units and the indoor units. The piping shall be carried out of Hard drawn copper pipes of type K with soldered / brazed socket fittings. Isolating valves shall be provided to isolate each compressor, strainers, sight glass and any other component requiring proper operation and maintenance. Both the suction and liquid lines shall be insulated with 19mm thick closed cell insulation for above 25mm dia , 13mm thick for pipes below 25mm dia . The insulation finished with treated woven glass fiber reinforced covering for inside Piping and including making required holes in the wall and re finishing and water tight of holes after laying holes as per the specifications and approved drawings at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 1 | 1 | 320000 | Lot |  | 320000 |  |  |  | 1 | 320000 |  | 80% | 400000
8 | 376 | Supply, Installation , Testing and Commissioning of Refnet joints to be provided in refrigerant pipe line. Material of construction for fittings shall be similar to refrigerant piping at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 15 | 10 | 4953 | Nos |  | 49530 |  |  |  | 10 | 49530 |  | 80% | 6191
[6 empty] | AE | 5
9 | 291 | Supply, installation, testing and commissioning of 16 G GI powder coated suitable single person entry air shower as per the Technical Specifications at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 1 | 1 | 248500 | Nos |  | 248500 |  |  |  | 1 | 248500 |  | 70% | 355000
10 | 287 | Double leaf clean room Doors : 46mm thick flush doors made of 0.8mm thick Powder coated GI sheets on both sides, 90 plus or minus 2 kg/m3 density Honeycomb with stand upto 220 Deg.C Temperature, and compressible strength upto 400 Kg/Sqm, 1.2 mm thick GPSP . door frames, double glazed vision panel with necessary adhesive tapes and silicon sealant, necessary hardware like SS304 ball bearing butt hinges, D- handles, push plates, Dorma make door closure, concealed tower bolt, drop seals for the double leaf door and provision for fixing magnetic type door interlocking system and automatic door bottoms, Both side lock and keys etc. complete. Size 1500 X 2100 mm with 300mm X 300mm double glazed view panels at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 5 | 4 | 36800 | Nos |  | 147200 |  |  |  | 4 | 147200 |  | 80% | 46000
[6 empty] | AE | 1
11 | Sup | Single leaf clean room Doors : 46mm thick flush doors made of 0.8mm thick Powder coated GI sheets on both sides, 90 plus or minus 2 kg/m3 density Honeycomb with stand upto 220 Deg.C Temperature, and compressible strength upto 400 Kg/Sqm, 1.2 mm thick GPSP . door frames, double glazed vision panel with necessary adhesive tapes and silicon sealant, necessary hardware like SS304 ball bearing butt hinges, D- handles, push plates, Dorma make door closure, concealed tower bolt, drop seals for the double leaf door and provision for fixing magnetic type door interlocking system and automatic door bottoms, Both side lock and keys etc. complete. Size 900 X 2100 mm with 300 mm x 300 mm View panelat MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 3 | 3 | 0 | Nos |  | 0 |  |  |  | 3 | 0 |  | 80%
12 | Sup | Emergency Fire Doors : 46mm thick flush doors made of 0.8mm thick Powder coated GI sheets on both sides, 90 plus or minus 2 kg/m3 density Honeycomb with stand upto 220 Deg.C Temperature, and compressible strength upto 400 Kg/Sqm, 1.2 mm thick GPSP . door frames, double glazed vision panel with necessary adhesive tapes and silicon sealant, necessary hardware like SS304 ball bearing butt hinges, D- handles, push plates, Dorma make door closure, concealed tower bolt, drop seals for the double leaf door and provision for fixing magnetic type door interlocking system and automatic door bottoms, Both side lock and keys etc. complete. Size 1500 X 2100 mm with 2 hours fire rated and panic push bar and accessories etc. at Gandhi Hospital
|  | Qty V.Pg.No:- of MB:- |  |  |  | 1 | 1 |  | Nos |  | 0 |  |  |  | 1 | 0 |  | 80%
13 | Sup | Emergency Fire Doors : 46mm thick flush doors made of 0.8mm thick Powder coated GI sheets on both sides, 90 plus or minus 2 kg/m3 density Honeycomb with stand upto 220 Deg.C Temperature, and compressible strength upto 400 Kg/Sqm, 1.2 mm thick GPSP . door frames, double glazed vision panel with necessary adhesive tapes and silicon sealant, necessary hardware like SS304 ball bearing butt hinges, D- handles, push plates, Dorma make door closure, concealed tower bolt, drop seals for the double leaf door and provision for fixing magnetic type door interlocking system and automatic door bottoms, Both side lock and keys etc. complete. Size 1000 X 2100 mm with 2 hours fire rated and panic push bar and accessories etc. at Gandhi Hospital
|  | Qty V.Pg.No:- of MB:- |  |  |  | 2 | 2 |  | Nos |  | 0 |  |  |  | 2 | 0 |  | 80%
14 | 285 | Supply and installation of 80mm thick double skin modular wall Panels made of 0.8 mm thick powder coated GI on both the sides, with 40 plus or minus 2 kg/m3 density PUF as infill, GI profiles all along the periphery, flush on both sides with maximum allowable gap of 3- 4mm filled with food grade silicon sealant and placed on cold rolled galvanised bottom tracks with a recess to provide floor to wall coving flush with the wall panel. This includes all required harware for completion Panels to be covered with a protective film to avoid any damages during transportation and installation at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 121.0376 | 121.04 | 4496 | Sqm |  | 544195.84 |  |  |  | 121.04 | 544195.84 |  | 80% | 5620
15 | 286 | Supply and installation of 50mm thick double skin ceiling system made of 0.8 mm thick Powder Coated GI sheets on both sides, 40 plus or minus 2 kg/m3 density PUF as infill, GI profiles all along the periphery, panels flush towards room side with maximum allowable gap of 3-4mm at panel to panel joints filled with silicon sealant. Ceiling panels are suspended from the RCC slab by using concealed AL ceiling grid with tie rod and adjustable turn buckle arrangement etc. This includes all required hardware for completion. Panels to be covered with a protective film to avoid any damages during transportation and installation at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 62.6622 | 60 | 4108 | Sqm |  | 246480 |  |  |  | 60 | 246480 |  | 80% | 5135
[6 empty] | AE | 2.6622
16 | 289 | Supply and installation of Extruded Aluminium Coving at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 109.83 | 100 | 468 | Sqm |  | 46800 |  |  |  | 100 | 46800 |  | 80% | 585
[6 empty] | AE | 9.83
17 | 292 | Supply, installation, Testing and Commissioning of Static Pass Boxes of Size 450X450mm with 1.2mm thick SS 304 Mat finish , with interlock doors, UV light On when doors closed condition. As per clean room standard and requirement. at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 2 | 2 | 42700 | Nos |  | 85400 |  |  |  | 2 | 85400 |  | 70% | 61000
18 | 259 | Supplying and fixing of Unplasticised Poly Vinyl Chloride UPVC 3 track sliding windows with mesh shutter – 2-glass shutters and 1-mesh shutter duly manufactured using UPVC reinforced profiles Composition of profile shall consists a minimum of 5.5 PHR of TiO2 and not more than 12 PHR of CaCo3 for every 100 parts of PVC resin of 94mm x 45 mm/80 mm x 52 mm x 2.20 mm for outer frames, 58 mm x 39 mm/54 mm x 38 mm x 2.20mm for sliding shutter frames capable of mounting single glazing system structurally reinforced with hot dip galvanized up to 50 microns of minimum thickness of 1.0/1.2 mm prefabricated and welded through fusion welding. The window sash shall be fitted with 5 mm thick clear float glass of reputed make and mesh shutter frame shall be 42 mm x 25mm/52 mm x 21.5 mm x 2.0 mm fitted with Vinyl Coated Fiber mesh- on rollers/ pulley duly fixed with Grey colour TPV Gasket for sash and Glazing bead shall be co-extruded with Grey colour soft PVC. System shall have single point locking with Touch Lock and the system is to be installed at the site using anchor fasteners, silicon rubber sealant, easy glazing/deglazing at site etc., including cost and conveyance of all materials, accessories, labour charges for transportation, erection at site includingetc., complete for finished item of work. at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 39.83 | 15 | 8565 | Nos |  | 128475 |  |  |  | 15 | 128475 |  | 90% | 9517
[6 empty] | AE | 24.83
19 | 260 | Providing, supplying and fixing of Fixed Louvered Ventilator made out of multi chambered uPVC sections with Glazing bead shall be co-extruded with Grey colour soft PVC. having isolated drainage and reinforced with Galvanized Iron profiles throughout the window. The outer frame having an overall size of 60 mm x 55 mm x 2.40 with reinforcement of 1 mm thickness and Mullion with overall size of 74 mm x 60 mm x 2.40 mm with reinforcement of 1 mm thickness. Composition of profile shall consists a minimum of 5.5 PHR of TiO2 and not more than 12 PHR of CaCo3 for every 100 parts of PVC resin. Ventilator shall be provided with 4.5 mm Pin Head glass, standard hardware. Wall thickness of frame and Mullion shall be 2.4 mm., including cost and conveyance of all materials, accessories, labour charges for transportation, erection at site etc., complete for finished item of work hinges IS:205 150mm long, 1 No. aldrop IS:2681 300mm long, 1 No. tower bolt IS:204 of 200 mm x 10 mm dia at top, 2 Nos. 150 mm at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 1.96 | 1.96 | 7708 | Nos |  | 15107.68 |  |  |  | 1.96 | 15107.68 |  | 90% | 8564
20 | 227 | Suction machine at Petlaburj Hospital
|  | Qty V.Pg.No:- of MB:- |  |  |  | 1 | 1 | 34650 | Nos |  | 34650 |  |  |  | 1 | 34650 |  | 70% | 49500
21 | 230 | Operative Hysteroscopy and Resectoscope Set Machine at Petlaburj Hospital
|  | Qty V.Pg.No:- of MB:- |  |  |  | 1 | 1 | 1487500 | Nos |  | 1487500 |  |  |  | 1 | 1487500 |  | 70% | 2125000
22 | 231 | Operative Laparoscopy Set at Petlaburj Hospital
|  | Qty V.Pg.No:- of MB:- |  |  |  | 1 | 1 | 2940000 | Nos |  | 2940000 |  |  |  | 1 | 2940000 |  | 70% | 4200000
[9 empty] | Sub-Total:- |  | 6567038.52 |  |  | 1856102 |  | 6567038.52
[8 empty] | Sub-Total(Civil+ Civil Suppl.+Equipment+Electrical+Ac Supply):- |  |  | 23476152.547 |  |  | 16909115.62 |  | 6567038.52
[9 empty] | Add GST 18% |  | 4225707.4585 |  |  | 3043640.8116 |  | 1182066.9336
[9 empty] | GrandTotal:- |  | 27701860.0055 |  |  | 19952756.4316 |  | 7749105.4536
Certificate
The work is in progress in according with the specification drawing and terms and condition the agreement.
[7 empty] | 1) | No recoveries are due for recovery from the contractor other than those proposed in the bill
[7 empty] | 2) | There are no further dues to be recovery from the contractor
[7 empty] | 3) | The contractor has conveyneced the materieals for use on the work as per the lead statement approved the agreement.
[7 empty] | 4) | The leads and lifts are covered in the contractor.
[7 empty] | 5) | The leads and lifts are covered in the contractor.

## CC-5
ABSTRACT
Name of Work:- Design, Fabriction, establishing and commissioning of In - Vitro ferility centers (IVFC) alongwith allied Services on Turnkey basis at MGMH Petlaburj,Hyd. | [7 empty] | Agency: | M/s. Asta Vardhman Consortium | [5 empty] | Agt.No:344/A/TSMIDC/Spl.Proj/IVFCs /2022-23,Dt.05.07.2023
S.No | Date of measurement/ S.No. in Agt. | Description Of Work etc., | Measurements Upto date |  |  |  |  | Rate |  | Per | Total Value to date |  | Deduct/previous Measurements |  | Since last measurement |  |  | Remarks
|  |  | No | L | B | D | Content | Rs | Ps. |  | Rs. | Ps | P.No. | Qty. | Qty | Value
[16 empty] | Rs. | Ps.
1 | 247 | Dismantling, clearing away and carefully stacking useful materials for re-use and disposal of unserviceable materials with 100m lead as directed by Executive Engineer duly taking actual premeasurements before dismantling including all labour charges , overheads & contractor profit etc., complete Finished item of work | [16 empty] | Original Rate
a) Brick Masonry
|  | Qty V.Pg.No:-01 of MB:-04 |  |  |  | 20.38 | 20.38 | 398 | Cum |  | 8111.24 |  | 20.38 | 8111.24 | - | - |  |  | 398
| 248 | b) Tiles Dismantling
|  | Qty V.Pg.No:-01 of MB:-04 |  |  |  | 729.9325 | 400 | 20 | Sqm |  | 8000 |  | 400 | 8000 | - | - |  |  | 20
[6 empty] | AE | 329.9325
2 | 249 | Dismantling doors, windows and clear storey windows, Ventilators etc., (wood or steel) shutters including Chowkhats, architraves,hold fasts and other attachments etc., and stacking them within 100m lead including labour charge etc., and overheads & contractors profit complete for finished item of work.
a)Not Exceeding 3.00Sqm Area
|  | Qty V.Pg.No:-01 of MB:-04 |  |  |  | 32 | 16 | 350 | Each |  | 5600 |  | 16 | 5600 | - | - |  |  | 350
[6 empty] | AE | 16
3 | 252 | Brick Masonry for panel walls in SuperStructure with CM (1:8) prop (cement: Screened sand) with Aerated Cellular Autoclaved Concrete Blocks conforming to IS:2185 (Part-3) - 1984 and IS:6441-1972 of Compressive strength 3 N/mm2 600x 230 x 200 mm from approved source having minimum crushing strength of 3 N/Sq.m including cost and conveyance of all materials like cement, sand, bricks, water etc., to site, including sales & other taxes on all materials, all operational, incidental and labour charges such as mixing cement mortar, constructing masonry, scaffolding charges, lift charges, curing, etc., complete but excluding seigniorage charges for finished item of work. (APSS No. 501 & 504).
|  | Qty V.Pg.No:-01 of MB:-04 |  |  |  | 16.3192 | 10.5 | 14558 | cum |  | 152859 |  | 10.5 | 152859 | - | - |  |  | 14558
[6 empty] | AE | 5.82
4 | 253 | Reinforced Masonry for partiton walls 100 mm thick in CM (1:4) prop (cement: Screened sand) in super structure with Aerated Cellular Autoclaved Concrete Blocks conforming to IS:2185 (Part-3) - 1984 and IS:6441-1972 of Compressive strength 3 N/mm2 600x 200 x 100 mm from approved source having minimum crushing strength of 3 N/Sq.m including cost and conveyance of all materials like cement, sand, bricks, water etc., to site, including sales & other taxes on all materials, all operational, incidental and labour charges such as mixing cement mortar, constructing masonry, scaffolding charges, lift charges, curing, etc., complete but excluding seigniorage charges for finished item of work. (APSS No. 501 & 504).
|  | Qty V.Pg.No:-02 of MB:-04 |  |  |  | 219.7595 | 215 | 1716 | Sqm |  | 368940 |  | 215 | 368940 | - | - |  |  | 1716
[6 empty] | AE | 4.7595
5 | 256 | Plastering 12mm thick in two coats using screened sand with base coat of 8mm thick in CM (1:6) and top coat of 4mm thick in CM (1:4) with dubara sponge finishing including cost and conveyance of all materials like cement, sand, water etc., to site, including sales & other taxes on all materials, and all operational, incidental charges on materials and including cost of all labour charges for mixing mortar, finishing, scaffolding, lift charges, curing, including cutting grooves as directed by Engineer-in-charge etc., and overheads & contractors profit complete for finished item of work. (SS 901,903 & 904).
|  | Qty V.Pg.No:-02 of MB:-04 |  |  |  | 822.13 | 430 | 906 | Sqm |  | 389580 |  | 430 | 389580 | 0 | 0 |  |  | 906
[6 empty] | AE:- | 392.13
6 | 263 | Flooring with soluble salt porcelain vitrified tiles screen printed and polished of size 600 x 600 mm and thickness between 8 to 10mm 1st quality conforming to IS: 13711, IS: 13712, IS: 13630Parts 1 to 15 of any colour and finish in all shades and designs with borders and design as per the approved flooring pattern as directed by the Engineer-In -Charge, laying tiles using spacers of 2mm thick, set over a base coat of CM 1:8 prop. 12mm thick using screened sand over CC bed already laid or RCC roof slab, including neat cement slurry of honey like consistency spread at the rate 3.3 kgs per Sqm. and jointed neatly with white cement paste to full depth mixed with pigment of matching shade including cost and conveyance of all materials like cement, sand, water, tiles, white cement etc., to site excluding cost of C.C. bed including cost of base coat and all labour charges for mixing of cement mortar, laying tiles to required slope as directed by the Engineer- in- charge etc., and complete for finished item of work. TSSS No.701 and 707.
|  | Qty V.Pg.No:-02 of MB:-04 |  |  |  | 294.66 | 294.659 | 1593 | Sqm |  | 469391.787 |  | 294.66 | 469393.38 | - | - |  |  | 1593
7 | 266 | Providing dadooing to walls with glazed full body porcelain wall tiles of size 300 x 600 mm with any type of design texture such as marble finish, wooden, bamboo, stone finishes etc., scratch less, stain free and thickness between 6-8 mm 1st quality conforming to IS:13711, IS:13712, IS:13630 Parts 1 to 15 of any colour and finish in all shades and designs with borders as approved by Engineer-in-Charge set over base coat of CM1:5 12 mm thick using screened sand with cement slurry of honey like consistency spread at the rate of 3.30 kgs per sqm and jointing with white cement paste mixed with pigment of matching shade to full depth, including cost of all materials like tiles, cement, sand and water etc., complete for finished item of work. 3rd Floor at Petlaburj Hospital
|  | Qty V.Pg.No:-03 of MB:-04 |  |  |  | 153.0952 | 30 | 1391 | Sqm |  | 41730 |  | 30 | 41730 | - | - |  |  | 1391
[6 empty] | AE | 123.0952
[9 empty] | Civil Sub-Total:- |  | 1444212.027 |  |  | 1444213.62 |  | 0
Civil Supplemental Items
1 |  | Dismantling, clearing away and carefully stacking useful materials for re-use and disposal of unserviceable materials with 100m lead as directed by Executive Engineer duly taking actual premeasurements before dismantling including all labour charges , overheads & contractor profit etc., complete Finished item of work
a)Old Cement Mortar
|  | Qty V.Pg.No:-03 of MB:-04 |  |  |  | 251.59 | 251.5889
b)Reinforced Cement Concrete
|  | Qty V.Pg.No:-03 of MB:-04 |  |  |  | 0.43 | 0.4293
2 |  | Providing Thermo Mechanically Treated ( TMT) ( Fe-500/500D/550D from primery producer TATA, SAIL, VSP, JSW Steel, Goel steel, Jindal panther, X- Vega & balaji Shakthi as per IS 1786-2008) of Different Diameters RCC Works , including labour charges for straightening, cutting, bending to required sizes and shapes, placing in position with cover blocks of approved materials and sizes and typing and lap - spacing with binding wire of 18 SWG, Forming grills for reinforcement work as per approved design and drawings, including and conveyanace of steel bars, including all wastages such as overlaps, coupling, chairs, spacer bars including cost and conveyance of binding wire cover blocks and incidential, operational, labour charges such as cutting bending, placing in position, typing incliding sales and other taxes on all materials etc., and overheads & contractors profit completefor finished item of work
|  | Qty V.Pg.No:-03 of MB:-04 |  |  |  |  | 0.2956
3 |  | Supply and placing of the Design Mix Concrete M 25 grade corresponding to IS 456 with minimum cement content of 380 kgs per 1 cum of concrete using Weight Batcher / Concrete mixer with 20mm size graded machine crushed hard granite metal (coarse aggregate - as per IS 383 - 1970 and IS 2386 Part 1 to Part 8) from approved quarry including cost and conveyance of all materials like cement, fine aggregate (sand) coarse aggregate, water etc., to site and sales & other taxes on all materials, centering using Casurina Ballies, Bamboos, Wooden Reapers, Runners, Wood Posts, Steel Plates etc., including all operational, incidental and labour charges such as weigh batching, machine mixing, lifting of concrete manually, laying concrete, curing , overheads & contractors profit etc., complete but excluding cost of steel and its fabrication charges for finished item of work (APSS No. 402)
For Lintels
|  | Qty V.Pg.No:-04 of MB:-04 |  |  |  | 0.75 | 0.74952
4 |  | Providing skirting to internal walls to 10 cm height with Double charged / multi charged stain free fullbody porcelain vitrified tiles with double layer pigment of size 600 x 600 mm and thickness between 8-10 mm 1st quality conforming to IS:15622 - 2017, IS:13630 (Parts 1 to 15) of any colour and finish in all shades and designs, length equal to flooring tiles, set over base coat of CM(1:5) 12 mm thick using screened sand with cement slurry of honey like consistency spread at the rate of 3.30 kgs per sqm and jointing with white cement paste mixed with pigment of matching shade to full depth, including cost of all materials like tiles, cement, sand and water etc.,and overheads & contractors profit complete for finished item of work.(APSS No.701 &707)
|  | Qty V.Pg.No:-04 of MB:-04 |  |  |  | 174.5 | 174.5
[8 empty] | Civil Suppl. Sub-Total:- |  |  | 0 |  |  | 0 |  | 0
Equipment Items
1 | 200 | IVF Test tube Warmers at Petlaburz Hospital
|  | Qty V.Pg.No:-04 of MB:-04 |  |  |  | 2 | 2 | 34650 | Nos |  | 69300 |  | 2 | 69300 |  |  |  | 70% | 49500
2 | 201 | DICOM compatible fully digital, compact, portable, Ultrasound Scan Machine Colour Doppler at Petlaburz Hospital
|  | Qty V.Pg.No:-04 of MB:-04 |  |  |  | 2 | 2 | 955500 | Nos |  | 1911000 |  | 2 | 1911000 |  |  |  | 70% | 1365000
3 | 202 | Multipurpose Electro hydraulic with manual override mobile OT Table, with divided leg section suitable for all Gynaecological surgical procedures, complete with 5cm Mattress and corded handset at Petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 1 | 1 | 394625 | Nos |  | 394625 |  | 1 | 394625 |  |  |  | 70% | 563750
4 | 203 | LED procedure Lights Double dome at petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 1 | 1 | 218750 | Nos |  | 218750 |  | 1 | 218750 |  |  |  | 70% | 312500
5 | 204 | LED procedure Lights Single dome at petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 1 | 1 | 131250 | Nos |  | 131250 |  | 1 | 131250 |  |  |  | 70% | 187500
6 | 207 | CO2 Incubators at Petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 2 | 2 | 577500 | Nos |  | 1155000 |  | 2 | 1155000 |  |  |  | 70% | 825000
7 | 212 | IVF Thermometer at Petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 1 | 1 | 43313 | Nos |  | 43313 |  | 1 | 43313 |  |  |  | 70% | 61875
8 | 213 | CO2 Cylinder and Manifold at Petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 2 | 2 | 35000 | Nos |  | 70000 |  | 2 | 70000 |  |  |  | 70% | 50000
9 | 214 | CO2 and O2 Analyzer at Petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 2 | 1 | 264600 | Nos |  | 264600 |  | 1 | 264600 |  |  |  | 70% | 378000
10 | 215 | PH Meter at Petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 1 | 1 | 65625 | Nos |  | 65625 |  | 1 | 65625 |  |  |  | 70% | 93750
11 | 217 | Sperm Counting Markler Chamber at Petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 1 | 1 | 52938 | Nos |  | 52938 |  | 1 | 52938 |  |  |  | 70% | 75625
12 | 220 | Clinical Centrifuge machine for Andrology at Petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 1 | 1 | 24150 | Nos |  | 24150 |  | 1 | 24150 |  |  |  | 70% | 34500
13 | 221 | DRY Incubator at Petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 1 | 1 | 394625 | Nos |  | 394625 |  | 1 | 394625 |  |  |  | 70% | 563750
14 | 223 | Pharmaceutical Refrigerator at Petlaburz Hospital
|  | Qty V.Pg.No:-06 of MB:-04 |  |  |  | 1 | 1 | 157500 | Nos |  | 157500 |  | 1 | 157500 |  |  |  | 70% | 225000
15 | 224 | Cryocane (TA 26 Ltr) with wheels at Petlaburz Hospital
|  | Qty V.Pg.No:-06 of MB:-04 |  |  |  | 2 | 2 | 43313 | Nos |  | 86626 |  | 2 | 86626 |  |  |  | 70% | 61875
16 | 225 | Defibrillator at Petlaburz Hospital
|  | Qty V.Pg.No:-06 of MB:-04 |  |  |  | 1 | 1 | 218750 | Nos |  | 218750 |  | 1 | 218750 |  |  |  | 70% | 312500
17 | 226 | 7 Para Patient Monitor at Petlaburz Hospital
|  | Qty V.Pg.No:-06 of MB:-04 |  |  |  | 2 | 2 | 196000 | Nos |  | 392000 |  | 2 | 392000 |  |  |  | 70% | 280000
18 | 228 | Anaesthesia Work station at Petlaburz Hospital
|  | Qty V.Pg.No:-06 of MB:-04 |  |  |  | 1 | 1 | 656250 | Nos |  | 656250 |  | 1 | 656250 |  |  |  | 70% | 937500
19 | 232 | Mulitfunctional Printer at Petlaburz Hospital
|  | Qty V.Pg.No:-06 of MB:-04 |  |  |  | 1 | 1 | 30625 | Nos |  | 30625 |  | 1 | 30625 |  |  |  | 70% | 43750
20 | 233 | Ultrasound Examination Couch at Petlaburz Hospital
|  | Qty V.Pg.No:-06 of MB:-04 |  |  |  | 1 | 1 | 56875 | Nos |  | 56875 |  | 1 | 56875 |  |  |  | 70% | 81250
21 | 235 | Laptop For Office Usage at Petlaburz Hospital
|  | Qty V.Pg.No:-06 of MB:-04 |  |  |  | 2 | 2 | 80500 | Nos |  | 161000 |  | 2 | 161000 |  |  |  | 70% | 115000
22 | 320 | 20 KVA UPS: Supply and installation of 20KVA 3ph in and 3ph out on line UPS system IGBT based rectifier with input power factor correction 32 bit microprocessor based with isolation transformers double conversion, SNMP controls, LCD display, Pure sine wave output, with auto static switch three phase input / Three phase output and modular structure for better thermal technology / cooling facility, with warranty up to three years.Makes: APC / Numeric / Emerson / Fuji Electric At Petlaburz
|  | Qty V.Pg.No:-06 of MB:-04 |  |  |  | 1 | 1 | 213500 | Nos |  | 213500 |  | 1 | 213500 |  |  |  | 70% | 305000
23 | 322 | Supply and providing of UPS Cum battery rack for 20 batteries at MGMH Petlaburz
|  | Qty V.Pg.No:-06 of MB:-04 |  |  |  | 1 | 1 | 4735 | Nos |  | 4735 |  | 1 | 4735 |  |  |  | 70% | 6764
1 | 199 | Ovum Aspiration Pumps at Petlaburj Hospital
|  | Qty V.Pg.No:-01 of MB:-05 |  |  |  | 2 | 2 | 168000 | Nos |  | 336000 |  | 2 | 336000 |  |  |  | 70% | 240000
2 | 205 | IVF Workstation with LAF at Petlaburj Hospital
|  | Qty V.Pg.No:-01 of MB:-05 |  |  |  | 1 | 1 | 481250 | Nos |  | 481250 |  | 1 | 481250 |  |  |  | 70% | 687500
3 | 206 | IVF Ant vibration Table for procedure at Petlaburj Hospital
|  | Qty V.Pg.No:-01 of MB:-05 |  |  |  | 1 | 1 | 67375 | Nos |  | 67375 |  | 1 | 67375 |  |  |  | 70% | 96250
4 | 208 | Trigas bench Top Incubators for Human Embryo culture at Petlaburj Hospital
|  | Qty V.Pg.No:-01 of MB:-05 |  |  |  | 1 | 1 | 577500 | Nos |  | 577500 |  | 1 | 577500 |  |  |  | 70% | 825000
5 | 209 | Trinocular Stereozoom Microscope at Petlaburj Hospital
|  | Qty V.Pg.No:-01 of MB:-05 |  |  |  | 1 | 1 | 216300 | Nos |  | 216300 |  | 1 | 216300 |  |  |  | 70% | 309000
6 | 210 | ICSI Micro manipulator with Inverted Microscope at Petlaburj Hospital
|  | Qty V.Pg.No:-02 of MB:-05 |  |  |  | 1 | 1 | 1837500 | Nos |  | 1837500 |  | 1 | 1837500 |  |  |  | 70% | 2625000
7 | 211 | IVF Laser System at Petlaburj Hospital
|  | Qty V.Pg.No:-02 of MB:-05 |  |  |  | 1 | 1 | 1792000 | Nos |  | 1792000 |  | 1 | 1792000 |  |  |  | 70% | 2560000
8 | 216 | VOC Meter for ART Lab at Petlaburj Hospital
|  | Qty V.Pg.No:-02 of MB:-05 |  |  |  | 1 | 1 | 511875 | Nos |  | 511875 |  | 1 | 511875 |  |  |  | 70% | 731250
9 | 218 | Binocular Microscope for Semen Analysis at Petlaburj Hospital
|  | Qty V.Pg.No:-02 of MB:-05 |  |  |  | 1 | 1 | 28875 | Nos |  | 28875 |  | 1 | 28875 |  |  |  | 70% | 41250
10 | 219 | Laminar flow cabinet with Andrology Work station at Petlaburj Hospital
|  | Qty V.Pg.No:-02 of MB:-05 |  |  |  | 1 | 1 | 175000 | Nos |  | 175000 |  | 1 | 175000 |  |  |  | 70% | 250000
11 | 222 | Pipetter and Denudation system at Petlaburj Hospital
|  | Qty V.Pg.No:-02 of MB:-05 |  |  |  | 1 | 1 | 72188 | Nos |  | 72188 |  | 1 | 72188 |  |  |  | 70% | 103125
12 | 229 | Autoclave at Petlaburj Hospital
|  | Qty V.Pg.No:-02 of MB:-05 |  |  |  | 1 | 1 | 393750 | Nos |  | 393750 |  | 1 | 393750 |  |  |  | 70% | 562500
13 | 236 | Reception Table at Petlaburj Hospital
|  | Qty V.Pg.No:-03 of MB:-05 |  |  |  | 1 | 1 | 77000 | Nos |  | 77000 |  | 1 | 77000 |  |  |  | 70% | 110000
14 | 238 | Filing Cabinet at Petlaburj Hospital
|  | Qty V.Pg.No:-03 of MB:-05 |  |  |  | 2 | 2 | 24150 | Nos |  | 48300 |  | 2 | 48300 |  |  |  | 70% | 34500
15 | 239 | Patient Seating 3 in 1 model at Petlaburj Hospital
|  | Qty V.Pg.No:-03 of MB:-05 |  |  |  | 3 | 3 | 26950 | Nos |  | 80850 |  | 3 | 80850 |  |  |  | 70% | 38500
16 | 244 | Wall Storage Cabinets at Petlaburj Hospital
|  | Qty V.Pg.No:-03 of MB:-05 |  |  |  | 8 | 8 | 12250 | Nos |  | 98000 |  | 8 | 98000 |  |  |  | 70% | 17500
17 | 245 | Office Table at Petlaburj Hospital
|  | Qty V.Pg.No:-03 of MB:-05 |  |  |  | 3 | 3 | 14000 | Nos |  | 42000 |  | 3 | 42000 |  |  |  | 70% | 20000
[11 empty] | 13608800 |  |  | 13608800
Electrical-1
1 | 294 | Supply and laying of ISI 25mm outer dia medium grade with IS:9537-part 3 rigid PVC pipe concealed in wall with all required PVC / Metallic Junction Boxes including masonry work and labour charges etc., Makes: Sudhakar / Precision /Universal/ Modi / Million Plast. at MGMH Petlaburj
[6 empty] | 463.5 | 200 | 93 | RMt |  | 18600 |  | 200 | 18600 |  |  |  | 80% | 116
[6 empty] | AE | 263.5
2 | 294 | Supply and laying of ISI 25mm outer dia medium grade with IS:9537-part 3 rigid PVC pipe surface on wall with all required PVC / Metallic Junction Boxes including masonry work and labour charges etc., Makes: Sudhakar / Precision /Universal/ Modi / Million Plast. at MGMH Petlaburj
[6 empty] | 1352.8 | 450 | 86 | Rmt |  | 38700 |  | 450 | 38700 |  |  |  | 80% | 107
[6 empty] | AE | 902.8
3 | 295 | Wiring with 2 runs of 22/0.3mm 1.5 Sq.mm FRLS / HFFR P.V.C. insulated flexible copper cable ISI MARK in existing pipe with 6A Modular switch, Ceiling rose/BH/SBH Modular switches with cover plate and GI switch box including all labour charges etc., complete. for Non- Residential Building Makes of wires: Polycab Makes of switches: - /Honeywell Blenge Plus at MGMH Petlaburj
[6 empty] | 148 | 100 | 756 | Nos |  | 75600 |  | 100 | 75600 |  |  |  | 80% | 945
[6 empty] | AE | 48
4 | 300 | Supply and run of 1 of 22 /0.3mm 1.5 Sq.mm FRLS / HFFR P.V.C. insulated flexible copper cable in existing conduit pipe for earth continuity including all labour charges etc., complete. Makes of wires: Finolex/ RR Cable/ Havells/ Polycab/ HPL. at MGMH Petlaburj
[6 empty] | 379.6 | 350 | 32 | Rmt |  | 11200 |  | 350 | 11200 |  |  |  | 80% | 40
[6 empty] | AE | 29.6
5 | 301 | Supply and run of 3 of 2.5 sq.mm 36/0.mm phase neutral and earth FRLS / HFFR PVC insulated flexible copper cable in existing conduit pipe for individual lighting circuits including labour charges etc., complete as required for switch boards. Makes of wires: Finolex/ RR Cable/ Havells/ Polycab/ HPL. at MGMH Petlaburj
[6 empty] | 1713.1 | 600 | 142 | Rmt |  | 85200 |  | 600 | 85200 |  |  |  | 80% | 177
[6 empty] | AE | 1113.1
6 | 302 | Supply and 3 runs of 4.0 sq mm 56/0.3 mm phase neutral and earth FRLS / HFFR PVC insulated flexible copper cable in existing conduit pipe including labour charges etc., complete for 16A sockets. Makes of wires: Finolex/ RR Cable/ Havells/ Polycab/ HPL. at MGMH Petlaburj
[6 empty] | 2421 | 1200 | 204 | Nos |  | 244800 |  | 1200 | 244800 |  |  |  | 80% | 255
[6 empty] | AE | 1221
7 | 303 | Supply and run of 5 of 6.0 Sqmm 90/0.3 mm 3 phases, neutral and earth FRLS / HFFR PVC insulated flexible copper cable in the existing conduit pipe for run of mains from Power panel board to TPN DBs with pin type lugs and connections etc., complete. for LDBs Makes of wires: Finolex/ RR Cable/ Havells/ Polycab/ HPL. at MGMH Petlaburj
[6 empty] | 240.1 | 60 | 485 | Rmt |  | 29100 |  | 60 | 29100 |  |  |  | 80% | 606
[6 empty] | AE | 180.1
8 | 304 | Supply and run of 5 of 10.0 Sqmm 140/0.3 mm 3 phases, neutral and earth FRLS / HFFR PVC insulated flexible copper cable in the existing conduit pipe for run of mains from Power panel board to TPN DBs with pin type lugs and connections etc., complete. for PDBs Makes of wires: Finolex/ RR Cable/ Havells/ Polycab/ HPL. at MGMH Petlaburj
[6 empty] | 284 | 40 | 774 | Rmt |  | 30960 |  | 40 | 30960 |  |  |  | 80% | 967
[6 empty] | AE | 244
9 | 306 | Supply and fixing of 4 Way TPN DB Horizontal with IP 43 Protection as per IS:13032 Makes: Legrand / Schneider and Supply and Fixing of 1 No., of 40A FP 30mA RCCB as incomer and 12 Nos 6-32 A 10kA SP MCBs Makes: Legrand-DX3 / Schneider-Acti9 as out goings including internal connections and labour charges for FLUSH Mounting etc., complete. For Lighting DBs at MGMH Petlaburj
[6 empty] | 10 | 3 | 14660 | Rmt |  | 43980 |  | 3 | 43980 |  |  |  | 80% | 18325
[6 empty] | AE | 7
10 | 308 | Supply and fixing of 8 Way VTPN DB Horizontal with IP 43 Protection as per IS:13032 Makes: Legrand / Schneider and Supply and Fixing of 1 No., of 100A FP 10KA MCB as incomer and 4 Nos 63 A 10kA TP MCBs, 4 Nos 40 A 10kA TP MCBs Makes: Legrand-DX3 / Schneider-Acti9 as out goings including internal connections and labour charges for FLUSH Mounting etc., complete. For UPS MDB DBs at MGMH Petlaburj
[7 empty] | 1 | 51254 | Nos |  | 51254 |  | 1 | 51254 |  |  |  | 80% | 64067
11 | 309 | Providing and fixing of 125A 25KA TPN Thermal Magnetic Release Based MCCB and Terminal Spreaders in Existing panel board with 1 No. and 1 Set of Indication Lamps, LED type, R,Y,B and breaker ON , OFF, TRIP and spring charged lamps. and replace with above Mentioned with required Drilling Holes, removing and Making Busbar connections etc, as required. Makes: Legrand / Schneider/ABB/LandT/CandS at MGMH Petlaburj
[7 empty] | 1 | 23106 | Nos |  | 23106 |  | 1 | 23106 |  |  |  | 80% | 28883
12 | 318 | SITC of Hot dip galvanized perforated cable tray of 100 mm Wide sizes for to run the cable from DBs to SBs and sockets and AC panel to Units units. All necessary supports and accessories are included. Cable tray for cables alone shall be included here Thickness shall be 1.6 mm. at MGMH Petlaburj
[6 empty] | 79 | 70 | 343 | Rmt |  | 24010 |  | 70 | 24010 |  |  |  | 80% | 429
[6 empty] | AE | 9
13 | 319 | SITC of Hot dip galvanized perforated cable tray of 300 mm Wide sizes for to run the cable from Floor Panel to Lab Panel and electrical room to AC panel and AC panel to Units. All necessary supports and accessories are included. Cable tray for cables alone shall be included here Thickness shall be 1.6 mm. at MGMH Petlaburj
[6 empty] | 102.5 | 80 | 1048 | Rmt |  | 83840 |  | 80 | 83840 |  |  |  | 80% | 1310
[6 empty] | AE | 22.5
14 | 325 | Supply and installation of 50x6 GI flat for body earthing of electrical panel and AC Panel which is laid in 300mm cable tray at MGMH Petlaburj
[6 empty] | 217.3 | 200 | 263 | Rmt |  | 52600 |  | 200 | 52600 |  |  |  | 80% | 329
[6 empty] | AE | 17.3
15 | 323 | Providing and Fixing maintenance free earthing which consists of G.I. Earth station, with 600X600X3.15mm GI Plate at 2500mm Depth including construction of brick pedestal, providing meshed funnel, GI cover and other civil Engineering works, spreading a homogenous mixture of salt, charcoal around the pipe etc., completely as per IS 3043, 1987 or latest revision. Earthing testing should be done as per IE Rules like Earth valve test Etc. at MGMH Petlaburj
[7 empty] | 2 | 6800 | Nos |  | 13600 |  | 2 | 13600 |  |  |  | 80% | 8500
16 | 324 | Providing and Fixing maintenance free earthing which consists of copper. Earth station, with 600X600X3.15mm Copper Plate at 2500mm Depth including construction of brick pedestal, providing meshed funnel, GI cover and other civil Engineering works, spreading a homogenous mixture of salt, charcoal around the pipe etc., completely as per IS 3043, 1987 or latest revision. Earthing testing should be done as per IE Rules like Earth valve test Etc. at MGMH Petlaburj
[6 empty] | 4 | 2 | 17826 | Nos |  | 35652 |  | 2 | 35652 |  |  |  | 80% | 22283
[6 empty] | AE | 2
17 | 327 | Supply and installation of 25x3 Copper flat for Neutral earthing of UPS and Equipment which is laid in 100mm cable tray at MGMH Petlaburj
[6 empty] | 207.3 | 200 | 722 | Rmt |  | 144400 |  | 200 | 144400 |  |  |  | 80% | 902
[6 empty] | AE | 7.3
18 | 328 | Supply and installation of 4 sqmm Copper wire for Earthing of DBs Equipment at MGMH Petlaburj
[6 empty] | 450.6 | 80 | 66 | Rmt |  | 5280 |  | 80 | 5280 |  |  |  | 80% | 83
[6 empty] | AE | 370.6
19 | 329 | Supply, Laying and testing of 3.5Cx95 sqmm XLPE Insulated Cable 1100V grade armoured aluminium cable with ISI mark as per specification confirming to IS:7098 Part - I with heavy duty type double compression weather proof type brass cable glands duly nickel plated as per BS 6121 and IP66 complete with brass checknut, outer sheath sealing gasket heavy duty long barrel aluminium lugs confirming to I.S specifications with complete nut, bolt and washer etc.. Make of Cable: Polycab/ KEI/Universal/Glostar/Finolex. Make of gland and Lungs: HMI/Commet/Dowell’s at MGMH Petlaburj
[6 empty] | 180 | 120 | 966 | Rmt |  | 115920 |  | 120 | 115920 |  |  |  | 80% | 1207
[6 empty] | AE | 60
20 | 330 | Supply, Lying and testing of 3.5CX50 sqmm XLPE Insulated Cable 1100V grade armoured aluminium cable with ISI mark as per specification confirming to IS:7098 Part - I with heavy duty type double compression weather proof type brass cable glands duly nickel plated as per BS 6121 and IP66 complete with brass checknut, outer sheath sealing gasket heavy duty long barrel aluminium lugs confirming to I.S specifications with complete nut, bolt and washer etc.. Make of Cable: Polycab Make of gland and Lungs: HMI at MGMH Petlaburj
[6 empty] | 180 | 70 | 578 | Rmt |  | 40460 |  | 70 | 40460 |  |  |  | 80% | 722
[6 empty] | AE | 110
21 | 331 | Supply, Lying and testing of 4Cx16 sqmm PVC Insulated Cable 1100V grade armoured Copper cable with ISI mark as per specification confirming to IS:7098 Part - I with heavy duty type double compression weather proof type brass cable glands duly nickel plated as per BS 6121 and IP66 complete with brass checknut, outer sheath sealing gasket heavy duty long barrel aluminium lugs confirming to I.S specifications with complete nut, bolt and washer etc.. Make of Cable: Polycab/ KEI/Universal/Glostar/Finolex. Make of gland and Lungs: HMI/Commet/Dowell’s at MGMH Petlaburj
[7 empty] | 100 | 1186 | Rmt |  | 118600 |  | 100 | 118600 |  |  |  | 80% | 1483
22 | 332 | Supply, Lying and testing of 4Cx6 sqmm PVC Insulated Cable 1100V grade armoured Copper cable with ISI mark as per specification confirming to IS:7098 Part - I with heavy duty type double compression weather proof type brass cable glands duly nickel plated as per BS 6121 and IP66 complete with brass checknut, outer sheath sealing gasket heavy duty long barrel aluminium lugs confirming to I.S specifications with complete nut, bolt and washer etc. Make of Cable: Polycab/ KEI/Universal/ Glostar/Finolex. Make of gland and Lungs: HMI/Commet/Dowell’s at MGMH Petlaburj
[7 empty] | 120 | 387 | Rmt |  | 46440 |  | 120 | 46440 |  |  |  | 80% | 484
23 | 333 | Supply, Lying and testing of 4Cx4 sqmm PVC Insulated Cable 1100V grade armoured Copper cable with ISI mark as per specification confirming to IS:7098 Part - I with heavy duty type double compression weather proof type brass cable glands duly nickel plated as per BS 6121 and IP66 complete with brass checknut, outer sheath sealing gasket heavy duty long barrel aluminium lugs confirming to I.S specifications with complete nut, bolt and washer etc. Make of Cable:Polycab/ KEI/Universal/Glostar/Finolex. Make of gland and Lungs: HMI/Commet/Dowell’s at MGMH Petlaburj
[7 empty] | 80 | 285 | Rmt |  | 22800 |  | 80 | 22800 |  |  |  | 80% | 356
24 | 334 | SITC of IVF Center Main Panel Indoor IP-42 wall/ free standing floor mounted dust and vermin proof compartmentalized cubical panel made out of CRCA sheet, required hardware, duly treated for de-rusting in 7 tank process with de-phosphate and with powder coating on both side of panel in desired shade. The panel having PU/ Neoprene rubber gasket of not less than 3mm thickness, separate detachable gland plate M.S. base channel, hinged door with locking arrangement for equipment/switchgear. Thickness of sheet shall not be less than 1.6 mm up to 600 mm length / width of any compartment and be of 2.0 mm above 600 mm. Load bearing structure shall be of 2.0 mm thick sheet supported by base M.S. channel if required. Side walls and cable alley compartments having bolted type doors with /without detachable extension type structure with all type of suitable switching accessories and bus-bar as per load requirement of respective IVF equipment’s. Which is including Lighting, power DBs and UPS at MGMH Petlaburj
[7 empty] | 1 | 284000 | Nos |  | 284000 |  | 1 | 284000 |  |  |  | 80% | 355000
25 | 335 | SITC of IVF center AC Panel outdoor IP-54 wall/ free standing floor mounted dust and vermin proof compartmentalized cubical panel made out of CRCA sheet, required hardware, duly treated for de-rusting in 7 tank process with de-phosphate and with powder coating on both side of panel in desired shade. The panel having PU/ Neoprene rubber gasket of not less than 3mm thickness, separate detachable gland plate M.S. base channel, hinged door with locking arrangement for equipment/switchgear. Thickness of sheet shall not be less than 1.6 mm up to 600 mm length / width of any compartment and be of 2.0 mm above 600 mm. Load bearing structure shall be of 2.0 mm thick sheet supported by base M.S. channel if required. Side walls and cable alley compartments having bolted type doors with / without detachable extension type structure with all type of suitable switching accessories and bus-bar as per load requirement of respective AC equipment’s. Which is including 1nos AHU’s stater with VFD by pass, Heater, ODU and VRF system at MGMH Petlaburj
[7 empty] | 1 | 216000 | Nos |  | 216000 |  | 1 | 216000 |  |  |  | 80% | 270000
1856102
1 | 346 | Supply, transportation and installation of split AC unit 1.5 TR inverter type 3 Star capable of delivering 18000 BTU/hr and above with high wall mounted indoor unit and outdoor condensing unit Hermetically sealed compressor suitable for operation on 230V, 50Hz, 1Phase AC supply capable of performing cooling dehumidifying air circulating and filtering with cooling and condensing units with 3.5 mts of copper piping, insulation kit and 4 mts of 3 core copper flexible chord , built-in stabilizer Voltage range 160- 264 volts and cordless remote control. Makes : Daikin / Thoshiba / O General at MGMH Petlaburj
[6 empty] | 3 | 1 | 38400 | Nos |  | 38400 |  |  |  | 1 | 38400 |  | 80% | 48000
[6 empty] | AE | 2
2 | Sup | Condensing units - VRF/VRV System : Supply, Installation, Nitrogen testing , Vacuuming and Commissioning of air cooled variable refrigerant flow modular type condensing units, each comprising of multiple scroll compressors all inverter driven, full charge of refrigerant gas R-410a including additional gas filling , lubricating oil and all accessories as per the specifications. The condensing units shall be suitable to work on cooling mode. The minimum Energy Efficiency Ratio shall be as per ASHRAE STANDARDS 90.1 -2001 table 6.2.1B . The COP of the system shall be greater than 4 under ARI conditions for 100percentage load . The condensing units shall be suitable for operation on 415 plus or minus 10percentage volts, 50Hz, 3 phase AC power supply and , outdoor units to be mounted on MS platform with suitable Vibration Isolation pads to avoid vibrations. All the supports and angle base frame structure to be duly black painted with synthetic epoxy paint. the condensing units shall be of following capacities: The VRF ODU should be capable of working with total capacity of connected indoor units ranging between 100percentage to 140percentage of ODU capacity . COP minimum 3.5. Make : Daikin / LG / O General / Toshiba at MGMH Petlaburj 16 HP
[6 empty] | 1 | 1 | 0 | Nos |  | 0 |  |  |  | 1 | 0 |  | 80%
3 | 371 | VRF Indoor Units : Hi wall Splits : Supply, Installation, Testing and Commissioning of variable refrigerant flow modular type indoor units wired/wireless remote suitable for R410a refrigerant comprising of all accessories as per the specifications. The indoor units shall be suitable to work on cooling.The minimum Energy Efficiency Ratio shall be as per ASHRAE STANDARDS 90.1 -2001 table 6.2.1B. The indoor units shall be suitable for operation on 220 plus or minus 6percentage volts, 50Hz, 1 phase AC power supply. 0.8 TR at MGMH Petlaburj
[6 empty] | 2 | 2 | 24560 | Nos |  | 49120 |  |  |  | 2 | 49120 |  | 80% | 30700
4 | 372 | VRF Indoor Units : Hi wall Splits : Supply, Installation, Testing and Commissioning of variable refrigerant flow modular type indoor units wired/wireless remote suitable for R410a refrigerant comprising of all accessories as per the specifications. The indoor units shall be suitable to work on cooling.The minimum Energy Efficiency Ratio shall be as per ASHRAE STANDARDS 90.1 -2001 table 6.2.1B. The indoor units shall be suitable for operation on 220 plus or minus 6percentage volts, 50Hz, 1 phase AC power supply. 1.0 TR at MGMH Petlaburj
[6 empty] | 6 | 3 | 24560 | Nos |  | 73680 |  |  |  | 3 | 73680 |  | 80% | 30700
[6 empty] | AE | 3
5 | 373 | VRF Indoor Units : Hi wall Splits : Supply, Installation, Testing and Commissioning of variable refrigerant flow modular type indoor units wired/wireless remote suitable for R410a refrigerant comprising of all accessories as per the specifications. The indoor units shall be suitable to work on cooling.The minimum Energy Efficiency Ratio shall be as per ASHRAE STANDARDS 90.1 -2001 table 6.2.1B. The indoor units shall be suitable for operation on 220 plus or minus 6percentage volts, 50Hz, 1 phase AC power supply. 1.5 TR at MGMH Petlaburj
[6 empty] | 6 | 4 | 28000 | Nos |  | 112000 |  |  |  | 4 | 112000 |  | 80% | 35000
[6 empty] | AE | 2
6 | Sup | Cassette Units : Supply, Installation, Testing and Commissioning of variable refrigerant flow modular type indoor units wired/wireless remote suitable for R410a refrigerant comprising of all accessories as per the specifications. The indoor units shall be suitable to work on cooling mode.The minimum Energy Efficiency Ratio shall be as per ASHRAE STANDARDS 90.1 -2001 table 6.2.1B. The indoor units shall be suitable for operation on 220 plus or minus 6percentage volts, 50Hz, 1 phase AC power supply. 3.0 TR – 4 way at MGMH Petlaburj
[6 empty] | 2 | 2 | 0 | Nos |  | 0 |  |  |  | 2 | 0 |  | 80%
7 | 375 | Supply, Installation, Testing and Commissioning of Hard copper REFRIGERANT PIPING of 16swg various sizes with necessary supports, fittings, interconnecting the liquid and suction lines between the aircooled outdoor units and the indoor units. The piping shall be carried out of Hard drawn copper pipes of type K with soldered / brazed socket fittings. Isolating valves shall be provided to isolate each compressor, strainers, sight glass and any other component requiring proper operation and maintenance. Both the suction and liquid lines shall be insulated with 19mm thick closed cell insulation for above 25mm dia , 13mm thick for pipes below 25mm dia . The insulation finished with treated woven glass fiber reinforced covering for inside Piping and including making required holes in the wall and re finishing and water tight of holes after laying holes as per the specifications and approved drawings at MGMH Petlaburj
[6 empty] | 1 | 1 | 320000 | Lot |  | 320000 |  |  |  | 1 | 320000 |  | 80% | 400000
8 | 376 | Supply, Installation , Testing and Commissioning of Refnet joints to be provided in refrigerant pipe line. Material of construction for fittings shall be similar to refrigerant piping at MGMH Petlaburj
[6 empty] | 15 | 10 | 4953 | Nos |  | 49530 |  |  |  | 10 | 49530 |  | 80% | 6191
[6 empty] | AE | 5
9 | 291 | Supply, installation, testing and commissioning of 16 G GI powder coated suitable single person entry air shower as per the Technical Specifications at MGMH Petlaburj
[6 empty] | 1 | 1 | 248500 | Nos |  | 248500 |  |  |  | 1 | 248500 |  | 70% | 355000
10 | 287 | Double leaf clean room Doors : 46mm thick flush doors made of 0.8mm thick Powder coated GI sheets on both sides, 90 plus or minus 2 kg/m3 density Honeycomb with stand upto 220 Deg.C Temperature, and compressible strength upto 400 Kg/Sqm, 1.2 mm thick GPSP . door frames, double glazed vision panel with necessary adhesive tapes and silicon sealant, necessary hardware like SS304 ball bearing butt hinges, D- handles, push plates, Dorma make door closure, concealed tower bolt, drop seals for the double leaf door and provision for fixing magnetic type door interlocking system and automatic door bottoms, Both side lock and keys etc. complete. Size 1500 X 2100 mm with 300mm X 300mm double glazed view panels at MGMH Petlaburj
|  | Door |  |  |  | 5 | 4 | 36800 | Nos |  | 147200 |  |  |  | 4 | 147200 |  | 80% | 46000
[6 empty] | AE | 1
11 | Sup | Single leaf clean room Doors : 46mm thick flush doors made of 0.8mm thick Powder coated GI sheets on both sides, 90 plus or minus 2 kg/m3 density Honeycomb with stand upto 220 Deg.C Temperature, and compressible strength upto 400 Kg/Sqm, 1.2 mm thick GPSP . door frames, double glazed vision panel with necessary adhesive tapes and silicon sealant, necessary hardware like SS304 ball bearing butt hinges, D- handles, push plates, Dorma make door closure, concealed tower bolt, drop seals for the double leaf door and provision for fixing magnetic type door interlocking system and automatic door bottoms, Both side lock and keys etc. complete. Size 900 X 2100 mm with 300 mm x 300 mm View panelat MGMH Petlaburj
|  | Door |  |  |  | 3 | 3 |  | Nos |  | 0 |  |  |  | 3 | 0 |  | 80% | 28700
12 | Sup | Emergency Fire Doors : 46mm thick flush doors made of 0.8mm thick Powder coated GI sheets on both sides, 90 plus or minus 2 kg/m3 density Honeycomb with stand upto 220 Deg.C Temperature, and compressible strength upto 400 Kg/Sqm, 1.2 mm thick GPSP . door frames, double glazed vision panel with necessary adhesive tapes and silicon sealant, necessary hardware like SS304 ball bearing butt hinges, D- handles, push plates, Dorma make door closure, concealed tower bolt, drop seals for the double leaf door and provision for fixing magnetic type door interlocking system and automatic door bottoms, Both side lock and keys etc. complete. Size 1500 X 2100 mm with 2 hours fire rated and panic push bar and accessories etc. at Gandhi Hospital
|  | Qty V.Pg.No:- of MB:- |  |  |  | 1 | 1 | 0 | Nos |  | 0 |  |  |  | 1 | 0 |  | 80%
13 | Sup | Emergency Fire Doors : 46mm thick flush doors made of 0.8mm thick Powder coated GI sheets on both sides, 90 plus or minus 2 kg/m3 density Honeycomb with stand upto 220 Deg.C Temperature, and compressible strength upto 400 Kg/Sqm, 1.2 mm thick GPSP . door frames, double glazed vision panel with necessary adhesive tapes and silicon sealant, necessary hardware like SS304 ball bearing butt hinges, D- handles, push plates, Dorma make door closure, concealed tower bolt, drop seals for the double leaf door and provision for fixing magnetic type door interlocking system and automatic door bottoms, Both side lock and keys etc. complete. Size 1000 X 2100 mm with 2 hours fire rated and panic push bar and accessories etc. at Gandhi Hospital
|  | Qty V.Pg.No:- of MB:- |  |  |  | 2 | 2 | 0 | Nos |  | 0 |  |  |  | 2 | 0 |  | 80%
14 | 285 | Supply and installation of 80mm thick double skin modular wall Panels made of 0.8 mm thick powder coated GI on both the sides, with 40 plus or minus 2 kg/m3 density PUF as infill, GI profiles all along the periphery, flush on both sides with maximum allowable gap of 3- 4mm filled with food grade silicon sealant and placed on cold rolled galvanised bottom tracks with a recess to provide floor to wall coving flush with the wall panel. This includes all required harware for completion Panels to be covered with a protective film to avoid any damages during transportation and installation at MGMH Petlaburj
[6 empty] | 121.04 | 121.04 | 4496 | Sqm |  | 544195.84 |  |  |  | 121.04 | 544195.84 |  | 80% | 5620
15 | 286 | Supply and installation of 50mm thick double skin ceiling system made of 0.8 mm thick Powder Coated GI sheets on both sides, 40 plus or minus 2 kg/m3 density PUF as infill, GI profiles all along the periphery, panels flush towards room side with maximum allowable gap of 3-4mm at panel to panel joints filled with silicon sealant. Ceiling panels are suspended from the RCC slab by using concealed AL ceiling grid with tie rod and adjustable turn buckle arrangement etc. This includes all required hardware for completion. Panels to be covered with a protective film to avoid any damages during transportation and installation at MGMH Petlaburj
[6 empty] | 62.66 | 60 | 4108 | Sqm |  | 246480 |  |  |  | 60 | 246480 |  | 80% | 5135
[6 empty] | AE | 2.66
16 | 289 | Supply and installation of Extruded Aluminium Coving at MGMH Petlaburj
[6 empty] | 109.83 | 100 | 468 | Sqm |  | 46800 |  |  |  | 100 | 46800 |  | 80% | 585
[6 empty] | AE | 9.83
17 | 292 | Supply, installation, Testing and Commissioning of Static Pass Boxes of Size 450X450mm with 1.2mm thick SS 304 Mat finish , with interlock doors, UV light On when doors closed condition. As per clean room standard and requirement. at MGMH Petlaburj
|  | Pass Box |  |  |  | 2 | 2 | 42700 | Nos |  | 85400 |  |  |  | 2 | 85400 |  | 70% | 61000
18 | 259 | Supplying and fixing of Unplasticised Poly Vinyl Chloride UPVC 3 track sliding windows with mesh shutter – 2-glass shutters and 1-mesh shutter duly manufactured using UPVC reinforced profiles Composition of profile shall consists a minimum of 5.5 PHR of TiO2 and not more than 12 PHR of CaCo3 for every 100 parts of PVC resin of 94mm x 45 mm/80 mm x 52 mm x 2.20 mm for outer frames, 58 mm x 39 mm/54 mm x 38 mm x 2.20mm for sliding shutter frames capable of mounting single glazing system structurally reinforced with hot dip galvanized up to 50 microns of minimum thickness of 1.0/1.2 mm prefabricated and welded through fusion welding. The window sash shall be fitted with 5 mm thick clear float glass of reputed make and mesh shutter frame shall be 42 mm x 25mm/52 mm x 21.5 mm x 2.0 mm fitted with Vinyl Coated Fiber mesh- on rollers/ pulley duly fixed with Grey colour TPV Gasket for sash and Glazing bead shall be co-extruded with Grey colour soft PVC. System shall have single point locking with Touch Lock and the system is to be installed at the site using anchor fasteners, silicon rubber sealant, easy glazing/deglazing at site etc., including cost and conveyance of all materials, accessories, labour charges for transportation, erection at site includingetc., complete for finished item of work. at MGMH Petlaburj
[6 empty] | 39.83 | 15 | 8565 | Nos |  | 128475 |  |  |  | 15 | 128475 |  | 90% | 9517
[6 empty] | AE | 24.83
19 | 260 | Providing, supplying and fixing of Fixed Louvered Ventilator made out of multi chambered uPVC sections with Glazing bead shall be co-extruded with Grey colour soft PVC. having isolated drainage and reinforced with Galvanized Iron profiles throughout the window. The outer frame having an overall size of 60 mm x 55 mm x 2.40 with reinforcement of 1 mm thickness and Mullion with overall size of 74 mm x 60 mm x 2.40 mm with reinforcement of 1 mm thickness. Composition of profile shall consists a minimum of 5.5 PHR of TiO2 and not more than 12 PHR of CaCo3 for every 100 parts of PVC resin. Ventilator shall be provided with 4.5 mm Pin Head glass, standard hardware. Wall thickness of frame and Mullion shall be 2.4 mm., including cost and conveyance of all materials, accessories, labour charges for transportation, erection at site etc., complete for finished item of work hinges IS:205 150mm long, 1 No. aldrop IS:2681 300mm long, 1 No. tower bolt IS:204 of 200 mm x 10 mm dia at top, 2 Nos. 150 mm at MGMH Petlaburj
[6 empty] | 1.96 | 1.96 | 7708 | Nos |  | 15107.68 |  |  |  | 1.96 | 15107.68 |  | 90% | 8564
20 | 227 | Suction machine at Petlaburj Hospital
[6 empty] | 1 | 1 | 34650 | Nos |  | 34650 |  |  |  | 1 | 34650 |  | 70% | 49500
21 | 230 | Operative Hysteroscopy and Resectoscope Set Machine at Petlaburj Hospital
[6 empty] | 1 | 1 | 1487500 | Nos |  | 1487500 |  |  |  | 1 | 1487500 |  | 70% | 2125000
22 | 231 | Operative Laparoscopy Set at Petlaburj Hospital
[6 empty] | 1 | 1 | 2940000 | Nos |  | 2940000 |  |  |  | 1 | 2940000 |  | 70% | 4200000
[9 empty] | Sub-Total:- |  | 6567038.52 |  |  | 1856102 |  | 6567038.52
[8 empty] | Sub-Total(Civil+ Civil Suppl.+Equipment):- |  |  | 23476152.547 |  |  | 16909115.62 |  | 6567038.52
[9 empty] | Add GST 18% |  | 4225707.4585 |  |  | 3043640.8116 |  | 1182066.9336
[9 empty] | GrandTotal:- |  | 27701860.0055 |  |  | 19952756.4316 |  | 7749105.4536
Certificate
[7 empty] | 1) | The work is in progress in according with the specification drawing and terms and condition the agreement.
[7 empty] | 2) | No recoveries are due for recovery from the contractor other than those proposed in the bill
[7 empty] | 3) | There are no further dues to be recovery from the contractor
[7 empty] | 4) | The contractor has conveyneced the materieals for use on the work as per the lead statement approved the agreement.
[7 empty] | 5) | The leads and lifts are covered in the contractor.

## supercheck statement
Design, fabrication,establishing & commissioning of In-Vitro Fertility Centres (IVFCs) along with allied services on Turnkey basis at MGMH Petlaburj, Hyderabad. Agency M/s. ASTA Vardhman Consortium
Supercheck Statement (For this bill i.e 3rd & part )
| 5th & part bill recommended for RS |  |  |  |  | 9721881.49
| 30% of the Work Super Check to be done |  |  |  |  | 2916564.447
SI. No. | item | Qty | Unit | Rate | amount | recording Dt: | Dy.EE Dt: | Mb No | item pg No | EE Sir Date | Amount (In Rs.) | SE Sir Date | Amount (In Rs.)
1st & part bill
1 | Flooring vitrified tiles 600 x 600mm | 294.66 | Sqm | 1593 | 469393 | 05.10.2023 | 06.10.2023 | 1 | 16 to 18 | 16.10.2023 | 469393
2 | Skirting | 174.5 | Rm | 95 | 16578 | 07.10.2023 | 08.10.2023 | 1 | 19 to 20 | 16.10.2023 | 16578
3 | Dadooing 300 x 600mm | 153.1 | Sqm | 1391 | 212962 | 15.10.2023 | 15.10.2023 | 1 | 21 | 16.10.2023 | 212962
2nd & part bill
1 | IVF Test tube Warmers | 2 | Each | 49500 | 99000 | 2023-12-06 | 2023-12-08 | 3 | 1 | 2023-12-11 | 99000 | 2023-12-17 | 99000
2 | DICOM compatible fully digital, compact | 2 | Each | 1365000 | 2730000 | 2023-12-06 | 2023-12-08 | 3 |  | 2023-12-11 | 2730000
3 | Multipurpose Electro hydraulic with manual override mobile OT Table | 1 | Each | 563750 | 563750 | 2023-12-06 | 2023-12-08 | 3 |  | 2023-12-11 | 563750
4 | LED procedure Lights Double dome | 1 | Each | 312500 | 312500 | 2023-12-06 | 2023-12-08 | 3 |  | 2023-12-11 | 312500
5 | LED procedure Lights Single dome | 1 | Each | 187500 | 187500 | 2023-12-06 | 2023-12-08 | 3 |  | 2023-12-11 | 187500
6 | CO2 Incubators | 2 | Each | 825000 | 1650000 | 2023-12-06 | 2023-12-08 | 3 |  | 2023-12-11 | 1650000 | 2023-12-17 | 1650000
7 | IVF Thermometer | 1 | Each | 61875 | 61875 | 2023-12-06 | 2023-12-08 | 3 |  | 2023-12-11 | 61875
8 | CO2 Cylinder and Manifold | 2 | Each | 50000 | 100000 | 2023-12-06 | 2023-12-08 | 3 |  | 2023-12-11 | 100000
9 | CO2 and O2 Analyzer | 1 | Each | 378000 | 378000 | 2023-12-06 | 2023-12-08 | 3 |  | 2023-12-11 | 378000
10 | PH Meter | 1 | Each | 93750 | 93750 | 2023-12-06 | 2023-12-08 | 3 |  | 2023-12-11 | 93750
11 | Sperm Counting Markler Chamber | 1 | Each | 75625 | 75625 | 2023-12-06 | 2023-12-08 | 3 |  | 2023-12-11 | 75625
12 | Clinical Centrifuge machine for Andrology | 1 | Each | 34500 | 34500 | 2023-12-06 | 2023-12-08 | 3 |  | 2023-12-11 | 34500
13 | DRY Incubator | 1 | Each | 563750 | 563750 | 2023-12-06 | 2023-12-08 | 3 |  | 2023-12-11 | 563750
14 | Pharmaceutical Refrigerator | 1 | Each | 225000 | 225000 | 2023-12-06 | 2023-12-08 | 3 |  | 2023-12-11 | 225000
15 | Cryocane (TA 26 Ltr) with wheels | 2 | Each | 61875 | 123750 | 2023-12-06 | 2023-12-08 | 3 | 1 | 2023-12-11 | 123750
3rd & part Bill
1 | Ovum Aspiration Pumps at Petlaburj Hospital | 2 | Each | 240000 | 480000 | 2024-01-12 | 2024-01-17 | 5 | 1
2 | IVF Workstation with LAF at Petlaburj Hospital | 1 | Each | 687500 | 687500 |  |  | 5
3 | IVF Ant vibration Table for procedure at Petlaburj Hospital | 1 | Each | 96250 | 96250 |  |  | 5
4 | Trigas bench Top Incubators for Human Embryo culture at Petlaburj Hospital | 1 | Each | 825000 | 825000 |  |  | 5
5 | Trinocular Stereozoom Microscope at Petlaburj Hospital | 1 | Each | 309000 | 309000 |  |  | 5
6 | ICSI Micro manipulator with Inverted Microscope at Petlaburj Hospital | 1 | Each | 2625000 | 2625000 |  |  | 5 | 2
7 | IVF Laser System at Petlaburj Hospital | 1 | Each | 2560000 | 2560000 |  |  | 5 |  |  |  | 19-1-21 | 2560000
8 | VOC Meter for ART Lab at Petlaburj Hospital | 1 | Each | 731250 | 731250 |  |  | 5
9 | Binocular Microscope for Semen Analysis at Petlaburj Hospital | 1 | Each | 41250 | 41250 |  |  | 5
10 | Laminar flow cabinet with Andrology Work station at Petlaburj Hospital | 1 | Each | 250000 | 250000 |  |  | 5
11 | Pipetter and Denudation system at Petlaburj Hospital | 1 | Each | 103125 | 103125 |  |  | 5
12 | Autoclave at Petlaburj Hospital | 1 | Each | 562500 | 562500 |  |  | 5 | 3
13 | Reception Table at Petlaburj Hospital | 1 | Each | 110000 | 110000 |  |  | 5
14 | Filing Cabinet at Petlaburj Hospital | 2 | Each | 34500 | 69000 | 12.01.2024 | 17.01.2024 | 5 | 3
15 | Patient Seating 3 in 1 model at Petlaburj Hospital | 3 | Each | 38500 | 115500 |  |  | 5
16 | Wall Storage Cabinets at Petlaburj Hospital | 8 | Each | 17500 | 140000 |  |  | 5
17 | Office Table at Petlaburj Hospital | 3 | Each | 20000 | 60000 |  |  | 5
4th & part Bill
1 | Supply and laying of ISI 25mm outer dia medium concealed | 463.5 | Rmt | 116 | 53766 | 17.01.2024 | 18.01.2024 | 7 | 1 to 2
2 | Supply and laying of ISI 25mm outer dia medium on Surface | 1352.8 | Rmt | 107 | 144749.6 | 17.01.2024 | 18.01.2024 | 7 | 2 to 4
3 | Wiring with 2 runs of 22/0.3mm 1.5 Sq.mm FRLS / HFFR P.V.C. insulated | 148 | Rmt | 945 | 139860 | 19.01.2024 | 20.01.2024 | 7 | 5
4 | Supply and run of 1 of 22 /0.3mm 1.5 Sq.mm FRLS / HFFR | 379.6 | Rmt | 40 | 15184 | 19.01.2024 | 20.01.2024 | 7 | 6
5 | Supply and run of 3 of 2.5 sq.mm 36/0.mm phase neutral and earth | 1713.1 | Rmt | 117 | 200432.7 | 19.01.2024 | 20.01.2024 | 7 | 6 to 7
6 | Supply and 3 runs of 4.0 sq mm 56/0.3 mm phase neutral and earth | 242 | Rmt | 255 | 61710 | 19.01.2024 | 20.01.2024 | 7 | 7 to 10
7 | Supply and run of 5 of 6.0 Sqmm 90/0.3 mm 3 phases, neutral | 240.1 | Rmt | 606 | 145500.6 | 19.01.2024 | 20.01.2024 | 7 | 10
8 | Supply and run of 5 of 10.0 Sqmm 140/0.3 mm 3 phases, neutral | 284 | Rmt | 967 | 274628 | 19.01.2024 | 20.01.2024 | 7 | 10
9 | Supply and fixing of 4 Way TPN DB Horizontal with IP 43 Protection | 4 | Nos | 18325 | 73300 | 21.01.2024 | 22.01.2024 | 7 | 10 to 11
10 | Supply and fixing of 8 Way VTPN DB Horizontal with IP 43 Protection as per IS:13032 | 1 | Nos | 64067 | 64067 | 21.01.2024 | 22.01.2024 | 7 | 11
11 | Providing and fixing of 125A 25KA TPN Thermal Magnetic Release Based MCCB | 1 | Nos | 28883 | 28883 | 21.01.2024 | 22.01.2024 | 7 | 11
12 | SITC of Hot dip galvanized perforated cable tray of 100 mm Wide sizes | 79 | Rmt | 429 | 33891 | 21.01.2024 | 22.01.2024 | 7 | 11
13 | SITC of Hot dip galvanized perforated cable tray of 300 mm Wide sizes | 102.5 | Rmt | 1310 | 134275 | 21.01.2024 | 22.01.2024 | 7 | 12
14 | Supply and installation of 50x6 GI flat for body earthing of electrical | 217.3 | Rmt | 329 | 71491.7 | 21.01.2024 | 22.01.2024 | 7 | 12
15 | Providing and Fixing maintenance free earthing which consists of G.I. | 2 | Nos | 8500 | 17000 | 21.01.2024 | 22.01.2024 | 7 | 12
16 | Providing and Fixing maintenance free earthing which consists of copper. | 4 | Nos | 22283 | 89132 | 21.01.2024 | 22.01.2024 | 7 | 12
17 | Supply and installation of 25x3 Copper flat for Neutral earthing of UPS | 207.3 | Rmt | 902 | 186984.6 | 23.01.2024 | 24.01.2024 | 7 | 13
18 | Supply and installation of 4 sqmm Copper wire for Earthing | 450.6 | Rmt | 83 | 37399.8 | 23.01.2024 | 24.01.2024 | 7 | 13
19 | Supply, Laying and testing of 3.5Cx95 sqmm XLPE Insulated Cable 1100V grade | 180 | Rmt | 1207 | 217260 | 23.01.2024 | 24.01.2024 | 7 | 13
20 | Supply, Lying and testing of 3.5CX50 sqmm XLPE Insulated Cable 1100V grade | 180 | Rmt | 722 | 129960 | 23.01.2024 | 24.01.2024 | 7 | 14
21 | Supply, Lying and testing of 4Cx16 sqmm PVC Insulated Cable 1100V grade | 100 | Rmt | 1483 | 148300 | 23.01.2024 | 24.01.2024 | 7 | 14
22 | Supply, Lying and testing of 4Cx6 sqmm PVC Insulated Cable 1100V grade armoured Copper | 120 | Rmt | 484 | 58080 | 23.01.2024 | 24.01.2024 | 7 | 14
23 | Supply, Lying and testing of 4Cx4 sqmm PVC Insulated Cable 1100V grade armoured Copper | 80 | Rmt | 350 | 28000 | 23.01.2024 | 24.01.2024 | 7 | 15
24 | SITC of IVF Center Main Panel Indoor IP-42 wall/ free standing floor mounted | 1 | Nos | 355000 | 355000 | 23.01.2024 | 24.01.2024 | 7 | 15 |  |  | 25/1/2024 | 355000
25 | SITC of IVF center AC Panel outdoor IP-54 wall/ free standing floor mounted | 1 | Nos | 270000 | 270000 | 23.01.2024 | 24.01.2024 | 7 | 16 |  |  | 25/1/2024 | 270000
5th Part Bill
1 | Supply, transportation and installation of split AC unit 1.5 TR | 3 | Nos | 48000 | 144000 | 2024-06-03 | 2024-11-03 | 9 | 1
2 | Condensing units - VRF/VRV System : Supply, Installation, Nitrogen testing , | 1 | Nos | 0 | 0 | 2024-06-03 | 2024-11-03 | 9 | 2
3 | VRF Indoor Units : Hi wall Splits : Supply, Installation, Testing and Commissioning 0.8 TR | 2 | Nos | 30700 | 61400 | 2024-06-03 | 2024-11-03 | 9 | 3
4 | VRF Indoor Units : Hi wall Splits : Supply, Installation, Testing and Commissioning 1.0 TR | 6 | Nos | 30700 | 184200 | 2024-06-03 | 2024-11-03 | 9 | 4
5 | VRF Indoor Units : Hi wall Splits : Supply, Installation, Testing and Commissioning 1.5 TR | 6 | Nos | 35000 | 210000 | 2024-06-03 | 2024-11-03 | 9 | 4
6 | Cassette Units : Supply, Installation, Testing and Commissioning of variable refrigerant 2.0 TR | 2 | Nos | 0 | 0 | 2024-06-03 | 2024-11-03 | 9 | 5
7 | Supply, Installation, Testing and Commissioning of Hard copper REFRIGERANT PIPING | 1 | Nos | 400000 | 400000 | 2024-06-03 | 2024-11-03 | 9 | 5
8 | Supply, Installation , Testing and Commissioning of Refnet joints | 15 | Nos | 6191 | 92865 | 2024-06-03 | 2024-11-03 | 9 | 6
9 | 16 G GI powder coated suitable single person entry air shower | 1 | Nos | 355000 | 355000 | 2024-06-03 | 2024-11-03 | 9 | 6
10 | Double leaf clean room Doors | 5 | Nos | 46000 | 230000 | 2024-06-03 | 2024-11-03 | 9 | 7
11 | Single leaf clean room Doors | 3 | Nos | 28700 | 86100 | 2024-06-03 | 2024-11-03 | 9 | 8
12 | Emergency Fire Exit Door Double Leaf | 1 | Nos | 0 | 0 | 2024-06-03 | 2024-11-03 | 9 | 8
13 | Emergency Fire Exit Door Single Leaf | 2 | Nos | 0 | 0 | 2024-06-03 | 2024-11-03 | 9 | 9
14 | 80mm thick double skin modular wall Panels | 121.04 | Sqm | 5620 | 680244.8 | 2024-06-03 | 2024-11-03 | 9 | 9 to 12
15 | 50mm thick double skin ceiling system | 62.66 | Sqm | 5135 | 321759.1 | 2024-06-03 | 2024-11-03 | 9 | 12 to 14
16 | Extruded Aluminium Coving | 109.83 | Rmt | 585 | 64250.55 | 2024-06-03 | 2024-11-03 | 9 | 14
17 | Statick Pass Boxes | 2 | Nos | 61000 | 122000 | 2024-06-03 | 2024-11-03 | 9 | 15
18 | Poly Vinyl Chloride UPVC 3 track sliding windows | 39.8 | Sqm | 9517 | 378776.6 | 2024-06-03 | 2024-11-03 | 9 | 16 & 17
19 | fixing of Fixed Louvered Ventilator | 1.96 | Sqm | 8564 | 16785.44 | 2024-06-03 | 2024-11-03 | 9 | 18
20 | Suction machine Portable suction unit | 1 | Nos | 49500 | 49500 | 2024-06-03 | 2024-11-03 | 9 | 19
21 | Operative Hysteroscopy and Resectoscope Set Machine | 1 | Nos | 2125000 | 2125000 | 2024-06-03 | 2024-11-03 | 9 | 19
22 | Operative Laparoscopy Set | 1 | Nos | 4200000 | 4200000 | 2024-06-03 | 2024-11-03 | 9 | 20
[5 empty] | 9721881.49 | [5 empty] | 7897933 |  | 4934000

## Measurements
DETAILED MEASUREMENTS
Name of the work:Design, Fabriction, establishing and commissioning of In - Vitro ferility centers (IVFC) alongwith allied Services on Turnkey basis at petlaburz Hyderabad. | [10 empty] | Agency: M/s. Asta vardhman Consortium | [5 empty] | Agt.No: 344/A/TSMIDC/Spl.Proj/IVFCs/2022-23, Dt. 05.07.2023
S.No | Agreement S.No | Discription Of Work etc., | Measurements Upto date | [5 empty] | Rate |  |  | Per | Total Volume |  | Deduct/previous Measurements |  | Since last measurement |  |  | Remarks
|  |  | No |  | L | B | D | Content | Units | Rs | Ps. |  | Rs. | Ps | P.No. | Qty. | Qty | Value
[18 empty] | Rs. | Ps.
1 | 247 | Dismantling, clearing away and carefully stacking useful materials for re-use and disposal of unserviceable materials with 100m lead as directed by Executive Engineer duly taking actual premeasurements before dismantling including all labour charges , overheads & contractor profit etc., complete Finished item of work Brick Work
|  | Supply Line Duct Enrty | 1 | 2 | 0.6 | 0.23 | 0.5 | 0.138
|  | Return Line Duct Entry | 1 | 2 | 0.4 | 0.23 | 0.3 | 0.0552
[6 empty] | Total |  | 0.1932 | Cum
2 | Sup | Dismantling, clearing away and carefully stacking useful materials for re-use and disposal of unserviceable materials with 100m lead as directed by Executive Engineer duly taking actual premeasurements before dismantling including all labour charges , overheads & contractor profit etc., complete Finished item of work Reinforcement Cement COncrete
|  | Lintels | 1 | 3 | 0.6 | 0.3 | 0.3 | 0.162
[6 empty] | Total |  | 0.162 | Cum
3 | Sup | Dismantling, clearing away and carefully stacking useful materials for re-use and disposal of unserviceable materials with 100m lead as directed by Executive Engineer duly taking actual premeasurements before dismantling including all labour charges , overheads & contractor profit etc., complete Finished item of work Waste Cement Remove ( Wall Cladding)
|  | Manifold Room Long Wall | 1 | 2 | 6.3 |  | 2.1 | 26.46
|  | Short Wall | 1 | 2 | 3.14 |  | 2.1 | 13.188
|  | Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
[6 empty] | Total |  | 37.548 | Sqm
4 | 253 | Reinforced Masonry for partition walls 100 mm thick in CM 1:4 prop. Aerated Cellular Autoclaved Concrete Blocks conforming to IS:2185 Part-3 - 1984 and IS:6441-1972 of Compressive strength 3 N/mm2 600 x 200 x 100 mm and placing 2Nos. of 6mm M.S plain rods in every third layer with free ends of the reinforcement pegged into mortar joints of main brick walls where applicable including cost and conveyance of all materials like cement, steel, sans, brick, water etc., to site, including sales and other taxes excluding GST on all materials, all operational, incidents charges, constructing masonry, lift charges, curing, complete for finished item of work. TSSS No. of 509. 3rd Floor at MGMH Petlaburj
|  | Electrical Room Main Door Wall | 1 | 1 | 3.17 |  | 3 | 9.51
|  | Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
[6 empty] | Total |  | 7.41 | Sqm
5 | 252 | Brick masonry for panel walls in superstructure with CM 1:8 prop: Aerated Cellular Autoclaved Concrete Blocks conforming to IS:2185 Part-3 - 1984 and IS:6441-1972 of Compressive strength 3 N/mm2 600 x 200 x 200 mm including cost and conveyance of all materials like cement, screened sand, bricks, water etc., to site, including sales and other taxes on all materials and such as labour charges, like mixing cement mortar, scaffolding charges, constructing masonry, lift charges, curing, etc.,complete for finished item of work. TSSS No.501 and 504. 3rd Floor at MGMH Petlaburj
|  | RO Plant Pedastal | 1 | 1 | 0.6 | 0.6 | 0.6 | 0.216
|  | AHU Pedastal | 1 | 1 | 5 | 1.5 | 0.3 | 2.25
|  | VRF Pedastal | 1 | 1 | 2.4 | 1.8 | 0.3 | 1.296
[6 empty] | Total |  | 3.762 | Cum
6 | 256 | Plastering 12mm thick in two coats using screened sand with base coat of 8mm thick in CM (1:6) and top coat of 4mm thick in CM (1:4) with dubara sponge finishing including cost and conveyance of all materials like cement, sand, water etc., to site, including sales & other taxes on all materials, and all operational, incidental charges on materials and including cost of all labour charges for mixing mortar, finishing, scaffolding, lift charges, curing, including cutting grooves as directed by Engineer-in-charge etc., and overheads & contractors profit complete for finished item of work. (SS 901,903 & 904).
|  | Electrical Room Main Door Wall | 1 | 2 | 3.17 |  | 3 | 19.02
|  | Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
|  | Door Jam | 1 | 1 | 5.2 | 0.1 |  | 0.52
|  | RO Plant Pedastal Top | 1 | 1 | 0.6 |  | 0.6 | 0.36
|  | Sides | 1 | 2 | 0.6 |  |  | 0.6
|  | Non Sterile Corridor | 1 | 2 | 7.1 |  | 2.1 | 29.82
|  | Counseling Room Corridor | 1 | 2 | 4.5 |  | 2.1 | 18.9
|  | Staff Change Room Corridor | 1 | 2 | 4.67 |  | 2.1 | 19.614
|  | Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
|  | do | -1 | 2 | 0.8 |  | 2.1 | -3.36
|  | Door Jam | 1 | 1 | 5.2 | 0.1 |  | 0.52
|  | do | 1 | 2 | 5 | 0.1 |  | 1
[6 empty] | Total |  | 82.794 | Sqm
7 | 255 | Plastering 20mm thick in two coats using screened sand with base coat of 16mm thick in CM1:6 and top coat of 4mm thick in CM1:4 with dubara sponge finishing including cost and conveyance of all materials like cement, sand, water etc., to site, including sales and other taxes on all materials, and all operational, incidental charges on materials and including cost of all labour charges for mixing mortar, finishing, scaffolding, lift charges, curing, including cutting grooves as directed by Engineer-in-charge etc., complete for finished item of work .SS 901,903and 904 3rd Floor at MGMH Petlaburj
|  | IVF OT And Embryology Lab | 1 | 3 | 1.9 |  | 1.8 | 10.26
|  | Major OT And Andrology Lab | 1 | 3 | 1.9 |  | 1.8 | 10.26
|  | AHU Pedastal Top | 1 | 1 | 5 | 1.5 |  | 7.5
|  | Sides Long | 1 | 2 | 5 |  | 0.3 | 3
|  | Sides Short | 1 | 2 | 1.5 |  | 0.3 | 0.9
|  | VRF Pedastal Top | 1 | 1 | 2.4 | 1.8 |  | 4.32
|  | Sides Long | 1 | 2 | 2.4 |  | 0.3 | 1.44
|  | Sides Short | 1 | 2 | 1.8 |  | 0.3 | 1.08
|  | Supply Duct | 1 | 2 | 0.6 |  | 0.4 | 0.48
|  | Return Duct | 1 | 2 | 0.4 |  | 0.4 | 0.32
[6 empty] | Total |  | 39.56 | Sqm
8 | 272 | Supply and fixing of Ashirvad/ Ajay/ Astral Flowguard or equivalent CPVC Pipes and Fittings SDR 13.5 to meet the requirement of ASTM-D 2846 and are produced in CTS Copper Tube Sizes 1/2inches to 2inches for hot and cold water IS 15778:2007 including cost and conveyance of all materials to site, labour charges for fixing,complete for finished item of work at all floor levels. 15.90mm OD pipe at MGMH Petlaburj
9 | 273 | Supply and fixing of Ashirvad/ Ajay/ Astral Flowguard or equivalent CPVC Pipes and Fittings SDR 13.5 to meet the requirement of ASTM-D 2846 and are produced in CTS Copper Tube Sizes 1/2inches to 2inches for hot and cold water IS 15778:2007 including cost and conveyance of all materials to site, labour charges for fixing,complete for finished item of work at all floor levels. 22.20mm OD pipe at MGMH Petlaburj
10 | 274 | Supplying and fixing of SWR PVC pipes Prince/Sudhakar/Kisan/Supreme or any ISI brand 4 Kg/Sq.cm. and fixing all special such as plain bends, off sets, door bends, single junctions, double junctions as per site requirement, fixing with PVC clamps if necessary with required number of Bombay nails including cost and conveyance of all materials to site, labour charges, complete for finished item of work at all floor levels. APSS No. 1302 1319 and 1326 - 75mm dia at MGMH Petlaburj
11 | 275 | Supplying and fixing of SWR PVC pipes Prince/Sudhakar/Kisan/Supreme or any ISI brand 4 Kg/Sq.cm. and fixing all special such as plain bends, off sets, door bends, single junctions, double junctions as per site requirement, fixing with PVC clamps if necessary with required number of Bombay nails including cost and conveyance of all materials to site, labour charges, complete for finished item of work at all floor levels. APSS No. 1302 1319 and 1326- 110mm dia at MGMH Petlaburj
12 | 266 | Providing dadooing to walls with glazed full body porcelain wall tiles of size 300 x 600 mm with any type of design texture such as marble finish, wooden, bamboo, stone finishes etc., scratch less, stain free and thickness between 6-8 mm 1st quality conforming to IS:13711, IS:13712, IS:13630 Parts 1 to 15 of any colour and finish in all shades and designs with borders as approved by Engineer-in-Charge set over base coat of CM1:5 12 mm thick using screened sand with cement slurry of honey like consistency spread at the rate of 3.30 kgs per sqm and jointing with white cement paste mixed with pigment of matching shade to full depth, including cost of all materials like tiles, cement, sand and water etc., complete for finished item of work. 3rd Floor at MGMH Petlaburj
Toilet @ Record Room
|  | Long Wall | 1 | 2 | 1.79 |  | 2.1 | 7.518
|  | Short wall | 1 | 2 | 1.19 |  | 2.1 | 4.998
|  | Door Deduction | -1 | 1 | 0.8 |  | 1.92 | -1.536
|  | Ventilator Deduction | -1 | 1 | 0.6 |  | 0.15 | -0.09
|  | Toilet @ Counselling Rooms | [5 empty] | 0
|  | Long Wall | 1 | 2 | 1.8 |  | 2.1 | 7.56
|  | Short wall | 1 | 2 | 1.25 |  | 2.1 | 5.25
|  | Door Deduction | -1 | 1 | 0.8 |  | 1.92 | -1.536
|  | Ventilator Deduction | -1 | 1 | 0.6 |  | 0.1 | -0.06
|  | Toilet @ Change Rooms | [5 empty] | 0
|  | Long Wall | 1 | 2 | 1.78 |  | 2.1 | 7.476
|  | Short wall |  |  | 1.35 |  | 2.1 | 0
|  | Door Deduction | -1 | 1 | 0.8 |  | 1.92 | -1.536
|  | Ventilator Deduction | -1 | 1 | 0.6 |  | 0.1 | -0.06
|  | Toilet @ Anesthetist Room | [5 empty] | 0
|  | Long Wall | 1 | 2 | 1.78 |  | 2.1 | 7.476
|  | Short wall | 1 | 2 | 1.2 |  | 2.1 | 5.04
|  | Door Deduction | -1 | 1 | 0.8 |  | 1.92 | -1.536
|  | Ventilator Deduction | -1 | 1 | 0.6 |  | 0.08 | -0.048
|  | Toilet @ post Operative ward | [5 empty] | 0
|  | Long Wall | 1 | 2 | 1.78 |  | 2.1 | 7.476
|  | Short wall | 1 | 2 | 1.2 |  | 2.1 | 5.04
|  | Door Deduction | -1 | 1 | 0.8 |  | 1.92 | -1.536
|  | Ventilator Deduction | -1 | 1 | 0.6 |  | 0.08 | -0.048
|  | Toilet @ Semen Collection Room | [5 empty] | 0
|  | Long Wall | 1 | 2 | 1.78 |  | 2.1 | 7.476
|  | Short wall | 1 | 2 | 1.18 |  | 2.1 | 4.956
|  | Door Deduction | -1 | 1 | 0.8 |  | 1.92 | -1.536
|  | Ventilator Deduction | -1 | 1 | 0.6 |  | 0.08 | -0.048
[6 empty] | Total |  | 60.696 | Sqm
13 | 264 | Flooring with non-skid full body ceramic floor tiles of size 300mm x 300mm and thickness between 7 - 8mm 1st quality conforming to IS: 13711, IS: 13712, IS: 13630Part 1 to 15 of any colour and finish in all shades and designs as approved by Engineer-in-charge, set over base coat of cement mortar 1:8, 12mm thick using screened sand over CC bed already laid or RCC roof slab, including neat cement slurry of honey like consistency spread at the rate 3.3 Kgs per Sqm and jointed neatly with white cement paste to full depth mixed with pigment of matching shade, including cost of all materials like cement, screened sand , water and tiles etc., complete for finished item of work. TSSS No.701 and 707 at MGMH Petlaburj
|  | Toilet @ Record Room | 1 | 1 | 1.19 | 1.79 |  | 2.1301
|  | Toilet @ Counselling Rooms | 1 | 1 | 1.25 | 1.8 |  | 2.25
|  | Toilet @ Change Rooms | 1 | 1 | 1.35 | 1.78 |  | 2.403
|  | Column Deduction | -1 | 1 | 0.38 | 0.26 |  | -0.0988
|  | Toilet @ Anesthetist Room | 1 | 1 | 1.2 | 1.78 |  | 2.136
|  | Column Deduction | -1 | 1 | 0.31 | 0.22 |  | -0.0682
|  | Toilet @ post Operative ward | 1 | 1 | 1.2 | 1.78 |  | 2.136
|  | Toilet @ Semen Collection Room | 1 | 1 | 1.18 | 1.78 |  | 2.1004
|  | Column Deduction | -1 | 1 | 0.3 | 0.19 |  | -0.057
[6 empty] | Total |  | 12.9315 | Sqm
14 | 267 | Providing and applying Wall putty of White Cement or Polymer or Cement based of average 1 to 2 mm thickness over plastered surface to prepare the surface even and smooth after thoroughly brushing the surface to remove all dirt and remains of loose powdered materials, applying emery paper, Sand the surface, clean and wipe off loose dust, applying knifing paste filler by putty knife / muslin pad, air dry for 2 - 3 hrs, sand with 180 and 320 No., emery paper for the surface preparation including cost and conveyance of all materials to work site and all operational, incidental, labour charges, over heads and etc., complete for finished item of work in 3rd floor Internal walls. at MGMH Petlaburj
|  | Counseling Room -1 Long Walls | 1 | 2 | 3.1 |  | 3.45 | 21.39
|  | Counseling Room -1 Short Walls | 1 | 2 | 2.1 |  | 3.45 | 14.49
|  | Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
|  | Counseling Room -2 Long Walls | 1 | 2 | 3.16 |  | 3.45 | 21.804
|  | Counseling Room -2 Short Walls | 1 | 2 | 2.1 |  | 3.45 | 14.49
|  | Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
|  | Window Deduction(-) | -1 | 1 | 1.8 |  | 1.7 | -3.06
|  | Window Jam | 1 | 1 | 7 | 0.1 |  | 0.7
|  | Toilet at Counseling Room -2 Long Wall | 1 | 2 | 1.8 |  | 1.35 | 4.86
|  | Short Wall | 1 | 2 | 1.2 |  | 1.35 | 3.24
|  | Counseling Room 1,2 Corridor Long Wall | 1 | 2 | 4.5 |  | 3.45 | 31.05
|  | Short Wall | 1 | 1 | 1.2 |  | 3.45 | 4.14
|  | Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
|  | do | -1 | 1 | 0.8 |  | 2.1 | -1.68
|  | Door Jam | 1 | 1 | 5.2 | 0.1 |  | 0.52
|  | Staff Change Room Corridor Long Wall | 1 | 2 | 4.67 |  | 3.45 | 32.223
|  | Short Wall | 1 | 2 | 1.3 |  | 3.45 | 8.97
|  | Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
|  | do | -1 | 1 | 0.8 |  | 2.1 | -1.68
|  | Door Jam | 1 | 1 | 5.2 | 0.1 |  | 0.52
|  | Staff Change Room Toilet Long Wall | 1 | 2 | 1.78 |  | 1.35 | 4.806
|  | Short Wall | 1 | 2 | 1.35 |  | 1.35 | 3.645
|  | Patient Change Room Long Wall | 1 | 2 | 3.12 |  | 3.45 | 21.528
|  | Short Wall | 1 | 2 | 2.18 |  | 3.45 | 15.042
|  | Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
|  | Window Deduction(-) | -1 | 1 | 1.7 |  | 1.8 | -3.06
|  | Window Jam | 1 | 1 | 7 | 0.1 |  | 0.7
|  | Door Jam | 1 | 1 | 5.2 | 0.1 |  | 0
|  | Staff Change Room-1 Long Wall | 1 | 2 | 4.67 |  | 3.45 | 32.223
|  | Short Wall | 1 | 2 | 1.32 |  | 3.45 | 9.108
|  | Door Deduction(-) | -1 | 1 | 0.73 |  | 2.1 | -1.533
|  | Staff Change Room-2 Long wall | 1 | 2 | 2.2 |  | 3.45 | 15.18
|  | Short Wall | 1 | 2 | 1.48 |  | 3.45 | 10.212
|  | Door Deduction(-) | -1 | 1 | 0.75 |  | 2.1 | -1.575
|  | Anesthestist Room Corridor Long Walls | 1 | 2 | 4.65 |  | 1.35 | 12.555
|  | Short Wall | 1 | 1 | 1.2 |  | 1.35 | 1.62
|  | Anesthestist Room Long Walls | 1 | 2 | 3.17 |  | 3.45 | 21.873
|  | Short Wall | 1 | 2 | 2.27 |  | 3.45 | 15.663
|  | Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
|  | Embryologist Room Long Wall | 1 | 2 | 3.13 |  | 3.45 | 21.597
|  | Short Wall | 1 | 2 | 2.24 |  | 3.45 | 15.456
|  | Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
|  | Toilet At Embryologist Room Long Wall | 1 | 2 | 1.78 |  | 1.35 | 4.806
|  | Short Wall | 1 | 2 | 1.2 |  | 1.35 | 3.24
|  | Post Operative Wards Long Walls | 1 | 2 | 4.5 |  | 1.35 | 12.15
|  | Short Wall | 1 | 2 | 3.35 |  | 1.35 | 9.045
|  | Long Walls | 1 | 2 | 2.01 |  | 1.35 | 5.427
|  | Short Wall | 1 | 2 | 1.95 |  | 1.35 | 5.265
|  | Post Operative Wards Toilet Long Walls | 1 | 2 | 1.78 |  | 1.35 | 4.806
|  | Short Wall | 1 | 2 | 1.2 |  | 1.35 | 3.24
|  | Waiting Room Corridor Long Wall | 1 | 2 | 1.85 |  | 3.45 | 12.765
|  | Short Wall | 1 | 2 | 1.2 |  | 3.45 | 8.28
|  | Waiting Room Long Wall | 1 | 2 | 2.3 |  | 3.45 | 15.87
|  | Short Wall | 1 | 2 | 1.85 |  | 3.45 | 12.765
|  | Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
|  | Semen Collection Room Long Wall | 1 | 2 | 3.9 |  | 3.45 | 26.91
|  | Short Wall | 1 | 2 | 2.29 |  | 3.45 | 15.801
|  | Long Walls | 1 | 2 | 2 |  | 3.45 | 13.8
|  | Short Wall | 1 | 2 | 1.35 |  | 3.45 | 9.315
|  | Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
|  | do | -1 | 1 | 0.8 |  | 2.1 | -1.68
|  | Window Deduction(-) | -1 | 1 | 1.8 |  | 1.7 | -3.06
|  | Window Jam | 1 | 1 | 7 | 0.1 |  | 0.7
|  | Semen Collection Toilet Long Wall | 1 | 2 | 1.78 |  | 1.35 | 4.806
|  | Short Wall | 1 | 2 | 1.18 |  | 1.35 | 3.186
|  | Andrology Lab Long Walls | 1 | 1 | 6.34 |  | 3.45 | 21.873
|  | do | 1 | 1 | 2.93 |  | 3.45 | 10.1085
|  | Short Wall | 1 | 2 | 3.39 |  | 3.45 | 23.391
|  | Door Deduction(-) | -1 | 1 | 1.2 |  | 2.1 | -2.52
|  | Cryo Room Long Walls | 1 | 2 | 2.82 |  | 3.45 | 19.458
|  | Short Wall | 1 | 2 | 2.21 |  | 3.45 | 15.249
|  | Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
|  | Majot OT Long Walls | 1 | 2 | 6.23 |  | 3.45 | 42.987
|  | Short Wall | 1 | 2 | 5.03 |  | 3.45 | 34.707
|  | Columns Sides | 1 | 4 | 0.38 |  | 3.45 | 5.244
|  | Door Deduction(-) | -1 | 1 | 1.5 |  | 2.1 | -3.15
|  | Electrical Room Long Walls | 1 | 2 | 3.2 |  | 3.45 | 22.08
|  | Short Wall | 1 | 2 | 3.12 |  | 3.45 | 21.528
|  | Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
|  | Short Wall Out Side | 1 | 1 | 3.12 |  | 3.45 | 10.764
|  | Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
|  | UPS Room Long Walls | 1 | 2 | 3.2 |  | 3.45 | 22.08
|  | Short Wall | 1 | 2 | 3 |  | 3.45 | 20.7
|  | Door Deduction(-) | -1 | 1 | 1 |  | 2.6 | -2.6
|  | Window Deduction(-) | -1 | 1 | 1.8 |  | 1.7 | -3.06
|  | Window Jam | 1 | 1 | 7 | 0.1 |  | 0.7
|  | Manifold Room Long Wall | 1 | 2 | 6.34 |  | 3.45 | 43.746
|  | Short Walls | 1 | 2 | 3.14 |  | 3.45 | 21.666
|  | Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
|  | Window Deduction(-) | -1 | 1 | 1.8 |  | 1.7 | -3.06
|  | Window Jam | 1 | 1 | 7 | 0.1 |  | 0.7
|  | Clean Store Corridor Long Wall | 1 | 2 | 3.8 |  | 1.35 | 10.26
|  | Short Wall | 1 | 1 | 1.55 |  | 1.35 | 2.0925
|  | Clean Store Room Long Wall | 1 | 2 | 3.87 |  | 3.45 | 26.703
|  | Short Walls | 1 | 2 | 1.95 |  | 3.45 | 13.455
|  | Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
|  | Auto Clave Room Long Walls | 1 | 2 | 3.61 |  | 3.45 | 24.909
|  | Short Walls | 1 | 2 | 2.42 |  | 3.45 | 16.698
|  | Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
|  | Window Deduction(-) | -1 | 1 | 1.8 |  | 1.7 | -3.06
|  | Window Jam | 1 | 1 | 7 | 0.1 |  | 0.7
|  | Pre Operative Wards Long Walls | 1 | 2 | 6.4 |  | 1.35 | 17.28
|  | Short Walls | 1 | 2 | 3.3 |  | 1.35 | 8.91
|  | Window Deduction(-) | -1 | 1 | 1.8 |  | 0.5 | -0.9
|  | Window Jam | 1 | 1 | 7 | 0.1 |  | 0.7
|  | Sample Collection Corridor Long Wall | 1 | 2 | 3.89 |  | 1.35 | 10.503
|  | Short Walls | 1 | 1 | 1.35 |  | 1.35 | 1.8225
|  | Sample Collection Room Long Walls | 1 | 2 | 3.9 |  | 3.45 | 26.91
|  | Short Walls | 1 | 2 | 1.79 |  | 3.45 | 12.351
|  | Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
|  | Srore Room Long Walls | 1 | 2 | 3.57 |  | 3.45 | 24.633
|  | Short Walls | 1 | 2 | 2.34 |  | 3.45 | 16.146
|  | Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
|  | Window Deduction(-) | -1 | 1 | 1.8 |  | 1.7 | -3.06
|  | Window Jam | 1 | 1 | 7 | 0.1 |  | 0.7
|  | Ultra Sound Room Long Walls | 1 | 2 | 3 |  | 3.45 | 20.7
|  | Short Walls | 1 | 2 | 2.8 |  | 3.45 | 19.32
|  | Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
|  | 1.20 M Wide Corridor Long Walls | 1 | 2 | 4.47 |  | 3.45 | 30.843
|  | Short Walls | 1 | 2 | 1.32 |  | 3.45 | 9.108
|  | Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
|  | do | -1 | 1 | 0.8 |  | 2.1 | -1.68
|  | Dr Change Room Long Walls | 1 | 2 | 3.05 |  | 3.45 | 21.045
|  | Short Walls | 1 | 2 | 3 |  | 3.45 | 20.7
|  | Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
|  | Dr Change Room Partiton | 1 | 2 | 1.9 |  | 3.45 | 13.11
|  | Record Room Corridor Long Wall | 1 | 2 | 2.5 |  | 3.45 | 17.25
|  | Short Walls | 1 | 2 | 1.32 |  | 3.45 | 9.108
|  | Door Deduction(-) | -1 | 1 | 1.2 |  | 2.1 | -2.52
|  | do | -1 | 1 | 1 |  | 2.1 | -2.1
|  | Record Room Long Wall | 1 | 2 | 2.46 |  | 3.45 | 16.974
|  | Short Walls | 1 | 2 | 1.83 |  | 3.45 | 12.627
|  | Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
|  | Window Deduction(-) | -1 | 1 | 1.8 |  | 1.7 | -3.06
|  | Window Jam | 1 | 1 | 7 | 0.1 |  | 0.7
|  | Seniour Faculty Room Long Walls | 1 | 2 | 3.38 |  | 3.45 | 23.322
|  | Short Walls | 1 | 2 | 3.21 |  | 3.45 | 22.149
|  | Door Deduction(-) | -1 | 1 | 1.2 |  | 2.1 | -2.52
|  | Window Deduction(-) | -1 | 1 | 1.8 |  | 1.7 | -3.06
|  | Window Jam | 1 | 1 | 7 | 0.1 |  | 0.7
|  | Toilet at Record Room Lomg Walls | 1 | 2 | 1.79 |  | 1.35 | 4.833
|  | Short Walls | 1 | 2 | 1.19 |  | 1.35 | 3.213
|  | Waiting Area Long Walls | 1 | 2 | 6.32 |  | 3.45 | 43.608
|  | Short Walls | 1 | 1 | 3.1 |  | 3.45 | 10.695
|  | Door Deduction(-) | -1 | 2 | 1.5 |  | 2.1 | -6.3
|  | Door Jam | 1 | 2 | 5.1 | 0.23 |  | 2.346
|  | Reception Entry Long Walls | 1 | 2 | 3.37 |  | 3.45 | 23.253
|  | Short Walls | 1 | 2 | 2.9 |  | 3.45 | 20.01
|  | Door Deduction(-) | -1 | 1 | 1.5 |  | 2.1 | -3.15
|  | Door Jam | 1 | 1 | 5.7 | 0.23 |  | 1.311
|  | Reception Long Walls | 1 | 2 | 5.96 |  | 3.45 | 41.124
|  | Short Walls | 1 | 2 | 3.14 |  | 3.45 | 21.666
|  | Window Deduction(-) | -1 | 1 | 1.8 |  | 1.7 | -3.06
|  | Window Jam | 1 | 1 | 7 | 0.1 |  | 0.7
|  | Non Sterile Corridor Long Walls | 1 | 2 | 7.12 |  | 3.45 | 49.128
|  | Short Walls | 1 | 2 | 2.37 |  | 3.45 | 16.353
|  | Corridor Deductions(-) | -1 | 3 | 1.2 |  | 3 | -10.8
|  | Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
|  | Access Control Door | 1 | 2 | 2.37 |  | 3.45 | 16.353
|  | Door Deduction(-) | -1 | 1 | 1.5 |  | 2.1 | -3.15
|  | Door Jam | 1 | 1 | 5.7 | 0.23 |  | 1.311
|  | Semi- Sterile Corridor Long Walls | 1 | 2 | 11.2 |  | 1.35 | 30.24
|  | Sterile Corridor Long Walls | 1 | 2 | 10.89 |  | 1.35 | 29.403
|  | Emergency Exit Door | 1 | 1 | 2.37 |  | 1.35 | 3.1995
|  | do | 1 | 1 | 2.37 |  | 3.45 | 8.1765
|  | Door Deduction(-) | -1 | 1 | 1.5 |  | 2.1 | -3.15
|  | Door Jam | 1 | 1 | 5.7 | 0.23 |  | 1.311
|  | Manifold Room Corridor Long Walls | 1 | 2 | 3.14 |  | 1.35 | 8.478
[6 empty] | Total |  | 1528.4165 | Sqm
15 | 265 | Providing and fixing in true horizontal level 14 mm - Mineral Fiber sheet 595 x 595 Square / Tegular Fissura fine model edge tiles with a Humidity Resistance of 90percentage RH, Average NRC 0.50, Light Reflectance greater than80percentage, Thermal Conductivity equal to 0.052 to 0.057 w/mk, Fire Performance Class 0/Class 1 using hot dipped Galvanized Steel section exposed surface with pre-coated capping, main Tee of size 24 x 32 mm at every 1200 mm c/c maximum and rotary stitched cross tee of size 24 x 27 mm at every 600 mm c/c and sub-cross tee of size 24 mm x 25 mm at 1200 mm c/c and wall angle of size 19 x 19 mm fixed to periphery of the wall and the above grid is suspended at every 1200 mm c/c in both directions using 2.0 mm thick pre-straightened GI Wire including cost and conveyance of all materials and labour charges such as cutting , fixing of standing of frame work exposing roof making etc., complete for finished item of work in 3rd floor. at MGMH Petlaburj
|  | Waiting Area @ Entrance | 1 | 1 | 3.1 | 6.32 |  | 19.592
|  | Reception | 1 | 1 | 3.14 | 5.96 |  | 18.7144
|  | Infront of Reception | 1 | 1 | 3.37 | 2.9 |  | 9.773
|  | Column Deduction(-) | -1 | 1 | 0.58 | 0.35 |  | -0.203
|  | Counselling rooms Corridar | 1 | 1 | 1.25 | 4.5 |  | 5.625
|  | Counselling room -1 | 1 | 1 | 2.1 | 3.1 |  | 6.51
|  | Counselling room-2 | 1 | 1 | 2.1 | 3.16 |  | 6.636
|  | Corridar @ Staff Change rooms | 1 | 1 | 1.32 | 4.67 |  | 6.1644
|  | Column Deduction(-) | -1 | 1 | 0.25 | 0.6 |  | -0.15
|  | Staff Change room-1 | 1 | 1 | 2.18 | 1.63 |  | 3.5534
|  | Staff Change room-2 | 1 | 1 | 2.2 | 1.48 |  | 3.256
|  | Column Deduction(-) | -1 | 1 | 0.47 | 0.25 |  | -0.1175
|  | Patient Change room | 1 | 1 | 2.18 | 3.12 |  | 6.8016
|  | Corridar Infront Senior Faculty room | 1 | 1 | 2.5 | 1.32 |  | 3.3
|  | Corridar infront Toilet@Record Room | 1 | 1 | 1.32 | 4.47 |  | 5.9004
|  | Sr Faculty Room | 1 | 1 | 3.38 | 3.21 |  | 10.8498
|  | Column Deduction(-) | -1 | 1 | 0.4 | 0.2 |  | -0.08
|  | Record Room | 1 | 1 | 2.46 | 1.83 |  | 4.5018
|  | Dr Change Rooms | 1 | 1 | 3 | 3.05 |  | 9.15
|  | Ultra Sound Room | 1 | 1 | 2.8 | 3 |  | 8.4
|  | Non Sterile Corridar | 1 | 1 | 7.12 | 2.37 |  | 16.8744
|  | Corridar @ Embryologist Room | 1 | 1 | 1.2 | 4.65 |  | 5.58
|  | Column Deduction(-) | -1 | 1 | 0.2 | 0.5 |  | -0.1
|  | Embryologist room | 1 | 1 | 2.24 | 3.13 |  | 7.0112
|  | Anesthetist Room | 1 | 1 | 2.27 | 3.17 |  | 7.1959
|  | Corridar Infront of Store | 1 | 1 | 1.65 | 3.89 |  | 6.4185
|  | Column Deduction(-) | -1 | 1 | 0.2 | 0.44 |  | -0.088
|  | Store room | 1 | 1 | 3.57 | 2.34 |  | 8.3538
|  | Column Deduction(-) | -1 | 1 | 0.3 | 0.22 |  | -0.066
|  | Sample Collection room | 1 | 1 | 1.79 | 3.9 |  | 6.981
|  | pre Operative Ward | 1 | 1 | 3.3 | 6.4 |  | 21.12
|  | Post Operative Ward | 1 | 1 | 3.35 | 4.51 |  | 15.1085
|  | infront of toilet in post op ward | 1 | 1 | 2.01 | 1.95 |  | 3.9195
|  | Corridar infront autoclave room | 1 | 1 | 1.55 | 3.88 |  | 6.014
|  | Column Deduction(-) | 1 | 1 | 0.42 | -0.22 |  | -0.0924
|  | Autoclave room | 1 | 1 | 3.61 | 2.42 |  | 8.7362
|  | Column Deduction(-) | -1 | 1 | 0.32 | 0.23 |  | -0.0736
|  | Clean Store | 1 | 1 | 1.95 | 3.87 |  | 7.5465
|  | Semen Collection room | 1 | 1 | 2.29 | 3.9 |  | 8.931
|  | infront toilet in semen collection room | 1 | 1 | 1.34 | 2 |  | 2.68
|  | Waiting Area @ Semen collection room | 1 | 1 | 2.3 | 1.85 |  | 4.255
|  | Corridar infront semen collection room | 1 | 1 | 1.2 | 1.85 |  | 2.22
|  | Semi Sterile Corridar | 1 | 1 | 11.22 | 2.36 |  | 26.4792
|  | At Air Shower | 1 | 1 | 3.35 | 0.58 |  | 1.943
|  | Sterile Corridar | 1 | 1 | 10.89 | 2.39 |  | 26.0271
|  | Andrology Lab | 1 | 1 | 3.37 | 6.34 |  | 21.3658
|  | Andrology Lab beside Cryo room | 1 | 1 | 2.93 | 2.33 |  | 6.8269
|  | Column Deduction(-) | -1 | 1 | 0.38 | 0.28 |  | -0.1064
|  | Cryo Room | 1 | 1 | 2.21 | 2.82 |  | 6.2322
|  | Major OT | 1 | 1 | 5.02 | 6.23 |  | 31.2746
|  | Column Deduction(-) | -1 | 1 | 0.38 | 0.3 |  | -0.114
|  | Manifold Room | 1 | 1 | 3.14 | 6.34 |  | 19.9076
|  | Column Deduction(-) | -2 | 1 | 0.34 | 0.13 |  | -0.0884
|  | Electrical Room | 1 | 1 | 3.2 | 3.12 |  | 9.984
|  | Column Deduction(-) | -1 | 1 | 0.33 | 0.18 |  | -0.0594
|  | UPS Room | 1 | 1 | 3.2 | 3 |  | 9.6
|  | Column Deduction(-) | -1 | 1 | 0.33 | 0.18 |  | -0.0594
|  | Toilet @ record Room | 1 | 1 | 1.19 | 1.79 |  | 2.1301
|  | Toilet @ Counselling Rooms | 1 | 1 | 1.25 | 1.8 |  | 2.25
|  | Toilet @ Change rooms | 1 | 1 | 1.35 | 1.78 |  | 2.403
|  | Column Deduction(-) | -1 | 1 | 0.38 | 0.26 |  | -0.0988
|  | Toilet @ Anesthetist Room | 1 | 1 | 1.2 | 1.78 |  | 2.136
|  | Column Deduction(-) | -1 | 1 | 0.31 | 0.22 |  | -0.0682
|  | Toilet in Post operative ward | 1 | 1 | 1.2 | 1.78 |  | 2.136
|  | Toilet in semen Collection Room | 1 | 1 | 1.18 | 1.78 |  | 2.1004
|  | Column Deduction(-) | -1 | 1 | 0.3 | 0.19 |  | -0.057
[6 empty] | Total |  | 438.8471 | Sqm
16 | 269 | Supply and application of one coat water based cement primer of interior grade I and two coats of water based PU paint having anti bacterial applications content less than 50 grams/litre for internal walls including cost and conveyance of all materials to site, sales and other taxes, incidental, operational and all labour charges etc., and complete for finished item of work in 3rd floor. at MGMH Petlaburj
|  | Counseling Room -1 Long Walls | 1 | 2 | 3.1 |  | 3.45 | 21.39
|  | Counseling Room -1 Short Walls | 1 | 2 | 2.1 |  | 3.45 | 14.49
|  | Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
|  | Counseling Room -2 Long Walls | 1 | 2 | 3.16 |  | 3.45 | 21.804
|  | Counseling Room -2 Short Walls | 1 | 2 | 2.1 |  | 3.45 | 14.49
|  | Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
|  | Window Deduction(-) | -1 | 1 | 1.8 |  | 1.7 | -3.06
|  | Window Jam | 1 | 1 | 7 | 0.1 |  | 0.7
|  | Toilet at Counseling Room -2 Long Wall | 1 | 2 | 1.8 |  | 1.35 | 4.86
|  | Short Wall | 1 | 2 | 1.2 |  | 1.35 | 3.24
|  | Counseling Room 1,2 Corridor Long Wall | 1 | 2 | 4.5 |  | 3.45 | 31.05
|  | Short Wall | 1 | 1 | 1.2 |  | 3.45 | 4.14
|  | Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
|  | do | -1 | 1 | 0.8 |  | 2.1 | -1.68
|  | Door Jam | 1 | 1 | 5.2 | 0.1 |  | 0.52
|  | Staff Change Room Corridor Long Wall | 1 | 2 | 4.67 |  | 3.45 | 32.223
|  | Short Wall | 1 | 2 | 1.3 |  | 3.45 | 8.97
|  | Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
|  | do | -1 | 1 | 0.8 |  | 2.1 | -1.68
|  | Door Jam | 1 | 1 | 5.2 | 0.1 |  | 0.52
|  | Staff Change Room Toilet Long Wall | 1 | 2 | 1.78 |  | 1.35 | 4.806
|  | Short Wall | 1 | 2 | 1.35 |  | 1.35 | 3.645
|  | Patient Change Room Long Wall | 1 | 2 | 3.12 |  | 3.45 | 21.528
|  | Short Wall | 1 | 2 | 2.18 |  | 3.45 | 15.042
|  | Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
|  | Window Deduction(-) | -1 | 1 | 1.7 |  | 1.8 | -3.06
|  | Window Jam | 1 | 1 | 7 | 0.1 |  | 0.7
|  | Door Jam | 1 | 1 | 5.2 | 0.1 |  | 0
|  | Staff Change Room-1 Long Wall | 1 | 2 | 4.67 |  | 3.45 | 32.223
|  | Short Wall | 1 | 2 | 1.32 |  | 3.45 | 9.108
|  | Door Deduction(-) | -1 | 1 | 0.73 |  | 2.1 | -1.533
|  | Staff Change Room-2 Long wall | 1 | 2 | 2.2 |  | 3.45 | 15.18
|  | Short Wall | 1 | 2 | 1.48 |  | 3.45 | 10.212
|  | Door Deduction(-) | -1 | 1 | 0.75 |  | 2.1 | -1.575
|  | Anesthestist Room Corridor Long Walls | 1 | 2 | 4.65 |  | 1.35 | 12.555
|  | Short Wall | 1 | 1 | 1.2 |  | 1.35 | 1.62
|  | Anesthestist Room Long Walls | 1 | 2 | 3.17 |  | 3.45 | 21.873
|  | Short Wall | 1 | 2 | 2.27 |  | 3.45 | 15.663
|  | Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
|  | Embryologist Room Long Wall | 1 | 2 | 3.13 |  | 3.45 | 21.597
|  | Short Wall | 1 | 2 | 2.24 |  | 3.45 | 15.456
|  | Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
|  | Toilet At Embryologist Room Long Wall | 1 | 2 | 1.78 |  | 1.35 | 4.806
|  | Short Wall | 1 | 2 | 1.2 |  | 1.35 | 3.24
|  | Post Operative Wards Long Walls | 1 | 2 | 4.5 |  | 1.35 | 12.15
|  | Short Wall | 1 | 2 | 3.35 |  | 1.35 | 9.045
|  | Long Walls | 1 | 2 | 2.01 |  | 1.35 | 5.427
|  | Short Wall | 1 | 2 | 1.95 |  | 1.35 | 5.265
|  | Post Operative Wards Toilet Long Walls | 1 | 2 | 1.78 |  | 1.35 | 4.806
|  | Short Wall | 1 | 2 | 1.2 |  | 1.35 | 3.24
|  | Waiting Room Corridor Long Wall | 1 | 2 | 1.85 |  | 3.45 | 12.765
|  | Short Wall | 1 | 2 | 1.2 |  | 3.45 | 8.28
|  | Waiting Room Long Wall | 1 | 2 | 2.3 |  | 3.45 | 15.87
|  | Short Wall | 1 | 2 | 1.85 |  | 3.45 | 12.765
|  | Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
|  | Semen Collection Room Long Wall | 1 | 2 | 3.9 |  | 3.45 | 26.91
|  | Short Wall | 1 | 2 | 2.29 |  | 3.45 | 15.801
|  | Long Walls | 1 | 2 | 2 |  | 3.45 | 13.8
|  | Short Wall | 1 | 2 | 1.35 |  | 3.45 | 9.315
|  | Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
|  | do | -1 | 1 | 0.8 |  | 2.1 | -1.68
|  | Window Deduction(-) | -1 | 1 | 1.8 |  | 1.7 | -3.06
|  | Window Jam | 1 | 1 | 7 | 0.1 |  | 0.7
|  | Semen Collection Toilet Long Wall | 1 | 2 | 1.78 |  | 1.35 | 4.806
|  | Short Wall | 1 | 2 | 1.18 |  | 1.35 | 3.186
|  | Andrology Lab Long Walls | 1 | 1 | 6.34 |  | 3.45 | 21.873
|  | do | 1 | 1 | 2.93 |  | 3.45 | 10.1085
|  | Short Wall | 1 | 2 | 3.39 |  | 3.45 | 23.391
|  | Door Deduction(-) | -1 | 1 | 1.2 |  | 2.1 | -2.52
|  | Cryo Room Long Walls | 1 | 2 | 2.82 |  | 3.45 | 19.458
|  | Short Wall | 1 | 2 | 2.21 |  | 3.45 | 15.249
|  | Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
|  | Majot OT Long Walls | 1 | 2 | 6.23 |  | 3.45 | 42.987
|  | Short Wall | 1 | 2 | 5.03 |  | 3.45 | 34.707
|  | Columns Sides | 1 | 4 | 0.38 |  | 3.45 | 5.244
|  | Door Deduction(-) | -1 | 1 | 1.5 |  | 2.1 | -3.15
|  | Electrical Room Long Walls | 1 | 2 | 3.2 |  | 3.45 | 22.08
|  | Short Wall | 1 | 2 | 3.12 |  | 3.45 | 21.528
|  | Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
|  | Short Wall Out Side | 1 | 1 | 3.12 |  | 3.45 | 10.764
|  | Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
|  | UPS Room Long Walls | 1 | 2 | 3.2 |  | 3.45 | 22.08
|  | Short Wall | 1 | 2 | 3 |  | 3.45 | 20.7
|  | Door Deduction(-) | -1 | 1 | 1 |  | 2.6 | -2.6
|  | Window Deduction(-) | -1 | 1 | 1.8 |  | 1.7 | -3.06
|  | Window Jam | 1 | 1 | 7 | 0.1 |  | 0.7
|  | Manifold Room Long Wall | 1 | 2 | 6.34 |  | 3.45 | 43.746
|  | Short Walls | 1 | 2 | 3.14 |  | 3.45 | 21.666
|  | Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
|  | Window Deduction(-) | -1 | 1 | 1.8 |  | 1.7 | -3.06
|  | Window Jam | 1 | 1 | 7 | 0.1 |  | 0.7
|  | Clean Store Corridor Long Wall | 1 | 2 | 3.8 |  | 1.35 | 10.26
|  | Short Wall | 1 | 1 | 1.55 |  | 1.35 | 2.0925
|  | Clean Store Room Long Wall | 1 | 2 | 3.87 |  | 3.45 | 26.703
|  | Short Walls | 1 | 2 | 1.95 |  | 3.45 | 13.455
|  | Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
|  | Auto Clave Room Long Walls | 1 | 2 | 3.61 |  | 3.45 | 24.909
|  | Short Walls | 1 | 2 | 2.42 |  | 3.45 | 16.698
|  | Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
|  | Window Deduction(-) | -1 | 1 | 1.8 |  | 1.7 | -3.06
|  | Window Jam | 1 | 1 | 7 | 0.1 |  | 0.7
|  | Pre Operative Wards Long Walls | 1 | 2 | 6.4 |  | 1.35 | 17.28
|  | Short Walls | 1 | 2 | 3.3 |  | 1.35 | 8.91
|  | Window Deduction(-) | -1 | 1 | 1.8 |  | 0.5 | -0.9
|  | Window Jam | 1 | 1 | 7 | 0.1 |  | 0.7
|  | Sample Collection Corridor Long Wall | 1 | 2 | 3.89 |  | 1.35 | 10.503
|  | Short Walls | 1 | 1 | 1.35 |  | 1.35 | 1.8225
|  | Sample Collection Room Long Walls | 1 | 2 | 3.9 |  | 3.45 | 26.91
|  | Short Walls | 1 | 2 | 1.79 |  | 3.45 | 12.351
|  | Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
|  | Srore Room Long Walls | 1 | 2 | 3.57 |  | 3.45 | 24.633
|  | Short Walls | 1 | 2 | 2.34 |  | 3.45 | 16.146
|  | Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
|  | Window Deduction(-) | -1 | 1 | 1.8 |  | 1.7 | -3.06
|  | Window Jam | 1 | 1 | 7 | 0.1 |  | 0.7
|  | Ultra Sound Room Long Walls | 1 | 2 | 3 |  | 3.45 | 20.7
|  | Short Walls | 1 | 2 | 2.8 |  | 3.45 | 19.32
|  | Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
|  | 1.20 M Wide Corridor Long Walls | 1 | 2 | 4.47 |  | 3.45 | 30.843
|  | Short Walls | 1 | 2 | 1.32 |  | 3.45 | 9.108
|  | Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
|  | do | -1 | 1 | 0.8 |  | 2.1 | -1.68
|  | Dr Change Room Long Walls | 1 | 2 | 3.05 |  | 3.45 | 21.045
|  | Short Walls | 1 | 2 | 3 |  | 3.45 | 20.7
|  | Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
|  | Dr Change Room Partiton | 1 | 2 | 1.9 |  | 3.45 | 13.11
|  | Record Room Corridor Long Wall | 1 | 2 | 2.5 |  | 3.45 | 17.25
|  | Short Walls | 1 | 2 | 1.32 |  | 3.45 | 9.108
|  | Door Deduction(-) | -1 | 1 | 1.2 |  | 2.1 | -2.52
|  | do | -1 | 1 | 1 |  | 2.1 | -2.1
|  | Record Room Long Wall | 1 | 2 | 2.46 |  | 3.45 | 16.974
|  | Short Walls | 1 | 2 | 1.83 |  | 3.45 | 12.627
|  | Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
|  | Window Deduction(-) | -1 | 1 | 1.8 |  | 1.7 | -3.06
|  | Window Jam | 1 | 1 | 7 | 0.1 |  | 0.7
|  | Seniour Faculty Room Long Walls | 1 | 2 | 3.38 |  | 3.45 | 23.322
|  | Short Walls | 1 | 2 | 3.21 |  | 3.45 | 22.149
|  | Door Deduction(-) | -1 | 1 | 1.2 |  | 2.1 | -2.52
|  | Window Deduction(-) | -1 | 1 | 1.8 |  | 1.7 | -3.06
|  | Window Jam | 1 | 1 | 7 | 0.1 |  | 0.7
|  | Toilet at Record Room Lomg Walls | 1 | 2 | 1.79 |  | 1.35 | 4.833
|  | Short Walls | 1 | 2 | 1.19 |  | 1.35 | 3.213
|  | Waiting Area Long Walls | 1 | 2 | 6.32 |  | 3.45 | 43.608
|  | Short Walls | 1 | 1 | 3.1 |  | 3.45 | 10.695
|  | Door Deduction(-) | -1 | 2 | 1.5 |  | 2.1 | -6.3
|  | Door Jam | 1 | 2 | 5.1 | 0.23 |  | 2.346
|  | Reception Entry Long Walls | 1 | 2 | 3.37 |  | 3.45 | 23.253
|  | Short Walls | 1 | 2 | 2.9 |  | 3.45 | 20.01
|  | Door Deduction(-) | -1 | 1 | 1.5 |  | 2.1 | -3.15
|  | Door Jam | 1 | 1 | 5.7 | 0.23 |  | 1.311
|  | Reception Long Walls | 1 | 2 | 5.96 |  | 3.45 | 41.124
|  | Short Walls | 1 | 2 | 3.14 |  | 3.45 | 21.666
|  | Window Deduction(-) | -1 | 1 | 1.8 |  | 1.7 | -3.06
|  | Window Jam | 1 | 1 | 7 | 0.1 |  | 0.7
|  | Non Sterile Corridor Long Walls | 1 | 2 | 7.12 |  | 3.45 | 49.128
|  | Short Walls | 1 | 2 | 2.37 |  | 3.45 | 16.353
|  | Corridor Deductions(-) | -1 | 3 | 1.2 |  | 3 | -10.8
|  | Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
|  | Access Control Door | 1 | 2 | 2.37 |  | 3.45 | 16.353
|  | Door Deduction(-) | -1 | 1 | 1.5 |  | 2.1 | -3.15
|  | Door Jam | 1 | 1 | 5.7 | 0.23 |  | 1.311
|  | Semi- Sterile Corridor Long Walls | 1 | 2 | 11.2 |  | 1.35 | 30.24
|  | Sterile Corridor Long Walls | 1 | 2 | 10.89 |  | 1.35 | 29.403
|  | Emergency Exit Door | 1 | 1 | 2.37 |  | 1.35 | 3.1995
|  | do | 1 | 1 | 2.37 |  | 3.45 | 8.1765
|  | Door Deduction(-) | -1 | 1 | 1.5 |  | 2.1 | -3.15
|  | Door Jam | 1 | 1 | 5.7 | 0.23 |  | 1.311
|  | Manifold Room Corridor Long Walls | 1 | 2 | 3.14 |  | 1.35 | 8.478
[6 empty] | Total |  | 1528.4165 | Sqm
17 | Sup | Supply and Installation change room Cubicles at Petlaburj Hospital GENERAL SPECIFICATIONS: Thickness of compact Laminate:12mm Thick Colour OF HPL Boards,In Single Colour,Size of Cubicle As per DWG, Door Size For Normal Cubicles AS per DWG Overall Height of Cubicle,2105mm Including bottom gap of 100mm,Accessories , Manufacturers standard makes of aluminium , SS Accessories .a Aluminium H Top Rail b. SS Hinges c. SS privacy Thumb turn occupancy indicator d.SS coat hook e. SS Door knob f. Aluminium U Channel g.Aluminium Door Stopper Channel h. Runner lining i.SS Screw And PVC Wall Plugs
|  | Patient Change room | 1 | 1 | 2.18 |  | 2.1 | 4.578
|  | Dr.Change room-1 | 1 | 1 | 1.53 |  | 2.24 | 3.4272
|  | Dr.Change room-2 | 1 | 1 | 1.46 |  | 2.24 | 3.2704
[6 empty] | Total |  | 11.2756 | Sqm
18 | 277 | Supplying and fixing of 4inches 101.6mm multi floor trap with jali - UPVC/SWR pipe fittings as per site requirements with standard practice for all floors including cost and conveyance of all materials to site, labour charges ,etc., complete for finished item of work. at MGMH Petlaburj
|  | Record Room Toilet | 1 | 1 |  |  |  | 1
|  | Counseling Room Toilet | 1 | 1 |  |  |  | 1
|  | Patient Change Room Toilet | 1 | 1 |  |  |  | 1
|  | Embryologist Room Toilet | 1 | 1 |  |  |  | 1
|  | Post Operative Wards Toilet | 1 | 1 |  |  |  | 1
|  | Semen Collection Room Toilet | 1 | 1 |  |  |  | 1
|  | Scrub | 1 | 1 |  |  |  | 1
[6 empty] | Total |  | 7 | Nos
19 | 278 | Supplying and fixing Indian make Flat Back Wash Hand Basin 1st quality conforming to IS:2556-Part-4:1972 of size 550mm x 400mm with 32 mm nominal size C.P. Fitting with parallel pipe thread conforming to IS:2963- 1979 and fitted with 15 mm nominal bore Chromium Plated Pillar Tap of 1st quality Indian make heavy duty complete with standard CI brackets including wooden blocks ,1 No.12.70mm PVC connection with brass union nuts CP coated , angle stop cock 12.70mm dia. first quality Indian make heavy duty, 30mm dia. PVC flexible waste pipe 914.4mm length of 1st quality including cost and conveyance of all materials to site, labour charges , for finished item of work at MGMH Petlaburj
|  | Record Room Toilet | 1 | 1 |  |  |  | 1
|  | Counseling Room Toilet | 1 | 1 |  |  |  | 1
|  | Patient Change Room Toilet | 1 | 1 |  |  |  | 1
|  | Embryologist Room Toilet | 1 | 1 |  |  |  | 1
|  | Post Operative Wards Toilet | 1 | 1 |  |  |  | 1
|  | Semen Collection Room Toilet | 1 | 1 |  |  |  | 1
[6 empty] | Total |  | 6 | Nos
20 | 279 | Supply, Installation and commissioning approved make floor mounted Anglo Indian wash down EWC conforming to IS:2556 Part 8-2004 suit with P or S trap with dual flush porcelain cistern fixed on wash down EWC with all internal parts of dual flush cistern, ultra solid seat cover of approved make with rubber buffer and cap and 15 mm angle stop cock and 450 mm long PVC inter connection pipe wall flanges all of approved make etc. complete for finished item of work in all respects: TBSP-E.II-03 at MGMH Petlaburj
|  | Record Room Toilet | 1 | 1 |  |  |  | 1
|  | Counseling Room Toilet | 1 | 1 |  |  |  | 1
|  | Patient Change Room Toilet | 1 | 1 |  |  |  | 1
|  | Embryologist Room Toilet | 1 | 1 |  |  |  | 1
|  | Post Operative Wards Toilet | 1 | 1 |  |  |  | 1
|  | Semen Collection Room Toilet | 1 | 1 |  |  |  | 1
[6 empty] | Total |  | 6 | Nos
21 | 280 | Supplying and fixing Chromium plated finish brass body quarter turn Bibcock cum Health Faucet with 1m long tube and wall hook with necessary fittings etc., complete including cost and conveyance of all materials, labour charges, complete for finished item of work in all floors. at MGMH Petlaburj
|  | Record Room Toilet | 1 | 1 |  |  |  | 1
|  | Counseling Room Toilet | 1 | 1 |  |  |  | 1
|  | Patient Change Room Toilet | 1 | 1 |  |  |  | 1
|  | Embryologist Room Toilet | 1 | 1 |  |  |  | 1
|  | Post Operative Wards Toilet | 1 | 1 |  |  |  | 1
|  | Semen Collection Room Toilet | 1 | 1 |  |  |  | 1
[6 empty] | Total |  | 6 | Nos
22 | 281 | Supplying and fixing CP finish brass soap dish of approved make ISI quality including cost and conveyance of all materials, labour charges for fixing, for finished item of work in all floors at MGMH Petlaburj
|  | Record Room Toilet | 1 | 1 |  |  |  | 1
|  | Counseling Room Toilet | 1 | 1 |  |  |  | 1
|  | Patient Change Room Toilet | 1 | 1 |  |  |  | 1
|  | Embryologist Room Toilet | 1 | 1 |  |  |  | 1
|  | Post Operative Wards Toilet | 1 | 1 |  |  |  | 1
|  | Semen Collection Room Toilet | 1 | 1 |  |  |  | 1
[6 empty] | Total |  | 6 | Nos
23 | 282 | Supplying and fixing TV shape mirror with plastic frame of size 609.6mm x 457.2mm, plywood back with NP screws 1st quality including cost and conveyance of all materials, labour charges, for finished item of work in all floors. at MGMH Petlaburj
|  | Record Room Toilet | 1 | 1 |  |  |  | 1
|  | Counseling Room Toilet | 1 | 1 |  |  |  | 1
|  | Patient Change Room Toilet | 1 | 1 |  |  |  | 1
|  | Embryologist Room Toilet | 1 | 1 |  |  |  | 1
|  | Post Operative Wards Toilet | 1 | 1 |  |  |  | 1
|  | Semen Collection Room Toilet | 1 | 1 |  |  |  | 1
[6 empty] | Total |  | 6 | Nos
24 | 283 | Supplying and fixing of CP finish brass wall mounted towel ring at MGMH Petlaburj
|  | Record Room Toilet | 1 | 1 |  |  |  | 1
|  | Counseling Room Toilet | 1 | 1 |  |  |  | 1
|  | Patient Change Room Toilet | 1 | 1 |  |  |  | 1
|  | Embryologist Room Toilet | 1 | 1 |  |  |  | 1
|  | Post Operative Wards Toilet | 1 | 1 |  |  |  | 1
|  | Semen Collection Room Toilet | 1 | 1 |  |  |  | 1
[6 empty] | Total |  | 6 | Nos
25 | 284 | Supplying and fixing 15 mm brass body CP finish self closing tap push type conforming to IS 1711 as approved by the Engineer-In-Charge including cost and conveyance of all materials, labour charges, complete for finished item of work in all floors. at MGMH Petlaburj
|  | Record Room Toilet | 1 | 1 |  |  |  | 1
|  | Counseling Room Toilet | 1 | 1 |  |  |  | 1
|  | Patient Change Room Toilet | 1 | 1 |  |  |  | 1
|  | Embryologist Room Toilet | 1 | 1 |  |  |  | 1
|  | Post Operative Wards Toilet | 1 | 1 |  |  |  | 1
|  | Semen Collection Room Toilet | 1 | 1 |  |  |  | 1
[6 empty] | Total |  | 6 | Nos
26 | 290 | Providing, laying of scratch proof PVC/Vinyl flooring of 2mm thickness with proper welded joints air tight, along with leveling compound to match the existing flooring levels as per engineer in charge instructions. Sub floor preparation with self leveling compound. After the sub floor preparation, it should be suitable for ESD flooring. Rate inclusive of sifting of material and labour charges. at MGMH Petlaburj
|  | Major OT | 1 | 1 | 5.02 | 6.23 |  | 31.2746
|  | Column Deduction | -1 | 2 | 0.38 | 0.3 |  | -0.228
|  | Andrology Lab | 1 | 1 | 3.37 | 6.34 |  | 21.3658
|  | Andrology Lab beside Cryo Room | 1 | 1 | 2.93 | 2.33 |  | 6.8269
|  | Column Deduction | -1 | 1 | 0.38 | 0.28 |  | -0.1064
|  | Cryo Room | 1 | 1 | 2.21 | 2.82 |  | 6.2322
|  | IVF OT | 1 | 1 | 5.66 | 6.1 |  | 34.526
|  | Column Deduction | -1 | 2 | 0.6 | 0.35 |  | -0.42
|  | Embryology Lab | 1 | 1 | 4.565 | 6.126 |  | 27.9652
|  | Column Deduction | -1 | 1 | 0.6 | 0.35 |  | -0.21
|  | Sterile Corridar | 1 | 1 | 11.221 | 2.39 |  | 26.8182
|  | At Scrub Area | 1 | 1 | 1.95 | 0.58 |  | 1.131
|  | At Air Shower Backside | 1 | 1 | 2.901 | 0.3 |  | 0.8703
|  | Beside Air Shower | 1 | 1 | 1.14 | 1 |  | 1.14
[6 empty] | Total |  | 157.1858 | Sqm
27 | 356 | SITC of Factory fabricated and boxed ducting using Aluminium Sheets / coils, should be fabricated as per SMACNA, galvanised hardware and supports, silicon sealant at all longitudinal joints, Galvanized /GI Electroplated iron angle flanges for all the joints, bracing angles and minimum 5mm thick neoprene rubber gasket.- Duct pressure testing at 75mm to be carried out before insulatiting the duct. pressure testing to be done as per SMACNA. Procedure to be approved by consultant. 20G - 1.0 mm Thick at MGMH Petlaburj
|  | Supply Duct Elbow 900 x 400 mm Terrus | 1 | 1 | 1.2 | 2.6 |  | 3.12
|  | Elbow 900 x 400 mm Turrus | 1 | 1 | 2.1 | 2.6 |  | 5.46
|  | Straight 900 400 mm Terrus | 1 | 1 | 0.7 | 2.6 |  | 1.82
|  | Heater Straight 900 x 400 mm Teerus | 1 | 1 | 0.7 | 2.6 |  | 1.82
|  | Fire Damper Straight 900 x 400 mm | 1 | 1 | 0.35 | 2.6 |  | 0.91
|  | Y Piece 600 x 400 mm Terrus | 1 | 2 | 0.7 | 2 |  | 2.8
|  | Return Duct Elbow 900 x400 Terrus | 1 | 1 | 1.5 | 2.6 |  | 3.9
|  | Straight 900 x 400 mm Terrus | 1 | 1 | 0.25 | 2.6 |  | 0.65
|  | Y Piece 500 x 400 mm Terrus | 1 | 1 | 0.8 | 1.8 |  | 1.44
|  | Y Piece 600 x 400 mm Terrus | 1 | 1 | 1.2 | 2 |  | 2.4
|  | Taper 500 x 400 x 450 x 300 mm Terrus | 1 | 1 | 0.4 | 1.65 |  | 0.66
[6 empty] | Total |  | 24.98 | Sqm
28 | 357 | SITC of Factory fabricated and boxed ducting using Aluminium Sheets / coils, should be fabricated as per SMACNA, galvanised hardware and supports, silicon sealant at all longitudinal joints, Galvanized /GI Electroplated iron angle flanges for all the joints, bracing angles and minimum 5mm thick neoprene rubber gasket.- Duct pressure testing at 75mm to be carried out before insulatiting the duct. pressure testing to be done as per SMACNA. Procedure to be approved by consultant. 22G - 0.8 mm Thick at MGMH Petlaburj
|  | Straight 600 x400 mm Terrus | 1 | 1 | 0.4 | 2 |  | 0.8
|  | Straight 600 x400 mm Terrus | 1 | 1 | 0.7 | 2 |  | 1.4
|  | Elbow 600 x 400 mm Terrus | 1 | 1 | 1.5 | 2 |  | 3
|  | Straight 600 x400 mm Terrus | 1 | 1 | 1.23 | 2 |  | 2.46
|  | Taper 600 x 400 x300 Terrus | 1 | 1 | 0.8 | 2.3 |  | 1.84
|  | Elbow 600 x 300 mm Terrus | 1 | 1 | 0.9 | 1.8 |  | 1.62
|  | Straight 600 x 300 mm Terrus | 1 | 2 | 1.23 | 1.8 |  | 4.428
|  | Straight 600 x 300 mm Terrus | 1 | 1 | 0.45 | 1.8 |  | 0.81
|  | Straight 600 x 300 mm Terrus | 1 | 1 | 0.65 | 1.8 |  | 1.17
|  | Straight 600 x 300 mm Terrus | 1 | 4 | 1.23 | 1.8 |  | 8.856
|  | Elbow 600 x 300 mm IVF OT | 1 | 1 | 0.9 | 1.8 |  | 1.62
|  | Straight 600 x 300 mm IVF OT | 1 | 6 | 1.23 | 1.8 |  | 13.284
|  | Taper 600 x 300 x 250mm IVF OT | 1 | 1 | 0.5 | 1.75 |  | 0.875
|  | Straight 300 x 250 mm IVF OT | 1 | 1 | 0.5 | 1.1 |  | 0.55
|  | Straight 300 x 250 mm IVF OT | 1 | 1 | 1.23 | 1.1 |  | 1.353
|  | Dummy 400 x 350 IVF OT | 1 | 1 | 0.4 |  | 0.35 | 0.14
|  | Straight 600 x400 mm Terrus | 1 | 5 | 1.23 | 2 |  | 12.3
|  | Elbow 600 x 400 mm Terrus | 1 | 1 | 1.5 | 2 |  | 3
|  | Taper 600 x 400 x 300 mm Terrus | 1 | 1 | 0.5 | 1.9 |  | 0.95
|  | Straight 600 x 300 mm Terrus | 1 | 1 | 1.23 | 1.8 |  | 2.214
|  | Elbow 600 x 300 mm Terrus | 1 | 1 | 0.9 | 1.8 |  | 1.62
|  | Straight 600 x 300 mm Terrus | 1 | 6 | 1.23 | 1.8 |  | 13.284
|  | Elboe 600 x 300mm Terrus | 1 | 1 | 0.9 | 1.8 |  | 1.62
|  | Straight 600 x 300 mm Terrus | 1 | 1 | 1.23 | 1.8 |  | 2.214
|  | Straight 600 x 300mm Lab | 1 | 1 | 0.8 | 1.8 |  | 1.44
|  | Straight 600 x 300mm Lab | 1 | 2 | 1.23 | 1.8 |  | 4.428
|  | Taper 600x 300 x 250 mm Lab | 1 | 1 | 0.5 | 1.75 |  | 0.875
|  | Straight 300 x 250 mm Lab | 1 | 1 | 0.5 | 1.1 |  | 0.55
|  | Straight 300 x 250 mm Lab | 1 | 1 | 1.23 | 1.1 |  | 1.353
|  | Dummy 400 x 350 IVF Lab | 1 | 1 | 0.4 |  | 0.35 | 0.14
|  | Elbow 450 x 300 mm Terrus | 1 | 1 | 0.8 | 1.5 |  | 1.2
|  | Straight 450 x 300 mm Terrus | 1 | 1 | 1.23 | 1.5 |  | 1.845
|  | Straight 450 x 300 mm Terrus | 1 | 1 | 2 | 1.5 |  | 3
|  | Straight 450 x 300 mm Terrus | 1 | 1 | 1.23 | 1.5 |  | 1.845
|  | Straight 450 x 300 mm Terrus | 1 | 1 | 0.9 | 1.5 |  | 1.35
|  | Elbow 450 x 300 mm Terrus | 1 | 1 | 0.8 | 1.5 |  | 1.2
|  | Straight 450 x 300 mm Terrus | 1 | 1 | 1.23 | 1.5 |  | 1.845
|  | Straight 450 x 300 mm Terrus | 1 | 1 | 0.7 | 1.5 |  | 1.05
|  | Straight 450 x 300 mm Terrus | 1 | 1 | 0.5 | 1.5 |  | 0.75
|  | Straight 450 x 300 mm Terrus | 1 | 5 | 1.23 | 1.5 |  | 9.225
|  | Elbow 450 x 300 mm Terrus | 1 | 1 | 0.8 | 1.5 |  | 1.2
|  | Straight 450 x 300 mm Terrus | 1 | 1 | 1.23 | 1.5 |  | 1.845
|  | Straight 450 x 300 mm Terrus | 1 | 1 | 0.5 | 1.5 |  | 0.75
|  | Straight 450 x 300 mm IVF OT | 1 | 3 | 1.23 | 1.5 |  | 5.535
|  | Taper450 x 300 x 250 x 250 mm IVF OT | 1 | 1 | 0.6 | 1.25 |  | 0.75
|  | Straight 250 x 300 mm IVT OT | 1 | 1 | 0.6 | 1.1 |  | 0.66
|  | Elbow 250 x 300 mm IVF OT | 1 | 1 | 0.9 | 1.1 |  | 0.99
|  | Straight 250 x 300 mm IVT OT | 1 | 1 | 1.23 | 1.1 |  | 1.353
|  | Dummy 350 x 400 mm IVF OT | 1 | 1 | 0.35 |  | 0.4 | 0.14
|  | Offse 600 x 400 Terrus | 1 | 1 | 1 | 2 |  | 2
|  | Offse 600 x 400 Terrus | 1 | 1 | 0.6 | 2 |  | 1.2
|  | Elbow 600 x 400 mm Terrus | 1 | 3 | 1.4 | 2 |  | 8.4
|  | Straight 600 x 400 mm Terrus | 1 | 1 | 0.5 | 2 |  | 1
|  | Straight 600 x 400 mm Terrus | 1 | 1 | 1.23 | 2 |  | 2.46
|  | Y Piece 600 x 400 mm Terrus | 1 | 1 | 0.25 | 2 |  | 0.5
|  | Elboe 400 x 400mm Terrus | 1 | 1 | 0.65 | 1.6 |  | 1.04
|  | Straight 400 x 400 mm Terrus | 1 | 1 | 1.2 | 1.6 |  | 1.92
|  | Straight 400 x 400 mm Terrus | 1 | 4 | 1.23 | 1.6 |  | 7.872
|  | Elbow 400 x 400 mm Terrus | 1 | 1 | 1.2 | 1.6 |  | 1.92
|  | Taper 450 x 400 x 350 x 300 mm | 1 | 1 | 0.7 | 1.5 |  | 1.05
|  | Straight 350 x 300 mm Terrus | 1 | 1 | 1.23 | 1.3 |  | 1.599
|  | Elbow 350 x 300 mm Terrus | 1 | 1 | 1 | 1.3 |  | 1.3
|  | Straight 350 x 300 mm Terrus | 1 | 1 | 1 | 1.3 |  | 1.3
|  | Straight 350 x 300 mm Terrus | 1 | 1 | 1.23 | 1.3 |  | 1.599
|  | Straight 350 x 300 mm Terrus | 1 | 1 | 0.6 | 1.3 |  | 0.78
|  | Straight 350 x 300 mm Terrus | 1 | 3 | 1.23 | 1.3 |  | 4.797
|  | Elbow 350 x 300 mm Terrus | 1 | 1 | 1 | 1.3 |  | 1.3
|  | Straight 350 x 300 mm Terrus | 1 | 2 | 1.23 | 1.3 |  | 3.198
|  | Taper 350 x 300 x 250 x 250 mm | 1 | 1 | 0.6 | 1.15 |  | 0.69
|  | Straight 250 x 250 mm Terrus | 1 | 1 | 1.23 | 1 |  | 1.23
|  | Straight 250 x 250 mm Terrus | 1 | 1 | 0.6 | 1 |  | 0.6
|  | Straight 250 x 250 mm Terrus | 1 | 1 | 1.23 | 1 |  | 1.23
|  | Dummy 350 x 350 mm Terrus | 1 | 1 | 0.35 |  | 0.35 | 0.1225
|  | Straight 400 x 400 mm Terrus | 1 | 1 | 1 | 1.6 |  | 1.6
|  | Straight 400 x 400 mm Terrus | 1 | 1 | 1.23 | 1.6 |  | 1.968
|  | Elbow 400 x 400 mm Terrus | 1 | 1 | 1.2 | 1.6 |  | 1.92
|  | Straight 400 x 400 mm Terrus | 1 | 1 | 1.23 | 1.6 |  | 1.968
|  | Straight 400 x 400 mm Terrus | 1 | 1 | 0.5 | 1.6 |  | 0.8
|  | Straight 400 x 400 mm Terrus | 1 | 1 | 1 | 1.6 |  | 1.6
|  | Straight 400 x 400 mm Terrus | 1 | 1 | 0.6 | 1.6 |  | 0.96
|  | Straight 400 x 400 mm Terrus | 1 | 3 | 1.23 | 1.6 |  | 5.904
|  | Dummy 500 x 500 mm Turres | 1 | 1 | 0.5 |  | 0.5 | 0.25
|  | Coller 400 x 350 x 300 x 300 mm Lab | 1 | 1 | 0.6 | 1.35 |  | 0.81
|  | Elobow 350 x 300 mm Lab | 1 | 1 | 0.8 | 1.3 |  | 1.04
|  | Straight 300 x 3500 mm Lab | 1 | 1 | 1.23 | 1.3 |  | 1.599
|  | Straight 300 x 3500 mm Lab | 1 | 1 | 0.8 | 1.3 |  | 1.04
|  | Straight 300 x 3500 mm Lab | 1 | 1 | 1.23 | 1.3 |  | 1.599
|  | Tapper 350 x 300 x 250 x 250 mm | 1 | 1 | 0.6 | 1.15 |  | 0.69
|  | Straight 250 x 250 mm Lab | 1 | 2 | 1.23 | 1 |  | 2.46
|  | Straight 250 x 250 mm Lab | 1 | 1 | 0.6 | 1 |  | 0.6
|  | Elbow 250 x 250 mm Lab | 1 | 1 | 0.5 | 1 |  | 0.5
|  | Straight 250 x 250 mm Lab | 1 | 1 | 1.23 | 1 |  | 1.23
|  | Dummy 350 x 350 mm Lab | 1 | 1 | 0.35 |  | 0.35 | 0.1225
|  | Coller 350 x 250mm Lab | 1 | 1 | 0.3 | 1.2 |  | 0.36
|  | Elbow 250 x 250 mm Lab | 1 | 1 | 0.6 | 1 |  | 0.6
|  | Straight 250 x 250 mm Lab | 1 | 2 | 1.23 | 1 |  | 2.46
|  | Dummy 350 x 350 mm | 1 | 1 | 0.35 |  | 0.35 | 0.1225
|  | Tapping 800 x 100 mm OT And Lab | 1 | 6 | 0.75 | 1.8 |  | 8.1
|  | Tapping 700 x 400 mm OT And Lab | 1 | 6 | 1.25 | 2.2 |  | 16.5
[6 empty] | Total |  | 232.6375 | Sqm
29 | 369 | Supply, laying of Class O Nitrile rubber with factory laminated Glass cloth, all joints shall be covered with self-adhesive tapes 19mm Thick for Return air running inside the building. at MGMH Petlaburj
|  | Return Duct Straight 450 x 300mm OT | 1 | 3 | 1.23 | 1.5 |  | 5.535
|  | Taper 450 x 300 x 250 x 250 mm IVF OT | 1 | 1 | 0.6 | 1.25 |  | 0.75
|  | Straight 250 x 300 mm IVT OT | 1 | 1 | 0.6 | 1.1 |  | 0.66
|  | Elbow 250 x 300 mm IVF OT | 1 | 1 | 0.9 | 1.1 |  | 0.99
|  | Straight 250 x 300 mm IVT OT | 1 | 1 | 1.23 | 1.1 |  | 1.353
|  | Dummy 350 x 400 mm IVF OT | 1 | 1 | 0.35 |  | 0.4 | 0.14
|  | Elboe 370 x 320 mm Terrus | 1 | 1 | 1.2 | 1.38 |  | 1.656
|  | Straight 370 x 320 mm Terrus | 1 | 1 | 1.2 | 1.38 |  | 1.656
|  | Straight 370 x 320 mm Terrus | 1 | 1 | 1.43 | 1.38 |  | 1.9734
|  | Straight 370 x 320 mm Terrus | 1 | 1 | 0.8 | 1.38 |  | 1.104
|  | Straight 370 x 320 mm Terrus | 1 | 3 | 1.43 | 1.38 |  | 5.9202
|  | Straight 370 x 320 mm Terrus | 1 | 1 | 1.2 | 1.38 |  | 1.656
|  | Straight 370 x 320 mm Terrus | 1 | 2 | 1.43 | 1.38 |  | 3.9468
|  | Taper 370 x 320 x 270 x 270 mm | 1 | 1 | 0.8 | 1.23 |  | 0.984
|  | Straight 270 x 270mm Terrus | 1 | 1 | 1.43 | 1.08 |  | 1.5444
|  | Dummy 375 x 357mm Terrus | 1 | 1 | 0.375 |  | 0.375 | 0.14062
|  | Straight 420 x 420 mm Terrus | 1 | 1 | 1.2 | 1.68 |  | 2.016
|  | Straight 420 x 420 mm Terrus | 1 | 1 | 1.43 | 1.68 |  | 2.4024
|  | Elbow 420 x 420 mm Terrus | 1 | 1 | 1.4 | 1.68 |  | 2.352
|  | Straight 420 x 420 mm Terrus | 1 | 1 | 1.43 | 1.68 |  | 2.4024
|  | Straight 420 x 420 mm Terrus | 1 | 1 | 0.7 | 1.68 |  | 1.176
|  | Straight 420 x 420 mm Terrus | 1 | 1 | 1.2 | 1.68 |  | 2.016
|  | Straight 420 x 420 mm Terrus | 1 | 1 | 0.8 | 1.68 |  | 1.344
|  | Straight 420 x 420 mm Terrus | 1 | 3 | 1.43 | 1.68 |  | 7.2072
|  | Dummy 520 x 520 mm | 1 | 1 | 0.52 |  | 0.52 | 0.2704
|  | Sh Coller 420 x 320 x 370 x 320 mm | 1 | 1 | 0.8 | 1.43 |  | 1.144
|  | Elbow 370 x 320 mm Lab | 1 | 1 | 1 | 1.38 |  | 1.38
|  | Straight 370 x 320 mm Lab | 1 | 1 | 1.43 | 1.38 |  | 1.9734
|  | Straight 370 x 320 mm Lab | 1 | 1 | 1 | 1.38 |  | 1.38
|  | Straight 370 x 320 mm Lab | 1 | 1 | 1.43 | 1.38 |  | 1.9734
|  | Taper 370 x 320 x 370 x 320 mm Lab | 1 | 1 | 0.8 | 1.38 |  | 1.104
|  | Straight 370 x 320 mm Terrus Lab | 1 | 2 | 1.43 | 1.38 |  | 3.9468
|  | Straight 370 x 320 mm Terrus Lab | 1 | 1 | 0.8 | 1.38 |  | 1.104
|  | Elbow 370 x 320 mm Lab | 1 | 1 | 0.7 | 1.38 |  | 0.966
|  | Straight 370 x 320 mm Lab | 1 | 1 | 1.43 | 1.38 |  | 1.9734
|  | Dummy 370 x 370 Lab | 1 | 1 | 0.37 |  | 0.37 | 0.1369
|  | Sh Coller 370 x 270 mm Lab | 1 | 1 | 0.5 | 1.28 |  | 0.64
|  | Elbow 270 x 270 mm Lab | 1 | 1 | 0.8 | 1.08 |  | 0.864
|  | Straight 270 x 250mm Lab | 1 | 2 | 1.43 | 1.04 |  | 2.9744
|  | Dummy 370 x 370 Lab | 1 | 1 | 0.37 |  | 0.37 | 0.1369
|  | Tapping 800 x 100 mm OT And Lab | 1 | 6 | 0.75 | 1.8 |  | 8.1
|  | Tapping 700 x 400 mm OT And Lab | 1 | 6 | 1.25 | 2.2 |  | 16.5
[6 empty] | Total |  | 97.493 | Sqm
30 | 368 | Supply, laying of Class O Nitrile rubber with factory laminated Glass cloth, all joints shall be covered with self-adhesive tapes 25mm Thick for Supply air duct running inside the building. at MGMH Petlaburj
|  | Supply DuctElbow 625 x 325 mm Terrus | 1 | 1 | 1.1 | 1.9 |  | 2.09
|  | Straight 625 x 325 mm Terrus | 1 | 2 | 1.43 | 1.9 |  | 5.434
|  | Straight 625 x 325 mm Terrus | 1 | 1 | 0.65 | 1.9 |  | 1.235
|  | Straight 625 x 325 mm Terrus | 1 | 1 | 0.85 | 1.9 |  | 1.615
|  | Straight 625 x 325 mm Terrus | 1 | 4 | 1.43 | 1.9 |  | 10.868
|  | Elbow 625 x 325 mm IVF OT | 1 | 2 | 1.1 | 1.9 |  | 4.18
|  | Straight 625 x 425 mm Terrus | 1 | 5 | 1.43 | 2.1 |  | 15.015
|  | Elboe 625 x 425 mm Terrus | 1 | 1 | 1.7 | 2.1 |  | 3.57
|  | Taper 625 x 425 mm Terrus | 1 | 1 | 0.7 | 2.1 |  | 1.47
|  | Straight 625 x 425 mm Terrus | 1 | 1 | 1.43 | 2.1 |  | 3.003
|  | Elbow 625 x 425 mm Terrus | 1 | 1 | 1.1 | 2.1 |  | 2.31
|  | Straight 625 x 425 mm Terrus | 1 | 6 | 1.43 | 2.1 |  | 18.018
|  | Elbow 625 x 425 mm Terrus | 1 | 1 | 1.1 | 2.1 |  | 2.31
|  | Straight 625 x 425 mm Terrus | 1 | 1 | 1.43 | 2.1 |  | 3.003
|  | Straight 625 x 425 mm Lab | 1 | 1 | 1.23 | 2.1 |  | 2.583
[6 empty] | Total |  | 76.704 | Sqm
31 | 367 | Supply, laying of Class O Nitrile rubber with factory laminated Glass cloth, all joints shall be covered with self-adhesive tapes 25mm Thick for Exposed Return Air Duct and finished with UV Protective Paint. at MGMH Petlaburj
|  | Straight 625 x 325 mm IVF OT | 1 | 6 | 1.43 | 1.9 |  | 16.302
|  | Taper 625 x 325 x 325 x 275 mm OT | 1 | 1 | 0.7 | 1.55 |  | 1.085
|  | Straight 325 x 275 mm IVF OT | 1 | 1 | 0.7 | 1.2 |  | 0.84
|  | Taper325 x 275 x 300 x 250 mm IVF OT | 1 | 1 | 1.43 | 1.15 |  | 1.6445
|  | Dummy 425 x 375 mm IVF OT | 1 | 1 | 0.425 |  | 0.375 | 0.15937
|  | Straight 625 x 325 mm Lab | 1 | 2 | 1.43 | 1.9 |  | 5.434
|  | Taper 625 x 325 x 325 x 275 mm Lab | 1 | 1 | 0.7 | 1.55 |  | 1.085
|  | Straight 325 x 275 mm IVF Lab | 1 | 1 | 0.7 | 1.2 |  | 0.84
|  | Straight 325 x 275 mm IVF Lab | 1 | 1 | 1.43 | 1.2 |  | 1.716
|  | Dummy 425 x 375 mm IVF Lab | 1 | 1 | 0.425 |  | 0.375 | 0.15937
|  | Retutn Duct Straight 425 x 325 mm Terrus | 1 | 1 | 1.23 | 1.5 |  | 1.845
|  | Straight 475 x 325 mm Terrus | 1 | 1 | 2.2 | 1.6 |  | 3.52
|  | Straight 475 x 325 mm Terrus | 1 | 1 | 1.43 | 1.6 |  | 2.288
|  | Straight 475 x 325 mm Terrus | 1 | 1 | 1.1 | 1.6 |  | 1.76
|  | Elbow 475 x 325 mm Terrus | 1 | 1 | 1 | 1.6 |  | 1.6
|  | Straight 475 x 325 mm Terrus | 1 | 1 | 1.43 | 1.6 |  | 2.288
|  | Straight 475 x 325 mm Terrus | 1 | 1 | 0.9 | 1.6 |  | 1.44
|  | Straight 475 x 325 mm Terrus | 1 | 1 | 0.7 | 1.6 |  | 1.12
|  | Straight 475 x 325 mm Terrus | 1 | 5 | 1.43 | 1.6 |  | 11.44
|  | Straight 475 x 325 mm Terrus | 1 | 1 | 1 | 1.6 |  | 1.6
|  | Straight 475 x 325 mm Terrus | 1 | 2 | 1.43 | 1.6 |  | 4.576
|  | Straight 475 x 325 mm Terrus | 1 | 1 | 0.7 | 1.6 |  | 1.12
|  | Offse 625 x 425Terrus | 1 | 1 | 1.2 | 2.1 |  | 2.52
|  | Offse 625 x 425Terrus | 1 | 1 | 0.8 | 2.1 |  | 1.68
|  | Elbow 625 x 425 mm Terrus | 1 | 2 | 1.6 | 2.1 |  | 6.72
|  | Straight 625 x 425 mm Terrus | 1 | 1 | 0.7 | 2.1 |  | 1.47
|  | Straight 625 x 425 mm Terrus | 1 | 1 | 1.43 | 2.1 |  | 3.003
|  | Y Piece 625 x 425 mm Terrus | 1 | 1 | 0.45 | 2.1 |  | 0.945
|  | Elbow 625 x 425 mm Terrus | 1 | 1 | 0.85 | 2.1 |  | 1.785
|  | Straight 625 x 425 mm Terrus | 1 | 1 | 1.4 | 2.1 |  | 2.94
|  | Straight 625 x 425 mm Terrus | 1 | 4 | 1.43 | 2.1 |  | 12.012
|  | Elbow 625 x 425 mm Terrus | 1 | 1 | 1.4 | 2.1 |  | 2.94
|  | Tapper 475 x 425 x 325 x 375 mm | 1 | 1 | 0.9 | 1.6 |  | 1.44
|  | Straight 375 x 325 mm Terrus | 1 | 1 | 1.43 | 1.4 |  | 2.002
[6 empty] | Total |  | 103.3192 | Sqm
32 | 366 | Supply, laying of Class O Nitrile rubber with factory laminated Glass cloth, all joints shall be covered with self-adhesive tapes 32mm Thick for Exposed Supply Air duct and finished with UV Protective Paint. at MGMH Petlaburj
|  | Supply Duct Elbow 932 x 432 Mm Terrus | 1 | 1 | 1.4 | 2.728 |  | 3.8192
|  | Elbow 932 x 432 Mm Terrus | 1 | 1 | 2.3 | 2.728 |  | 6.2744
|  | Straight 932 x 432 mm Terrus | 1 | 1 | 0.9 | 2.728 |  | 2.4552
|  | Heater Straight 932 x 432 mm Terrus | 1 | 1 | 0.9 | 2.728 |  | 2.4552
|  | Fire Damper Straight 932 x 432 mm Terrus | 1 | 1 | 0.55 | 2.728 |  | 1.5004
|  | Y Pice 632 x 432 mm Terrus | 1 | 1 | 0.9 | 2.128 |  | 1.9152
|  | Y Pice 632 x 432 mm Terrus | 1 | 1 | 0.9 | 2.128 |  | 1.9152
|  | Straight 632 x 432 mm Terrus | 1 | 1 | 0.6 | 2.128 |  | 1.2768
|  | Straight 632 x 432 mm Terrus | 1 | 1 | 0.9 | 2.128 |  | 1.9152
|  | Elbow 632 x 432 mm Terrus | 1 | 1 | 1.7 | 2.128 |  | 3.6176
|  | Straight 632 x 432 mm Terrus | 1 | 1 | 1.43 | 2.128 |  | 3.043
|  | Taper 632 x 432 x 632 x 432mm | 1 | 1 | 1 | 2.128 |  | 2.128
|  | Elbow 932 x 432 Mm Terrus | 1 | 1 | 1.7 | 2.73 |  | 4.641
|  | Staright 932 x 432 mm Terrus | 1 | 1 | 0.45 | 2.73 |  | 1.2285
|  | Y Pice 532 x 432 mm Terrus | 1 | 1 | 1 | 1.928 |  | 1.928
|  | Y Pice 632 x 432 mm Terrus | 1 | 1 | 1.4 | 2.128 |  | 2.9792
|  | Taper 532 x 432 x 482 x 332mm Terrus | 1 | 1 | 0.6 | 1.778 |  | 1.0668
|  | Elbow 482 x 332 mm Terrus | 1 | 1 | 1 | 1.628 |  | 1.628
[6 empty] | Total |  | 45.7869 | Sqm
33 | Sup | Modular Double skin floor mounted EUROVENT Certified Air Handling Unit 4400CFM / 11.0 TR / 150mm SP made out of 45 plus or minus 2mm thick PUF insulated panels Thermal break aluminium profile frame work with 0.8mm thick pre painted / powder coated inner and outer skins comprising of mixing box with fresh air and return air dampers, pre filters with 10 and 5 microns combination filters in single frame, Interlaced/Intertwined DX Cooling Coil suitable for connecting 2 nos of 11.0TR capacity 1W plus 1S out door condensing units, SS304 drain pan with , blower section with Nicotra / Kruger make direct drive/ Plug type fan, vibration isolators, EFF1 motor and blower section with on/off switches to operate from outside, limit switch for the fan section access door with a view port, fine filter section with 3 microns filters inspection doors for all filter and fan sections and damper at the outlet of unit. Ports for differential pressure gauges across all filters and blower to measure differential pressure. AHU Make : VTS / Systemair, Make - Blower - Nicotra / Kruger ; Motor - Crompton Greaves / Siemens ; Filter - Thermodyne / Freudenberg / Ultrafil at MGMH Petlaburj
|  | 11.0 TR AHU | 1 | 1 |  |  |  | 1
[6 empty] | Total |  | 1 | Nos
34 | 349 | SITC of filter module made out of heavy duty Aluminium powder coated extrusion with minimum of 13G . and to house 610 mm X 610 mm HEPA Filter at the rate 0.3 microns , 99.9997, H-14 Grade, Filter loading from clean room side with bewel gear arrangement damper with access from clean room suitable to house the following filter sizes pressure drop and Integrity testing ports into room. Includes SS capsule perforated diffuser. This includes all required supports and accessories etc. Capacity 1000 CFM. at MGMH Petlaburj
|  | IVF OT | 1 | 3 |  |  |  | 3
|  | Embryology Lab | 1 | 3 |  |  |  | 3
[6 empty] | Total |  | 6 | Nos
35 | Sup | SITC of air cooled condensing units with two scroll compressors, air cooled condenser, power panel, vibration isolating pads, stand for ODU, thermostat, etc. of the following capacities. The nominal capacity of the condensing unit shall be as under. Air cooled condensing unit shall have horizontal discharge. All refrigerant piping accessories sight glass, drier, expansion valve, etc. shall be supplied with the condensing units and suitable to connect above AHUs. Refrigerant shall be R 407C / R 410A. Necessary thermostat, control wiring, etc. shall be included. Derating of the unit shall not be more than 15percentage under 45 deg. C ambient temperature. Condensing unit shall be capable of operating up 50 deg. C ambient temperature. 11.0 TR capacity at MGMH Petlaburj
|  | 11.0 TR | 1 | 2 |  |  |  | 2
[6 empty] | Total |  | 2 | Nos
36 | 351 | SITC of Flange type, Flame proof FLP duct heaters of 5 kW capacity with Mineral Filled AISI SS304/SS321 Sheathed Tubular Heater with GI Helical fins, Tube dia 8.2mm min and Helical Finn dia 25mm min, enclosed in the frame, FLP Terminal box etc., Nickel Chromium Inner Element, Silicon Sealing to Restrict Moisture pickup, Silver brazed mounting plate etc., and heaters shall be controlled with PID thyrestor controller based on the analog output signal of 0-10 V DC of controller . And this should have saftey thermostat and cutouts and air stat etc. all safety controls. The capacities as follows and sizes of the heaters shall be as per the duct sizes and approved drawing. at MGMH Petlaburj
|  | Terrus | 1 | 1 |  |  |  | 1
[6 empty] | Total |  | 1 | Nos
37 | 352 | SITC of 20/21 G hard drawn copper refrigerant piping with all fittings, supports, insulation with 19 mm thk class O nitrile rubber insulation with factory laminated glass cloth for physical protection and UV protection etc. Quality of copper piping fittings shall be suitable for 18 G piping. Copper piping shall be clamped at every 1.5 mt. distance. copper piping shall be laid on inverted GI perforated cable trays and clamps as per specification inside the building. Copper piping on the terrace shall be laid with bottom and top cable tray. Thickness of the tray shall be 1.6 mm. Copper pipe size shall be as per OEM standards. Liquid Line at MGMH Petlaburjl
|  |  | 1 | 16 |  |  |  | 16
38 | 353 | SITC of 20/21 G hard drawn copper refrigerant piping with all fittings, supports, insulation with 19 mm thk class O nitrile rubber insulation with factory laminated glass cloth for physical protection and UV protection etc. Quality of copper piping fittings shall be suitable for 18 G piping. Copper piping shall be clamped at every 1.5 mt. distance. copper piping shall be laid on inverted GI perforated cable trays and clamps as per specification inside the building. Copper piping on the terrace shall be laid with bottom and top cable tray. Thickness of the tray shall be 1.6 mm. Copper pipe size shall be as per OEM standards. Suction Line at MGMH Petlaburj
|  |  | 1 | 16 |  |  |  | 16
39 | 355 | SITC of CPVC drain ping with supports, clamps and 9 mm thk. Nitrile rubber tube insulation of the following sizes. Insulation shall have factory laminated glass cloth. 25mm Dia at MGMH Petlaburj
|  |  | 1 | 9 |  |  |  | 9
40 | Sup | MS Angles 50 x 50 mm x 5 mm thick
|  |  | 1 | 4 | 1.6 |  |  | 6.4
|  |  | 1 | 6 | 0.62 |  |  | 3.72
|  |  | 1 | 8 | 0.31 |  |  | 2.48
|  |  | 1 | 8 | 0.15 |  |  | 1.2
|  |  | 1 | 12 | 2.2 |  |  | 26.4
|  |  | 1 | 2 | 0.56 |  |  | 1.12
|  |  | 1 | 6 | 0.7 |  |  | 4.2
|  |  | 1 | 10 | 1.05 |  |  | 10.5
|  |  | 1 | 10 | 0.5 |  |  | 5
|  |  | 1 | 8 | 0.2 |  |  | 1.6
[6 empty] | Total |  | 62.62 | Rmt
41 | Sup | MS Angles 32 x 32 mm x 5 mm thick
|  |  | 1 | 2 | 1.63 |  |  | 3.26
|  |  | 1 | 2 | 0.92 |  |  | 1.84
|  |  | 1 | 2 | 1.65 |  |  | 3.3
|  |  | 1 | 2 | 0.71 |  |  | 1.42
|  |  | 1 | 4 | 2.16 |  |  | 8.64
|  |  | 1 | 2 | 1 |  |  | 2
|  |  | 1 | 2 | 0.5 |  |  | 1
|  |  | 1 | 12 | 0.36 |  |  | 4.32
|  |  | 1 | 6 | 0.33 |  |  | 1.98
|  |  | 1 | 18 | 0.1 |  |  | 1.8
[6 empty] | Total |  | 29.56 | Rmt
42 | 337 | Supply, installation, testing and commissioning of 20nos LAN points with cat 6 cable and with suitable network rack and 5nos of telephone points with krone box to existing EPABEX. at MGMH Petlaburj
|  |  | 1 | 1 |  |  |  | 1
[6 empty] | Total |  | 1 | Job
43 | 338 | Supply, installation, testing and commissioning of 1 no of Access control system with egress switch, Power Cable, communication cable to control panel with necessary required items Etc. at MGMH Petlaburj
|  |  | 1 | 1 |  |  |  | 1
[6 empty] | Total |  | 1 | Job
44 | 339 | Supply, installation, testing and commissioning of Automatic Fire Alarm System which is including 30 nos of smoke Detectors 1nos manual call point, 1 no of Hooter with fire alarm cable connected to the existing fire control panel with necessary Required items etc.. at MGMH Petlaburj
|  |  | 1 | 1 |  |  |  | 1
[6 empty] | Total |  | 1 | Job
45 | 340 | Supply, installation, testing and commissioning of 5nos IP Based CCTV cameras and Cat 6 Cable with NVR system. at MGMH Petlaburj
|  |  | 1 | 1 |  |  |  | 1
[6 empty] | Total |  | 1 | Job
46 | 341 | Supply, installation, testing and commissioning of Audio and video recording of counseling rooms at MGMH Petlaburj
|  |  | 1 | 1 |  |  |  | 1
[6 empty] | Total |  | 1 | Job
47 | 342 | Supply and installation of Fire Extinguishers of CO2 4.50 Kg at MGMH Petlaburj
|  |  | 1 | 5 |  |  |  | 5
[6 empty] | Total |  | 5 | Nos
48 | 343 | Supply and installation of ceiling mounted Fire Extinguishers of ABC MAP 90, 5.0 Kg stored pressure type at MGMH Petlaburj
|  |  | 1 | 5 |  |  |  | 5
[6 empty] | Total |  | 5 | Nos
49 | 344 | Supply and installation of 2.0 Kg clean agent HCFC 123 Fire Extinguishers at MGMH Petlaburj
|  |  | 1 | 5 |  |  |  | 5
[6 empty] | Total |  | 5 | Nos
50 | 345 | Supply and fixing of Fire escape signage Boards at MGMH Petlaburj
|  |  | 1 | 1 |  |  |  | 1
[6 empty] | Total |  | 1 | Job
51 | Sup | V- Board Partition
|  | partition B/w Staff Change rooms | 1 | 1 | 2.18 |  | 3.35 | 7.303
|  | Partition B/w Doctor Change rooms | 1 | 1 | 1.91 |  | 3.35 | 6.3985
[6 empty] | Total |  | 13.7015 | Sqm

## Abs -6
ABSTRACT
Name of Work:- Design, Fabriction, establishing and commissioning of In - Vitro ferility centers (IVFC) alongwith allied Services on Turnkey basis at MGMH Petlaburj,Hyd. | [7 empty] | Agency: | [6 empty] | Agt.No:344/A/TSMIDC/Spl.Proj/IVFCs /2022-23,Dt.05.07.2023
S.No | Date of measurement/ S.No. in Agt. | Description Of Work etc., | Measurements Upto date |  |  |  |  | Rate |  | Per | Total Value to date |  | Deduct/previous Measurements |  | Since last measurement |  |  | Remarks
|  |  | No | L | B | D | Content | Rs | Ps. |  | Rs. | Ps | P.No. | Qty. | Qty | Value
[16 empty] | Rs. | Ps.
1 | 247 | Dismantling, clearing away and carefully stacking useful materials for re-use and disposal of unserviceable materials with 100m lead as directed by Executive Engineer duly taking actual premeasurements before dismantling including all labour charges , overheads & contractor profit etc., complete Finished item of work | [16 empty] | Original Rate
a) Brick Masonry
|  | Qty V.Pg.No:-01 of MB:-10 |  |  |  | 20.38 | 20.38 | 398 | Cum |  | 8111.24 |  | 20.38 | 8111.24 | 0 | 0 |  |  | 398
|  | Qty V.Pg.No:-01 of MB:-11 |  |  |  | 0.1932 | 0.1932 | 398 | Cum |  | 76.8936 |  | 0 | 0 | 0.1932 | 76.8936
| 248 | b) Tiles Dismantling
|  | Qty V.Pg.No:-01 of MB:-10 |  |  |  | 729.9325 | 400 | 20 | Sqm |  | 8000 |  | 400 | 8000 | 0 | 0 |  |  | 20
[6 empty] | AE | 329.9325
2 | 249 | Dismantling doors, windows and clear storey windows, Ventilators etc., (wood or steel) shutters including Chowkhats, architraves,hold fasts and other attachments etc., and stacking them within 100m lead including labour charge etc., and overheads & contractors profit complete for finished item of work.
a)Not Exceeding 3.00Sqm Area
|  | Qty V.Pg.No:-01 of MB:-04 |  |  |  | 32 | 16 | 350 | Each |  | 5600 |  | 16 | 5600 | 0 | 0 |  |  | 350
[6 empty] | AE | 16
3 | 252 | Brick Masonry for panel walls in SuperStructure with CM (1:8) prop (cement: Screened sand) with Aerated Cellular Autoclaved Concrete Blocks conforming to IS:2185 (Part-3) - 1984 and IS:6441-1972 of Compressive strength 3 N/mm2 600x 230 x 200 mm from approved source having minimum crushing strength of 3 N/Sq.m including cost and conveyance of all materials like cement, sand, bricks, water etc., to site, including sales & other taxes on all materials, all operational, incidental and labour charges such as mixing cement mortar, constructing masonry, scaffolding charges, lift charges, curing, etc., complete but excluding seigniorage charges for finished item of work. (APSS No. 501 & 504).
|  | Qty V.Pg.No:-01 of MB:-04 |  |  |  | 16.3192 | 10.5 | 14558 | cum |  | 152859 |  | 10.5 | 152859 | 0 | 0 |  |  | 14558
|  | Qty V.Pg.No:-01 of MB:-011 |  |  |  | 3.762 | 3.762 |  | cum
[6 empty] | AE | 9.58
4 | 253 | Reinforced Masonry for partiton walls 100 mm thick in CM (1:4) prop (cement: Screened sand) in super structure with Aerated Cellular Autoclaved Concrete Blocks conforming to IS:2185 (Part-3) - 1984 and IS:6441-1972 of Compressive strength 3 N/mm2 600x 200 x 100 mm from approved source having minimum crushing strength of 3 N/Sq.m including cost and conveyance of all materials like cement, sand, bricks, water etc., to site, including sales & other taxes on all materials, all operational, incidental and labour charges such as mixing cement mortar, constructing masonry, scaffolding charges, lift charges, curing, etc., complete but excluding seigniorage charges for finished item of work. (APSS No. 501 & 504).
|  | Qty V.Pg.No:-02 of MB:-04 |  |  |  | 219.7595 | 215 | 1716 | Sqm |  | 368940 |  | 215 | 368940 | 0 | 0 |  |  | 1716
|  | Qty V.Pg.No:-01 of MB:-011 |  |  |  | 7.41 | 7.41 | 0 | Sqm |  | 0 |  | 0 |  | 7.41 | 0
[6 empty] | AE | 12.1695
5 | 256 | Plastering 12mm thick in two coats using screened sand with base coat of 8mm thick in CM (1:6) and top coat of 4mm thick in CM (1:4) with dubara sponge finishing including cost and conveyance of all materials like cement, sand, water etc., to site, including sales & other taxes on all materials, and all operational, incidental charges on materials and including cost of all labour charges for mixing mortar, finishing, scaffolding, lift charges, curing, including cutting grooves as directed by Engineer-in-charge etc., and overheads & contractors profit complete for finished item of work. (SS 901,903 & 904).
|  | Qty V.Pg.No:-02 of MB:-04 |  |  |  | 822.13 | 430 | 906 | Sqm |  | 389580 |  | 430 | 389580 | 0 | 0 |  |  | 906
|  | Qty V.Pg.No:-02 of MB:-011 |  |  |  | 82.794 | 82.794 |  | Sqm
[6 empty] | AE:- | 474.92
6 | 263 | Flooring with soluble salt porcelain vitrified tiles screen printed and polished of size 600 x 600 mm and thickness between 8 to 10mm 1st quality conforming to IS: 13711, IS: 13712, IS: 13630Parts 1 to 15 of any colour and finish in all shades and designs with borders and design as per the approved flooring pattern as directed by the Engineer-In -Charge, laying tiles using spacers of 2mm thick, set over a base coat of CM 1:8 prop. 12mm thick using screened sand over CC bed already laid or RCC roof slab, including neat cement slurry of honey like consistency spread at the rate 3.3 kgs per Sqm. and jointed neatly with white cement paste to full depth mixed with pigment of matching shade including cost and conveyance of all materials like cement, sand, water, tiles, white cement etc., to site excluding cost of C.C. bed including cost of base coat and all labour charges for mixing of cement mortar, laying tiles to required slope as directed by the Engineer- in- charge etc., and complete for finished item of work. TSSS No.701 and 707.
|  | Qty V.Pg.No:-02 of MB:-04 |  |  |  | 294.66 | 294.659 | 1593 | Sqm |  | 469391.787 |  | 294.66 | 469393.38 | 0 | 0 |  |  | 1593
7 | 266 | Providing dadooing to walls with glazed full body porcelain wall tiles of size 300 x 600 mm with any type of design texture such as marble finish, wooden, bamboo, stone finishes etc., scratch less, stain free and thickness between 6-8 mm 1st quality conforming to IS:13711, IS:13712, IS:13630 Parts 1 to 15 of any colour and finish in all shades and designs with borders as approved by Engineer-in-Charge set over base coat of CM1:5 12 mm thick using screened sand with cement slurry of honey like consistency spread at the rate of 3.30 kgs per sqm and jointing with white cement paste mixed with pigment of matching shade to full depth, including cost of all materials like tiles, cement, sand and water etc., complete for finished item of work. 3rd Floor at Petlaburj Hospital
|  | Qty V.Pg.No:-03 of MB:-04 |  |  |  | 153.0952 | 30 | 1391 | Sqm |  | 41730 |  | 30 | 41730 | 0 | 0 |  |  | 1391
[6 empty] | AE | 123.0952
[9 empty] | Civil Sub-Total:- |  | 1444288.9206 |  |  | 1444213.62 |  | 76.8936
Civil Supplemental Items
1 |  | Dismantling, clearing away and carefully stacking useful materials for re-use and disposal of unserviceable materials with 100m lead as directed by Executive Engineer duly taking actual premeasurements before dismantling including all labour charges , overheads & contractor profit etc., complete Finished item of work
a)Old Cement Mortar
|  | Qty V.Pg.No:-03 of MB:-04 |  |  |  | 251.59 | 251.5889 |  | Sqm
|  | Qty V.Pg.No:-01 of MB:-011 |  |  |  | 37.548 | 37.548 |  | Sqm
b)Reinforced Cement Concrete
|  | Qty V.Pg.No:-03 of MB:-04 |  |  |  | 0.43 | 0.4293 |  | Cum
|  | Qty V.Pg.No:-01 of MB:-011 |  |  |  | 0.162 | 0.162 |  | Cum
2 |  | Providing Thermo Mechanically Treated ( TMT) ( Fe-500/500D/550D from primery producer TATA, SAIL, VSP, JSW Steel, Goel steel, Jindal panther, X- Vega & balaji Shakthi as per IS 1786-2008) of Different Diameters RCC Works , including labour charges for straightening, cutting, bending to required sizes and shapes, placing in position with cover blocks of approved materials and sizes and typing and lap - spacing with binding wire of 18 SWG, Forming grills for reinforcement work as per approved design and drawings, including and conveyanace of steel bars, including all wastages such as overlaps, coupling, chairs, spacer bars including cost and conveyance of binding wire cover blocks and incidential, operational, labour charges such as cutting bending, placing in position, typing incliding sales and other taxes on all materials etc., and overheads & contractors profit completefor finished item of work
|  | Qty V.Pg.No:-03 of MB:-04 |  |  |  | 0.3 | 0.2956
3 |  | Supply and placing of the Design Mix Concrete M 25 grade corresponding to IS 456 with minimum cement content of 380 kgs per 1 cum of concrete using Weight Batcher / Concrete mixer with 20mm size graded machine crushed hard granite metal (coarse aggregate - as per IS 383 - 1970 and IS 2386 Part 1 to Part 8) from approved quarry including cost and conveyance of all materials like cement, fine aggregate (sand) coarse aggregate, water etc., to site and sales & other taxes on all materials, centering using Casurina Ballies, Bamboos, Wooden Reapers, Runners, Wood Posts, Steel Plates etc., including all operational, incidental and labour charges such as weigh batching, machine mixing, lifting of concrete manually, laying concrete, curing , overheads & contractors profit etc., complete but excluding cost of steel and its fabrication charges for finished item of work (APSS No. 402)
For Lintels
|  | Qty V.Pg.No:-04 of MB:-04 |  |  |  | 0.75 | 0.74952
4 |  | Providing skirting to internal walls to 10 cm height with Double charged / multi charged stain free fullbody porcelain vitrified tiles with double layer pigment of size 600 x 600 mm and thickness between 8-10 mm 1st quality conforming to IS:15622 - 2017, IS:13630 (Parts 1 to 15) of any colour and finish in all shades and designs, length equal to flooring tiles, set over base coat of CM(1:5) 12 mm thick using screened sand with cement slurry of honey like consistency spread at the rate of 3.30 kgs per sqm and jointing with white cement paste mixed with pigment of matching shade to full depth, including cost of all materials like tiles, cement, sand and water etc.,and overheads & contractors profit complete for finished item of work.(APSS No.701 &707)
|  | Qty V.Pg.No:-04 of MB:-04 |  |  |  | 174.5 | 174.5
[8 empty] | Civil Suppl. Sub-Total:- |  |  | 0 |  |  | 0 |  | 0
Equipment Items
1 | 200 | IVF Test tube Warmers at Petlaburz Hospital
|  | Qty V.Pg.No:-04 of MB:-04 |  |  |  | 2 | 2 | 44550 | Nos |  | 89100 |  | 2 | 69300 | 2 | 19800 |  | 20% | 49500
2 | 201 | DICOM compatible fully digital, compact, portable, Ultrasound Scan Machine Colour Doppler at Petlaburz Hospital
|  | Qty V.Pg.No:-04 of MB:-04 |  |  |  | 2 | 2 | 1228500 | Nos |  | 2457000 |  | 2 | 1911000 | 2 | 546000 |  | 20% | 1365000
3 | 202 | Multipurpose Electro hydraulic with manual override mobile OT Table, with divided leg section suitable for all Gynaecological surgical procedures, complete with 5cm Mattress and corded handset at Petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 1 | 1 | 507375 | Nos |  | 507375 |  | 1 | 394625 | 1 | 112750 |  | 20% | 563750
4 | 203 | LED procedure Lights Double dome at petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 1 | 1 | 281250 | Nos |  | 281250 |  | 1 | 218750 | 1 | 62500 |  | 20% | 312500
5 | 204 | LED procedure Lights Single dome at petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 1 | 1 | 168750 | Nos |  | 168750 |  | 1 | 131250 | 1 | 37500 |  | 20% | 187500
6 | 207 | CO2 Incubators at Petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 2 | 2 | 742500 | Nos |  | 1485000 |  | 2 | 1155000 | 2 | 330000 |  | 20% | 825000
7 | 212 | IVF Thermometer at Petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 1 | 1 | 55688 | Nos |  | 55688 |  | 1 | 43313 | 1 | 12375 |  | 20% | 61875
8 | 213 | CO2 Cylinder and Manifold at Petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 2 | 2 | 45000 | Nos |  | 90000 |  | 2 | 70000 | 2 | 20000 |  | 20% | 50000
9 | 214 | CO2 and O2 Analyzer at Petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 1 | 1 | 340200 | Nos |  | 340200 |  | 1 | 264600 | 1 | 75600 |  | 20% | 378000
10 | 215 | PH Meter at Petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 1 | 1 | 84375 | Nos |  | 84375 |  | 1 | 65625 | 1 | 18750 |  | 20% | 93750
11 | 217 | Sperm Counting Markler Chamber at Petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 1 | 1 | 68063 | Nos |  | 68063 |  | 1 | 52938 | 1 | 15125 |  | 20% | 75625
12 | 220 | Clinical Centrifuge machine for Andrology at Petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 1 | 1 | 31050 | Nos |  | 31050 |  | 1 | 24150 | 1 | 6900 |  | 20% | 34500
13 | 221 | DRY Incubator at Petlaburz Hospital
|  | Qty V.Pg.No:-05 of MB:-04 |  |  |  | 1 | 1 | 507375 | Nos |  | 507375 |  | 1 | 394625 | 1 | 112750 |  | 20% | 563750
14 | 223 | Pharmaceutical Refrigerator at Petlaburz Hospital
|  | Qty V.Pg.No:-06 of MB:-04 |  |  |  | 1 | 1 | 202500 | Nos |  | 202500 |  | 1 | 157500 | 1 | 45000 |  | 20% | 225000
15 | 224 | Cryocane (TA 26 Ltr) with wheels at Petlaburz Hospital
|  | Qty V.Pg.No:-06 of MB:-04 |  |  |  | 2 | 2 | 55688 | Nos |  | 111376 |  | 2 | 86626 | 2 | 24750 |  | 20% | 61875
16 | 225 | Defibrillator at Petlaburz Hospital
|  | Qty V.Pg.No:-06 of MB:-04 |  |  |  | 1 | 1 | 281250 | Nos |  | 281250 |  | 1 | 218750 | 1 | 62500 |  | 20% | 312500
17 | 226 | 7 Para Patient Monitor at Petlaburz Hospital
|  | Qty V.Pg.No:-06 of MB:-04 |  |  |  | 2 | 2 | 252000 | Nos |  | 504000 |  | 2 | 392000 | 2 | 112000 |  | 20% | 280000
18 | 228 | Anaesthesia Work station at Petlaburz Hospital
|  | Qty V.Pg.No:-06 of MB:-04 |  |  |  | 1 | 1 | 843750 | Nos |  | 843750 |  | 1 | 656250 | 1 | 187500 |  | 20% | 937500
19 | 232 | Mulitfunctional Printer at Petlaburz Hospital
|  | Qty V.Pg.No:-06 of MB:-04 |  |  |  | 1 | 1 | 39375 | Nos |  | 39375 |  | 1 | 30625 | 1 | 8750 |  | 20% | 43750
20 | 233 | Ultrasound Examination Couch at Petlaburz Hospital
|  | Qty V.Pg.No:-06 of MB:-04 |  |  |  | 1 | 1 | 73125 | Nos |  | 73125 |  | 1 | 56875 | 1 | 16250 |  | 20% | 81250
21 | 235 | Laptop For Office Usage at Petlaburz Hospital
|  | Qty V.Pg.No:-06 of MB:-04 |  |  |  | 2 | 2 | 103500 | Nos |  | 207000 |  | 2 | 161000 | 2 | 46000 |  | 20% | 115000
22 | 320 | 20 KVA UPS: Supply and installation of 20KVA 3ph in and 3ph out on line UPS system IGBT based rectifier with input power factor correction 32 bit microprocessor based with isolation transformers double conversion, SNMP controls, LCD display, Pure sine wave output, with auto static switch three phase input / Three phase output and modular structure for better thermal technology / cooling facility, with warranty up to three years.Makes: APC / Numeric / Emerson / Fuji Electric At Petlaburz
|  | Qty V.Pg.No:-06 of MB:-04 |  |  |  | 1 | 1 | 274500 | Nos |  | 274500 |  | 1 | 213500 | 1 | 61000 |  | 20% | 305000
23 | 322 | Supply and providing of UPS Cum battery rack for 20 batteries at MGMH Petlaburz
|  | Qty V.Pg.No:-06 of MB:-04 |  |  |  | 1 | 1 | 6088 | Nos |  | 6088 |  | 1 | 4735 | 1 | 1353 |  | 20% | 6764
6773037
1 | 199 | Ovum Aspiration Pumps at Petlaburj Hospital
|  | Qty V.Pg.No:-01 of MB:-05 |  |  |  | 2 | 2 | 216000 | Nos |  | 432000 |  | 2 | 336000 | 2 | 96000 |  | 20% | 240000
2 | 205 | IVF Workstation with LAF at Petlaburj Hospital
|  | Qty V.Pg.No:-01 of MB:-05 |  |  |  | 1 | 1 | 618750 | Nos |  | 618750 |  | 1 | 481250 | 1 | 137500 |  | 20% | 687500
3 | 206 | IVF Ant vibration Table for procedure at Petlaburj Hospital
|  | Qty V.Pg.No:-01 of MB:-05 |  |  |  | 1 | 1 | 86625 | Nos |  | 86625 |  | 1 | 67375 | 1 | 19250 |  | 20% | 96250
4 | 208 | Trigas bench Top Incubators for Human Embryo culture at Petlaburj Hospital
|  | Qty V.Pg.No:-01 of MB:-05 |  |  |  | 1 | 1 | 742500 | Nos |  | 742500 |  | 1 | 577500 | 1 | 165000 |  | 20% | 825000
5 | 209 | Trinocular Stereozoom Microscope at Petlaburj Hospital
|  | Qty V.Pg.No:-01 of MB:-05 |  |  |  | 1 | 1 | 278100 | Nos |  | 278100 |  | 1 | 216300 | 1 | 61800 |  | 20% | 309000
6 | 210 | ICSI Micro manipulator with Inverted Microscope at Petlaburj Hospital
|  | Qty V.Pg.No:-02 of MB:-05 |  |  |  | 1 | 1 | 2362500 | Nos |  | 2362500 |  | 1 | 1837500 | 1 | 525000 |  | 20% | 2625000
7 | 211 | IVF Laser System at Petlaburj Hospital
|  | Qty V.Pg.No:-02 of MB:-05 |  |  |  | 1 | 1 | 2304000 | Nos |  | 2304000 |  | 1 | 1792000 | 1 | 512000 |  | 20% | 2560000
8 | 216 | VOC Meter for ART Lab at Petlaburj Hospital
|  | Qty V.Pg.No:-02 of MB:-05 |  |  |  | 1 | 1 | 658125 | Nos |  | 658125 |  | 1 | 511875 | 1 | 146250 |  | 20% | 731250
9 | 218 | Binocular Microscope for Semen Analysis at Petlaburj Hospital
|  | Qty V.Pg.No:-02 of MB:-05 |  |  |  | 1 | 1 | 37125 | Nos |  | 37125 |  | 1 | 28875 | 1 | 8250 |  | 20% | 41250
10 | 219 | Laminar flow cabinet with Andrology Work station at Petlaburj Hospital
|  | Qty V.Pg.No:-02 of MB:-05 |  |  |  | 1 | 1 | 225000 | Nos |  | 225000 |  | 1 | 175000 | 1 | 50000 |  | 20% | 250000
11 | 222 | Pipetter and Denudation system at Petlaburj Hospital
|  | Qty V.Pg.No:-02 of MB:-05 |  |  |  | 1 | 1 | 92813 | Nos |  | 92813 |  | 1 | 72188 | 1 | 20625 |  | 20% | 103125
12 | 229 | Autoclave at Petlaburj Hospital
|  | Qty V.Pg.No:-02 of MB:-05 |  |  |  | 1 | 1 | 506250 | Nos |  | 506250 |  | 1 | 393750 | 1 | 112500 |  | 20% | 562500
13 | 236 | Reception Table at Petlaburj Hospital
|  | Qty V.Pg.No:-03 of MB:-05 |  |  |  | 1 | 1 | 99000 | Nos |  | 99000 |  | 1 | 77000 | 1 | 22000 |  | 20% | 110000
14 | 238 | Filing Cabinet at Petlaburj Hospital
|  | Qty V.Pg.No:-03 of MB:-05 |  |  |  | 2 | 2 | 31050 | Nos |  | 62100 |  | 2 | 48300 | 2 | 13800 |  | 20% | 34500
15 | 239 | Patient Seating 3 in 1 model at Petlaburj Hospital
|  | Qty V.Pg.No:-03 of MB:-05 |  |  |  | 3 | 3 | 34650 | Nos |  | 103950 |  | 3 | 80850 | 3 | 23100 |  | 20% | 38500
16 | 244 | Wall Storage Cabinets at Petlaburj Hospital
|  | Qty V.Pg.No:-03 of MB:-05 |  |  |  | 8 | 8 | 15750 | Nos |  | 126000 |  | 8 | 98000 | 8 | 28000 |  | 20% | 17500
17 | 245 | Office Table at Petlaburj Hospital
|  | Qty V.Pg.No:-03 of MB:-05 |  |  |  | 3 | 3 | 18000 | Nos |  | 54000 |  | 3 | 42000 | 3 | 12000 |  | 20% | 20000
[11 empty] | 17497028 |  |  | 6835763
Electrical-1
1 | 293 | Supply and laying of ISI 25mm outer dia medium grade with IS:9537-part 3 rigid PVC pipe concealed in wall with all required PVC / Metallic Junction Boxes including masonry work and labour charges etc., Makes: Sudhakar / Precision /Universal/ Modi / Million Plast. at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 463.5 | 200 | 93 | RMt |  | 18600 |  | 200 | 18600 |  |  |  | 80% | 116
[6 empty] | AE | 263.5
2 | 294 | Supply and laying of ISI 25mm outer dia medium grade with IS:9537-part 3 rigid PVC pipe surface on wall with all required PVC / Metallic Junction Boxes including masonry work and labour charges etc., Makes: Sudhakar / Precision /Universal/ Modi / Million Plast. at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 1352.8 | 450 | 86 | Rmt |  | 38700 |  | 450 | 38700 |  |  |  | 80% | 107
[6 empty] | AE | 902.8
3 | 295 | Wiring with 2 runs of 22/0.3mm 1.5 Sq.mm FRLS / HFFR P.V.C. insulated flexible copper cable ISI MARK in existing pipe with 6A Modular switch, Ceiling rose/BH/SBH Modular switches with cover plate and GI switch box including all labour charges etc., complete. for Non- Residential Building Makes of wires: Polycab Makes of switches: - /Honeywell Blenge Plus at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 148 | 100 | 756 | Nos |  | 75600 |  | 100 | 75600 |  |  |  | 80% | 945
[6 empty] | AE | 48
4 | 300 | Supply and run of 1 of 22 /0.3mm 1.5 Sq.mm FRLS / HFFR P.V.C. insulated flexible copper cable in existing conduit pipe for earth continuity including all labour charges etc., complete. Makes of wires: Finolex/ RR Cable/ Havells/ Polycab/ HPL. at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 379.6 | 350 | 32 | Rmt |  | 11200 |  | 350 | 11200 |  |  |  | 80% | 40
[6 empty] | AE | 29.6
5 | 301 | Supply and run of 3 of 2.5 sq.mm 36/0.mm phase neutral and earth FRLS / HFFR PVC insulated flexible copper cable in existing conduit pipe for individual lighting circuits including labour charges etc., complete as required for switch boards. Makes of wires: Finolex/ RR Cable/ Havells/ Polycab/ HPL. at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 1713.1 | 600 | 142 | Rmt |  | 85200 |  | 600 | 85200 |  |  |  | 80% | 177
[6 empty] | AE | 1113.1
6 | 302 | Supply and 3 runs of 4.0 sq mm 56/0.3 mm phase neutral and earth FRLS / HFFR PVC insulated flexible copper cable in existing conduit pipe including labour charges etc., complete for 16A sockets. Makes of wires: Finolex/ RR Cable/ Havells/ Polycab/ HPL. at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 2421 | 1200 | 204 | Nos |  | 244800 |  | 1200 | 244800 |  |  |  | 80% | 255
[6 empty] | AE | 1221
7 | 303 | Supply and run of 5 of 6.0 Sqmm 90/0.3 mm 3 phases, neutral and earth FRLS / HFFR PVC insulated flexible copper cable in the existing conduit pipe for run of mains from Power panel board to TPN DBs with pin type lugs and connections etc., complete. for LDBs Makes of wires: Finolex/ RR Cable/ Havells/ Polycab/ HPL. at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 240.1 | 60 | 485 | Rmt |  | 29100 |  | 60 | 29100 |  |  |  | 80% | 606
[6 empty] | AE | 180.1
8 | 304 | Supply and run of 5 of 10.0 Sqmm 140/0.3 mm 3 phases, neutral and earth FRLS / HFFR PVC insulated flexible copper cable in the existing conduit pipe for run of mains from Power panel board to TPN DBs with pin type lugs and connections etc., complete. for PDBs Makes of wires: Finolex/ RR Cable/ Havells/ Polycab/ HPL. at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 284 | 40 | 774 | Rmt |  | 30960 |  | 40 | 30960 |  |  |  | 80% | 967
[6 empty] | AE | 244
9 | 306 | Supply and fixing of 4 Way TPN DB Horizontal with IP 43 Protection as per IS:13032 Makes: Legrand / Schneider and Supply and Fixing of 1 No., of 40A FP 30mA RCCB as incomer and 12 Nos 6-32 A 10kA SP MCBs Makes: Legrand-DX3 / Schneider-Acti9 as out goings including internal connections and labour charges for FLUSH Mounting etc., complete. For Lighting DBs at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 10 | 3 | 14660 | Rmt |  | 43980 |  | 3 | 43980 |  |  |  | 80% | 18325
[6 empty] | AE | 7
10 | 308 | Supply and fixing of 8 Way VTPN DB Horizontal with IP 43 Protection as per IS:13032 Makes: Legrand / Schneider and Supply and Fixing of 1 No., of 100A FP 10KA MCB as incomer and 4 Nos 63 A 10kA TP MCBs, 4 Nos 40 A 10kA TP MCBs Makes: Legrand-DX3 / Schneider-Acti9 as out goings including internal connections and labour charges for FLUSH Mounting etc., complete. For UPS MDB DBs at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 1 | 1 | 51254 | Nos |  | 51254 |  | 1 | 51254 |  |  |  | 80% | 64067
11 | 309 | Providing and fixing of 125A 25KA TPN Thermal Magnetic Release Based MCCB and Terminal Spreaders in Existing panel board with 1 No. and 1 Set of Indication Lamps, LED type, R,Y,B and breaker ON , OFF, TRIP and spring charged lamps. and replace with above Mentioned with required Drilling Holes, removing and Making Busbar connections etc, as required. Makes: Legrand / Schneider/ABB/LandT/CandS at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 1 | 1 | 23106 | Nos |  | 23106 |  | 1 | 23106 |  |  |  | 80% | 28883
12 | 318 | SITC of Hot dip galvanized perforated cable tray of 100 mm Wide sizes for to run the cable from DBs to SBs and sockets and AC panel to Units units. All necessary supports and accessories are included. Cable tray for cables alone shall be included here Thickness shall be 1.6 mm. at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 79 | 70 | 343 | Rmt |  | 24010 |  | 70 | 24010 |  |  |  | 80% | 429
[6 empty] | AE | 9
13 | 319 | SITC of Hot dip galvanized perforated cable tray of 300 mm Wide sizes for to run the cable from Floor Panel to Lab Panel and electrical room to AC panel and AC panel to Units. All necessary supports and accessories are included. Cable tray for cables alone shall be included here Thickness shall be 1.6 mm. at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 102.5 | 80 | 1048 | Rmt |  | 83840 |  | 80 | 83840 |  |  |  | 80% | 1310
[6 empty] | AE | 22.5
14 | 325 | Supply and installation of 50x6 GI flat for body earthing of electrical panel and AC Panel which is laid in 300mm cable tray at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 217.3 | 200 | 263 | Rmt |  | 52600 |  | 200 | 52600 |  |  |  | 80% | 329
[6 empty] | AE | 17.3
15 | 323 | Providing and Fixing maintenance free earthing which consists of G.I. Earth station, with 600X600X3.15mm GI Plate at 2500mm Depth including construction of brick pedestal, providing meshed funnel, GI cover and other civil Engineering works, spreading a homogenous mixture of salt, charcoal around the pipe etc., completely as per IS 3043, 1987 or latest revision. Earthing testing should be done as per IE Rules like Earth valve test Etc. at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 2 | 2 | 6800 | Nos |  | 13600 |  | 2 | 13600 |  |  |  | 80% | 8500
16 | 324 | Providing and Fixing maintenance free earthing which consists of copper. Earth station, with 600X600X3.15mm Copper Plate at 2500mm Depth including construction of brick pedestal, providing meshed funnel, GI cover and other civil Engineering works, spreading a homogenous mixture of salt, charcoal around the pipe etc., completely as per IS 3043, 1987 or latest revision. Earthing testing should be done as per IE Rules like Earth valve test Etc. at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 4 | 2 | 17826 | Nos |  | 35652 |  | 2 | 35652 |  |  |  | 80% | 22283
[6 empty] | AE | 2
17 | 327 | Supply and installation of 25x3 Copper flat for Neutral earthing of UPS and Equipment which is laid in 100mm cable tray at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 207.3 | 200 | 722 | Rmt |  | 144400 |  | 200 | 144400 |  |  |  | 80% | 902
[6 empty] | AE | 7.3
18 | 328 | Supply and installation of 4 sqmm Copper wire for Earthing of DBs Equipment at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 450.6 | 80 | 66 | Rmt |  | 5280 |  | 80 | 5280 |  |  |  | 80% | 83
[6 empty] | AE | 370.6
19 | 329 | Supply, Laying and testing of 3.5Cx95 sqmm XLPE Insulated Cable 1100V grade armoured aluminium cable with ISI mark as per specification confirming to IS:7098 Part - I with heavy duty type double compression weather proof type brass cable glands duly nickel plated as per BS 6121 and IP66 complete with brass checknut, outer sheath sealing gasket heavy duty long barrel aluminium lugs confirming to I.S specifications with complete nut, bolt and washer etc.. Make of Cable: Polycab/ KEI/Universal/Glostar/Finolex. Make of gland and Lungs: HMI/Commet/Dowell’s at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 180 | 120 | 966 | Rmt |  | 115920 |  | 120 | 115920 |  |  |  | 80% | 1207
[6 empty] | AE | 60
20 | 330 | Supply, Lying and testing of 3.5CX50 sqmm XLPE Insulated Cable 1100V grade armoured aluminium cable with ISI mark as per specification confirming to IS:7098 Part - I with heavy duty type double compression weather proof type brass cable glands duly nickel plated as per BS 6121 and IP66 complete with brass checknut, outer sheath sealing gasket heavy duty long barrel aluminium lugs confirming to I.S specifications with complete nut, bolt and washer etc.. Make of Cable: Polycab Make of gland and Lungs: HMI at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 180 | 70 | 578 | Rmt |  | 40460 |  | 70 | 40460 |  |  |  | 80% | 722
[6 empty] | AE | 110
21 | 331 | Supply, Lying and testing of 4Cx16 sqmm PVC Insulated Cable 1100V grade armoured Copper cable with ISI mark as per specification confirming to IS:7098 Part - I with heavy duty type double compression weather proof type brass cable glands duly nickel plated as per BS 6121 and IP66 complete with brass checknut, outer sheath sealing gasket heavy duty long barrel aluminium lugs confirming to I.S specifications with complete nut, bolt and washer etc.. Make of Cable: Polycab/ KEI/Universal/Glostar/Finolex. Make of gland and Lungs: HMI/Commet/Dowell’s at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 100 | 100 | 1186 | Rmt |  | 118600 |  | 100 | 118600 |  |  |  | 80% | 1483
22 | 332 | Supply, Lying and testing of 4Cx6 sqmm PVC Insulated Cable 1100V grade armoured Copper cable with ISI mark as per specification confirming to IS:7098 Part - I with heavy duty type double compression weather proof type brass cable glands duly nickel plated as per BS 6121 and IP66 complete with brass checknut, outer sheath sealing gasket heavy duty long barrel aluminium lugs confirming to I.S specifications with complete nut, bolt and washer etc. Make of Cable: Polycab/ KEI/Universal/ Glostar/Finolex. Make of gland and Lungs: HMI/Commet/Dowell’s at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 120 | 120 | 387 | Rmt |  | 46440 |  | 120 | 46440 |  |  |  | 80% | 484
23 | 333 | Supply, Lying and testing of 4Cx4 sqmm PVC Insulated Cable 1100V grade armoured Copper cable with ISI mark as per specification confirming to IS:7098 Part - I with heavy duty type double compression weather proof type brass cable glands duly nickel plated as per BS 6121 and IP66 complete with brass checknut, outer sheath sealing gasket heavy duty long barrel aluminium lugs confirming to I.S specifications with complete nut, bolt and washer etc. Make of Cable:Polycab/ KEI/Universal/Glostar/Finolex. Make of gland and Lungs: HMI/Commet/Dowell’s at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 80 | 80 | 285 | Rmt |  | 22800 |  | 80 | 22800 |  |  |  | 80% | 356
24 | 334 | SITC of IVF Center Main Panel Indoor IP-42 wall/ free standing floor mounted dust and vermin proof compartmentalized cubical panel made out of CRCA sheet, required hardware, duly treated for de-rusting in 7 tank process with de-phosphate and with powder coating on both side of panel in desired shade. The panel having PU/ Neoprene rubber gasket of not less than 3mm thickness, separate detachable gland plate M.S. base channel, hinged door with locking arrangement for equipment/switchgear. Thickness of sheet shall not be less than 1.6 mm up to 600 mm length / width of any compartment and be of 2.0 mm above 600 mm. Load bearing structure shall be of 2.0 mm thick sheet supported by base M.S. channel if required. Side walls and cable alley compartments having bolted type doors with /without detachable extension type structure with all type of suitable switching accessories and bus-bar as per load requirement of respective IVF equipment’s. Which is including Lighting, power DBs and UPS at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 1 | 1 | 284000 | Nos |  | 284000 |  | 1 | 284000 |  |  |  | 80% | 355000
25 | 335 | SITC of IVF center AC Panel outdoor IP-54 wall/ free standing floor mounted dust and vermin proof compartmentalized cubical panel made out of CRCA sheet, required hardware, duly treated for de-rusting in 7 tank process with de-phosphate and with powder coating on both side of panel in desired shade. The panel having PU/ Neoprene rubber gasket of not less than 3mm thickness, separate detachable gland plate M.S. base channel, hinged door with locking arrangement for equipment/switchgear. Thickness of sheet shall not be less than 1.6 mm up to 600 mm length / width of any compartment and be of 2.0 mm above 600 mm. Load bearing structure shall be of 2.0 mm thick sheet supported by base M.S. channel if required. Side walls and cable alley compartments having bolted type doors with / without detachable extension type structure with all type of suitable switching accessories and bus-bar as per load requirement of respective AC equipment’s. Which is including 1nos AHU’s stater with VFD by pass, Heater, ODU and VRF system at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 1 | 1 | 216000 | Nos |  | 216000 |  | 1 | 216000 |  |  |  | 80% | 270000
[11 empty] | 1856102 |  |  | 1856102
1 | 346 | Supply, transportation and installation of split AC unit 1.5 TR inverter type 3 Star capable of delivering 18000 BTU/hr and above with high wall mounted indoor unit and outdoor condensing unit Hermetically sealed compressor suitable for operation on 230V, 50Hz, 1Phase AC supply capable of performing cooling dehumidifying air circulating and filtering with cooling and condensing units with 3.5 mts of copper piping, insulation kit and 4 mts of 3 core copper flexible chord , built-in stabilizer Voltage range 160- 264 volts and cordless remote control. Makes : Daikin / Thoshiba / O General at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 3 | 1 | 43200 | Nos |  | 43200 |  | 1 | 38400 | 1 | 4800 |  | 10% | 48000
[6 empty] | AE | 2
2 | Sup | Condensing units - VRF/VRV System : Supply, Installation, Nitrogen testing , Vacuuming and Commissioning of air cooled variable refrigerant flow modular type condensing units, each comprising of multiple scroll compressors all inverter driven, full charge of refrigerant gas R-410a including additional gas filling , lubricating oil and all accessories as per the specifications. The condensing units shall be suitable to work on cooling mode. The minimum Energy Efficiency Ratio shall be as per ASHRAE STANDARDS 90.1 -2001 table 6.2.1B . The COP of the system shall be greater than 4 under ARI conditions for 100percentage load . The condensing units shall be suitable for operation on 415 plus or minus 10percentage volts, 50Hz, 3 phase AC power supply and , outdoor units to be mounted on MS platform with suitable Vibration Isolation pads to avoid vibrations. All the supports and angle base frame structure to be duly black painted with synthetic epoxy paint. the condensing units shall be of following capacities: The VRF ODU should be capable of working with total capacity of connected indoor units ranging between 100percentage to 140percentage of ODU capacity . COP minimum 3.5. Make : Daikin / LG / O General / Toshiba at MGMH Petlaburj 16 HP
|  | Qty V.Pg.No:- of MB:- |  |  |  | 1 | 1 | 0 | Nos |  | 0 |  | 1 | 0
3 | 371 | VRF Indoor Units : Hi wall Splits : Supply, Installation, Testing and Commissioning of variable refrigerant flow modular type indoor units wired/wireless remote suitable for R410a refrigerant comprising of all accessories as per the specifications. The indoor units shall be suitable to work on cooling.The minimum Energy Efficiency Ratio shall be as per ASHRAE STANDARDS 90.1 -2001 table 6.2.1B. The indoor units shall be suitable for operation on 220 plus or minus 6percentage volts, 50Hz, 1 phase AC power supply. 0.8 TR at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 2 | 2 | 27630 | Nos |  | 55260 |  | 2 | 49120 | 2 | 6140 |  | 10% | 30700
4 | 372 | VRF Indoor Units : Hi wall Splits : Supply, Installation, Testing and Commissioning of variable refrigerant flow modular type indoor units wired/wireless remote suitable for R410a refrigerant comprising of all accessories as per the specifications. The indoor units shall be suitable to work on cooling.The minimum Energy Efficiency Ratio shall be as per ASHRAE STANDARDS 90.1 -2001 table 6.2.1B. The indoor units shall be suitable for operation on 220 plus or minus 6percentage volts, 50Hz, 1 phase AC power supply. 1.0 TR at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 6 | 3 | 27630 | Nos |  | 82890 |  | 3 | 73680 | 3 | 9210 |  | 10% | 30700
[6 empty] | AE | 3
5 | 373 | VRF Indoor Units : Hi wall Splits : Supply, Installation, Testing and Commissioning of variable refrigerant flow modular type indoor units wired/wireless remote suitable for R410a refrigerant comprising of all accessories as per the specifications. The indoor units shall be suitable to work on cooling.The minimum Energy Efficiency Ratio shall be as per ASHRAE STANDARDS 90.1 -2001 table 6.2.1B. The indoor units shall be suitable for operation on 220 plus or minus 6percentage volts, 50Hz, 1 phase AC power supply. 1.5 TR at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 6 | 4 | 31500 | Nos |  | 126000 |  | 4 | 112000 | 4 | 14000 |  | 10% | 35000
[6 empty] | AE | 2
6 | Sup | Cassette Units : Supply, Installation, Testing and Commissioning of variable refrigerant flow modular type indoor units wired/wireless remote suitable for R410a refrigerant comprising of all accessories as per the specifications. The indoor units shall be suitable to work on cooling mode.The minimum Energy Efficiency Ratio shall be as per ASHRAE STANDARDS 90.1 -2001 table 6.2.1B. The indoor units shall be suitable for operation on 220 plus or minus 6percentage volts, 50Hz, 1 phase AC power supply. 3.0 TR – 4 way at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 2 | 2 | 0 | Nos |  | 0 |  | 2 | 0
7 | 375 | Supply, Installation, Testing and Commissioning of Hard copper REFRIGERANT PIPING of 16swg various sizes with necessary supports, fittings, interconnecting the liquid and suction lines between the aircooled outdoor units and the indoor units. The piping shall be carried out of Hard drawn copper pipes of type K with soldered / brazed socket fittings. Isolating valves shall be provided to isolate each compressor, strainers, sight glass and any other component requiring proper operation and maintenance. Both the suction and liquid lines shall be insulated with 19mm thick closed cell insulation for above 25mm dia , 13mm thick for pipes below 25mm dia . The insulation finished with treated woven glass fiber reinforced covering for inside Piping and including making required holes in the wall and re finishing and water tight of holes after laying holes as per the specifications and approved drawings at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 1 | 1 | 360000 | Lot |  | 360000 |  | 1 | 320000 | 1 | 40000 |  | 10% | 400000
8 | 376 | Supply, Installation , Testing and Commissioning of Refnet joints to be provided in refrigerant pipe line. Material of construction for fittings shall be similar to refrigerant piping at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 15 | 10 | 5572 | Nos |  | 55720 |  | 10 | 49530 | 10 | 6190 |  | 10% | 6191
[6 empty] | AE | 5
9 | 291 | Supply, installation, testing and commissioning of 16 G GI powder coated suitable single person entry air shower as per the Technical Specifications at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 1 | 1 | 319500 | Nos |  | 319500 |  | 1 | 248500 | 1 | 71000 |  | 20% | 355000
10 | 287 | Double leaf clean room Doors : 46mm thick flush doors made of 0.8mm thick Powder coated GI sheets on both sides, 90 plus or minus 2 kg/m3 density Honeycomb with stand upto 220 Deg.C Temperature, and compressible strength upto 400 Kg/Sqm, 1.2 mm thick GPSP . door frames, double glazed vision panel with necessary adhesive tapes and silicon sealant, necessary hardware like SS304 ball bearing butt hinges, D- handles, push plates, Dorma make door closure, concealed tower bolt, drop seals for the double leaf door and provision for fixing magnetic type door interlocking system and automatic door bottoms, Both side lock and keys etc. complete. Size 1500 X 2100 mm with 300mm X 300mm double glazed view panels at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 5 | 4 | 41400 | Nos |  | 165600 |  | 4 | 147200 | 4 | 18400 |  | 10% | 46000
[6 empty] | AE | 1
11 | Sup | Single leaf clean room Doors : 46mm thick flush doors made of 0.8mm thick Powder coated GI sheets on both sides, 90 plus or minus 2 kg/m3 density Honeycomb with stand upto 220 Deg.C Temperature, and compressible strength upto 400 Kg/Sqm, 1.2 mm thick GPSP . door frames, double glazed vision panel with necessary adhesive tapes and silicon sealant, necessary hardware like SS304 ball bearing butt hinges, D- handles, push plates, Dorma make door closure, concealed tower bolt, drop seals for the double leaf door and provision for fixing magnetic type door interlocking system and automatic door bottoms, Both side lock and keys etc. complete. Size 900 X 2100 mm with 300 mm x 300 mm View panelat MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 3 | 3 | 0 | Nos |  | 0 |  | 3 | 0
12 | Sup | Emergency Fire Doors : 46mm thick flush doors made of 0.8mm thick Powder coated GI sheets on both sides, 90 plus or minus 2 kg/m3 density Honeycomb with stand upto 220 Deg.C Temperature, and compressible strength upto 400 Kg/Sqm, 1.2 mm thick GPSP . door frames, double glazed vision panel with necessary adhesive tapes and silicon sealant, necessary hardware like SS304 ball bearing butt hinges, D- handles, push plates, Dorma make door closure, concealed tower bolt, drop seals for the double leaf door and provision for fixing magnetic type door interlocking system and automatic door bottoms, Both side lock and keys etc. complete. Size 1500 X 2100 mm with 2 hours fire rated and panic push bar and accessories etc. at Gandhi Hospital
|  | Qty V.Pg.No:- of MB:- |  |  |  | 1 | 1 |  | Nos |  | 0 |  | 1 | 0
13 | Sup | Emergency Fire Doors : 46mm thick flush doors made of 0.8mm thick Powder coated GI sheets on both sides, 90 plus or minus 2 kg/m3 density Honeycomb with stand upto 220 Deg.C Temperature, and compressible strength upto 400 Kg/Sqm, 1.2 mm thick GPSP . door frames, double glazed vision panel with necessary adhesive tapes and silicon sealant, necessary hardware like SS304 ball bearing butt hinges, D- handles, push plates, Dorma make door closure, concealed tower bolt, drop seals for the double leaf door and provision for fixing magnetic type door interlocking system and automatic door bottoms, Both side lock and keys etc. complete. Size 1000 X 2100 mm with 2 hours fire rated and panic push bar and accessories etc. at Gandhi Hospital
|  | Qty V.Pg.No:- of MB:- |  |  |  | 2 | 2 |  | Nos |  | 0 |  | 2 | 0
14 | 285 | Supply and installation of 80mm thick double skin modular wall Panels made of 0.8 mm thick powder coated GI on both the sides, with 40 plus or minus 2 kg/m3 density PUF as infill, GI profiles all along the periphery, flush on both sides with maximum allowable gap of 3- 4mm filled with food grade silicon sealant and placed on cold rolled galvanised bottom tracks with a recess to provide floor to wall coving flush with the wall panel. This includes all required harware for completion Panels to be covered with a protective film to avoid any damages during transportation and installation at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 121.0376 | 121.04 | 5058 | Sqm |  | 612220.32 |  | 121.04 | 544196 | 121.04 | 68024.48 |  | 10% | 5620
15 | 286 | Supply and installation of 50mm thick double skin ceiling system made of 0.8 mm thick Powder Coated GI sheets on both sides, 40 plus or minus 2 kg/m3 density PUF as infill, GI profiles all along the periphery, panels flush towards room side with maximum allowable gap of 3-4mm at panel to panel joints filled with silicon sealant. Ceiling panels are suspended from the RCC slab by using concealed AL ceiling grid with tie rod and adjustable turn buckle arrangement etc. This includes all required hardware for completion. Panels to be covered with a protective film to avoid any damages during transportation and installation at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 62.6622 | 60 | 4622 | Sqm |  | 277320 |  | 60 | 246480 | 60 | 30840 |  | 10% | 5135
[6 empty] | AE | 2.6622
16 | 289 | Supply and installation of Extruded Aluminium Coving at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 109.83 | 100 | 527 | Sqm |  | 52700 |  | 100 | 46800 | 100 | 5900 |  | 10% | 585
[6 empty] | AE | 9.83
17 | 292 | Supply, installation, Testing and Commissioning of Static Pass Boxes of Size 450X450mm with 1.2mm thick SS 304 Mat finish , with interlock doors, UV light On when doors closed condition. As per clean room standard and requirement. at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 2 | 2 | 54900 | Nos |  | 109800 |  | 2 | 85400 | 2 | 24400 |  | 20% | 61000
18 | 259 | Supplying and fixing of Unplasticised Poly Vinyl Chloride UPVC 3 track sliding windows with mesh shutter – 2-glass shutters and 1-mesh shutter duly manufactured using UPVC reinforced profiles Composition of profile shall consists a minimum of 5.5 PHR of TiO2 and not more than 12 PHR of CaCo3 for every 100 parts of PVC resin of 94mm x 45 mm/80 mm x 52 mm x 2.20 mm for outer frames, 58 mm x 39 mm/54 mm x 38 mm x 2.20mm for sliding shutter frames capable of mounting single glazing system structurally reinforced with hot dip galvanized up to 50 microns of minimum thickness of 1.0/1.2 mm prefabricated and welded through fusion welding. The window sash shall be fitted with 5 mm thick clear float glass of reputed make and mesh shutter frame shall be 42 mm x 25mm/52 mm x 21.5 mm x 2.0 mm fitted with Vinyl Coated Fiber mesh- on rollers/ pulley duly fixed with Grey colour TPV Gasket for sash and Glazing bead shall be co-extruded with Grey colour soft PVC. System shall have single point locking with Touch Lock and the system is to be installed at the site using anchor fasteners, silicon rubber sealant, easy glazing/deglazing at site etc., including cost and conveyance of all materials, accessories, labour charges for transportation, erection at site includingetc., complete for finished item of work. at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 39.83 | 15 | 8565 | Nos |  | 128475 |  | 15 | 128475 | 0 | 0 |  | 90% | 9517
[6 empty] | AE | 24.83
19 | 260 | Providing, supplying and fixing of Fixed Louvered Ventilator made out of multi chambered uPVC sections with Glazing bead shall be co-extruded with Grey colour soft PVC. having isolated drainage and reinforced with Galvanized Iron profiles throughout the window. The outer frame having an overall size of 60 mm x 55 mm x 2.40 with reinforcement of 1 mm thickness and Mullion with overall size of 74 mm x 60 mm x 2.40 mm with reinforcement of 1 mm thickness. Composition of profile shall consists a minimum of 5.5 PHR of TiO2 and not more than 12 PHR of CaCo3 for every 100 parts of PVC resin. Ventilator shall be provided with 4.5 mm Pin Head glass, standard hardware. Wall thickness of frame and Mullion shall be 2.4 mm., including cost and conveyance of all materials, accessories, labour charges for transportation, erection at site etc., complete for finished item of work hinges IS:205 150mm long, 1 No. aldrop IS:2681 300mm long, 1 No. tower bolt IS:204 of 200 mm x 10 mm dia at top, 2 Nos. 150 mm at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:- |  |  |  | 1.96 | 1.96 | 7708 | Nos |  | 15107.68 |  | 1.96 | 15107.68 | 0 | 0 |  | 90% | 8564
20 | 227 | Suction machine at Petlaburj Hospital
|  | Qty V.Pg.No:- of MB:- |  |  |  | 1 | 1 | 44550 | Nos |  | 44550 |  | 1 | 34650 | 1 | 9900 |  | 20% | 49500
21 | 230 | Operative Hysteroscopy and Resectoscope Set Machine at Petlaburj Hospital
|  | Qty V.Pg.No:- of MB:- |  |  |  | 1 | 1 | 1912500 | Nos |  | 1912500 |  | 1 | 1487500 | 1 | 425000 |  | 20% | 2125000
22 | 231 | Operative Laparoscopy Set at Petlaburj Hospital
|  | Qty V.Pg.No:- of MB:- |  |  |  | 1 | 1 | 3780000 | Nos |  | 3780000 |  | 1 | 2940000 | 1 | 840000 |  | 20% | 4200000
| 255 | Plastering 20mm thick in two coats using screened sand with base coat of 16mm thick in CM1:6 and top coat of 4mm thick in CM1:4 with dubara sponge finishing including cost and conveyance of all materials like cement, sand, water etc., to site, including sales and other taxes on all materials, and all operational, incidental charges on materials and including cost of all labour charges for mixing mortar, finishing, scaffolding, lift charges, curing, including cutting grooves as directed by Engineer-in-charge etc., complete for finished item of work .SS 901,903and 904 3rd Floor at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:-0 |  |  |  | 39.56 | 39.56 | 945 | Sqm |  | 37384.2 |  | 0 | 0 | 39.56 | 37384.2 |  |  | 945
| 272 | Supply and fixing of Ashirvad/ Ajay/ Astral Flowguard or equivalent CPVC Pipes and Fittings SDR 13.5 to meet the requirement of ASTM-D 2846 and are produced in CTS Copper Tube Sizes 1/2inches to 2inches for hot and cold water IS 15778:2007 including cost and conveyance of all materials to site, labour charges for fixing,complete for finished item of work at all floor levels. 15.90mm OD pipe at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:-0 | [6 empty] | RMt | [5 empty] | 0 | 0 |  |  | 199
| 273 | Supply and fixing of Ashirvad/ Ajay/ Astral Flowguard or equivalent CPVC Pipes and Fittings SDR 13.5 to meet the requirement of ASTM-D 2846 and are produced in CTS Copper Tube Sizes 1/2inches to 2inches for hot and cold water IS 15778:2007 including cost and conveyance of all materials to site, labour charges for fixing,complete for finished item of work at all floor levels. 22.20mm OD pipe at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:-0 | [6 empty] | RMt | [5 empty] | 0 | 0 |  |  | 229
| 274 | Supplying and fixing of SWR PVC pipes Prince/Sudhakar/Kisan/Supreme or any ISI brand 4 Kg/Sq.cm. and fixing all special such as plain bends, off sets, door bends, single junctions, double junctions as per site requirement, fixing with PVC clamps if necessary with required number of Bombay nails including cost and conveyance of all materials to site, labour charges, complete for finished item of work at all floor levels. APSS No. 1302 1319 and 1326 - 75mm dia at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:-0 | [6 empty] | RMt | [5 empty] | 0 | 0 |  |  | 327
| 275 | Supplying and fixing of SWR PVC pipes Prince/Sudhakar/Kisan/Supreme or any ISI brand 4 Kg/Sq.cm. and fixing all special such as plain bends, off sets, door bends, single junctions, double junctions as per site requirement, fixing with PVC clamps if necessary with required number of Bombay nails including cost and conveyance of all materials to site, labour charges, complete for finished item of work at all floor levels. APSS No. 1302 1319 and 1326- 110mm dia at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:-0 | [6 empty] | RMt | [5 empty] | 0 | 0 |  |  | 444
| 266 | Providing dadooing to walls with glazed full body porcelain wall tiles of size 300 x 600 mm with any type of design texture such as marble finish, wooden, bamboo, stone finishes etc., scratch less, stain free and thickness between 6-8 mm 1st quality conforming to IS:13711, IS:13712, IS:13630 Parts 1 to 15 of any colour and finish in all shades and designs with borders as approved by Engineer-in-Charge set over base coat of CM1:5 12 mm thick using screened sand with cement slurry of honey like consistency spread at the rate of 3.30 kgs per sqm and jointing with white cement paste mixed with pigment of matching shade to full depth, including cost of all materials like tiles, cement, sand and water etc., complete for finished item of work. 3rd Floor at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:-0 |  |  |  | 60.696 | 60.696 | 1391 | Sqm |  | 84428.136 |  | 0 | 0 | 60.696 | 84428.136 |  |  | 1391
| 264 | Flooring with non-skid full body ceramic floor tiles of size 300mm x 300mm and thickness between 7 - 8mm 1st quality conforming to IS: 13711, IS: 13712, IS: 13630Part 1 to 15 of any colour and finish in all shades and designs as approved by Engineer-in-charge, set over base coat of cement mortar 1:8, 12mm thick using screened sand over CC bed already laid or RCC roof slab, including neat cement slurry of honey like consistency spread at the rate 3.3 Kgs per Sqm and jointed neatly with white cement paste to full depth mixed with pigment of matching shade, including cost of all materials like cement, screened sand , water and tiles etc., complete for finished item of work. TSSS No.701 and 707 at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:-0 |  |  |  | 12.9315 | 12.93 | 1395 | Sqm |  | 18037.35 |  | 0 | 0 | 12.93 | 18037.35 |  |  | 1395
| 267 | Providing and applying Wall putty of White Cement or Polymer or Cement based of average 1 to 2 mm thickness over plastered surface to prepare the surface even and smooth after thoroughly brushing the surface to remove all dirt and remains of loose powdered materials, applying emery paper, Sand the surface, clean and wipe off loose dust, applying knifing paste filler by putty knife / muslin pad, air dry for 2 - 3 hrs, sand with 180 and 320 No., emery paper for the surface preparation including cost and conveyance of all materials to work site and all operational, incidental, labour charges, over heads and etc., complete for finished item of work in 3rd floor Internal walls. at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:-0 |  |  |  | 1528.4165 | 975 | 315 | Sqm |  | 307125 |  | 0 | 0 | 975 | 307125 |  |  | 315
[6 empty] | AE | 553.4 | [7 empty] | 553.4
| 265 | Providing and fixing in true horizontal level 14 mm - Mineral Fiber sheet 595 x 595 Square / Tegular Fissura fine model edge tiles with a Humidity Resistance of 90percentage RH, Average NRC 0.50, Light Reflectance greater than80percentage, Thermal Conductivity equal to 0.052 to 0.057 w/mk, Fire Performance Class 0/Class 1 using hot dipped Galvanized Steel section exposed surface with pre-coated capping, main Tee of size 24 x 32 mm at every 1200 mm c/c maximum and rotary stitched cross tee of size 24 x 27 mm at every 600 mm c/c and sub-cross tee of size 24 mm x 25 mm at 1200 mm c/c and wall angle of size 19 x 19 mm fixed to periphery of the wall and the above grid is suspended at every 1200 mm c/c in both directions using 2.0 mm thick pre-straightened GI Wire including cost and conveyance of all materials and labour charges such as cutting , fixing of standing of frame work exposing roof making etc., complete for finished item of work in 3rd floor. at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:-0 |  |  |  | 438.8471 | 300 | 1636 | Sqm |  | 490800 |  | 0 | 0 | 300 | 490800 |  |  | 1636
[6 empty] | AE | 138.8 | [7 empty] | 138.8
| 269 | Supply and application of one coat water based cement primer of interior grade I and two coats of water based PU paint having anti bacterial applications content less than 50 grams/litre for internal walls including cost and conveyance of all materials to site, sales and other taxes, incidental, operational and all labour charges etc., and complete for finished item of work in 3rd floor. at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:-0 |  |  |  | 1528.4165 | 975 | 259 | Sqm |  | 252525 |  | 0 | 0 | 975 | 252525 |  |  | 259
[6 empty] | AE | 553.4165 | [7 empty] | 553.4165
| Sup | Supply and Installation change room Cubicles at Petlaburj Hospital GENERAL SPECIFICATIONS: Thickness of compact Laminate:12mm Thick Colour OF HPL Boards,In Single Colour,Size of Cubicle As per DWG, Door Size For Normal Cubicles AS per DWG Overall Height of Cubicle,2105mm Including bottom gap of 100mm,Accessories , Manufacturers standard makes of aluminium , SS Accessories .a Aluminium H Top Rail b. SS Hinges c. SS privacy Thumb turn occupancy indicator d.SS coat hook e. SS Door knob f. Aluminium U Channel g.Aluminium Door Stopper Channel h. Runner lining i.SS Screw And PVC Wall Plugs
|  | Qty V.Pg.No:- of MB:-0 |  |  |  | 11.2756 | 11.2756 |  | Sqm |  | 0 |  | 0 | 0 | 11.2756 | 0
| 277 | Supplying and fixing of 4inches 101.6mm multi floor trap with jali - UPVC/SWR pipe fittings as per site requirements with standard practice for all floors including cost and conveyance of all materials to site, labour charges ,etc., complete for finished item of work. at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:-0 |  |  |  | 7 | 6 | 220 | Nos |  | 1320 |  | 0 | 0 | 6 | 1320 |  |  | 220
[6 empty] | AE | 1 | [7 empty] | 1
| 278 | Supplying and fixing Indian make Flat Back Wash Hand Basin 1st quality conforming to IS:2556-Part-4:1972 of size 550mm x 400mm with 32 mm nominal size C.P. Fitting with parallel pipe thread conforming to IS:2963- 1979 and fitted with 15 mm nominal bore Chromium Plated Pillar Tap of 1st quality Indian make heavy duty complete with standard CI brackets including wooden blocks ,1 No.12.70mm PVC connection with brass union nuts CP coated , angle stop cock 12.70mm dia. first quality Indian make heavy duty, 30mm dia. PVC flexible waste pipe 914.4mm length of 1st quality including cost and conveyance of all materials to site, labour charges , for finished item of work at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:-0 |  |  |  | 6 | 6 | 3800 | Nos |  | 22800 |  | 0 | 0 | 6 | 22800 |  |  | 3800
| 279 | Supply, Installation and commissioning approved make floor mounted Anglo Indian wash down EWC conforming to IS:2556 Part 8-2004 suit with P or S trap with dual flush porcelain cistern fixed on wash down EWC with all internal parts of dual flush cistern, ultra solid seat cover of approved make with rubber buffer and cap and 15 mm angle stop cock and 450 mm long PVC inter connection pipe wall flanges all of approved make etc. complete for finished item of work in all respects: TBSP-E.II-03 at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:-0 |  |  |  | 6 | 6 | 7590 | Nos |  | 45540 |  | 0 | 0 | 6 | 45540 |  |  | 7590
| 280 | Supplying and fixing Chromium plated finish brass body quarter turn Bibcock cum Health Faucet with 1m long tube and wall hook with necessary fittings etc., complete including cost and conveyance of all materials, labour charges, complete for finished item of work in all floors. at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:-0 |  |  |  | 6 | 6 | 4579 | Nos |  | 27474 |  | 0 | 0 | 6 | 27474 |  |  | 4579
| 281 | Supplying and fixing CP finish brass soap dish of approved make ISI quality including cost and conveyance of all materials, labour charges for fixing, for finished item of work in all floors at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:-0 |  |  |  | 6 | 6 | 872 | Nos |  | 5232 |  | 0 | 0 | 6 | 5232 |  |  | 872
| 282 | Supplying and fixing TV shape mirror with plastic frame of size 609.6mm x 457.2mm, plywood back with NP screws 1st quality including cost and conveyance of all materials, labour charges, for finished item of work in all floors. at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:-0 |  |  |  | 6 | 6 | 727 | Nos |  | 4362 |  | 0 | 0 | 6 | 4362 |  |  | 727
| 283 | Supplying and fixing of CP finish brass wall mounted towel ring at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:-0 |  |  |  | 6 | 6 | 873 | Nos |  | 5238 |  | 0 | 0 | 6 | 5238 |  |  | 873
| 284 | Supplying and fixing 15 mm brass body CP finish self closing tap push type conforming to IS 1711 as approved by the Engineer-In-Charge including cost and conveyance of all materials, labour charges, complete for finished item of work in all floors. at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:-0 |  |  |  | 6 | 6 | 418 | Nos |  | 2508 |  | 0 | 0 | 6 | 2508 |  |  | 418
| 290 | Providing, laying of scratch proof PVC/Vinyl flooring of 2mm thickness with proper welded joints air tight, along with leveling compound to match the existing flooring levels as per engineer in charge instructions. Sub floor preparation with self leveling compound. After the sub floor preparation, it should be suitable for ESD flooring. Rate inclusive of sifting of material and labour charges. at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:-0 |  |  |  | 157.1858 | 140 | 4070 | Sqm |  | 569800 |  | 0 | 0 | 140 | 569800 |  |  | 4070
[6 empty] | AE | 17.1858 | [7 empty] | 17.1858
| 356 | SITC of Factory fabricated and boxed ducting using Aluminium Sheets / coils, should be fabricated as per SMACNA, galvanised hardware and supports, silicon sealant at all longitudinal joints, Galvanized /GI Electroplated iron angle flanges for all the joints, bracing angles and minimum 5mm thick neoprene rubber gasket.- Duct pressure testing at 75mm to be carried out before insulatiting the duct. pressure testing to be done as per SMACNA. Procedure to be approved by consultant. 20G - 1.0 mm Thick at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:-0 |  |  |  | 24.98 | 24.98 | 2600 | Sqm |  | 64948 |  | 0 | 0 | 24.98 | 64948 |  |  | 2600
| 357 | SITC of Factory fabricated and boxed ducting using Aluminium Sheets / coils, should be fabricated as per SMACNA, galvanised hardware and supports, silicon sealant at all longitudinal joints, Galvanized /GI Electroplated iron angle flanges for all the joints, bracing angles and minimum 5mm thick neoprene rubber gasket.- Duct pressure testing at 75mm to be carried out before insulatiting the duct. pressure testing to be done as per SMACNA. Procedure to be approved by consultant. 22G - 0.8 mm Thick at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:-0 |  |  |  | 232.6375 | 232.64 | 2325 | Sqm |  | 540888 |  | 0 | 0 | 232.64 | 540888 |  |  | 2325
| 369 | Supply, laying of Class O Nitrile rubber with factory laminated Glass cloth, all joints shall be covered with self-adhesive tapes 19mm Thick for Return air running inside the building. at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:-0 |  |  |  | 97.493 | 40 | 660 | Sqm |  | 26400 |  | 0 | 0 | 40 | 26400 |  |  | 660
[6 empty] | AE | 57.493 | [7 empty] | 57.493
| 368 | Supply, laying of Class O Nitrile rubber with factory laminated Glass cloth, all joints shall be covered with self-adhesive tapes 25mm Thick for Supply air duct running inside the building. at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:-0 |  |  |  | 76.704 | 40 | 785 | Sqm |  | 31400 |  | 0 | 0 | 40 | 31400 |  |  | 785
[6 empty] | AE | 36.704 | [7 empty] | 36.704
| 367 | Supply, laying of Class O Nitrile rubber with factory laminated Glass cloth, all joints shall be covered with self-adhesive tapes 25mm Thick for Exposed Return Air Duct and finished with UV Protective Paint. at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:-0 |  |  |  | 103.3192 | 103.32 | 1075 | Sqm |  | 111069 |  | 0 | 0 | 103.32 | 111069 |  |  | 1075
| 366 | Supply, laying of Class O Nitrile rubber with factory laminated Glass cloth, all joints shall be covered with self-adhesive tapes 32mm Thick for Exposed Supply Air duct and finished with UV Protective Paint. at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:-0 |  |  |  | 45.7869 | 45.79 | 1225 | Sqm |  | 56092.75 |  | 0 | 0 | 45.79 | 56092.75 |  |  | 1225
| Sup | Modular Double skin floor mounted EUROVENT Certified Air Handling Unit 4400CFM / 11.0 TR / 150mm SP made out of 45 plus or minus 2mm thick PUF insulated panels Thermal break aluminium profile frame work with 0.8mm thick pre painted / powder coated inner and outer skins comprising of mixing box with fresh air and return air dampers, pre filters with 10 and 5 microns combination filters in single frame, Interlaced/Intertwined DX Cooling Coil suitable for connecting 2 nos of 11.0TR capacity 1W plus 1S out door condensing units, SS304 drain pan with , blower section with Nicotra / Kruger make direct drive/ Plug type fan, vibration isolators, EFF1 motor and blower section with on/off switches to operate from outside, limit switch for the fan section access door with a view port, fine filter section with 3 microns filters inspection doors for all filter and fan sections and damper at the outlet of unit. Ports for differential pressure gauges across all filters and blower to measure differential pressure. AHU Make : VTS / Systemair, Make - Blower - Nicotra / Kruger ; Motor - Crompton Greaves / Siemens ; Filter - Thermodyne / Freudenberg / Ultrafil at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:-0 |  |  |  | 1 | 1 | 0 | Nos |  | 0 |  | 0 | 0 | 1 | 0
| 349 | SITC of filter module made out of heavy duty Aluminium powder coated extrusion with minimum of 13G . and to house 610 mm X 610 mm HEPA Filter at the rate 0.3 microns , 99.9997, H-14 Grade, Filter loading from clean room side with bewel gear arrangement damper with access from clean room suitable to house the following filter sizes pressure drop and Integrity testing ports into room. Includes SS capsule perforated diffuser. This includes all required supports and accessories etc. Capacity 1000 CFM. at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:-0 |  |  |  | 6 | 1 | 42000 | Nos |  | 42000 |  | 0 | 0 | 1 | 42000 |  |  | 42000
| Sup | SITC of air cooled condensing units with two scroll compressors, air cooled condenser, power panel, vibration isolating pads, stand for ODU, thermostat, etc. of the following capacities. The nominal capacity of the condensing unit shall be as under. Air cooled condensing unit shall have horizontal discharge. All refrigerant piping accessories sight glass, drier, expansion valve, etc. shall be supplied with the condensing units and suitable to connect above AHUs. Refrigerant shall be R 407C / R 410A. Necessary thermostat, control wiring, etc. shall be included. Derating of the unit shall not be more than 15percentage under 45 deg. C ambient temperature. Condensing unit shall be capable of operating up 50 deg. C ambient temperature. 11.0 TR capacity at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:-0 |  |  |  | 2 | 2 | 0 | Nos |  | 0 |  | 0 | 0 | 2 | 0
| 351 | SITC of Flange type, Flame proof FLP duct heaters of 5 kW capacity with Mineral Filled AISI SS304/SS321 Sheathed Tubular Heater with GI Helical fins, Tube dia 8.2mm min and Helical Finn dia 25mm min, enclosed in the frame, FLP Terminal box etc., Nickel Chromium Inner Element, Silicon Sealing to Restrict Moisture pickup, Silver brazed mounting plate etc., and heaters shall be controlled with PID thyrestor controller based on the analog output signal of 0-10 V DC of controller . And this should have saftey thermostat and cutouts and air stat etc. all safety controls. The capacities as follows and sizes of the heaters shall be as per the duct sizes and approved drawing. at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:-0 |  |  |  | 1 | 1 | 205000 | Nos |  | 205000 |  | 0 | 0 | 1 | 205000 |  |  | 205000
| 352 | SITC of 20/21 G hard drawn copper refrigerant piping with all fittings, supports, insulation with 19 mm thk class O nitrile rubber insulation with factory laminated glass cloth for physical protection and UV protection etc. Quality of copper piping fittings shall be suitable for 18 G piping. Copper piping shall be clamped at every 1.5 mt. distance. copper piping shall be laid on inverted GI perforated cable trays and clamps as per specification inside the building. Copper piping on the terrace shall be laid with bottom and top cable tray. Thickness of the tray shall be 1.6 mm. Copper pipe size shall be as per OEM standards. Liquid Line at MGMH Petlaburjl
|  | Qty V.Pg.No:- of MB:-0 |  |  |  | 16 | 16 | 1020 | Rmt |  | 16320 |  | 0 | 0 | 16 | 16320 |  |  | 1020
| 353 | SITC of 20/21 G hard drawn copper refrigerant piping with all fittings, supports, insulation with 19 mm thk class O nitrile rubber insulation with factory laminated glass cloth for physical protection and UV protection etc. Quality of copper piping fittings shall be suitable for 18 G piping. Copper piping shall be clamped at every 1.5 mt. distance. copper piping shall be laid on inverted GI perforated cable trays and clamps as per specification inside the building. Copper piping on the terrace shall be laid with bottom and top cable tray. Thickness of the tray shall be 1.6 mm. Copper pipe size shall be as per OEM standards. Suction Line at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:-0 |  |  |  | 16 | 16 | 1190 | Rmt |  | 19040 |  | 0 | 0 | 16 | 19040 |  |  | 1190
| 355 | SITC of CPVC drain ping with supports, clamps and 9 mm thk. Nitrile rubber tube insulation of the following sizes. Insulation shall have factory laminated glass cloth. 25mm Dia at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:-0 |  |  |  | 9 | 9 | 515 | Rmt |  | 4635 |  | 0 | 0 | 9 | 4635 |  |  | 515
| Sup | MS Angles 50 x 50 mm x 5 mm thick
|  | Qty V.Pg.No:- of MB:-0 |  |  |  | 62.62 | 62.62 |  | Rmt |  | 0 |  | 0 | 0 | 62.62 | 0
| Sup | MS Angles 32 x 32 mm x 5 mm thick
|  | Qty V.Pg.No:- of MB:-0 |  |  |  | 29.56 | 29.56 |  | Rmt |  | 0 |  | 0 | 0 | 29.56 | 0
| 337 | Supply, installation, testing and commissioning of 20nos LAN points with cat 6 cable and with suitable network rack and 5nos of telephone points with krone box to existing EPABEX. at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:-0 |  |  |  | 1 | 1 | 383000 | Job |  | 383000 |  | 0 | 0 | 1 | 383000 |  |  | 383000
| 338 | Supply, installation, testing and commissioning of 1 no of Access control system with egress switch, Power Cable, communication cable to control panel with necessary required items Etc. at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:-0 |  |  |  | 1 | 1 | 124000 | Job |  | 124000 |  | 0 | 0 | 1 | 124000 |  |  | 124000
| 339 | Supply, installation, testing and commissioning of Automatic Fire Alarm System which is including 30 nos of smoke Detectors 1nos manual call point, 1 no of Hooter with fire alarm cable connected to the existing fire control panel with necessary Required items etc.. at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:-0 |  |  |  | 1 | 1 | 510000 | Job |  | 510000 |  | 0 | 0 | 1 | 510000 |  |  | 510000
| 340 | Supply, installation, testing and commissioning of 5nos IP Based CCTV cameras and Cat 6 Cable with NVR system. at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:-0 |  |  |  | 1 | 1 | 182000 | Job |  | 182000 |  | 0 | 0 | 1 | 182000 |  |  | 182000
| 341 | Supply, installation, testing and commissioning of Audio and video recording of counseling rooms at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:-0 |  |  |  | 1 | 1 | 138000 | Job |  | 138000 |  | 0 | 0 | 1 | 138000 |  |  | 138000
| 342 | Supply and installation of Fire Extinguishers of CO2 4.50 Kg at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:-0 |  |  |  | 5 | 5 | 11225 | Nos |  | 56125 |  | 0 | 0 | 5 | 56125 |  |  | 11225
| 343 | Supply and installation of ceiling mounted Fire Extinguishers of ABC MAP 90, 5.0 Kg stored pressure type at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:-0 |  |  |  | 5 | 5 | 7686 | Nos |  | 38430 |  | 0 | 0 | 5 | 38430 |  |  | 7686
| 344 | Supply and installation of 2.0 Kg clean agent HCFC 123 Fire Extinguishers at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:-0 |  |  |  | 5 | 5 | 15065 | Nos |  | 75325 |  | 0 | 0 | 5 | 75325 |  |  | 15065
| 345 | Supply and fixing of Fire escape signage Boards at MGMH Petlaburj
|  | Qty V.Pg.No:- of MB:-0 |  |  |  | 1 | 1 | 56000 | Job |  | 56000 |  | 0 | 0 | 1 | 56000 |  |  | 56000
| Sup | V- Board Partition
|  | Qty V.Pg.No:- of MB:-0 |  |  |  | 13.7015 | 13.7 | 0 | Sqm |  | 0 |  | 0 | 0 | 13.7 | 0
[9 empty] | Sub-Total:- |  | 12696089.436 |  |  | 6567038.68 |  | 10017355.8096
[8 empty] | Sub-Total(Civil+ Civil Suppl.+Equipment+Electrical+Ac Supply):- |  |  | 33493508.3566 |  |  | 23476154.3 |  | 10017355.8096
[9 empty] | Add GST 18% |  | 6028831.5042 |  |  | 4225707.774 |  | 1803124.0457
[9 empty] | GrandTotal:- |  | 39522339.8608 |  |  | 27701862.074 |  | 11820479.8553
Certificate
The work is in progress in according with the specification drawing and terms and condition the agreement.
[7 empty] | 1) | No recoveries are due for recovery from the contractor other than those proposed in the bill
[7 empty] | 2) | There are no further dues to be recovery from the contractor
[7 empty] | 3) | The contractor has conveyneced the materieals for use on the work as per the lead statement approved the agreement.
[7 empty] | 4) | The leads and lifts are covered in the contractor.
[7 empty] | 5) | The leads and lifts are covered in the contractor.