## Sheet1
Name of the work: Design, fabrication, establishing & commissioning of In-Vitro Fertility Centers (IVFCs) along with allied services on Turnkey basis at Gandhi Hospital, Secunderabad, MGMH Petlaburj, Hyderabad, and MGM Hospital, Warangal.
Comparative Statement
S.No | Description | As Per WorkDone/To be done |  |  | Totals
|  | IVF Gandhi | IVF Petlaburj | IVF Warangal
1 | Equipment | 25908225 | 26020475 | 26020476
2 | Civil Works | 5612831 | 7012631 | 9771661.15
3 | Plumbing works | 126489 | 136973 | 156101
4 | Electrical works | 4027908 | 5641335 | 5402274.4
5 | ELV works | 827000 | 689000 | 1337000
6 | Fire Fighting works | 735880 | 873880 | 225880
7 | Air Conditioning works | 3839121 | 2725391 | 4247076
8 | MGPS works | 1180151.6 | 1141255 | 1046572
| Sub Total (Agreement Part-A) | 42257605.6 | 44240940 | 48207040.55 | 134705586.15
9 | Equipment supplimental | 931300 | 221000 | 317600
10 | Civil supplimental works | 1912429 | 1156237 | 920706
11 | Plumbing supplimental works | 21690 | 8985 | 8985
12 | Electrical supplimental works | 456452.1 | 496686 | 486635
13 | Fire Fighting supplimental works | 291366 | 0 | 291366
14 | Air Conditioning supplimental works | 120788 | 1749744 | 65250
15 | MGPS supplimental works | 814670 | 814670 | 814670
16 | Water Proofing Works | 0 | 0 | 1500000
| Sub Total (Supplimental Part-B) | 4548695.1 | 4447322 | 4405212 | 13401229.1
| Total (Part-A+Part-B) | 46806300.7 | 48688262 | 52612252.55 | 148106815.25
17 | Provision towards Engineering Supervision Charges @ 4% on RE Value | 1872252 | 1947530 | 2104490
| GST @ 18% | 8762139 | 8763887 | 9470205
| Total | 57440691.7 | 59399679 | 64186947.55 | 181027318.25
18 | Labour Cess @ 1% on Basic Price of Revised Estimate | 468063 | 486883 | 526123
19 | NAC @ 0.1% on Basic Price of Revised estimate | 46806 | 48688 | 52612
20 | Provision towards Seniorage Charges on Civil Component | 308 | 448 | 1001
21 | Provision towards DMF Charges 30% on Seniorage Charges | 92 | 134 | 300
22 | Provision towards SMFT Charges 2% on seniorage Charges | 6 | 9 | 20
23 | Provision towards Haritha Nidhi | 4681 | 4869 | 5261
| Sub total of S.No 17 to 22 | 519956 | 541031 | 585317
24 | Provision towards GST 18% on Seniorage Charges | 93592 | 97386 | 105357
25 | Provision towards Unforseen items and rounding off (LS) - | 0 | 910280 | 0
| Sub total of S.No 23 to 25 | 613548 | 1548697 | 690674
| Total | 58054239.7 | 60948376 | 64877621.55 | 183880237.25
26 | TSMSIDC Charges, NAC & Labour Cess @ 5.1% (on S.No 25) | 0 | 46424.28 | 0
27 | New Additional Items As Per IVF Gandhi | 0 | 859451 | 1163790 | 2023241
28 | Extra Items as per Enduser Letter | 0 | 365109 | 652211 | 1017320
29 | Provision towards (LS) - Inaugration Expenses | 200000 | 300000 | 300000 | 800000
| Sub Total (26 to 29) | 200000 | 1570984.28 | 2116001 | 3886985.28
| Grand Total | 58254239.7 | 62519360.28 | 66993622.55 | 187767222.53
| As Per Agreement | 55000000 | 55000000 | 55000000 | 165000000
| As Per Workdone | 58254239.7 | 62519360.28 | 66993622.55 | 187767222.53
| Excess | 3254239.7 | 7519360.28 | 11993622.55 | 22767222.53
| Total Agreement Value | 165000000
| Total Workdone Value | 187767222.53
| Total Excess | 22767222.53

## New_Abstract
Name of the work: Design, fabrication, establishing & commissioning of In-Vitro Fertility Centers (IVFCs) along with allied services on Turnkey basis at Gandhi Hospital, Secunderabad, MGMH Petlaburj, Hyderabad, and MGM Hospital, Warangal.
ABSTRACT COMPARATIVE STATEMENT FOR 3 SITES
S.No | Description |  | IVF Gandhi |  |  | IVF Petlaburj |  |  | IVF Warangal |  |  |  | As Per Workdone/To be done |  |  |  | Excess/Less | Remarks
|  |  | As Per Agreement | As Per Workdone | Excess/Less | As Per Agreement | As Per Workdone | Excess/Less | As Per Agreement | As Per Workdone | Excess/Less | As Per Agreement | IVF Gandhi | IVF Petlaburj | IVF Warangal | Total
PART-A
1 | Equipment |  | 26018225 | 25908225 | -110000 | 26020475 | 26020475 | 0 | 26020476 | 26020476 | 0 | 78059176 |  |  |  | 207939303 | 129880127
2 | Civil Works |  | 7431553 | 5612831 | -1818722 | 5915529 | 7012631 | 1097102 | 7320696 | 9771662 | 2450966 | 20667778 |  |  |  | 58030473 | 37362695
3 | Plumbing works |  | 204480 | 126489 | -77991 | 215122 | 136973 | -78149 | 160285 | 156101 | -4184 | 579887 |  |  |  | 1214533 | 634646
4 | Electrical works |  | 3732008 | 4027908 | 295900 | 3719411 | 5641335 | 1921924 | 3832437 | 5402274 | 1569837 | 11283856 |  |  |  | 37694882 | 26411026
5 | ELV works |  | 827000 | 827000 | 0 | 689000 | 689000 | 0 | 1337000 | 1337000 | 0 | 2853000 |  |  |  | 7732000 | 4879000
6 | Fire Fighting works |  | 735880 | 735880 | 0 | 873880 | 873880 | 0 | 225880 | 225880 | 0 | 1835640 |  |  |  | 4771040 | 2935400
7 | Air Conditioning works |  | 3879885 | 3839121 | -40764 | 3946060 | 2725391 | -1220669 | 3888485 | 4247076 | 358591 | 11714430 |  |  |  | 29457721 | 17743291
8 | MGPS works |  | 1025822 | 1180151.6 | 154329.6 | 1025822 | 1141255 | 115433 | 1025822 | 1046572 | 20750 | 3077466 |  |  |  | 8787601.2 | 5710135.2
9 | Sub Total (Agreement Part-A) (1 to 8) |  | 43854853 | 42257605.6 | -1597247.4 | 42405299 | 44240940 | 1835641 | 43811081 | 48207041 | 4395960 | 130071233 | 42257605.6 | 44240940 | 48207041 | 355627553.2 | 225556320.2
10 | PART-B
11 | Equipment supplimental |  |  | 931300 | 931300 |  | 221000 | 221000 |  | 317600 | 317600 | 0 |  |  |  | 2939800 | 2939800
12 | Civil supplimental works |  |  | 1912429 | 1912429 |  | 1156237 | 1156237 |  | 920706 | 920706 | 0 |  |  |  | 7978744 | 7978744
13 | Plumbing supplimental works |  |  | 21690 | 21690 |  | 8985 | 8985 |  | 8985 | 8985 | 0 |  |  |  | 79320 | 79320
14 | Electrical supplimental works |  |  | 456452.1 | 456452.1 |  | 496686 | 496686 |  | 486635 | 486635 | 0 |  |  |  | 2879546.2 | 2879546.2
15 | Fire Fighting Supplimental works |  |  | 291366 | 291366 |  |  | 0 |  | 291366 | 291366 | 0 |  |  |  | 1165464 | 1165464
16 | Air Conditioning supplimental works |  |  | 120788 | 120788 |  | 1749744 | 1749744 |  | 65250 | 65250 | 0 |  |  |  | 3871564 | 3871564
17 | MGPS supplimental works |  |  | 814670 | 814670 |  | 814670 | 814670 |  | 814670 | 814670 | 0 |  |  |  | 4888020 | 4888020
18 | Water Proofing Works |  |  |  | 0 |  |  | 0 |  | 1500000 | 1500000 | 0 |  |  |  | 0 | 0
19 | Sub Total (Supplimental Part-B) (11 to 18) |  | 0 | 4548695.1 | 4548695.1 | 0 | 4447322 | 4447322 | 0 | 4405212 | 4405212 | 0 | 0 | 0 | 4405212 | 23802458.2 | 23802458.2
20 | Basic Total (Part-A+Part-B) (19+9) |  | 43854853 | 46806300.7 | 2951447.7 | 42405299 | 48688262 | 6282963 | 43811081 | 52612253 | 8801172 | 130071233 | 42257605.6 | 44240940 | 52612253 | 379430011.4 | 249358778.4
21 | Provision towards Engineering Supervision Charges @ 4% on RE Value (on 20) | 4% | 1754194 | 1872252 | 118058 | 1696212 | 1947530 | 251318 | 1752443 | 2104490 | 352047 | 5202849 | 1690304 | 1769638 | 2104490 | 5564432 | 361583
22 | GST @ 18% (on 20) |  | 8209628 | 8762139 | 552511 | 7632954 | 8763887 | 1130933 | 7885995 | 9470206 | 1584211 | 23728577 | 7910624 | 7963369 | 9470206 | 25344199 | 1615622
23 | Total (Part-A+Part-B) (20 to 22) |  | 53818675 | 57440692 | 3622017 | 51734465 | 59399679 | 7665214 | 53449519 | 64186949 | 10737430 | 159002659 | 51858534 | 53973947 | 64186949 | 410338642 | 251335983
24 | TGMSIDC Mandatory Charges
25 | Labour Cess @ 1% on Basic Price of Revised Estimate (on 20) | 1% |  | 468063 | 468063 |  | 486883 | 486883 |  | 526123 | 526123 |  | 422576 | 442409 | 526123 | 1391108 | 1391108
26 | NAC @ 0.1% on Basic Price of Revised estimate (on 20) | 0.1% |  | 46806 | 46806 |  | 48688 | 48688 |  | 52612 | 52612 |  | 42258 | 44241 | 52612 | 139111 | 139111
27 | Provision towards Seniorage Charges on Civil Component |  |  | 308 | 308 |  | 448 | 448 |  | 1001 | 1001 |  | 308 | 448 |  | 756 | 756
28 | Provision towards DMF Charges 30% on Seniorage Charges (on 27) | 30% |  | 92 | 92 |  | 134 | 134 |  | 300 | 300 |  | 92 | 134 | 1001 | 1227 | 1227
29 | Provision towards SMFT Charges 2% on seniorage Charges (On 27) | 2% |  | 6 | 6 |  | 9 | 9 |  | 20 | 20 |  | 6 | 9 | 0 | 15 | 15
30 | Provision towards Haritha Nidhi (on 20) | 0.01% |  | 4681 | 4681 |  | 4869 | 4869 |  | 5261 | 5261 |  | 4226 | 4424 | 5261 | 13911 | 13911
31 | Sub total of S.No (25 to 30) |  | 0 | 519956 | 519956 | 0 | 541031 | 541031 | 0 | 585317 | 585317 | 0 | 469466 | 491665 | 584997 | 1546128 | 1546128
32 | Provision towards GST 18% on Above Charges (on 31) | 18% | [10 empty] | 84503.88 | 88499.7 | 105299.46 | 278303.04 | 278303.04
33 | Provision towards Unforseen items and rounding off (LS) - |  | 1181325 |  |  | 3265535 |  |  | 1550481 |  |  | 5997341 | 0 | 910280 |  | 910280 | -5087061
34 | Sub total of S.No (31 to 33) |  | 1181325 |  |  | 3265535 |  |  | 1550481 |  |  | 5997341 | 553969.88 | 1490444.7 | 690296.46 | 2734711.04 | -3262629.96
35 | Total (34+23) |  | 55000000 |  |  | 55000000 |  |  | 55000000 |  |  | 165000000 | 52412503.88 | 55464391.7 | 64877245.46 | 413073353.04 | 248073353.04
36 | TGMSIDC Mandatory Charges For LS Amount (Rs. 9,10,280) (For PBJ Only) | [16 empty] | Rs. 9,10,280 is inclusive of GST @18%
37 | Labour Cess @ 1% on LS Amount | 1% | [11 empty] | 9103 |  | 9103 | 9103 | For PBJ Only
38 | NAC @ 0.1% on LS Amount | 0.1% | [11 empty] | 910 |  | 910 | 910 | For PBJ Only
39 | Provision towards Haritha Nidhi on LS Amount | 0.01% | [11 empty] | 91 |  | 91 | 91 | For PBJ Only
40 | Provision towards Engineering Supervision Charges @ 4% on LS Amount | 4% | [11 empty] | 36411 |  | 36411 | 36411 | For PBJ Only
41 | Sub Total (37 to 40) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 46515 | 0 | 46515 | 46515
42 | Total (41+35) |  | 55000000 |  |  | 55000000 |  |  | 55000000 |  |  | 165000000 | 52412503.88 | 55510906.7 | 64877245.46 | 413119868.04 | 248119868.04
43 | PART-C
44 | Interior Works As Per IVF Petlaburj | [10 empty] | 0 |  |  | 406531 | 406531 | 406531 | For WGL Only
45 | GST @ 18% on 44 | [10 empty] | 0 | 0 | 0 | 73176 | 73176 | 73176 | For WGL Only
46 | Total (44 to 45) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 479707 | 479707 | 479707 | For WGL Only
47 | TGMSIDC Mandatory Charges | [16 empty] | For WGL Only
48 | Labour Cess @ 1% on Part-C (S.No 44) | 1% | [12 empty] | 4065 | 4065 | 4065 | For WGL Only
49 | NAC @ 0.1% on Part-C (S.No 44) | 0.1% | [12 empty] | 407 | 407 | 407 | For WGL Only
50 | Provision towards Haritha Nidhi on Part-C (S.No 44) | 0.01% | [12 empty] | 41 | 41 | 41 | For WGL Only
51 | Provision towards Engineering Supervision Charges @ 4% on Part-C (S.No 44) | 4% | [12 empty] | 16261 | 16261 | 16261 | For WGL Only
52 | Sub Total (48 to 51) | [10 empty] | 0 | 0 | 0 | 20774 | 20774 | 20774
53 | Provision towards GST 18% on Above Charges (on 52) | [10 empty] | 0 | 0 | 0 | 3739 | 3739 | 3739
54 | Sub Total (52 to 53) | [10 empty] | 0 | 0 | 0 | 24513 | 24513 | 24513
55 | Total (PART-C) (54+46) | [10 empty] | 0 | 0 | 0 | 504220 | 504220 | 504220
56 | Total (Part-A+B+C) (55+35) |  | 55000000 |  |  | 55000000 |  |  | 55000000 |  |  | 165000000 | 52412503.88 | 55464391.7 | 65381465.46 | 413577573.04 | 248577573.04
57 | PART-D
58 | Equipment | [12 empty] | 549100 | 549100 | 1098200 | 1098200 | For PBJ & WGL Only
59 | Furniture | [12 empty] | 143905 | 121385 | 265290 | 265290 | For PBJ & WGL Only
60 | Basic Sub Total (58 to 59) | [10 empty] | 0 | 0 | 693005 | 670485 | 1363490 | 1363490 | For PBJ & WGL Only
61 | GST @ 18% on 60 | [10 empty] | 0 | 0 | 124741 | 120687 | 245428 | 245428 | For PBJ & WGL Only
62 | Total (60 to 61) | [10 empty] | 0 | 0 | 817746 | 791172 | 1608918 | 1608918 | For PBJ & WGL Only
63 | TGMSIDC Mandatory Charges | [16 empty] | For PBJ & WGL Only
64 | Labour Cess @ 1% on Part-D (S.No 60) | 1% | [10 empty] | 0 | 6930 | 6705 | 13635 | 13635 | For PBJ & WGL Only
65 | NAC @ 0.1% on Part-D (S.No 60) | 0.1% | [10 empty] | 0 | 693 | 670 | 1363 | 1363 | For PBJ & WGL Only
66 | Provision towards Haritha Nidhi Part-D (S.No 60) | 0.01% | [10 empty] | 0 | 69 | 67 | 136 | 136 | For PBJ & WGL Only
67 | Provision towards Engineering Supervision Charges @ 4% on Part-D (S.No 60) | 4% | [10 empty] | 0 | 27720 | 26819 | 54539 | 54539 | For PBJ & WGL Only
68 | Sub Total (64 to 67) | [10 empty] | 0 | 0 | 35412 | 34261 | 69673 | 69673
69 | Provision towards GST 18% on Above Charges (on 68) | [10 empty] | 0 | 0 | 6374 | 6167 | 12541 | 12541
70 | Sub Total (68 to 69) | [10 empty] | 0 | 0 | 41786 | 40428 | 82214 | 82214
71 | Total (PART-D) (70+62) | [10 empty] | 0 | 0 | 859532 | 831600 | 1691132 | 1691132
72 | Total (PART-A+B+C+D) (71+56) |  | 55000000 |  |  | 55000000 |  |  | 55000000 |  |  | 165000000 | 52412503.88 | 56323923.7 | 66213065.46 | 415268705.04 | 250268705.04
73 | PART-E
74 | Additional Items As Per End User Letter | [12 empty] | 294400 | 525900 | 820300 | 820300 | For PBJ & WGL Only
75 | GST @ 18% on 74 | [11 empty] | 0 | 52992 | 94662 | 147654 | 147654 | For PBJ & WGL Only
76 | Sub Total (74 to 75) | [10 empty] | 0 | 0 | 347392 | 620562 | 967954 | 967954 | For PBJ & WGL Only
77 | TGMSIDC Mandatory Charges | [16 empty] | For PBJ & WGL Only
78 | Labour Cess @ 1% on Part-E (S.No 74) | 1% | [10 empty] | 0 | 2944 | 5259 | 8203 | 8203 | For PBJ & WGL Only
79 | NAC @ 0.1% on Part-E (S.No 74) | 0.1% | [10 empty] | 0 | 294 | 526 | 820 | 820 | For PBJ & WGL Only
80 | Provision towards Haritha Nidhi on Part-E (S.No 74) | 0.01% | [10 empty] | 0 | 29 | 53 | 82 | 82 | For PBJ & WGL Only
81 | Provision towards Engineering Supervision Charges @ 4% on Part-E (S.No 74) | 4% | [10 empty] | 0 | 11776 | 21036 | 32812 | 32812 | For PBJ & WGL Only
82 | Sub Total (78 to 81) | [10 empty] | 0 | 0 | 15043 | 26874 | 41917 | 41917 | For PBJ & WGL Only
83 | Provision towards GST 18% on Above Charges (on 82) | [10 empty] | 0 | 0 | 2708 | 4837 | 7545 | 7545 | For PBJ & WGL Only
84 | Sub Total (82 to 83) | [10 empty] | 0 | 0 | 17751 | 31711 | 49462 | 49462
85 | Total (PART-E) (84+76) | [10 empty] | 0 | 0 | 365143 | 652273 | 1017416 | 1017416
86 | Total (PART-A+B+C+D+E) (85+72) |  | 55000000 |  |  | 55000000 |  |  | 55000000 |  |  | 165000000 | 52412503.88 | 56689066.7 | 66865338.46 | 416286121.04 | 251286121.04
87 | Provision towards (LS) - Inaugration Expenses | [11 empty] | 200000 | 300000 | 300000 | 800000 | 800000
| Grand Total (86 to 87) |  | 55000000 |  |  | 55000000 |  |  | 55000000 |  |  | 165000000 | 52612503.88 | 56989066.7 | 67165338.46 | 417086121.04 | 252086121.04
[12 empty] | As per Admn. Sanction | 165000000
[12 empty] | As per Work done | 417086121.04
[12 empty] | Difference | 252086121.04