## 3 Site Consolidated
|  | MCH Building, Gandhi Hospital |  |  | MGMH PETLABURZ |  |  | MGM WARANGAL |  |  | Difference (PTB - GH) | Total |  |  | Remarks
A | B | C | D | E | F | G | H | I | J | K |  | L | M | N | O
| Layout Area (SQM) | 447.8 | 418.415 |  | 453.08 | 594.38 | 31.19% | 503 | 597.3 | 18.75% |  | 1403.88 | 1610.095 | 14.69%
S.No | Description | As per Agreement | As per workdone | Excess / Less | As per Agreement | As per workdone | Excess / Less | As per Agreement | As per workdone | Excess / Less |  | As per Agreement | As per workdone | Excess / Less
PART-A
1 | Equipment & Furniture | 26018225 | 25908225 | -110000 | 26020475 | 26020475 | 0 | 26020476 | 26020476 | 0 | 110000 | 78059176 | 77949176 | -110000 | As Per RE
2 | Civil Works | 7431553 | 5612831 | -1818722 | 5915529 | 7012631 | 1097102 | 7320696 | 9771662 | 2450966 | 2915824 | 20667778 | 22397124 | 1729346 | As Per RE
3 | Plumbing works | 204480 | 126489 | -77991 | 215122 | 136973 | -78149 | 160285 | 156101 | -4184 | -158 | 579887 | 419563 | -160324 | As Per RE
4 | Electrical works | 3732008 | 4027908 | 295900 | 3719411 | 5641335 | 1921924 | 3832437 | 5402274 | 1569837 | 1626024 | 11283856 | 15071517 | 3787661 | As Per RE
5 | ELV works | 827000 | 827000 | 0 | 689000 | 689000 | 0 | 1337000 | 1337000 | 0 | 0 | 2853000 | 2853000 | 0 | As Per RE
6 | Fire Fighting works | 735880 | 735880 | 0 | 873880 | 873880 | 0 | 225880 | 225880 | 0 | 0 | 1835640 | 1835640 | 0 | As Per RE
7 | Air Conditioning works | 3879885 | 3839121 | -40764 | 3946060 | 2725391 | -1220669 | 3888485 | 4247076 | 358591 | -1179905 | 11714430 | 10811588 | -902842 | As Per RE
8 | MGPS works | 1025822 | 1180151.6 | 154329.6 | 1025822 | 1141255 | 115433 | 1025822 | 1046572 | 20750 | -38896.6 | 3077466 | 3367978.6 | 290512.6 | As Per RE
9 | Total (Part-A) (1 to 8) | 43854853 | 42257605.6 | -1597247.4 | 42405299 | 44240940 | 1835641 | 43811081 | 48207041 | 4395960 | 3432888.4 | 130071233 | 134705586.6 | 4634353.6
10 | PART-B
11 | Equipment & Furniture supplimental |  | 931300 | 931300 |  | 221000 | 221000 |  | 317600 | 317600 | -710300 | 0 | 1469900 | 1469900 | As Per RE
12 | Civil supplimental works |  | 1912429 | 1912429 |  | 1156237 | 1156237 |  | 920706 | 920706 | -756192 | 0 | 3989372 | 3989372 | As Per RE
13 | Plumbing supplimental works |  | 21690 | 21690 |  | 8985 | 8985 |  | 8985 | 8985 | -12705 | 0 | 39660 | 39660 | As Per RE
14 | Electrical supplimental works |  | 456452.1 | 456452.1 |  | 496686 | 496686 |  | 486635 | 486635 | 40233.9 | 0 | 1439773.1 | 1439773.1 | As Per RE
15 | Fire Fighting supplimental works |  | 291366 | 291366 |  |  | 0 |  | 291366 | 291366 | -291366 | 0 | 582732 | 582732 | As Per RE
16 | Air Conditioning supplimental works |  | 120788 | 120788 |  | 1749744 | 1749744 |  | 65250 | 65250 | 1628956 | 0 | 1935782 | 1935782 | As Per RE
17 | MGPS supplimental works |  | 814670 | 814670 |  | 814670 | 814670 |  | 814670 | 814670 | 0 | 0 | 2444010 | 2444010 | As Per RE
A: 18; B: Water Proofing Works; MCH Building, Gandhi Hospital E: 0; MGMH PETLABURZ H: 0; MGM WARANGAL J: 1500000; MGM WARANGAL K: 1500000 |  | 0 | 1500000 | 1500000 | As Per RE
19 | Total (Part-B) (11 to 18) | 0 | 4548695.1 | 4548695.1 | 0 | 4447322 | 4447322 | 0 | 4405212 | 4405212 | -101373.1 | 0 | 13401229.1 | 13401229.1
20 | Total (Part-A+B) (19+9) | 43854853 | 46806300.7 | 2951447.7 | 42405299 | 48688262 | 6282963 | 43811081 | 52612253 | 8801172 | 3331515.3 | 130071233 | 148106815.7 | 18035582.7
21 | PART-C
A: 22; B: Interior Works; MGMH PETLABURZ G: 771424; MGMH PETLABURZ H: 771424; MGM WARANGAL J: 406531; MGM WARANGAL K: 406531 |  | 0 | 1177955 | 1177955 | As Per Annexure-01
A: 23; B: Equipment; MGMH PETLABURZ G: 549100; MGMH PETLABURZ H: 549100; MGM WARANGAL J: 549100; MGM WARANGAL K: 549100 |  | 0 | 1098200 | 1098200 | As Per Annexure-02
A: 24; B: Furniture; MGMH PETLABURZ G: 143905; MGMH PETLABURZ H: 143905; MGM WARANGAL J: 108985; MGM WARANGAL K: 108985 |  | 0 | 252890 | 252890 | As Per Annexure-02
A: 25; B: Additional Items As Per End User Letter; MGMH PETLABURZ G: 294400; MGMH PETLABURZ H: 294400; MGM WARANGAL J: 525900; MGM WARANGAL K: 525900 |  | 0 | 820300 | 820300 | As Per Annexure-03
26 | Total (Part-C) (22 to 25) | 0 | 0 | 0 | 0 | 1758829 | 1758829 | 0 | 1590516 | 1590516 | 0 | 0 | 3349345 | 3349345
27 | Total (Part-A+B+C) (26+20) | 43854853 | 46806300.7 | 2951447.7 | 42405299 | 50447091 | 8041792 | 43811081 | 54202769 | 10391688 | 3331515.3 | 130071233 | 151456160.7 | 21384927.7
28 | TGMSIDC Mandatory Charges
29 | Provision towards Seniorage Charges on Civil Component | 0 | 308 | 308 |  | 448 | 448 |  | 1001 | 1001 |  | 0 | 1757 | 1757
30 | Provision towards DMF & SMFT Charges @32% | 0 | 99 | 99 |  | 143 | 143 |  | 320 | 320 |  | 0 | 562 | 562 | (DMF-30%+SMFT-2% Charges)
31 | TGMSIDC Mandatory Charges @5.11% | 1754194 | 2391802 | 637608 | 1696212 | 2577846 | 881634 | 1752443 | 2769761 | 1017318 |  | 5202849 | 7739409 | 2536560 | (Supervision Charges-4%+Labour Cess-1% +NAC-0.1%+Haritha Nidhi-0.01%)
32 | Sub Total (28 to 31) | 1754194 | 2392209 | 638015 | 1696212 | 2578437 | 882225 | 1752443 | 2771082 | 1018639 | 0 | 5202849 | 7741728 | 2538879
33 | Total (27+32) | 45609047 | 49198509.7 | 3589462.7 | 44101511 | 53025528 | 8924017 | 45563524 | 56973851 | 11410327 | 3331515.3 | 135274082 | 159197888.7 | 23923806.7
34 | GST @18% | 8209628 | 8855732 | 646104 | 7632954 | 9181376 | 1548422 | 7885995 | 9865033 | 1979038 |  | 23728577 | 27902141 | 4173564
35 | Provision towards (LS) - Inaugration Expenses | 1181325 | 200000 | -981325 | 3265535 | 300000 | -2965535 | 1550481 | 300000 | -1250481 |  | 5997341 | 800000 | -5197341
36 | Grand Total (33 to 35) | 55000000 | 58254241.7 | 3254241.7 | 55000000 | 62506904 | 7506904 | 55000000 | 67138884 | 12138884 | 3331515.3 | 165000000 | 187900029.7 | 22900029.7
|  |  | As Per Agreement | 165000000
|  |  | As per workdone | 187900029.7
|  |  | Difference | 22900029.7
The Net Difference Amount = 2,29,00,030 Rupees

## Annexure-01
Annexure-01
IVF PETLABURJ
S.No | Item Description | UOM | Qty | Rate (Rs.) | Amount (Rs.) | Remarks
1 | Powder coated GI stand in IVF OT | Nos | 1 | 80000 | 80000
2 | High Quality IVF Procedural photos at Entrance and Reception | Nos | 12 | 9000 | 108000
3 | 60mm Thick Box framing as the back support for the name plate at Entrance | Sqm | 3.98 | 11012 | 43828
4 | Door Frame side Paneling at Entrance | Sqm | 7.551 | 9250 | 69847
5 | 32mm Double Flush Door (1800 x 2100 mm door) at Entrance | Nos | 1 | 56500 | 56500
6 | Name Plate With Glossy Laminate at Entrance | Sqm | 2.6 | 9580 | 24908
7 | MIRROR GOLD TITANIUM LETTERS & S.S. MIRROR LETTERS at Entrance | Job | 1 | 67500 | 67500
8 | Double side ACP sheet (Name board wth three languages fixed at IVF Entrance Corridor) | Nos | 1 | 6000 | 6000
9 | Foam Board (Name board wth three languages with direction to IVF Center fixed at 3rd floor) | Nos | 2 | 2800 | 5600
10 | Foam Board (Name board wth with direction to Rooms fixed to wall in IVF Corridor,) | Nos | 2 | 3200 | 6400
11 | Main IVF logo with LED arcylic board at Entrance | Nos | 1 | 11475 | 11475
12 | Addressable fire control panel at Entrance | Nos | 1 | 291366 | 291366
|  |  |  | TOTAL | 771424
IVF WARANGAL
S.No | Item Description | UOM | Qty | Rate (Rs.) | Amount (Rs.) | Remarks
1 | High Quality IVF Procedural photos at Entrance and Reception | Nos | 12 | 9000 | 108000 | As Per IVF Petlaburj
2 | 60mm Thick Box framing as the back support for the name plate at Entrance | Sqm | 3.98 | 11012 | 43828 | As Per IVF Petlaburj
3 | Door Frame side Paneling at Entrance | Sqm | 7.551 | 9250 | 69847 | As Per IVF Petlaburj
4 | 32mm Double Flush Door (1800 x 2100 mm door) at Entrance | Nos | 1 | 56500 | 56500 | As Per IVF Petlaburj
5 | Name Plate With Glossy Laminate at Entrance | Sqm | 2.6 | 9580 | 24908 | As Per IVF Petlaburj
6 | MIRROR GOLD TITANIUM LETTERS & S.S. MIRROR LETTERS at Entrance | Job | 1 | 67500 | 67500 | As Per IVF Petlaburj
7 | Double side ACP sheet (Name board wth three languages fixed at IVF Entrance Corridor) | Nos | 1 | 6000 | 6000 | As Per IVF Petlaburj
8 | Foam Board (Name board wth three languages with direction to IVF Center fixed at 3rd floor) | Nos | 2 | 2800 | 5600 | As Per IVF Petlaburj
9 | Foam Board (Name board wth with direction to Rooms fixed to wall in IVF Corridor,) | Nos | 2 | 3200 | 6400 | As Per IVF Petlaburj
10 | Main IVF logo with LED arcylic board at Entrance | Nos | 1 | 11475 | 11475 | As Per IVF Petlaburj
11 | PVC frames on the walls for covering the area over DB Boxes | Sqm | 1 | 6473 | 6473 | As Per IVF Petlaburj
|  |  |  | Sub Total | 406531

## Annexure-02
ANNEXURE-02
Additional Items As Per IVF Gandhi
S.No | Item Description | UOM | Rate (Rs.) | IVF Petlaburj |  | IVF Warangal
|  |  |  | Qty | Amount (Rs.) | Qty | Amount (Rs.) | Remarks
Equipment
1 | Fowler Two Function Bed with ABS Panel in Pre and Post Operative wards and Semen Collection room | Nos | 39000 | 5 | 195000 | 5 | 195000 | As Per IVF Gandhi
2 | Bed side Table with ABS Plastic body in Pre and Post Operative wards and Semen Collection room | Nos | 9000 | 5 | 45000 | 5 | 45000 | As Per IVF Gandhi
3 | Corporate Deluxe Locker with SS 304 grade Top in Sample Collection and Injection Room | Nos | 8400 | 1 | 8400 | 1 | 8400 | As Per IVF Gandhi
4 | Bed side stand with full SS 304 grade constructionof in Sample Collection and Injection Room | Nos | 9300 | 1 | 9300 | 1 | 9300 | As Per IVF Gandhi
5 | Bed side stand with full GI Powder coated constructionof in Semen Collection room | Nos | 4200 | 1 | 4200 | 1 | 4200 | As Per IVF Gandhi
6 | Supply of a Sample collection chair in Sample Collection and Injection Room | Nos | 16200 | 1 | 16200 | 1 | 16200 | As Per IVF Gandhi
7 | Sample collection bed in Sample Collection and Injection Room | Nos | 29000 | 1 | 29000 | 1 | 29000 | As Per IVF Gandhi
8 | Cryo Can 11 Ltr without wheels in Cryo room | Nos | 32000 | 1 | 32000 | 1 | 32000 | As Per IVF Gandhi
9 | The Multipurpose Electro Hydraulic Mobile OT Table in Major OT | Nos | 210000 | 1 | 210000 | 1 | 210000 | As Per IVF Gandhi
|  |  | Total |  | 549100 |  | 549100
Furniture
10 | Writing board in Counselling rooms | Nos | 2100 | 1 | 2100 | 2 | 4200 | As Per IVF Gandhi
11 | MDF wooden table in Reception and Ultrasound room | Nos | 14500 | 2 | 29000 | 1 | 14500 | As Per IVF Gandhi
12 | Office table in Embryologist and Anesthetist room | Nos | 16000 | 2 | 32000 |  | 0 | As Per IVF Gandhi
13 | Window blinds (For semen collection room & Counselling room Windows) | Sqm | 2187 | 15 | 32805 |  | 0 | As Per IVF Gandhi
14 | Hydraullic door closer for ABS Doors | Nos | 2819 |  | 0 | 15 | 42285
15 | 3 Seater Sofa | Nos | 24000 | 2 | 48000 | 2 | 48000 | As Per IVF Gandhi
|  |  | Total |  | 143905 |  | 108985

## Annexure-03
ANNEXURE-03
Extra Items As Per End User Letter
S.NO | Description | UOM | Rate (Rs.) | IVF Petlaburj |  | IVF Warangal |  | Remarks
|  |  |  | QTY | Amount (Rs.) | QTY | Amount (Rs.)
1 | Consultant Chair in Embryologist and Anesthetist room | Nos | 20000 | 3 | 60000 | 3 | 60000 | Extra Items
2 | Patient Chair Embryologist and Anesthetist room | Nos | 13500 | 6 | 81000 | 6 | 81000 | Extra Items
3 | Lab Chairs Type I (DCA Price) in Andrology Lab & Embryology Lab | Nos | 15340 | 10 | 153400 | 10 | 153400 | Extra Items
4 | IUI Couch/ Table in IUI Room | Nos | 50000 |  | 0 | 2 | 100000 | Extra Items
5 | office table in Embryologist room | Nos | 16000 |  | 0 | 1 | 16000 | Extra Items
6 | Patient Seating 3 in 1 model in waiting area | Nos | 38500 |  | 0 | 3 | 115500 | Extra Items
|  |  | Total |  | 294400 |  | 525900