## 3 Site Consolidated
|  | Gandhi Hospital, Secunderabad |  |  | MGMH PETLABURZ |  |  | MGM WARANGAL |  |  | Difference (PTB - GH) | Total |  |  | Remarks
A | B | C | D | E | F | G | H | I | J | K |  | L | M | N | O
S.No | Description | As per Agreement | As per workdone | Excess / Less | As per Agreement | As per workdone | Excess / Less | As per Agreement | As per workdone | Excess / Less |  | As per Agreement | As per workdone | Excess / Less
| Layout Area (SQM) | 447.8 | 418.415 |  | 453.08 | 594.38 |  | 503 | 597.3 |  |  | 1403.88 | 1610.095
As Per Agreement (PART-A)
1 | Equipment | 25009375 | 25009375 | 0 | 25009375 | 25009375 | 0 | 25009376 | 25009376 | 0 | 0 | 75028126 | 75028126 | 0 | As Per RE/WE
2 | Furniture | 1008850 | 898850 | -110000 | 1011100 | 1011100 | 0 | 1011100 | 1011100 | 0 |  | 3031050 | 2921050 | -110000 | As Per RE/WE
3 | Civil Works | 7431553 | 5612831 | -1818722 | 5915529 | 7012631 | 1097102 | 7320696 | 9771662 | 2450966 | 2915824 | 20667778 | 22397124 | 1729346 | As Per RE/WE
4 | Plumbing works | 204480 | 126489 | -77991 | 215122 | 136973 | -78149 | 160285 | 156101 | -4184 | -158 | 579887 | 419563 | -160324 | As Per RE/WE
5 | Electrical works | 3732008 | 4027908 | 295900 | 3719411 | 5641335 | 1921924 | 3832437 | 5402274 | 1569837 | 1626024 | 11283856 | 15071517 | 3787661 | As Per RE/WE
6 | ELV works | 827000 | 827000 | 0 | 689000 | 689000 | 0 | 1337000 | 1337000 | 0 | 0 | 2853000 | 2853000 | 0 | As Per RE/WE
7 | Fire Fighting works | 735880 | 735880 | 0 | 873880 | 873880 | 0 | 225880 | 225880 | 0 | 0 | 1835640 | 1835640 | 0 | As Per RE/WE
8 | Air Conditioning works | 3879885 | 3839121 | -40764 | 3946060 | 2725391 | -1220669 | 3888485 | 4247076 | 358591 | -1179905 | 11714430 | 10811588 | -902842 | As Per RE/WE
9 | MGPS works | 1025822 | 1180151.6 | 154329.6 | 1025822 | 1141255 | 115433 | 1025822 | 1046572 | 20750 | -38896.6 | 3077466 | 3367978.6 | 290512.6 | As Per RE/WE
10 | Total (Part-A) (1 to 9) | 43854853 | 42257605.6 | -1597247.4 | 42405299 | 44240940 | 1835641 | 43811081 | 48207041 | 4395960 | 3322888.4 | 130071233 | 134705586.6 | 4634353.6
11 | Supplimental (PART-B)
12 | Equipment supplimental |  | 850100 | 850100 |  | 850100 | 850100 |  | 850100 | 850100 | 0 | 0 | 2550300 | 2550300 | As Per RE/WE
13 | Furniture supplimental |  | 234600 | 234600 |  | 405500 | 405500 |  | 607100 | 607100 |  | 0 | 1247200 | 1247200 | As Per RE/WE
14 | Interior and other works |  | 1151096 | 1151096 |  | 532451 | 532451 |  | 592908 | 592908 |  | 0 | 2276455 | 2276455 | As Per RE/WE
15 | Civil supplimental works |  | 802549 | 802549 |  | 1056649 | 1056649 |  | 841331 | 841331 | 254100 | 0 | 2700529 | 2700529 | As Per RE/WE
16 | Plumbing supplimental works |  | 21690 | 21690 |  | 8985 | 8985 |  | 8985 | 8985 | -12705 | 0 | 39660 | 39660 | As Per RE/WE
17 | Electrical supplimental works |  | 415236 | 415236 |  | 496686 | 496686 |  | 486635 | 486635 | 81450 | 0 | 1398557 | 1398557 | As Per RE/WE
18 | Fire Fighting supplimental works |  | 291366 | 291366 |  | 291366 | 291366 |  | 291366 | 291366 | 0 | 0 | 874098 | 874098 | As Per RE/WE
19 | Air Conditioning supplimental works |  | 120788 | 120788 |  | 1749744 | 1749744 |  | 65250 | 65250 | 1628956 | 0 | 1935782 | 1935782 | As Per RE/WE
20 | MGPS supplimental works |  | 814670 | 814670 |  | 814670 | 814670 |  | 814670 | 814670 | 0 | 0 | 2444010 | 2444010 | As Per RE/WE
A: 21; B: Water Proofing Works; Gandhi Hospital, Secunderabad E: 0; MGMH PETLABURZ H: 0; MGM WARANGAL J: 1500000; MGM WARANGAL K: 1500000 |  | 0 | 1500000 | 1500000 | As Per RE/WE
22 | Total (Part-B) (12 to 21) | 0 | 4702095 | 4702095 | 0 | 6206151 | 6206151 | 0 | 6058345 | 6058345 | 1951801 | 0 | 16966591 | 16966591
23 | Total (Part-A+B) (10+22) | 43854853 | 46959700.6 | 3104847.6 | 42405299 | 50447091 | 8041792 | 43811081 | 54265386 | 10454305 | 5274689.4 | 130071233 | 151672177.6 | 21600944.6
24 | Mandatory Charges
25 | Provision towards Seniorage Charges on Civil Component | 0 | 308 | 308 |  | 448 | 448 |  | 1001 | 1001 |  | 0 | 1757 | 1757
26 | Provision towards DMF & SMFT Charges @32% (DMF-30%+SMFT-2% Charges) | 0 | 99 | 99 |  | 143 | 143 |  | 320 | 320 |  | 0 | 562 | 562
27 | Mandatory Charges @5.11% (TGMSIDC Supervision Charges-4%+Labour Cess-1% +NAC-0.1%+Haritha Nidhi-0.01%) | 1754194 | 2399641 | 645447 | 1696212 | 2577846 | 881634 | 1752443 | 2772961 | 1020518 |  | 5202849 | 7750448 | 2547599
28 | Sub Total (25 to 27) | 1754194 | 2400048 | 645854 | 1696212 | 2578437 | 882225 | 1752443 | 2774282 | 1021839 | 0 | 5202849 | 7752767 | 2549918
29 | Total (23+28) | 45609047 | 49359748.6 | 3750701.6 | 44101511 | 53025528 | 8924017 | 45563524 | 57039668 | 11476144 | #REF! | 135274082 | 159424944.6 | 24150862.6
30 | GST @18% on S.No 29 | 8209628 | 8884755 | 675127 | 7632954 | 9181376 | 1548422 | 7885995 | 9876429 | 1990434 |  | 23728577 | 27942560 | 4213983
31 | Provision towards (LS) - Inaugration Expenses | 1181325 | 200000 | -981325 | 3265535 | 300000 | -2965535 | 1550481 | 300000 | -1250481 |  | 5997341 | 800000 | -5197341
32 | Grand Total (29 to 31) | 55000000 | 58444503.6 | 3444503.6 | 55000000 | 62506904 | 7506904 | 55000000 | 67216097 | 12216097 | #REF! | 165000000 | 188167504.6 | 23167504.6
|  |  | As Per Agreement | 165000000
|  |  | As per workdone | 188167504.6
|  |  | Difference | 23167504.6
The Net Difference Amount = 2,31,67,505 Rupees

## IVF Gandhi
IVF Gandhi, Secunderabad
S. No | DESCRIPTION | As per Work Done/To be done Estimate
|  | QTY | UNIT | RATE | AMOUNT RS. | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7
Equipment Supplemental Works
1 | Fowler Two Function Bed with ABS Panel, and accessories in Pre/post Operative Ward and Semen Collection room | 5 | Nos | 39000 | 195000 | Completed
2 | Bed side Table with ABS Plastic body construction in Pre/post Operative Ward and Semen Collection room | 5 | Nos | 9000 | 45000 | Completed
3 | Corporate Deluxe Locker with SS 304 grade Top of size 508 x 406 x 762 mm in Sample and Injection room. | 1 | Nos | 8400 | 8400 | Completed
4 | Bed side stand with full SS 304 grade constructionof size 406 x 203 x 762 mm in Sample and Injection room. | 1 | Nos | 9300 | 9300 | Completed
5 | Bed side stand with full GI Powder coated constructionof size 406 x 203 x 762 mm in Semen Collection Room | 1 | Nos | 4200 | 4200 | Completed
6 | Cryo Can 11 Ltr without wheels in Cryo room | 1 | Nos | 32000 | 32000 | Completed
7 | 3-Bay Surgical Scrub Station/Sink with accessories at Sterile Corridor | 1 | Nos | 97000 | 97000 | Completed
8 | Supply of Sample collection bed of size 1850x620x700 mm in Sample and Injection room | 1 | Nos | 29000 | 29000 | Completed
9 | Supply of a Sample collection chair of size 800x580x700 mm in Sample and Injection room | 1 | Nos | 16200 | 16200 | Completed
10 | Supply and installation of Stainless Steel 304 grade CSSD Rectangular Working table of size 1200x480x1050 mm with in-built sink in Autoclave room | 1 | Nos | 46000 | 46000 | Completed
11 | SS-304 working table of size 685x685x762 mm in Embryology lab & Andrology Lab | 1 | Job | 78000 | 78000 | Completed
12 | Supply and fixing of Powder coated GI stand with 4 nos height adjustable racks of size 670x410x1570 mm in IVF OT | 1 | Nos | 80000 | 80000 | Completed
13 | The Multipurpose Electro Hydraulic Mobile OT Table in Major OT | 1 | Nos | 210000 | 210000 | Completed
|  |  |  | Total | 850100
Furniture Supplimental Works
14 | Writing board made of Pressed wood coated with melamine surface in Counselling rooms | 2 | Nos | 2100 | 4200 | Completed
15 | Providing MDF 18 mm thick wooden table of size 900x450 mm at Reception and Ultrasound room | 2 | Nos | 14500 | 29000 | Completed
16 | Supply of a 3-seater sofa upholstered with PU leather, with a high-quality finish at Entrance corridor | 2 | Nos | 24000 | 48000 | Completed
17 | Lab Chairs Type I (DCA Price) in Andrology Lab & Embryology Lab | 10 | Nos | 15340 | 153400 | Not Completed
|  |  |  | Total | 234600
Civil Supplementary Works
18 | Supply and application of one coat water based cement primer of interior grade I for internal walls in 5th floor (for Ceiling) at Gandhi Hospital | 536.11 | Sqm | 85 | 45569 | Completed
19 | Dismantling of unreinforced cement concrete | 3.89 | Cum | 4036 | 15700 | Completed
20 | Dismantling, clearing away of Old Cement Mortor (Plaster) | 37.13 | Sqm | 13 | 483 | Completed
21 | Dismantling, clearing away of Reinforced Cement Concrete | 0.7 | Cum | 4424 | 3097 | Completed
22 | Providing skirting to internal walls to 10 cm height with Double charged / multi charged stain free full body porcelain vitrified tiles with double layer pigment of size 600 x 600 mm and thickness between 8-10 mm | 107.18 | Rmt | 162 | 17363 | Completed
23 | Providing of Factory made prelaminated FPVC (Foamed Polyvinyl Chloride) Door frame of the size 105x40mm with Maximum shutter size of : 910 x 2030 mm | 23.463 | Sqm | 9241 | 216822 | Completed
24 | Flooring with 16 to 18 mm thick high polished granite stone slabs black colour (for Reception Table). | 10.17 | Sqm | 5839 | 59383 | Completed
25 | 50 LPH storage type RO of dimensions 525 x 425 x 1450 mm in Autoclave room | 1 | Nos | 75000 | 75000 | Completed
26 | Supply and placing of the Design Mix Concrete M 25 grade corresponding to IS 456 (for Lintels) | 0.43 | Cum | 15969 | 6867 | Completed
27 | Supply and fixing of doors as per approved drawings with (WPC) single extruded Door Frame section of 100*65 MM and30mm thick Wood Plastic Composite (WPC) Door shutter (800mm x 2100mm) (For Wash Rooms). | 6.72 | Sqm | 6734 | 45252 | Completed
28 | Supplying and fixing of windows / in open court yards using 25mm x 6mm MS flat alround and 10mm MS square bars (for Window Grills) | 10.8435 | Sqm | 1569 | 17013 | Completed
29 | AHU shed with provision for fencing, door with lock- key arrangement on Terrace Floor) | 1 | Iob | 300000 | 300000 | Completed
|  |  |  | Total | 802549
Interior and other works
30 | Wall Paneling 14mm thick Indoor WPC louvers panneling till slab | 18.58 | Sqm | 15500 | 287990 | Completed
31 | 2 WPC Louvers Ceiling Praviding and fixing WPC Louvers to the Celling | 7.58 | Sqm | 17450 | 132271 | Completed
32 | Providing and fixing of wooden box celling at the top of Reception table with Imm thick laminate | 2.58 | Sqm | 11335 | 29244 | Completed
33 | Back Pannelling with laminate Finish of 1 mm thick | 7.5 | Sqm | 10500 | 78750 | Completed
34 | Providing and fixing ISI marked Magnetic 25mm Block Board door shutters | 1 | Nos | 13800 | 13800 | Completed
35 | Providing and fixing PVC frames on the walls for covering the area over DB Boxes | 4.45 | Sqm | 6473 | 28805 | Completed
36 | Providing and Fixing of (25X25) mm WPC corner L-Patties at the topper edge of the wall tile cladding | 38 | Rmt | 230 | 8740 | Completed
37 | Providing and Fixing of SS-ROSE GOLD corner & L-Patties at the SIDE edge of the wall tile cladding | 7 | Nos | 1500 | 10500 | Completed
38 | Providing and fixing of Door Frame panneling with 18mm BWP 710 Gurjan Ply | 11.58 | Rmt | 2166 | 25082 | Completed
39 | Providing and fixing the 60mm Thick Box framing as the back support for the name plate | 1.32 | Sqm | 11012 | 14536 | Completed
40 | Providing and Fixing of 32mm Double Flush Door (1500 x 200 mm door) | 1 | Nos | 50400 | 50400 | Completed
41 | Providing and fixing of Side wall decor Frame for photo hangings panneling | 10.97 | Rmt | 2170 | 23805 | Completed
42 | Supply and fixing of Wall paper as approved by the Engineer In-charge. | 2 | Nos | 5175 | 10350 | Completed
43 | Supply and fixing of Main IVF logo with LED arcylic board ( 520 mm dia & 50 mm thick) | 1 | Nos | 11475 | 11475 | Completed
44 | Supply and fixing of Main Entrance LED 3D Arcylic letter board (2890 mm x 465 mm) | 1 | Nos | 44250 | 44250 | Completed
45 | Providing and fixing Aluminium Extruded Section Body Tubular Type Hydraulic Door Closer | 8 | Nos | 2819 | 22552 | Completed
46 | Providing, Fabricating and fixing full height V-board partitions of overall thickness of 75mm Partition frame work | 89.11 | Sqm | 1625 | 144804 | Completed
47 | Supply and fixing of Dress Hangers | 5 | Nos | 510 | 2550 | Completed
48 | Name Plates (Room Names) as approved by the Engineer In-charge. | 31 | Nos | 600 | 18600 | Completed
49 | Supply and fixing of High Quality IVF Procedural photos (2' x 2' and above) | 14 | Nos | 9000 | 126000 | Completed
50 | Supply of Sun Control film to the glazed windows (For Windows & Door view Windows) | 14.55 | Sqm | 381 | 5544 | Completed
51 | Supplying and fixing Rectangular Mirror Frameless of size 457 .2 mm x 609.6 mm (For Change room) | 5 | Nos | 1775 | 8875 | Completed
52 | Supply of Venetian blinds Vertical blinds 100 mm wide with all accessories. (For semen collection room & Counselling room Windows) | 5.01 | Sqm | 2187 | 10957 | Completed
53 | POINT WIRING and LIGHT FIXTURES & FITTINGS | 13 | Nos | 1200 | 15600 | Completed
54 | Proving and fixing Profile lights at wpc Louvers | 10.66 | Rmt | 1182 | 12600.12 | Completed
55 | Proving and fixing Track lights at side wall décor frame with 4 fixtures and 2 tracks | 1 | Job | 9600 | 9600 | Completed
56 | External Profile light at Name Plate | 2.89 | Rmt | 1182 | 3415.98 | Completed
1151096.1
Plumbing Supplemental Works
57 | Supplying and fixing of 3" (75mm) Nahany trap with jali | 5 | Nos | 133 | 665 | Completed
58 | Supplying and fixing 50 mm Nominal Bore GI pipe Medium Grade properties (For Autoclave) | 35.1 | Rmt | 599 | 21025 | Completed
|  |  |  | Total | 21690
Electrical Supplemental Works
59 | Supply and Transportation 56W Clean room Light fixture, 2' x2' (600mm x600mm) LED luminaire (In Embryology lab and IVF OT) | 12 | Nos | 17241 | 206892 | Completed
60 | Supply and Transportation of 48" ( 1200 mm) High Speed Fan Sweep Celing Fan with all accessories etc., complete. Make Havells S S 390 | 14 | Nos | 4317 | 60438 | Completed
61 | Labour charges for fixing of ceiling fan and regulator including transportation and giving connections with twin core wire etc., complete. | 14 | Nos | 185 | 2590 | Completed
62 | Supply and erecting 19/20mm steel tube down rod of one meter length with bolts & nuts duly painted with matching colour of fan complete | 14 | Nos | 162 | 2268 | Completed
63 | Supply & fixing of 2nos6A, 2 in one socket - 2 Nos with 6A switch control - 2 Nos modular type | 30 | Nos | 1178 | 35340 | Completed
64 | Supply,Transportation of 15" (375mm) ISI, 900 RPM Heavy duty exhaust fan with metallic blades | 1 | Nos | 4310 | 4310 | Completed
65 | Labour charges for fixing the exhaust fan in wall with necessary connections | 1 | Nos | 788 | 788 | Completed
66 | Supply and fixing of 12 Way SPN DB with IP 43 Protection as per IS:13032 | 1 | No | 9444 | 9444 | Completed
67 | Supply and fixing of cable adapteres box with cover for DBs including, massanory work etc., complete., | 8 | Nos | 5085 | 40680 | Completed
68 | Supply and Installation of control cum transmission wiring of size 4C x 2.5 Sqmm copper wire | 20 | Rmt | 289 | 5780 | Completed
69 | Supply and Installation of control cum transmission wiring of size 2C x 1.5 Sqmm copper wire | 190 | Rmt | 173 | 32870 | Completed
70 | 4C x 1.5 Sqmm Copper Flexible Cable For Condensing Unit to Electrical Panel | 74.1 | Rmt | 130 | 9633 | Completed
71 | Supply and fixing of FP Metal Enclosure with IP 20 Protection DB Make with 1 No 63A, 10 KA FP MCB | 1 | Nos | 4203 | 4203 | Completed
|  |  |  | Total | 415236
Fire Fighting Supplimental Works
72 | Supply, Installation, testing and commissioning of EN54-2 Listed and LPCB approved based analog addressable fire control panel (At Reception) | 1 | Nos | 291366 | 291366 | Completed
|  |  |  | Total | 291366
Air Conditioning Supplimental Works
73 | Supply and installation of 2.2 TR 3 Star Split AC (At reception) | 1 | Nos | 72225 | 72225 | Completed
74 | CPVC drain piping 25mm Dia at Gandhi Hospital | 66 | Rmt | 200 | 13200 | Completed
75 | MS Angle for Duct Support of size 40 X 40 x 5 mm Thick. (Terrace Floor) | 92.2 | Kg | 190 | 17518 | Completed
76 | MS Angle for Duct Support of size 25 X 25 x 5 mm Thick. (Terrace Floor) | 25.5 | Kg | 190 | 4845 | Completed
77 | Canvas Connections For AHUS (Terrace Floor) | 2 | Nos | 6500 | 13000 | Completed
|  |  |  | Total | 120788
MGPS Supplemental Works
78 | Fully Automatic Control Panel for Oxygen, Trigas, and CO2 System (In Manifold room) | 3 | Nos | 175180 | 525540 | Completed
79 | Trigas Emergency Manifold (In Manifold room) | 1 | Set | 9620 | 9620 | Completed
80 | SITC of Medical Air-4 Outlet (In IVF-OT, Major OT and Pre/Post Operatve ward) | 6 | Nos | 12470 | 74820 | Completed
81 | 12 mm Valve for 12 mm OD Pipe | 3 | Nos. | 930 | 2790 | Completed
82 | CO2, O2, Trigas, N2O cylinders in Manifold room | 1 | Job | 201900 | 201900 | Completed
|  |  |  | Total | 814670
|  |  |  | Total Basic Value | 4702095.1

## IVF Petlaburj
IVF Petlaburj, MGMH Hyderabad
S. No | DESCRIPTION | As Per Workdone Estimate |  |  |  | REMARKS
|  | QTY | UNIT | RATE (Rs.) | AMOUNT (Rs.)
MGMH Petlaburj Hospital
Equipment Supplimental
1 | 3-Bay Surgical Scrub Station/Sink | 1 | Nos | 97000 | 97000 | Completed
2 | Stainless Steel 304 grade CSSD Rectangular Working table | 1 | Nos | 46000 | 46000 | Completed
3 | SS-304 working table of size 685 x 685 x 762 mm | 2 | Nos | 16300 | 32600 | Completed
4 | SS-304 working table of size 457 x 457 x 762 mm | 1 | Nos | 14500 | 14500 | Completed
5 | SS-304 working table of size 61 x 610 x 762 mm | 1 | Nos | 15100 | 15100 | Completed
6 | SS-304 working table of size 660 x 610 x 762 mm | 1 | Nos | 15800 | 15800 | Completed
Other Mandatory Equipment Suppliental
7 | Fowler Two Function Bed with ABS Panel | 5 | Nos | 39000 | 195000 | Not Completed
8 | Bed side Table with ABS Plastic body construction | 5 | Nos | 9000 | 45000 | Not Completed
9 | Corporate Deluxe Locker with SS 304 grade Top | 1 | Nos | 8400 | 8400 | Not Completed
10 | Bed side stand with full SS 304 grade construction | 1 | Nos | 9300 | 9300 | Not Completed
11 | Bed side stand with full GI Powder coated construction | 1 | Nos | 4200 | 4200 | Not Completed
12 | Supply of a Sample collection chair | 1 | Nos | 16200 | 16200 | Not Completed
13 | Cryo Can 11 Ltr without wheels | 1 | Nos | 32000 | 32000 | Not Completed
14 | Supply of Sample collection bed | 1 | Nos | 29000 | 29000 | Not Completed
15 | Supply and fixing of Powder coated GI stand with 4 nos height adjustable racks of size 670x410x1570 mm | 1 | Nos | 80000 | 80000 | Not Completed
16 | The Multipurpose Electro Hydraulic Mobile OT Table | 1 | Nos | 210000 | 210000 | Not Completed
850100
Furniture Supplimental Works
17 | Writing board in Counselling rooms | 1 | Nos | 2100 | 2100 | Not Completed
18 | MDF wooden table in Reception and Ultrasound room | 2 | Nos | 14500 | 29000 | Not Completed
19 | 3 Seater Sofa | 2 | Nos | 24000 | 48000 | Not Completed
| Other Mandatory Furniture Suppliental |  |  |  |  | Not Completed
20 | Office table in Embryologist and Anesthetist room | 2 | Nos | 16000 | 32000 | Not Completed
21 | Consultant Chair in Embryologist and Anesthetist room | 3 | Nos | 20000 | 60000 | Not Completed
22 | Patient Chair Embryologist and Anesthetist room | 6 | Nos | 13500 | 81000 | Not Completed
23 | Lab Chairs Type I (DCA Price) in Andrology Lab & Embryology Lab | 10 | Nos | 15340 | 153400 | Not Completed
405500
Interior Works
24 | Supply of Sun Control film to the glazed windows (For Windows & Door view Windows) | 48 | Sqm | 381 | 18288 | Completed
25 | Providing and fixing Aluminium Extruded Section Body Tubular Type Hydraulic Door Closer | 15 | Nos | 2819 | 42285 | Completed
26 | Supply and fixing of Dress Hangers (in change rooms). | 5 | Nos | 510 | 2550 | Completed
27 | Supplying and fixing Rectangular Mirror Frameless of size 457 .2 mm x 609.6 mm (For Change room) | 5 | Nos | 1775 | 8875 | Completed
28 | Name Plates (Room Names) | 38 | Nos | 600 | 22800 | Completed
29 | Providing and fixing PVC frames on the walls for covering the area over DB Boxes | 0.74 | Sqm | 6473 | 4790 | Completed
30 | Supply and fixing of High Quality IVF Procedural photos placed on DBs. (2' x 2' and above) | 12 | Nos | 9000 | 108000 | Completed
31 | B) Providing and fixing the 60mm Thick Box framing | 3.98 | Sqm | 11012 | 43828 | Completed
32 | Door Frame Paneling with laminate Finish of 1 mm thick. | 7.551 | Sqm | 9250 | 69847 | Completed
33 | Providing and Fixing of 32mm Double Flush Door (1800 x 2100 mm door) | 1 | Nos | 56500 | 56500 | Completed
34 | Providing and Fixing of 2 Feet Deep Of Ceiling Top Of The Name Plate | 2.6 | Sqm | 9580 | 24908 | Completed
35 | Double side ACP sheet with vinyl stickering . (Name board wth three languages fixed at IVF Entrance Corridor) | 1 | Nos | 6000 | 6000 | Completed
36 | Foam Board with eco solvent vinyl pasting (Name board wth three languages with direction to IVF Center fixed at 3rd floor) | 2 | Nos | 2800 | 5600 | Completed
37 | Foam Board with eco solvent vinyl pasting (Name board wth with direction to Rooms fixed to wall in IVF Corridor,) | 2 | Nos | 3200 | 6400 | Completed
38 | MIRROR GOLD TITANIUM LETTERS & S.S. MIRROR LETTERS at Entrance | 1 | Job | 67500 | 67500 | Completed
39 | Main IVF logo with LED arcylic board at Entrance | 1 | Nos | 11475 | 11475 | Completed
40 | Supply of Venetian blinds Vertical blinds 100 mm wide with all accessories. (For semen collection room & Counselling room Windows) | 15 | Sqm | 2187 | 32805 | Not Completed
532451
Civil Supplimental Works
41 | Dismantling, clearing away of Old Cement Mortar | 289.14 | Sqm | 13 | 3759 | Completed
42 | Dismantling, clearing away of Reinforced Cement Concrete | 0.59 | Cum | 4424 | 2610 | Completed
43 | Supply and Installation change room Cubicles at Petlaburj | 11.3 | Sqm | 9055 | 102322 | Completed
44 | Providing, Fabricating and fixing full height V-board partitions | 13.7 | Sqm | 1625 | 22263 | Completed
45 | Emergency Fire Doors : Size 1500 X 2100 mm | 1 | Nos | 55000 | 55000 | Completed
46 | Providing of Factory made prelaminated FPVC doors of size 910 x 2030 mm | 32.08 | Sqm | 9241 | 296451 | Completed
47 | WPS Doors (For Toilets) | 9.21 | Sqm | 6734 | 62020 | Completed
48 | 50 LPH storage type RO | 1 | Nos | 75000 | 75000 | Completed
49 | AHU shed with provision for fencing, door with lock- key | 1 | Job | 300000 | 300000 | Completed
50 | Providing Thermo Mechanically Treated ( TMT) ( Fe-500/500D/550D | 0.3 | MT | 95386 | 28616 | Completed
51 | Supplying and fixing of to windows / in open court yards using 25mm x 6mm MS flat alround and 10mm MS square bars | 39.78 | Sqm | 1791 | 71246 | Completed
52 | Supply and placing of the Design Mix Concrete M 25 grade corresponding to IS 456 | 0.75 | Cum | 14683 | 11012 | Completed
53 | Providing skirting to internal walls to 10 cm height | 174.5 | Rmt | 151 | 26350 | Completed
1056649
Plumbing Supplimental Works
54 | Supplying and fixing 50 mm Nominal Bore GI pipe Medium Grade properties (For Autoclave) | 15 | Rmt | 599 | 8985 | Completed
8985
Electrical Supplimental Works
55 | Supply and Transportation 56W Clean room Light fixture, 2' x2' (600mm x600mm) LED luminaire | 12 | Nos | 17241 | 206892 | Completed
56 | Supply and Transportation of 48" ( 1200 mm) High Speed Fan | 28 | Nos | 4317 | 120876 | Completed
57 | Labour charges for fixing of ceiling fan and regulator | 28 | Nos | 185 | 5180 | Completed
58 | Supply & fixing of 2nos6A, 2 in one socket - 2 Nos with 6A switch control - 2 Nos modular type | 20 | Nos | 1178 | 23560 | Completed
59 | Supply and erecting 19/20mm steel tube down rod | 28 | Nos | 162 | 4536 | Completed
60 | Supply and fixing of 12 Way SPN DB Horizontal with IP 43 Protection as per IS:13032 (For UPS DBs) | 2 | Nos | 9444 | 18888 | Completed
61 | Supply and fixing of cable adopteres box with cover for DBs including, massanory work etc., complete., | 8 | Nos | 5085 | 40680 | Completed
62 | Supply and fixing of FP Metal Enclosure with IP 20 Protection DB Make with 1 No 63A, 10 KA DP MCB | 2 | Nos | 4203 | 8406 | Completed
63 | 4C x 1.5 Sqmm Copper Flexible Cable For Condensing Unit to Electrical Panel | 210 | Rmt | 130 | 27300 | Completed
64 | Proving and fixing Track lights at side wall décor frame with 4 fixtures and 2 tracks | 1 | Job | 9600 | 9600 | Completed
65 | Supply and fixing of suitable out door feeder piller box, 9 Nos 6-32A SP MCBs | 1 | Nos | 30768 | 30768 | Completed
496686
Fire Fighting Supplimental Works
66 | Supply, Installation, testing and commissioning of Addressable fire control panel | 1 | Nos | 291366 | 291366 | Completed
291366
Air Conditioning Supplimental Works
67 | Supply & Installation of MS Angle for Duct Support, Cable Tray Support and Condensing Unit Stand of size 50 X 50 x 5 mm Thick. | 211.24 | Kg | 190 | 40136 | Completed
68 | Supply & Installation of MS Angle for Duct Support, Cable Tray Support and Condensing Unit Stand of size 32 X 32 x 5 mm Thick. | 74.25 | Kg | 190 | 14108 | Completed
69 | Supply and installation of Canvas Connections For AHUS | 2 | Nos | 6500 | 13000 | Completed
70 | Condensing units - VRF/VRV System : 22 HP | 1 | Nos | 402500 | 402500 | Completed
71 | Cassette Units : 2.0 TR – 4 way | 2 | Nos | 40000 | 80000 | Completed
72 | Modular Double skin floor mounted EUROVENT Certified Air Handling Unit 4400CFM / 11.0 TR / 150mm SP | 1 | Nos | 718500 | 718500 | Completed
73 | SITC of air cooled condensing units of 11.0 TR capacity | 2 | Nos | 240750 | 481500 | Completed
1749744
MGPS Supplimetal Works
74 | Fully Automatic Control Panel for Oxygen System | 1 | Nos | 175180 | 175180 | Completed
75 | Trigas Emergency Manifold | 1 | Nos | 9620 | 9620 | Completed
76 | Fully Automatic Control Panel for Trigas System | 1 | Nos | 175180 | 175180 | Completed
77 | Fully Automatic Control Panel for CO2 System | 1 | Nos | 175180 | 175180 | Completed
78 | SITC of Medical Air-4 Outlet with matching probe | 6 | Nos | 12470 | 74820 | Completed
79 | 12 mm Valve for 12 mm OD Pipe | 3 | Nos | 930 | 2790 | Completed
80 | Supply and installation of 46.7 liter size CO2 cylinders confirming to IS:7285 Part-2 (2017). | 2 | Nos | 20850 | 41700 | Completed
81 | Supply and installation of 46.7 liter size O2 cylinders confirming to IS:7285 Part-2 (2017) | 2 | Nos | 17850 | 35700 | Completed
82 | Supply and installation of 46.7 liter size Trigas cylinders confirming to IS:7285 Part-2 (2017). | 2 | Nos | 29250 | 58500 | Completed
83 | Supply and installation of 46.7 liter size N2O cylinders confirming to IS:7285 Part-2 (2017). | 2 | Nos | 33000 | 66000 | Completed
814670
|  |  |  | Total Basic Value | 6206151

## IVF Warangal
IVF Warangal, MGM Warangal
S.No | Description | As Per Working Estimate |  |  |  | Remarks
|  | QTY | UOM | RATE (Rs.) | AMOUNT (Rs.)
MGM Hospital, Warangal
EQUIPMENT SUPPLIMENTAL
1 | 3-Bay Surgical Scrub Station/Sink | 1 | Nos | 97000 | 97000
2 | Supply and installation of Stainless Steel 304 grade CSSD Rectangular Working table | 1 | Nos | 46000 | 46000
3 | SS-304 working table of size 685 x 685 x 762 mm | 2 | Nos | 16300 | 32600
4 | SS-304 working table of size 457 x 457 x 762 mm | 1 | Nos | 14500 | 14500
5 | SS-304 working table of size 61 x 610 x 762 mm | 1 | Nos | 15100 | 15100
6 | SS-304 working table of size 660 x 610 x 762 mm | 1 | Nos | 15800 | 15800
7 | Supply and fixing of Powder coated GI stand with 4 nos height adjustable racks | 1 | Nos | 80000 | 80000
Other Mandatory Equipment Supplimental
8 | Fowler Two Function Bed with ABS Panel in Pre and Post Operative wards and Semen Collection room | 5 | Nos | 39000 | 195000
9 | Bed side Table with ABS Plastic body in Pre and Post Operative wards and Semen Collection room | 5 | Nos | 9000 | 45000
10 | Corporate Deluxe Locker with SS 304 grade Top in Sample Collection and Injection Room | 1 | Nos | 8400 | 8400
11 | Bed side stand with full SS 304 grade constructionof in Sample Collection and Injection Room | 1 | Nos | 9300 | 9300
12 | Bed side stand with full GI Powder coated construction of in Semen Collection room | 1 | Nos | 4200 | 4200
13 | Supply of a Sample collection chair in Sample Collection and Injection Room | 1 | Nos | 16200 | 16200
14 | Sample collection bed in Sample Collection and Injection Room | 1 | Nos | 29000 | 29000
15 | Cryo Can 11 Ltr without wheels in Cryo room | 1 | Nos | 32000 | 32000
16 | The Multipurpose Electro Hydraulic Mobile OT Table in Major OT | 1 | Nos | 210000 | 210000
|  |  |  | Total | 850100
Furniture Supplimental
17 | Writing board made of Pressed wood coated with melamine surface. | 2 | Nos | 2100 | 4200
18 | Providing MDF 18 mm thick wooden table of size 900x450 mm | 2 | Nos | 14500 | 29000
| Other Mandatory Furniture Supplimental |  |  |  | 0
19 | 3 Seater Sofa | 2 | Nos | 24000 | 48000
20 | Consultant Chair in Embryologist and Anesthetist room | 3 | Nos | 20000 | 60000
21 | Patient Chair Embryologist and Anesthetist room | 6 | Nos | 13500 | 81000
22 | Lab Chairs Type I (DCA Price) in Andrology Lab & Embryology Lab | 10 | Nos | 15340 | 153400
23 | IUI Couch/ Table in IUI Room | 2 | Nos | 50000 | 100000
24 | office table in Embryologist room | 1 | Nos | 16000 | 16000
25 | Patient Seating 3 in 1 model in waiting area | 3 | Nos | 38500 | 115500
|  |  |  | Total | 607100
Interior Supplimental Works
26 | Supply of Sun Control film to the glazed windows (For Windows & Door view Windows) | 45 | Sqm | 381 | 17145
27 | Supply of Venetian blinds Vertical blinds (For semen collection room & Counselling room Windows) | 15 | Sqm | 2187 | 32805
28 | Supply and fixing of Dress Hangers (in change rooms). | 5 | Nos | 510 | 2550
29 | Supplying and fixing Rectangular Mirror Frameless of size 457 .2 mm x 609.6 mm (For Change room) | 5 | Nos | 1775 | 8875
30 | Name Plates (Room Names) as approved by the Engineer In-charge. | 30 | Nos | 600 | 18000
31 | High Quality IVF Procedural photos at Entrance and Reception | 15 | Nos | 9000 | 135000
32 | Hydraullic door closer for ABS Doors | 15 | Nos | 2819 | 42285
33 | 60mm Thick Box framing as the back support for the name plate at Entrance | 5 | Sqm | 11012 | 55060
34 | Door Frame side Paneling at Entrance | 10 | Sqm | 9250 | 92500
35 | 32mm Double Flush Door (1800 x 2100 mm door) at Entrance | 1 | Nos | 56500 | 56500
36 | Name Plate With Glossy Laminate at Entrance | 3 | Sqm | 9580 | 28740
37 | MIRROR GOLD TITANIUM LETTERS & S.S. MIRROR LETTERS at Entrance | 1 | Job | 67500 | 67500
38 | Double side ACP sheet (Name board wth three languages fixed at IVF Entrance Corridor) | 1 | Nos | 6000 | 6000
39 | Foam Board (Name board wth three languages with direction to IVF Center fixed at 3rd floor) | 2 | Nos | 2800 | 5600
40 | Foam Board (Name board wth with direction to Rooms fixed to wall in IVF Corridor,) | 2 | Nos | 3200 | 6400
41 | Main IVF logo with LED arcylic board at Entrance | 1 | Nos | 11475 | 11475
42 | PVC frames on the walls for covering the area over DB Boxes | 1 | Sqm | 6473 | 6473
|  |  |  | Total | 592908
CIVIL SUPPLIMENTAL
43 | Providing, Fabricating and fixing full height V-board partitions | 15 | Sqm | 1625 | 24375
44 | Providing of Factory made prelaminated FPVC (Foamed Polyvinyl Chloride) Door of size 910 x 2030 mm | 26 | Sqm | 9241 | 240266
45 | WPC Door | 6.5 | Sqm | 6734 | 43771
46 | 50 LPH storage type RO | 1 | Nos | 75000 | 75000
47 | AHU shed with provision for fencing, door with lock- key | 1 | Job | 300000 | 300000
48 | Providing Thermo Mechanically Treated ( TMT) ( Fe-500/500D/550D | 0.3 | MT | 95386 | 28616
49 | Supplying and fixing of to windows / in open court yards using 25mm x 6mm MS flat alround and 10mm MS square bars | 26 | Sqm | 1791 | 46566
50 | Supply and placing of the Design Mix Concrete M 25 grade corresponding to IS 456 | 0.75 | Cum | 14683 | 11012
51 | Providing skirting to internal walls to 10 cm height | 475 | Rmt | 151 | 71725
|  |  |  | Total | 841331
PLUMBING SUPPLIMENTAL
52 | Supplying and fixing 50 mm Nominal Bore GI pipe Medium Grade properties (For Autoclave) | 15 | Rmt | 599 | 8985
|  |  |  | Total | 8985
ELECTRICAL SUPPLIMENTAL
53 | Supply and Transportation 56W Clean room Light fixture, 2' x2' (600mm x600mm) LED luminaire | 12 | Nos | 17241 | 206892
54 | Supply and Transportation of 48" ( 1200 mm) High Speed Fan | 32 | Nos | 4317 | 138144
55 | Labour charges for fixing of ceiling fan and regulator | 32 | Nos | 185 | 5920
56 | Supply and fixing of Anchor fastner with fan hook / Providing MS Fan hook with grouting and cement plastering. | 32 | Nos | 122 | 3904
57 | Supply & fixing of 2nos6A, 2 in one socket - 2 Nos with 6A switch control - 2 Nos modular type | 23 | Nos | 1178 | 27094
58 | Supply and erecting 19/20mm steel tube down rod | 32 | Nos | 162 | 5184
59 | Supply and fixing of 12 Way SPN DB Horizontal with IP 43 Protection as per IS:13032 (For UPS DBs) | 1 | Nos | 9444 | 9444
60 | Supply and fixing of cable adopteres box with cover for DBs including, massanory work etc., complete., | 10 | Nos | 5085 | 50850
61 | Supply and fixing of FP Metal Enclosure with IP 20 Protection DB Make with 1 No 63A, 10 KA DP MCB | 1 | Nos | 4203 | 4203
62 | Supply and fixing of suitable out door feeder piller box, 9 Nos 6-32A SP MCBs | 1 | No | 35000 | 35000
|  |  |  | Total | 486635
FIRE FIGHTING SUPPLIMENTAL
63 | Supply, Installation, testing and commissioning of Addressable fire control panel | 1 | Nos | 291366 | 291366
|  |  |  | Total | 291366
AIR CONDITIONING SUPPLIMENTAL
64 | Supply & Installation of MS Angle for Duct Support, Cable Tray Support and Condensing Unit Stand of size 50 X 50 x 5 mm Thick. | 200 | Kg | 190 | 38000
65 | Supply & Installation of MS Angle for Duct Support, Cable Tray Support and Condensing Unit Stand of size 32 X 32 x 5 mm Thick. | 75 | Kg | 190 | 14250
66 | Supply and installation of Canvas Connections For AHUS | 2 | Nos | 6500 | 13000
|  |  |  | Total | 65250
MGPS SUPPLIMENTAL
67 | Fully Automatic Control Panel for Oxygen System | 1 | Set | 175180 | 175180
68 | Trigas Emergency Manifold | 1 | Set | 9620 | 9620
69 | Fully Automatic Control Panel for Trigas System | 1 | Set | 175180 | 175180
70 | Fully Automatic Control Panel for CO2 System | 1 | Set | 175180 | 175180
71 | SITC of Medical Air-4 Outlet with matching probe | 6 | Nos | 12470 | 74820
72 | 12 mm Valve for 12 mm OD Pipe | 3 | Nos. | 930 | 2790
73 | Supply and installation of 46.7 liter size CO2 cylinders confirming to IS:7285 Part-2 (2017). | 2 | Nos | 20850 | 41700
74 | Supply and installation of 46.7 liter size O2 cylinders confirming to IS:7285 Part-2 (2017). | 2 | Nos | 17850 | 35700
75 | Supply and installation of 46.7 liter size Trigas cylinders confirming to IS:7285 Part-2 (2017). | 2 | Nos | 29250 | 58500
76 | Supply and installation of 46.7 liter size N2O cylinders confirming to IS:7285 Part-2 (2017). | 2 | Nos | 33000 | 66000
|  |  |  | Total | 814670
Water Proofing Works
77 | Water Proofing on Terrace Floor | 1 | Job | 1500000 | 1500000
|  |  |  | Total | 1500000
|  |  |  | Total Basic Value | 6058345