## 3 Site Consolidated
|  | Gandhi Hospital, Secunderabad |  |  | MGMH PETLABURZ |  |  | MGM WARANGAL |  |  | Difference (PTB - GH) | Total |  |  | Remarks
A | B | C | D | E | F | G | H | I | J | K |  | L | M | N | O
S.No | Description | As per Agreement | As per workdone | Excess / Less | As per Agreement | As per workdone | Excess / Less | As per Agreement | As per workdone | Excess / Less |  | As per Agreement | As per workdone | Excess / Less
| Layout Area (SQM) | 447.8 | 418.415 |  | 453.08 | 594.38 |  | 503 | 597.3 |  |  | 1403.88 | 1610.095
As Per Agreement (PART-A)
1 | Equipment | 25009375 | 25009375 | 0 | 25009375 | 25009375 | 0 | 25009376 | 25009376 | 0 | 0 | 75028126 | 75028126 | 0 | As Per RE/WE
2 | Furniture | 1008850 | 898850 | -110000 | 1011100 | 1011100 | 0 | 1011100 | 1011100 | 0 |  | 3031050 | 2921050 | -110000 | As Per RE/WE
3 | Civil Works | 7431553 | 5612831 | -1818722 | 5915529 | 7012631 | 1097102 | 7320696 | 9771662 | 2450966 | 2915824 | 20667778 | 22397124 | 1729346 | As Per RE/WE
4 | Plumbing works | 204480 | 126489 | -77991 | 215122 | 136973 | -78149 | 160285 | 156101 | -4184 | -158 | 579887 | 419563 | -160324 | As Per RE/WE
5 | Electrical works | 3732008 | 4027908 | 295900 | 3719411 | 5641335 | 1921924 | 3832437 | 5402274 | 1569837 | 1626024 | 11283856 | 15071517 | 3787661 | As Per RE/WE
6 | ELV works | 827000 | 827000 | 0 | 689000 | 689000 | 0 | 1337000 | 1337000 | 0 | 0 | 2853000 | 2853000 | 0 | As Per RE/WE
7 | Fire Fighting works | 735880 | 735880 | 0 | 873880 | 873880 | 0 | 225880 | 225880 | 0 | 0 | 1835640 | 1835640 | 0 | As Per RE/WE
8 | Air Conditioning works | 3879885 | 3839121 | -40764 | 3946060 | 2725391 | -1220669 | 3888485 | 4247076 | 358591 | -1179905 | 11714430 | 10811588 | -902842 | As Per RE/WE
9 | MGPS works | 1025822 | 1180151.6 | 154329.6 | 1025822 | 1141255 | 115433 | 1025822 | 1046572 | 20750 | -38896.6 | 3077466 | 3367978.6 | 290512.6 | As Per RE/WE
10 | Total (Part-A) (1 to 9) | 43854853 | 42257605.6 | -1597247.4 | 42405299 | 44240940 | 1835641 | 43811081 | 48207041 | 4395960 | 3322888.4 | 130071233 | 134705586.6 | 4634353.6
11 | Supplimental Items (PART-B)
12 | Equipment supplimental |  | 221000 | 221000 |  | 221000 | 221000 |  | 221000 | 221000 | 0 | 0 | 663000 | 663000 | As Per RE/WE
13 | Civil supplimental works |  | 802549 | 802549 |  | 1056649 | 1056649 |  | 841331 | 841331 | 254100 | 0 | 2700529 | 2700529 | As Per RE/WE
14 | Plumbing supplimental works |  | 21690 | 21690 |  | 8985 | 8985 |  | 8985 | 8985 | -12705 | 0 | 39660 | 39660 | As Per RE/WE
15 | Electrical supplimental works |  | 415236 | 415236 |  | 496686 | 496686 |  | 486635 | 486635 | 81450 | 0 | 1398557 | 1398557 | As Per RE/WE
16 | Fire Fighting supplimental works |  | 291366 | 291366 |  | 291366 | 291366 |  | 291366 | 291366 | 0 | 0 | 874098 | 874098 | As Per RE/WE
17 | Air Conditioning supplimental works |  | 120788 | 120788 |  | 1749744 | 1749744 |  | 65250 | 65250 | 1628956 | 0 | 1935782 | 1935782 | As Per RE/WE
18 | MGPS supplimental works |  | 814670 | 814670 |  | 814670 | 814670 |  | 814670 | 814670 | 0 | 0 | 2444010 | 2444010 | As Per RE/WE
A: 19; B: Water Proofing Works; Gandhi Hospital, Secunderabad E: 0; MGMH PETLABURZ H: 0; MGM WARANGAL J: 1500000; MGM WARANGAL K: 1500000 |  | 0 | 1500000 | 1500000 | As Per RE/WE
20 | Total (Part-B) (12 to 19) | 0 | 2687299 | 2687299 | 0 | 4639100 | 4639100 | 0 | 4229237 | 4229237 | 1951801 | 0 | 11555636 | 11555636
21 | Total (Part-A+B) (10+20) | 43854853 | 44944904.6 | 1090051.6 | 42405299 | 48880040 | 6474741 | 43811081 | 52436278 | 8625197 | 5274689.4 | 130071233 | 146261222.6 | 16189989.6
22 | Other Supplimental Items (PART-C)
23 | Interior Works |  | 1151096 | 1151096 |  | 532451 | 532451 |  | 592908 | 592908 |  | 0 | 2276455 | 2276455 | As Per Annexure-A,B,C
24 | Equipment |  | 629100 | 629100 |  | 629100 | 629100 |  | 629100 | 629100 |  | 0 | 1887300 | 1887300 | As Per Annexure-D,E,F
25 | Furniture |  | 81200 | 81200 |  | 111100 | 111100 |  | 81200 | 81200 |  | 0 | 273500 | 273500 | As Per Annexure-D,E,F
26 | Additional Items As Per End User Letter |  | 153400 | 153400 |  | 294400 | 294400 |  | 525900 | 525900 |  | 0 | 973700 | 973700 | As Per Annexure-G
27 | Total (Part-C) (23 to 26) | 0 | 2014796 | 2014796 | 0 | 1567051 | 1567051 | 0 | 1829108 | 1829108 | 0 | 0 | 5410955 | 5410955
28 | Total (Part-A+B+C) (21+27) | 43854853 | 46959700.6 | 3104847.6 | 42405299 | 50447091 | 8041792 | 43811081 | 54265386 | 10454305 | 5274689.4 | 130071233 | 151672177.6 | 21600944.6
29 | Mandatory Charges
30 | Provision towards Seniorage Charges on Civil Component | 0 | 308 | 308 |  | 448 | 448 |  | 1001 | 1001 |  | 0 | 1757 | 1757
31 | Provision towards DMF & SMFT Charges @32% (DMF-30%+SMFT-2% Charges) | 0 | 99 | 99 |  | 143 | 143 |  | 320 | 320 |  | 0 | 562 | 562
32 | Mandatory Charges @5.11% (TGMSIDC Supervision Charges-4%+Labour Cess-1% +NAC-0.1%+Haritha Nidhi-0.01%) | 1754194 | 2399641 | 645447 | 1696212 | 2577846 | 881634 | 1752443 | 2772961 | 1020518 |  | 5202849 | 7750448 | 2547599
33 | Sub Total (30 to 32) | 1754194 | 2400048 | 645854 | 1696212 | 2578437 | 882225 | 1752443 | 2774282 | 1021839 | 0 | 5202849 | 7752767 | 2549918
34 | Total (28+33) | 45609047 | 49359748.6 | 3750701.6 | 44101511 | 53025528 | 8924017 | 45563524 | 57039668 | 11476144 | 5274689.4 | 135274082 | 159424944.6 | 24150862.6
35 | GST @18% on S.No 34 | 8209628 | 8884755 | 675127 | 7632954 | 9181376 | 1548422 | 7885995 | 9876429 | 1990434 |  | 23728577 | 27942560 | 4213983
36 | Provision towards (LS) - Inaugration Expenses | 1181325 | 200000 | -981325 | 3265535 | 300000 | -2965535 | 1550481 | 300000 | -1250481 |  | 5997341 | 800000 | -5197341
37 | Grand Total (34 to 36) | 55000000 | 58444503.6 | 3444503.6 | 55000000 | 62506904 | 7506904 | 55000000 | 67216097 | 12216097 | 5274689.4 | 165000000 | 188167504.6 | 23167504.6
|  |  | As Per Agreement | 165000000
|  |  | As per workdone | 188167504.6
|  |  | Difference | 23167504.6
The Net Difference Amount = 2,31,67,505 Rupees

## Annexure-A,B,C
ANNEXURE-A
Interior Works
IVF Gandhi
S.No | Item Description | UOM | Qty | Rate (Rs.) | Amount (Rs.) | Remarks
1 | Wall Paneling 14mm thick Indoor WPC louvers panneling till slab | Sqm | 18.58 | 15500 | 287990
2 | 2 WPC Louvers Ceiling Praviding and fixing WPC Louvers to the Celling | Sqm | 7.58 | 17450 | 132271
3 | Providing and fixing of wooden box celling at the top of Reception table with Imm thick laminate | Sqm | 2.58 | 11335 | 29244
4 | Back Pannelling with laminate Finish of 1 mm thick | Sqm | 7.5 | 10500 | 78750
5 | Providing and fixing ISI marked Magnetic 25mm Block Board door shutters | Nos | 1 | 13800 | 13800
6 | Providing and fixing PVC frames on the walls for covering the area over DB Boxes | Sqm | 4.45 | 6473 | 28805
7 | Providing and Fixing of (25X25) mm WPC corner L-Patties at the topper edge of the wall tile cladding | Rmt | 38 | 230 | 8740
8 | Providing and Fixing of SS-ROSE GOLD corner & L-Patties at the SIDE edge of the wall tile cladding | Nos | 7 | 1500 | 10500
9 | Providing and fixing of Door Frame panneling with 18mm BWP 710 Gurjan Ply | Rmt | 11.58 | 2166 | 25082
10 | Providing and fixing the 60mm Thick Box framing as the back support for the name plate | Sqm | 1.32 | 11012 | 14536
11 | Providing and Fixing of 32mm Double Flush Door (1500 x 200 mm door) | Nos | 1 | 50400 | 50400
12 | Providing and fixing of Side wall decor Frame for photo hangings panneling | Rmt | 10.97 | 2170 | 23805
13 | Supply and fixing of Wall paper as approved by the Engineer In-charge. | Nos | 2 | 5175 | 10350
14 | Supply and fixing of Main IVF logo with LED arcylic board ( 520 mm dia & 50 mm thick) | Nos | 1 | 11475 | 11475
15 | Supply and fixing of Main Entrance LED 3D Arcylic letter board (2890 mm x 465 mm) | Nos | 1 | 44250 | 44250
16 | Providing and fixing Aluminium Extruded Section Body Tubular Type Hydraulic Door Closer | Nos | 8 | 2819 | 22552
17 | Providing, Fabricating and fixing full height V-board partitions of overall thickness of 75mm Partition frame work | Sqm | 89.11 | 1625 | 144804
18 | Supply and fixing of Dress Hangers | Nos | 5 | 510 | 2550
19 | Name Plates (Room Names) as approved by the Engineer In-charge. | Nos | 31 | 600 | 18600
20 | Supply and fixing of High Quality IVF Procedural photos (2' x 2' and above) | Nos | 14 | 9000 | 126000
21 | Supply of Sun Control film to the glazed windows (For Windows & Door view Windows) | Sqm | 14.55 | 381 | 5544
22 | Supplying and fixing Rectangular Mirror Frameless of size 457 .2 mm x 609.6 mm (For Change room) | Nos | 5 | 1775 | 8875
23 | Supply of Venetian blinds Vertical blinds 100 mm wide with all accessories. (For semen collection room & Counselling room Windows) | Sqm | 5.01 | 2187 | 10957
24 | POINT WIRING and LIGHT FIXTURES & FITTINGS | Nos | 13 | 1200 | 15600
25 | Proving and fixing Profile lights at wpc Louvers | Rmt | 10.66 | 1182 | 12600
26 | Proving and fixing Track lights at side wall décor frame with 4 fixtures and 2 tracks | Job | 1 | 9600 | 9600
27 | External Profile light at Name Plate | Rmt | 2.89 | 1182 | 3416
|  |  |  | TOTAL | 1151096
ANNEXURE-B
Interior Works
IVF PETLABURJ
S.No | Item Description | UOM | Qty | Rate (Rs.) | Amount (Rs.) | Remarks
1 | High Quality IVF Procedural photos at Entrance and Reception | Nos | 12 | 9000 | 108000
2 | 60mm Thick Box framing as the back support for the name plate at Entrance | Sqm | 3.98 | 11012 | 43828
3 | Door Frame side Paneling at Entrance | Sqm | 7.551 | 9250 | 69847
4 | 32mm Double Flush Door (1800 x 2100 mm door) at Entrance | Nos | 1 | 56500 | 56500
5 | Name Plate With Glossy Laminate at Entrance | Sqm | 2.6 | 9580 | 24908
6 | MIRROR GOLD TITANIUM LETTERS & S.S. MIRROR LETTERS at Entrance | Job | 1 | 67500 | 67500
7 | Double side ACP sheet (Name board wth three languages fixed at IVF Entrance Corridor) | Nos | 1 | 6000 | 6000
8 | Foam Board (Name board wth three languages with direction to IVF Center fixed at 3rd floor) | Nos | 2 | 2800 | 5600
9 | Foam Board (Name board wth with direction to Rooms fixed to wall in IVF Corridor,) | Nos | 2 | 3200 | 6400
10 | Main IVF logo with LED arcylic board at Entrance | Nos | 1 | 11475 | 11475
11 | Window blinds (For semen collection room & Counselling room Windows) | Sqm | 15 | 2187 | 32805
12 | Hydraullic door closer for ABS Doors | Nos | 15 | 2819 | 42285
13 | Supply of Sun Control film to the glazed windows (For Windows & Door view Windows) | Sqm | 48 | 381 | 18288
14 | Supply and fixing of Dress Hangers (in change rooms). | Nos | 5 | 510 | 2550
15 | Supplying and fixing Rectangular Mirror Frameless of size 457 .2 mm x 609.6 mm (For Change room) | Nos | 5 | 1775 | 8875
16 | Name Plates (Room Names) | Nos | 38 | 600 | 22800
17 | Providing and fixing PVC frames on the walls for covering the area over DB Boxes | Sqm | 0.74 | 6473 | 4790
|  |  |  | TOTAL | 532451
ANNEXURE-C
Interior Works
IVF WARANGAL
S.No | Item Description | UOM | Qty | Rate (Rs.) | Amount (Rs.) | Remarks
1 | High Quality IVF Procedural photos at Entrance and Reception | Nos | 15 | 9000 | 135000 | As Per IVF Petlaburj
2 | 60mm Thick Box framing as the back support for the name plate at Entrance | Sqm | 5 | 11012 | 55060 | As Per IVF Petlaburj
3 | Door Frame side Paneling at Entrance | Sqm | 10 | 9250 | 92500 | As Per IVF Petlaburj
4 | 32mm Double Flush Door (1800 x 2100 mm door) at Entrance | Nos | 1 | 56500 | 56500 | As Per IVF Petlaburj
5 | Name Plate With Glossy Laminate at Entrance | Sqm | 3 | 9580 | 28740 | As Per IVF Petlaburj
6 | MIRROR GOLD TITANIUM LETTERS & S.S. MIRROR LETTERS at Entrance | Job | 1 | 67500 | 67500 | As Per IVF Petlaburj
7 | Double side ACP sheet (Name board wth three languages fixed at IVF Entrance Corridor) | Nos | 1 | 6000 | 6000 | As Per IVF Petlaburj
8 | Foam Board (Name board wth three languages with direction to IVF Center fixed at 3rd floor) | Nos | 2 | 2800 | 5600 | As Per IVF Petlaburj
9 | Foam Board (Name board wth with direction to Rooms fixed to wall in IVF Corridor,) | Nos | 2 | 3200 | 6400 | As Per IVF Petlaburj
10 | Main IVF logo with LED arcylic board at Entrance | Nos | 1 | 11475 | 11475 | As Per IVF Petlaburj
11 | PVC frames on the walls for covering the area over DB Boxes | Sqm | 1 | 6473 | 6473 | As Per IVF Petlaburj
12 | Window blinds (For semen collection room & Counselling room Windows) | Sqm | 15 | 2187 | 32805 | As Per IVF Petlaburj
13 | Hydraullic door closer for ABS Doors | Nos | 15 | 2819 | 42285 | As Per IVF Petlaburj
14 | Supply of Sun Control film to the glazed windows (For Windows & Door view Windows) | Sqm | 45 | 381 | 17145 | As Per IVF Petlaburj
15 | Supply and fixing of Dress Hangers (in change rooms). | Nos | 5 | 510 | 2550 | As Per IVF Petlaburj
16 | Supplying and fixing Rectangular Mirror Frameless of size 457 .2 mm x 609.6 mm (For Change room) | Nos | 5 | 1775 | 8875 | As Per IVF Petlaburj
17 | Name Plates (Room Names) as approved by the Engineer In-charge. | Nos | 30 | 600 | 18000 | As Per IVF Petlaburj
|  |  |  | Sub Total | 592908

## Annexure-D,E,F
ANNEXURE-D
Other Mandatory Supplimental Items
S.No | Item Description | UOM | Rate (Rs.) | IVF Gandhi
|  |  |  | Qty | Amount (Rs.) | Remarks
Equipment
1 | Fowler Two Function Bed with ABS Panel in Pre and Post Operative wards and Semen Collection room | Nos | 39000 | 5 | 195000
2 | Bed side Table with ABS Plastic body in Pre and Post Operative wards and Semen Collection room | Nos | 9000 | 5 | 45000
3 | Corporate Deluxe Locker with SS 304 grade Top in Sample Collection and Injection Room | Nos | 8400 | 1 | 8400
4 | Bed side stand with full SS 304 grade constructionof in Sample Collection and Injection Room | Nos | 9300 | 1 | 9300
5 | Bed side stand with full GI Powder coated constructionof in Semen Collection room | Nos | 4200 | 1 | 4200
6 | Supply of a Sample collection chair in Sample Collection and Injection Room | Nos | 16200 | 1 | 16200
7 | Sample collection bed in Sample Collection and Injection Room | Nos | 29000 | 1 | 29000
8 | Cryo Can 11 Ltr without wheels in Cryo room | Nos | 32000 | 1 | 32000
9 | The Multipurpose Electro Hydraulic Mobile OT Table in Major OT | Nos | 210000 | 1 | 210000
10 | Supply and fixing of Powder coated GI stand with 4 nos height adjustable racks of size 670x410x1570 mm | Nos | 80000 | 1 | 80000
|  |  | Total |  | 629100
Furniture
1 | Writing board in Counselling rooms | Nos | 2100 | 2 | 4200
2 | MDF wooden table in Reception and Ultrasound room | Nos | 14500 | 2 | 29000
3 | Office table in Embryologist and Anesthetist room | Nos | 16000 |  | 0
4 | 3 Seater Sofa | Nos | 24000 | 2 | 48000
|  |  | Total |  | 81200
ANNEXURE-E
Other Mandatory Supplimental Items
S.No | Item Description | UOM | Rate (Rs.) | IVF Gandhi
|  |  |  | Qty | Amount (Rs.) | Remarks
Equipment
1 | Fowler Two Function Bed with ABS Panel in Pre and Post Operative wards and Semen Collection room | Nos | 39000 | 5 | 195000 | As Per IVF Gandhi
2 | Bed side Table with ABS Plastic body in Pre and Post Operative wards and Semen Collection room | Nos | 9000 | 5 | 45000 | As Per IVF Gandhi
3 | Corporate Deluxe Locker with SS 304 grade Top in Sample Collection and Injection Room | Nos | 8400 | 1 | 8400 | As Per IVF Gandhi
4 | Bed side stand with full SS 304 grade constructionof in Sample Collection and Injection Room | Nos | 9300 | 1 | 9300 | As Per IVF Gandhi
5 | Bed side stand with full GI Powder coated constructionof in Semen Collection room | Nos | 4200 | 1 | 4200 | As Per IVF Gandhi
6 | Supply of a Sample collection chair in Sample Collection and Injection Room | Nos | 16200 | 1 | 16200 | As Per IVF Gandhi
7 | Sample collection bed in Sample Collection and Injection Room | Nos | 29000 | 1 | 29000 | As Per IVF Gandhi
8 | Cryo Can 11 Ltr without wheels in Cryo room | Nos | 32000 | 1 | 32000 | As Per IVF Gandhi
9 | The Multipurpose Electro Hydraulic Mobile OT Table in Major OT | Nos | 210000 | 1 | 210000 | As Per IVF Gandhi
10 | Supply and fixing of Powder coated GI stand with 4 nos height adjustable racks of size 670x410x1570 mm | Nos | 80000 | 1 | 80000 | As Per IVF Gandhi
|  |  | Total |  | 629100
Furniture
1 | Writing board in Counselling rooms | Nos | 2100 | 1 | 2100 | As Per IVF Gandhi
2 | MDF wooden table in Reception and Ultrasound room | Nos | 14500 | 2 | 29000 | As Per IVF Gandhi
3 | Office table in Embryologist and Anesthetist room | Nos | 16000 | 2 | 32000 | As Per IVF Gandhi
4 | 3 Seater Sofa | Nos | 24000 | 2 | 48000 | As Per IVF Gandhi
|  |  | Total |  | 111100
ANNEXURE-F
Other Mandatory Supplimental Items
S.No | Item Description | UOM | Rate (Rs.) | IVF Gandhi
|  |  |  | Qty | Amount (Rs.) | Remarks
Equipment
1 | Fowler Two Function Bed with ABS Panel in Pre and Post Operative wards and Semen Collection room | Nos | 39000 | 5 | 195000 | As Per IVF Gandhi
2 | Bed side Table with ABS Plastic body in Pre and Post Operative wards and Semen Collection room | Nos | 9000 | 5 | 45000 | As Per IVF Gandhi
3 | Corporate Deluxe Locker with SS 304 grade Top in Sample Collection and Injection Room | Nos | 8400 | 1 | 8400 | As Per IVF Gandhi
4 | Bed side stand with full SS 304 grade constructionof in Sample Collection and Injection Room | Nos | 9300 | 1 | 9300 | As Per IVF Gandhi
5 | Bed side stand with full GI Powder coated constructionof in Semen Collection room | Nos | 4200 | 1 | 4200 | As Per IVF Gandhi
6 | Supply of a Sample collection chair in Sample Collection and Injection Room | Nos | 16200 | 1 | 16200 | As Per IVF Gandhi
7 | Sample collection bed in Sample Collection and Injection Room | Nos | 29000 | 1 | 29000 | As Per IVF Gandhi
8 | Cryo Can 11 Ltr without wheels in Cryo room | Nos | 32000 | 1 | 32000 | As Per IVF Gandhi
9 | The Multipurpose Electro Hydraulic Mobile OT Table in Major OT | Nos | 210000 | 1 | 210000 | As Per IVF Gandhi
10 | Supply and fixing of Powder coated GI stand with 4 nos height adjustable racks of size 670x410x1570 mm | Nos | 80000 | 1 | 80000 | As Per IVF Gandhi
|  |  | Total |  | 629100
Furniture
1 | Writing board in Counselling rooms | Nos | 2100 | 2 | 4200 | As Per IVF Gandhi
2 | MDF wooden table in Reception and Ultrasound room | Nos | 14500 | 2 | 29000 | As Per IVF Gandhi
3 | Office table in Embryologist and Anesthetist room | Nos | 16000 |  | 0 | As Per IVF Gandhi
4 | 3 Seater Sofa | Nos | 24000 | 2 | 48000 | As Per IVF Gandhi
|  |  | Total |  | 81200

## Annexure-G
ANNEXURE-G
Other Additional Supplimental Works
S.NO | Description | UOM | Rate (Rs.) | IVF Gandhi |  | Remarks
|  |  |  | QTY | Amount (Rs.)
3 | Lab Chairs Type I (DCA Price) in Andrology Lab & Embryology Lab | Nos | 15340 | 10 | 153400 | Extra Items
|  |  | Total |  | 153400
S.NO | Description | UOM | Rate (Rs.) | IVF Petlaburj |  | Remarks
|  |  |  | QTY | Amount (Rs.)
1 | Consultant Chair in Embryologist and Anesthetist room | Nos | 20000 | 3 | 60000 | Extra Items
2 | Patient Chair Embryologist and Anesthetist room | Nos | 13500 | 6 | 81000 | Extra Items
3 | Lab Chairs Type I (DCA Price) in Andrology Lab & Embryology Lab | Nos | 15340 | 10 | 153400 | Extra Items
|  |  | Total |  | 294400
S.NO | Description | UOM | Rate (Rs.) | IVF Warangal |  | Remarks
|  |  |  | QTY | Amount (Rs.)
1 | Consultant Chair in Embryologist and Anesthetist room | Nos | 20000 | 3 | 60000 | Extra Items
2 | Patient Chair Embryologist and Anesthetist room | Nos | 13500 | 6 | 81000 | Extra Items
3 | Lab Chairs Type I (DCA Price) in Andrology Lab & Embryology Lab | Nos | 15340 | 10 | 153400 | Extra Items
4 | IUI Couch/ Table in IUI Room | Nos | 50000 | 2 | 100000 | Extra Items
5 | office table in Embryologist room | Nos | 16000 | 1 | 16000 | Extra Items
6 | Patient Seating 3 in 1 model in waiting area | Nos | 38500 | 3 | 115500 | Extra Items
|  |  | Total |  | 525900

## 3 Site Consolidated-2
|  | Gandhi Hospital, Secunderabad |  |  | MGMH PETLABURZ |  |  | MGM WARANGAL |  |  | Difference (PTB - GH) | Total |  |  | Remarks
A | B | C | D | E | F | G | H | I | J | K |  | L | M | N | O
S.No | Description | As per Agreement | As per workdone | Excess / Less | As per Agreement | As per workdone | Excess / Less | As per Agreement | As per workdone | Excess / Less |  | As per Agreement | As per workdone | Excess / Less
| Layout Area (SQM) | 447.8 | 418.415 |  | 453.08 | 594.38 |  | 503 | 597.3 |  |  | 1403.88 | 1610.095
As Per Agreement (PART-A)
1 | Equipment | 25009375 | 25009375 | 0 | 25009375 | 25009375 | 0 | 25009376 | 25009376 | 0 | 0 | 75028126 | 75028126 | 0 | As Per RE/WE
2 | Furniture | 1008850 | 898850 | -110000 | 1011100 | 1011100 | 0 | 1011100 | 1011100 | 0 |  | 3031050 | 2921050 | -110000 | As Per RE/WE
3 | Civil Works | 7431553 | 5612831 | -1818722 | 5915529 | 7012631 | 1097102 | 7320696 | 9771662 | 2450966 | 2915824 | 20667778 | 22397124 | 1729346 | As Per RE/WE
4 | Plumbing works | 204480 | 126489 | -77991 | 215122 | 136973 | -78149 | 160285 | 156101 | -4184 | -158 | 579887 | 419563 | -160324 | As Per RE/WE
5 | Electrical works | 3732008 | 4027908 | 295900 | 3719411 | 5641335 | 1921924 | 3832437 | 5402274 | 1569837 | 1626024 | 11283856 | 15071517 | 3787661 | As Per RE/WE
6 | ELV works | 827000 | 827000 | 0 | 689000 | 689000 | 0 | 1337000 | 1337000 | 0 | 0 | 2853000 | 2853000 | 0 | As Per RE/WE
7 | Fire Fighting works | 735880 | 735880 | 0 | 873880 | 873880 | 0 | 225880 | 225880 | 0 | 0 | 1835640 | 1835640 | 0 | As Per RE/WE
8 | Air Conditioning works | 3879885 | 3839121 | -40764 | 3946060 | 2725391 | -1220669 | 3888485 | 4247076 | 358591 | -1179905 | 11714430 | 10811588 | -902842 | As Per RE/WE
9 | MGPS works | 1025822 | 1180151.6 | 154329.6 | 1025822 | 1141255 | 115433 | 1025822 | 1046572 | 20750 | -38896.6 | 3077466 | 3367978.6 | 290512.6 | As Per RE/WE
10 | Total (Part-A) (1 to 9) | 43854853 | 42257605.6 | -1597247.4 | 42405299 | 44240940 | 1835641 | 43811081 | 48207041 | 4395960 | 3322888.4 | 130071233 | 134705586.6 | 4634353.6
11 | Supplimental Items (PART-B)
12 | Equipment supplimental |  | 221000 | 221000 |  | 221000 | 221000 |  | 221000 | 221000 | 0 | 0 | 663000 | 663000 | As Per RE/WE
13 | Civil supplimental works |  | 802549 | 802549 |  | 1056649 | 1056649 |  | 841331 | 841331 | 254100 | 0 | 2700529 | 2700529 | As Per RE/WE
14 | Plumbing supplimental works |  | 21690 | 21690 |  | 8985 | 8985 |  | 8985 | 8985 | -12705 | 0 | 39660 | 39660 | As Per RE/WE
15 | Electrical supplimental works |  | 415236 | 415236 |  | 496686 | 496686 |  | 486635 | 486635 | 81450 | 0 | 1398557 | 1398557 | As Per RE/WE
16 | Fire Fighting supplimental works |  | 291366 | 291366 |  | 291366 | 291366 |  | 291366 | 291366 | 0 | 0 | 874098 | 874098 | As Per RE/WE
17 | Air Conditioning supplimental works |  | 120788 | 120788 |  | 1749744 | 1749744 |  | 65250 | 65250 | 1628956 | 0 | 1935782 | 1935782 | As Per RE/WE
18 | MGPS supplimental works |  | 814670 | 814670 |  | 814670 | 814670 |  | 814670 | 814670 | 0 | 0 | 2444010 | 2444010 | As Per RE/WE
A: 19; B: Water Proofing Works; Gandhi Hospital, Secunderabad E: 0; MGMH PETLABURZ H: 0; MGM WARANGAL J: 1500000; MGM WARANGAL K: 1500000 |  | 0 | 1500000 | 1500000 | As Per RE/WE
20 | Total (Part-B) (12 to 19) | 0 | 2687299 | 2687299 | 0 | 4639100 | 4639100 | 0 | 4229237 | 4229237 | 1951801 | 0 | 11555636 | 11555636
21 | Total (Part-A+B) (10+20) | 43854853 | 44944904.6 | 1090051.6 | 42405299 | 48880040 | 6474741 | 43811081 | 52436278 | 8625197 | 5274689.4 | 130071233 | 146261222.6 | 16189989.6
22 | Other Supplimental Items(PART-C)
23 | Interior Works |  | 1151096 | 1151096 |  | 532451 | 532451 |  | 592908 | 592908 |  | 0 | 2276455 | 2276455 | As Per Annexure-01
24 | Equipment |  | 629100 | 629100 |  | 629100 | 629100 |  | 629100 | 629100 |  | 0 | 1887300 | 1887300 | As Per Annexure-02
25 | Furniture |  | 81200 | 81200 |  | 111100 | 111100 |  | 81200 | 81200 |  | 0 | 273500 | 273500 | As Per Annexure-02
26 | Additional Items As Per End User Letter |  | 153400 | 153400 |  | 294400 | 294400 |  | 525900 | 525900 |  | 0 | 973700 | 973700 | As Per Annexure-03
27 | Total (Part-C) (23 to 26) | 0 | 2014796 | 2014796 | 0 | 1567051 | 1567051 | 0 | 1829108 | 1829108 | 0 | 0 | 5410955 | 5410955
28 | Total (Part-A+B+C) (21+27) | 43854853 | 46959700.6 | 3104847.6 | 42405299 | 50447091 | 8041792 | 43811081 | 54265386 | 10454305 | 5274689.4 | 130071233 | 151672177.6 | 21600944.6
29 | Mandatory Charges
30 | Provision towards Seniorage Charges on Civil Component | 0 | 308 | 308 |  | 448 | 448 |  | 1001 | 1001 |  | 0 | 1757 | 1757
31 | Provision towards DMF & SMFT Charges @32% (DMF-30%+SMFT-2% Charges) | 0 | 99 | 99 |  | 143 | 143 |  | 320 | 320 |  | 0 | 562 | 562
32 | Mandatory Charges @5.11% (TGMSIDC Supervision Charges-4%+Labour Cess-1% +NAC-0.1%+Haritha Nidhi-0.01%) | 1754194 | 2399641 | 645447 | 1696212 | 2577846 | 881634 | 1752443 | 2772961 | 1020518 |  | 5202849 | 7750448 | 2547599
33 | Sub Total (30 to 32) | 1754194 | 2400048 | 645854 | 1696212 | 2578437 | 882225 | 1752443 | 2774282 | 1021839 | 0 | 5202849 | 7752767 | 2549918
34 | Total (28+33) | 45609047 | 49359748.6 | 3750701.6 | 44101511 | 53025528 | 8924017 | 45563524 | 57039668 | 11476144 | 5274689.4 | 135274082 | 159424944.6 | 24150862.6
35 | GST @18% on S.No 34 | 8209628 | 8884755 | 675127 | 7632954 | 9181376 | 1548422 | 7885995 | 9876429 | 1990434 |  | 23728577 | 27942560 | 4213983
36 | Provision towards (LS) - Inaugration Expenses | 1181325 | 200000 | -981325 | 3265535 | 300000 | -2965535 | 1550481 | 300000 | -1250481 |  | 5997341 | 800000 | -5197341
37 | Grand Total (34 to 36) | 55000000 | 58444503.6 | 3444503.6 | 55000000 | 62506904 | 7506904 | 55000000 | 67216097 | 12216097 | 5274689.4 | 165000000 | 188167504.6 | 23167504.6
|  |  | As Per Agreement | 165000000
|  |  | As per workdone | 188167504.6
|  |  | Difference | 23167504.6
The Net Difference Amount = 2,31,67,505 Rupees
-1861396

## Annexure-01
ANNEXURE-01
Interior Works
IVF Gandhi
S.No | Item Description | UOM | Qty | Rate (Rs.) | Amount (Rs.) | Remarks
1 | Wall Paneling 14mm thick Indoor WPC louvers panneling till slab | Sqm | 18.58 | 15500 | 287990
2 | 2 WPC Louvers Ceiling Praviding and fixing WPC Louvers to the Celling | Sqm | 7.58 | 17450 | 132271
3 | Providing and fixing of wooden box celling at the top of Reception table with Imm thick laminate | Sqm | 2.58 | 11335 | 29244
4 | Back Pannelling with laminate Finish of 1 mm thick | Sqm | 7.5 | 10500 | 78750
5 | Providing and fixing ISI marked Magnetic 25mm Block Board door shutters | Nos | 1 | 13800 | 13800
6 | Providing and fixing PVC frames on the walls for covering the area over DB Boxes | Sqm | 4.45 | 6473 | 28805
7 | Providing and Fixing of (25X25) mm WPC corner L-Patties at the topper edge of the wall tile cladding | Rmt | 38 | 230 | 8740
8 | Providing and Fixing of SS-ROSE GOLD corner & L-Patties at the SIDE edge of the wall tile cladding | Nos | 7 | 1500 | 10500
9 | Providing and fixing of Door Frame panneling with 18mm BWP 710 Gurjan Ply | Rmt | 11.58 | 2166 | 25082
10 | Providing and fixing the 60mm Thick Box framing as the back support for the name plate | Sqm | 1.32 | 11012 | 14536
11 | Providing and Fixing of 32mm Double Flush Door (1500 x 200 mm door) | Nos | 1 | 50400 | 50400
12 | Providing and fixing of Side wall decor Frame for photo hangings panneling | Rmt | 10.97 | 2170 | 23805
13 | Supply and fixing of Wall paper as approved by the Engineer In-charge. | Nos | 2 | 5175 | 10350
14 | Supply and fixing of Main IVF logo with LED arcylic board ( 520 mm dia & 50 mm thick) | Nos | 1 | 11475 | 11475
15 | Supply and fixing of Main Entrance LED 3D Arcylic letter board (2890 mm x 465 mm) | Nos | 1 | 44250 | 44250
16 | Providing and fixing Aluminium Extruded Section Body Tubular Type Hydraulic Door Closer | Nos | 8 | 2819 | 22552
17 | Providing, Fabricating and fixing full height V-board partitions of overall thickness of 75mm Partition frame work | Sqm | 89.11 | 1625 | 144804
18 | Supply and fixing of Dress Hangers | Nos | 5 | 510 | 2550
19 | Name Plates (Room Names) as approved by the Engineer In-charge. | Nos | 31 | 600 | 18600
20 | Supply and fixing of High Quality IVF Procedural photos (2' x 2' and above) | Nos | 14 | 9000 | 126000
21 | Supply of Sun Control film to the glazed windows (For Windows & Door view Windows) | Sqm | 14.55 | 381 | 5544
22 | Supplying and fixing Rectangular Mirror Frameless of size 457 .2 mm x 609.6 mm (For Change room) | Nos | 5 | 1775 | 8875
23 | Supply of Venetian blinds Vertical blinds 100 mm wide with all accessories. (For semen collection room & Counselling room Windows) | Sqm | 5.01 | 2187 | 10957
24 | POINT WIRING and LIGHT FIXTURES & FITTINGS | Nos | 13 | 1200 | 15600
25 | Proving and fixing Profile lights at wpc Louvers | Rmt | 10.66 | 1182 | 12600
26 | Proving and fixing Track lights at side wall décor frame with 4 fixtures and 2 tracks | Job | 1 | 9600 | 9600
27 | External Profile light at Name Plate | Rmt | 2.89 | 1182 | 3416
|  |  |  | TOTAL | 1151096
IVF PETLABURJ
S.No | Item Description | UOM | Qty | Rate (Rs.) | Amount (Rs.) | Remarks
1 | High Quality IVF Procedural photos at Entrance and Reception | Nos | 12 | 9000 | 108000
2 | 60mm Thick Box framing as the back support for the name plate at Entrance | Sqm | 3.98 | 11012 | 43828
3 | Door Frame side Paneling at Entrance | Sqm | 7.551 | 9250 | 69847
4 | 32mm Double Flush Door (1800 x 2100 mm door) at Entrance | Nos | 1 | 56500 | 56500
5 | Name Plate With Glossy Laminate at Entrance | Sqm | 2.6 | 9580 | 24908
6 | MIRROR GOLD TITANIUM LETTERS & S.S. MIRROR LETTERS at Entrance | Job | 1 | 67500 | 67500
7 | Double side ACP sheet (Name board wth three languages fixed at IVF Entrance Corridor) | Nos | 1 | 6000 | 6000
8 | Foam Board (Name board wth three languages with direction to IVF Center fixed at 3rd floor) | Nos | 2 | 2800 | 5600
9 | Foam Board (Name board wth with direction to Rooms fixed to wall in IVF Corridor,) | Nos | 2 | 3200 | 6400
10 | Main IVF logo with LED arcylic board at Entrance | Nos | 1 | 11475 | 11475
11 | Window blinds (For semen collection room & Counselling room Windows) | Sqm | 15 | 2187 | 32805
12 | Hydraullic door closer for ABS Doors | Nos | 15 | 2819 | 42285
13 | Supply of Sun Control film to the glazed windows (For Windows & Door view Windows) | Sqm | 48 | 381 | 18288
14 | Supply and fixing of Dress Hangers (in change rooms). | Nos | 5 | 510 | 2550
15 | Supplying and fixing Rectangular Mirror Frameless of size 457 .2 mm x 609.6 mm (For Change room) | Nos | 5 | 1775 | 8875
16 | Name Plates (Room Names) | Nos | 38 | 600 | 22800
17 | Providing and fixing PVC frames on the walls for covering the area over DB Boxes | Sqm | 0.74 | 6473 | 4790
|  |  |  | TOTAL | 532451
IVF WARANGAL
S.No | Item Description | UOM | Qty | Rate (Rs.) | Amount (Rs.) | Remarks
1 | High Quality IVF Procedural photos at Entrance and Reception | Nos | 15 | 9000 | 135000 | As Per IVF Petlaburj
2 | 60mm Thick Box framing as the back support for the name plate at Entrance | Sqm | 5 | 11012 | 55060 | As Per IVF Petlaburj
3 | Door Frame side Paneling at Entrance | Sqm | 10 | 9250 | 92500 | As Per IVF Petlaburj
4 | 32mm Double Flush Door (1800 x 2100 mm door) at Entrance | Nos | 1 | 56500 | 56500 | As Per IVF Petlaburj
5 | Name Plate With Glossy Laminate at Entrance | Sqm | 3 | 9580 | 28740 | As Per IVF Petlaburj
6 | MIRROR GOLD TITANIUM LETTERS & S.S. MIRROR LETTERS at Entrance | Job | 1 | 67500 | 67500 | As Per IVF Petlaburj
7 | Double side ACP sheet (Name board wth three languages fixed at IVF Entrance Corridor) | Nos | 1 | 6000 | 6000 | As Per IVF Petlaburj
8 | Foam Board (Name board wth three languages with direction to IVF Center fixed at 3rd floor) | Nos | 2 | 2800 | 5600 | As Per IVF Petlaburj
9 | Foam Board (Name board wth with direction to Rooms fixed to wall in IVF Corridor,) | Nos | 2 | 3200 | 6400 | As Per IVF Petlaburj
10 | Main IVF logo with LED arcylic board at Entrance | Nos | 1 | 11475 | 11475 | As Per IVF Petlaburj
11 | PVC frames on the walls for covering the area over DB Boxes | Sqm | 1 | 6473 | 6473 | As Per IVF Petlaburj
12 | Window blinds (For semen collection room & Counselling room Windows) | Sqm | 15 | 2187 | 32805 | As Per IVF Petlaburj
13 | Hydraullic door closer for ABS Doors | Nos | 15 | 2819 | 42285 | As Per IVF Petlaburj
14 | Supply of Sun Control film to the glazed windows (For Windows & Door view Windows) | Sqm | 45 | 381 | 17145 | As Per IVF Petlaburj
15 | Supply and fixing of Dress Hangers (in change rooms). | Nos | 5 | 510 | 2550 | As Per IVF Petlaburj
16 | Supplying and fixing Rectangular Mirror Frameless of size 457 .2 mm x 609.6 mm (For Change room) | Nos | 5 | 1775 | 8875 | As Per IVF Petlaburj
17 | Name Plates (Room Names) as approved by the Engineer In-charge. | Nos | 30 | 600 | 18000 | As Per IVF Petlaburj
|  |  |  | Sub Total | 592908

## Annexure-02
ANNEXURE-02
Additional Items As Per IVF Gandhi
S.No | Item Description | UOM | Rate (Rs.) | IVF Gandhi |  | IVF Petlaburj |  | IVF Warangal
|  |  |  | Qty | Amount (Rs.) | Qty | Amount (Rs.) | Qty | Amount (Rs.) | Remarks
Equipment
1 | Fowler Two Function Bed with ABS Panel in Pre and Post Operative wards and Semen Collection room | Nos | 39000 | 5 | 195000 | 5 | 195000 | 5 | 195000 | As Per IVF Gandhi
2 | Bed side Table with ABS Plastic body in Pre and Post Operative wards and Semen Collection room | Nos | 9000 | 5 | 45000 | 5 | 45000 | 5 | 45000 | As Per IVF Gandhi
3 | Corporate Deluxe Locker with SS 304 grade Top in Sample Collection and Injection Room | Nos | 8400 | 1 | 8400 | 1 | 8400 | 1 | 8400 | As Per IVF Gandhi
4 | Bed side stand with full SS 304 grade constructionof in Sample Collection and Injection Room | Nos | 9300 | 1 | 9300 | 1 | 9300 | 1 | 9300 | As Per IVF Gandhi
5 | Bed side stand with full GI Powder coated constructionof in Semen Collection room | Nos | 4200 | 1 | 4200 | 1 | 4200 | 1 | 4200 | As Per IVF Gandhi
6 | Supply of a Sample collection chair in Sample Collection and Injection Room | Nos | 16200 | 1 | 16200 | 1 | 16200 | 1 | 16200 | As Per IVF Gandhi
7 | Sample collection bed in Sample Collection and Injection Room | Nos | 29000 | 1 | 29000 | 1 | 29000 | 1 | 29000 | As Per IVF Gandhi
8 | Cryo Can 11 Ltr without wheels in Cryo room | Nos | 32000 | 1 | 32000 | 1 | 32000 | 1 | 32000 | As Per IVF Gandhi
9 | The Multipurpose Electro Hydraulic Mobile OT Table in Major OT | Nos | 210000 | 1 | 210000 | 1 | 210000 | 1 | 210000 | As Per IVF Gandhi
10 | Supply and fixing of Powder coated GI stand with 4 nos height adjustable racks of size 670x410x1570 mm | Nos | 80000 | 1 | 80000 | 1 | 80000 | 1 | 80000 | As Per IVF Gandhi
|  |  | Total |  | 629100 |  | 629100 |  | 629100
Furniture
1 | Writing board in Counselling rooms | Nos | 2100 | 2 | 4200 | 1 | 2100 | 2 | 4200 | As Per IVF Gandhi
2 | MDF wooden table in Reception and Ultrasound room | Nos | 14500 | 2 | 29000 | 2 | 29000 | 2 | 29000 | As Per IVF Gandhi
3 | Office table in Embryologist and Anesthetist room | Nos | 16000 |  | 0 | 2 | 32000 |  | 0 | As Per IVF Gandhi
4 | 3 Seater Sofa | Nos | 24000 | 2 | 48000 | 2 | 48000 | 2 | 48000 | As Per IVF Gandhi
|  |  | Total |  | 81200 |  | 111100 |  | 81200

## Annexure-03
ANNEXURE-03
S.NO | Description | UOM | Rate (Rs.) | IVF Gandhi |  | IVF Petlaburj |  | IVF Warangal |  | Remarks
|  |  |  | QTY | Amount (Rs.) | QTY | Amount (Rs.) | QTY | Amount (Rs.)
1 | Consultant Chair in Embryologist and Anesthetist room | Nos | 20000 | 0 | 0 | 3 | 60000 | 3 | 60000 | Extra Items
2 | Patient Chair Embryologist and Anesthetist room | Nos | 13500 | 0 | 0 | 6 | 81000 | 6 | 81000 | Extra Items
3 | Lab Chairs Type I (DCA Price) in Andrology Lab & Embryology Lab | Nos | 15340 | 10 | 153400 | 10 | 153400 | 10 | 153400 | Extra Items
4 | IUI Couch/ Table in IUI Room | Nos | 50000 | 0 | 0 |  | 0 | 2 | 100000 | Extra Items
5 | office table in Embryologist room | Nos | 16000 | 0 | 0 |  | 0 | 1 | 16000 | Extra Items
6 | Patient Seating 3 in 1 model in waiting area | Nos | 38500 | 0 | 0 |  | 0 | 3 | 115500 | Extra Items
|  |  | Total |  | 153400 |  | 294400 |  | 525900