## Sheet1
Name of the work: Design, fabrication, establishing & commissioning of In-Vitro Fertility Centers (IVFCs) along with allied services on Turnkey basis at Gandhi Hospital, Secunderabad, MGMH Petlaburj, Hyderabad, and MGM Hospital, Warangal.
Comparative Statement
S.No | Description | As Per WorkDone/To be done |  |  | Totals
|  | IVF Gandhi | IVF Petlaburj | IVF Warangal
1 | Equipment | 25908225 | 26020475 | 26020476
2 | Civil Works | 5612831 | 7012631 | 9771661.15
3 | Plumbing works | 126489 | 136973 | 156101
4 | Electrical works | 4027908 | 5641335 | 5402274.4
5 | ELV works | 827000 | 689000 | 1337000
6 | Fire Fighting works | 735880 | 873880 | 225880
7 | Air Conditioning works | 3839121 | 2725391 | 4247076
8 | MGPS works | 1180151.6 | 1141255 | 1046572
| Sub Total (Agreement Part-A) | 42257605.6 | 44240940 | 48207040.55 | 134705586.15
9 | Equipment supplimental | 931300 | 221000 | 317600
10 | Civil supplimental works | 1912429 | 1156237 | 920706
11 | Plumbing supplimental works | 21690 | 8985 | 8985
12 | Electrical supplimental works | 456452.1 | 496686 | 486635
13 | Fire Fighting supplimental works | 291366 | 0 | 291366
14 | Air Conditioning supplimental works | 120788 | 1749744 | 65250
15 | MGPS supplimental works | 814670 | 814670 | 814670
16 | Water Proofing Works | 0 | 0 | 1500000
| Sub Total (Supplimental Part-B) | 4548695.1 | 4447322 | 4405212 | 13401229.1
| Total (Part-A+Part-B) | 46806300.7 | 48688262 | 52612252.55 | 148106815.25
17 | Provision towards Engineering Supervision Charges @ 4% on RE Value | 1872252 | 1947530 | 2104490
| GST @ 18% | 8762139 | 8763887 | 9470205
| Total | 57440691.7 | 59399679 | 64186947.55 | 181027318.25
18 | Labour Cess @ 1% on Basic Price of Revised Estimate | 468063 | 486883 | 526123
19 | NAC @ 0.1% on Basic Price of Revised estimate | 46806 | 48688 | 52612
20 | Provision towards Seniorage Charges on Civil Component | 308 | 448 | 1001
21 | Provision towards DMF Charges 30% on Seniorage Charges | 92 | 134 | 300
22 | Provision towards SMFT Charges 2% on seniorage Charges | 6 | 9 | 20
23 | Provision towards Haritha Nidhi | 4681 | 4869 | 5261
| Sub total of S.No 17 to 22 | 519956 | 541031 | 585317
24 | Provision towards GST 18% on Seniorage Charges | 93592 | 97386 | 105357
25 | Provision towards Unforseen items and rounding off (LS) - | 0 | 910280 | 0
| Sub total of S.No 23 to 25 | 613548 | 1548697 | 690674
| Total | 58054239.7 | 60948376 | 64877621.55 | 183880237.25
26 | TSMSIDC Charges, NAC & Labour Cess @ 5.1% (on S.No 25) | 0 | 46424.28 | 0
27 | New Additional Items As Per IVF Gandhi | 0 | 859451 | 1163790 | 2023241
28 | Extra Items as per Enduser Letter | 0 | 365109 | 652211 | 1017320
29 | Provision towards (LS) - Inaugration Expenses | 200000 | 300000 | 300000 | 800000
| Sub Total (26 to 29) | 200000 | 1570984.28 | 2116001 | 3886985.28
| Grand Total | 58254239.7 | 62519360.28 | 66993622.55 | 187767222.53
| As Per Agreement | 55000000 | 55000000 | 55000000 | 165000000
| As Per Workdone | 58254239.7 | 62519360.28 | 66993622.55 | 187767222.53
| Excess | 3254239.7 | 7519360.28 | 11993622.55 | 22767222.53
| Total Agreement Value | 165000000
| Total Workdone Value | 187767222.53
| Total Excess | 22767222.53

## New_Abstract
Name of the work: Design, fabrication, establishing & commissioning of In-Vitro Fertility Centers (IVFCs) along with allied services on Turnkey basis at Gandhi Hospital, Secunderabad, MGMH Petlaburj, Hyderabad, and MGM Hospital, Warangal.
ABSTRACT COMPARATIVE STATEMENT FOR 3 SITES
S.No | Description |  | As Per Agreement |  |  |  | As Per Workdone/To be done |  |  |  | Excess/Less | Remarks
|  |  | IVF Gandhi | IVF Petlaburj | IVF Warangal | Total | IVF Gandhi | IVF Petlaburj | IVF Warangal | Total
PART-A
1 | Equipment |  | 26018225 | 26020475 | 26020476 | 78059176 | 25908225 | 26020475 | 26020476 | 77949176 | -110000
2 | Civil Works |  | 7431553 | 5915529 | 7320696 | 20667778 | 5612831 | 7012631 | 9771662 | 22397124 | 1729346
3 | Plumbing works |  | 204480 | 215122 | 160285 | 579887 | 126489 | 136973 | 156101 | 419563 | -160324
4 | Electrical works |  | 3732008 | 3719411 | 3832437 | 11283856 | 4027908 | 5641335 | 5402274 | 15071517 | 3787661
5 | ELV works |  | 827000 | 689000 | 1337000 | 2853000 | 827000 | 689000 | 1337000 | 2853000 | 0
6 | Fire Fighting works |  | 735880 | 873880 | 225880 | 1835640 | 735880 | 873880 | 225880 | 1835640 | 0
7 | Air Conditioning works |  | 3879885 | 3946060 | 3888485 | 11714430 | 3839121 | 2725391 | 4247076 | 10811588 | -902842
8 | MGPS works |  | 1025822 | 1025822 | 1025822 | 3077466 | 1180151.6 | 1141255 | 1046572 | 3367978.6 | 290512.6
9 | Sub Total (Agreement Part-A) (1 to 8) |  | 43854853 | 42405299 | 43811081 | 130071233 | 42257605.6 | 44240940 | 48207041 | 134705586.6 | 4634353.6
10 | PART-B
11 | Equipment supplimental | [5 empty] | 931300 | 221000 | 317600 | 1469900 | 1469900
12 | Civil supplimental works | [5 empty] | 1912429 | 1156237 | 920706 | 3989372 | 3989372
13 | Plumbing supplimental works | [5 empty] | 21690 | 8985 | 8985 | 39660 | 39660
14 | Electrical supplimental works | [5 empty] | 456452.1 | 496686 | 486635 | 1439773.1 | 1439773.1
15 | Fire Fighting Supplimental works | [5 empty] | 291366 |  | 291366 | 582732 | 582732
16 | Air Conditioning supplimental works | [5 empty] | 120788 | 1749744 | 65250 | 1935782 | 1935782
17 | MGPS supplimental works | [5 empty] | 814670 | 814670 | 814670 | 2444010 | 2444010
18 | Water Proofing Works | [7 empty] | 1500000 | 1500000 | 1500000
19 | Sub Total (Supplimental Part-B) (11 to 18) |  | 0 | 0 | 0 | 0 | 4548695.1 | 4447322 | 4405212 | 13401229.1 | 13401229.1
20 | Basic Total (Part-A+Part-B) (19+9) |  | 43854853 | 42405299 | 43811081 | 130071233 | 46806300.7 | 48688262 | 52612253 | 148106815.7 | 18035582.7
21 | Provision towards Engineering Supervision Charges @ 4% on RE Value (on 20) | 4% | 1754194 | 1696212 | 1752443 | 5202849 | 1872252 | 1947530 | 2104490 | 5924272 | 721423
22 | GST @ 18% (on 20) |  | 8209628 | 7632954 | 7885995 | 23728577 | 8762139 | 8763887 | 9470206 | 26996232 | 3267655
23 | Total (Part-A+Part-B) (20 to 22) |  | 53818675 | 51734465 | 53449519 | 159002659 | 57440692 | 59399679 | 64186949 | 181027320 | 22024661
24 | TGMSIDC Mandatory Charges
25 | Labour Cess @ 1% on Basic Price of Revised Estimate (on 20) | 1% |  |  |  |  | 468063 | 486883 | 526123 | 1481069 | 1481069
26 | NAC @ 0.1% on Basic Price of Revised estimate (on 20) | 0.1% |  |  |  |  | 46806 | 48688 | 52612 | 148106 | 148106
27 | Provision towards Seniorage Charges on Civil Component | [5 empty] | 308 | 448 | 1001 | 1757 | 1757
28 | Provision towards DMF Charges 30% on Seniorage Charges (on 27) | 30% |  |  |  |  | 92 | 134 | 300 | 526 | 526
29 | Provision towards SMFT Charges 2% on seniorage Charges (On 27) | 2% |  |  |  |  | 6 | 9 | 20 | 35 | 35
30 | Provision towards Haritha Nidhi (on 20) | 0.01% |  |  |  |  | 4681 | 4869 | 5261 | 14811 | 14811
31 | Sub total of S.No (25 to 30) | [5 empty] | 519956 | 541031 | 585317 | 1646304 | 1646304
32 | Provision towards GST 18% on Above Charges (on 31) | 18% |  |  |  |  | 93592.08 | 97385.58 | 105357.06 | 296334.72 | 296334.72
33 | Provision towards Unforseen items and rounding off (LS) - |  | 1181325 | 3265535 | 1550481 | 5997341 | 0 | 910280 |  | 910280 | -5087061
34 | Sub total of S.No (31 to 33) |  | 1181325 | 3265535 | 1550481 | 5997341 | 613548.08 | 1548696.58 | 690674.06 | 2852918.72 | -3144422.28
35 | Total (34+23) |  | 55000000 | 55000000 | 55000000 | 165000000 | 58054240.08 | 60948375.58 | 64877623.06 | 183880238.72 | 18880238.72
36 | TGMSIDC Mandatory Charges For LS Amount (Rs. 9,10,280) (For PBJ Only) | [10 empty] | Rs. 9,10,280 is inclusive of GST @18%
37 | Labour Cess @ 1% on LS Amount | 1% | [5 empty] | 9103 |  | 9103 | 9103 | For PBJ Only
38 | NAC @ 0.1% on LS Amount | 0.1% | [5 empty] | 910 |  | 910 | 910 | For PBJ Only
39 | Provision towards Haritha Nidhi on LS Amount | 0.01% | [5 empty] | 91 |  | 91 | 91 | For PBJ Only
40 | Provision towards Engineering Supervision Charges @ 4% on LS Amount | 4% | [5 empty] | 36411 |  | 36411 | 36411 | For PBJ Only
41 | Sub Total (37 to 40) |  | 0 | 0 | 0 | 0 | 0 | 46515 | 0 | 46515 | 46515
42 | Total (41+35) |  | 55000000 | 55000000 | 55000000 | 165000000 | 58054240.08 | 60994890.58 | 64877623.06 | 183926753.72 | 18926753.72
43 | PART-C
44 | Interior Works As Per IVF Petlaburj |  |  |  |  | 0 |  |  | 406531 | 406531 | 406531 | For WGL Only
45 | GST @ 18% on 44 |  |  |  |  | 0 | 0 | 0 | 73176 | 73176 | 73176 | For WGL Only
46 | Total (44 to 45) |  | 0 | 0 | 0 | 0 | 0 | 0 | 479707 | 479707 | 479707 | For WGL Only
47 | TGMSIDC Mandatory Charges | [10 empty] | For WGL Only
48 | Labour Cess @ 1% on Part-C (S.No 44) | 1% | [6 empty] | 4065 | 4065 | 4065 | For WGL Only
49 | NAC @ 0.1% on Part-C (S.No 44) | 0.1% | [6 empty] | 407 | 407 | 407 | For WGL Only
50 | Provision towards Haritha Nidhi on Part-C (S.No 44) | 0.01% | [6 empty] | 41 | 41 | 41 | For WGL Only
51 | Provision towards Engineering Supervision Charges @ 4% on Part-C (S.No 44) | 4% | [6 empty] | 16261 | 16261 | 16261 | For WGL Only
52 | Sub Total (48 to 51) |  |  |  |  | 0 | 0 | 0 | 20774 | 20774 | 20774
53 | Provision towards GST 18% on Above Charges (on 52) |  |  |  |  | 0 | 0 | 0 | 3739 | 3739 | 3739
54 | Sub Total (52 to 53) |  |  |  |  | 0 | 0 | 0 | 24513 | 24513 | 24513
55 | Total (PART-C) (54+46) |  |  |  |  | 0 | 0 | 0 | 504220 | 504220 | 504220
56 | Total (Part-A+B+C) (55+35) |  | 55000000 | 55000000 | 55000000 | 165000000 | 58054240.08 | 60948375.58 | 65381843.06 | 184384458.72 | 19384458.72
57 | PART-D
58 | Equipment | [6 empty] | 549100 | 549100 | 1098200 | 1098200 | For PBJ & WGL Only
59 | Furniture | [6 empty] | 143905 | 121385 | 265290 | 265290 | For PBJ & WGL Only
60 | Basic Sub Total (58 to 59) |  |  |  |  | 0 | 0 | 693005 | 670485 | 1363490 | 1363490 | For PBJ & WGL Only
61 | GST @ 18% on 60 |  |  |  |  | 0 | 0 | 124741 | 120687 | 245428 | 245428 | For PBJ & WGL Only
62 | Total (60 to 61) |  |  |  |  | 0 | 0 | 817746 | 791172 | 1608918 | 1608918 | For PBJ & WGL Only
63 | TGMSIDC Mandatory Charges | [10 empty] | For PBJ & WGL Only
64 | Labour Cess @ 1% on Part-D (S.No 60) | 1% |  |  |  |  | 0 | 6930 | 6705 | 13635 | 13635 | For PBJ & WGL Only
65 | NAC @ 0.1% on Part-D (S.No 60) | 0.1% |  |  |  |  | 0 | 693 | 670 | 1363 | 1363 | For PBJ & WGL Only
66 | Provision towards Haritha Nidhi Part-D (S.No 60) | 0.01% |  |  |  |  | 0 | 69 | 67 | 136 | 136 | For PBJ & WGL Only
67 | Provision towards Engineering Supervision Charges @ 4% on Part-D (S.No 60) | 4% |  |  |  |  | 0 | 27720 | 26819 | 54539 | 54539 | For PBJ & WGL Only
68 | Sub Total (64 to 67) |  |  |  |  | 0 | 0 | 35412 | 34261 | 69673 | 69673
69 | Provision towards GST 18% on Above Charges (on 68) |  |  |  |  | 0 | 0 | 6374 | 6167 | 12541 | 12541
70 | Sub Total (68 to 69) |  |  |  |  | 0 | 0 | 41786 | 40428 | 82214 | 82214
71 | Total (PART-D) (70+62) |  |  |  |  | 0 | 0 | 859532 | 831600 | 1691132 | 1691132
72 | Total (PART-A+B+C+D) (71+56) |  | 55000000 | 55000000 | 55000000 | 165000000 | 58054240.08 | 61807907.58 | 66213443.06 | 186075590.72 | 21075590.72
73 | PART-E
74 | Additional Items As Per End User Letter | [6 empty] | 294400 | 525900 | 820300 | 820300 | For PBJ & WGL Only
75 | GST @ 18% on 74 | [5 empty] | 0 | 52992 | 94662 | 147654 | 147654 | For PBJ & WGL Only
76 | Sub Total (74 to 75) |  |  |  |  | 0 | 0 | 347392 | 620562 | 967954 | 967954 | For PBJ & WGL Only
77 | TGMSIDC Mandatory Charges | [10 empty] | For PBJ & WGL Only
78 | Labour Cess @ 1% on Part-E (S.No 74) | 1% |  |  |  |  | 0 | 2944 | 5259 | 8203 | 8203 | For PBJ & WGL Only
79 | NAC @ 0.1% on Part-E (S.No 74) | 0.1% |  |  |  |  | 0 | 294 | 526 | 820 | 820 | For PBJ & WGL Only
80 | Provision towards Haritha Nidhi on Part-E (S.No 74) | 0.01% |  |  |  |  | 0 | 29 | 53 | 82 | 82 | For PBJ & WGL Only
81 | Provision towards Engineering Supervision Charges @ 4% on Part-E (S.No 74) | 4% |  |  |  |  | 0 | 11776 | 21036 | 32812 | 32812 | For PBJ & WGL Only
82 | Sub Total (78 to 81) |  |  |  |  | 0 | 0 | 15043 | 26874 | 41917 | 41917 | For PBJ & WGL Only
83 | Provision towards GST 18% on Above Charges (on 82) |  |  |  |  | 0 | 0 | 2708 | 4837 | 7545 | 7545 | For PBJ & WGL Only
84 | Sub Total (82 to 83) |  |  |  |  | 0 | 0 | 17751 | 31711 | 49462 | 49462
85 | Total (PART-E) (84+76) |  |  |  |  | 0 | 0 | 365143 | 652273 | 1017416 | 1017416
86 | Total (PART-A+B+C+D+E) (85+72) |  | 55000000 | 55000000 | 55000000 | 165000000 | 58054240.08 | 62173050.58 | 66865716.06 | 187093006.72 | 22093006.72
87 | Provision towards (LS) - Inaugration Expenses | [5 empty] | 200000 | 300000 | 300000 | 800000 | 800000
| Grand Total (86 to 87) |  | 55000000 | 55000000 | 55000000 | 165000000 | 58254240.08 | 62473050.58 | 67165716.06 | 187893006.72 | 22893006.72
[6 empty] | As per Admn. Sanction | 165000000
[6 empty] | As per Work done | 187893006.72
[6 empty] | Difference | 22893006.72