## Sheet1
Name of the work: Design, fabrication, establishing & commissioning of In-Vitro Fertility Centers (IVFCs) along with allied services on Turnkey basis at Gandhi Hospital, Secunderabad, MGMH Petlaburj, Hyderabad, and MGM Hospital, Warangal.
Comparative Statement
S.No | Description | As Per WorkDone/To be done |  |  | Totals
|  | IVF Gandhi | IVF Petlaburj | IVF Warangal
1 | Equipment | 25908225 | 26020475 | 26020476
2 | Civil Works | 5612831 | 7012631 | 9771661.15
3 | Plumbing works | 126489 | 136973 | 156101
4 | Electrical works | 4027908 | 5641335 | 5402274.4
5 | ELV works | 827000 | 689000 | 1337000
6 | Fire Fighting works | 735880 | 873880 | 225880
7 | Air Conditioning works | 3839121 | 2725391 | 4247076
8 | MGPS works | 1180151.6 | 1141255 | 1046572
| Sub Total (Agreement Part-A) | 42257605.6 | 44240940 | 48207040.55 | 134705586.15
9 | Equipment supplimental | 931300 | 221000 | 317600
10 | Civil supplimental works | 1912429 | 1156237 | 920706
11 | Plumbing supplimental works | 21690 | 8985 | 8985
12 | Electrical supplimental works | 456452.1 | 496686 | 486635
13 | Fire Fighting supplimental works | 291366 | 0 | 291366
14 | Air Conditioning supplimental works | 120788 | 1749744 | 65250
15 | MGPS supplimental works | 814670 | 814670 | 814670
16 | Water Proofing Works | 0 | 0 | 1500000
| Sub Total (Supplimental Part-B) | 4548695.1 | 4447322 | 4405212 | 13401229.1
| Total (Part-A+Part-B) | 46806300.7 | 48688262 | 52612252.55 | 148106815.25
17 | Provision towards Engineering Supervision Charges @ 4% on RE Value | 1872252 | 1947530 | 2104490
| GST @ 18% | 8762139 | 8763887 | 9470205
| Total | 57440691.7 | 59399679 | 64186947.55 | 181027318.25
18 | Labour Cess @ 1% on Basic Price of Revised Estimate | 468063 | 486883 | 526123
19 | NAC @ 0.1% on Basic Price of Revised estimate | 46806 | 48688 | 52612
20 | Provision towards Seniorage Charges on Civil Component | 308 | 448 | 1001
21 | Provision towards DMF Charges 30% on Seniorage Charges | 92 | 134 | 300
22 | Provision towards SMFT Charges 2% on seniorage Charges | 6 | 9 | 20
23 | Provision towards Haritha Nidhi | 4681 | 4869 | 5261
| Sub total of S.No 17 to 22 | 519956 | 541031 | 585317
24 | Provision towards GST 18% on Seniorage Charges | 93592 | 97386 | 105357
25 | Provision towards Unforseen items and rounding off (LS) - | 0 | 910280 | 0
| Sub total of S.No 23 to 25 | 613548 | 1548697 | 690674
| Total | 58054239.7 | 60948376 | 64877621.55 | 183880237.25
26 | TSMSIDC Charges, NAC & Labour Cess @ 5.1% (on S.No 25) | 0 | 46424.28 | 0
27 | New Additional Items As Per IVF Gandhi | 0 | 859451 | 1163790 | 2023241
28 | Extra Items as per Enduser Letter | 0 | 365109 | 652211 | 1017320
29 | Provision towards (LS) - Inaugration Expenses | 200000 | 300000 | 300000 | 800000
| Sub Total (26 to 29) | 200000 | 1570984.28 | 2116001 | 3886985.28
| Grand Total | 58254239.7 | 62519360.28 | 66993622.55 | 187767222.53
| As Per Agreement | 55000000 | 55000000 | 55000000 | 165000000
| As Per Workdone | 58254239.7 | 62519360.28 | 66993622.55 | 187767222.53
| Excess | 3254239.7 | 7519360.28 | 11993622.55 | 22767222.53
| Total Agreement Value | 165000000
| Total Workdone Value | 187767222.53
| Total Excess | 22767222.53