## LumpSumItems
S.No | Item Description | UOM | Qty | Rate (Rs.) | Amount (Rs.)
1 | Powder coated GI stand in IVF OT | Nos | 1 | 80000 | 80000
2 | High Quality IVF Procedural photos at Entrance and Reception | Nos | 12 | 9000 | 108000
3 | 60mm Thick Box framing as the back support for the name plate at Entrance | Sqm | 3.98 | 11012 | 43828
4 | Door Frame side Paneling at Entrance | Sqm | 7.551 | 9250 | 69847
5 | 32mm Double Flush Door (1800 x 2100 mm door) at Entrance | Nos | 1 | 56500 | 56500
6 | Name Plate With Glossy Laminate at Entrance | Sqm | 2.6 | 9580 | 24908
7 | MIRROR GOLD TITANIUM LETTERS & S.S. MIRROR LETTERS at Entrance | Job | 1 | 67500 | 67500
8 | Double side ACP sheet (Name board wth three languages fixed at IVF Entrance Corridor) | Nos | 1 | 6000 | 6000
9 | Foam Board (Name board wth three languages with direction to IVF Center fixed at 3rd floor) | Nos | 2 | 2800 | 5600
10 | Foam Board (Name board wth with direction to Rooms fixed to wall in IVF Corridor,) | Nos | 2 | 3200 | 6400
11 | Main IVF logo with LED arcylic board at Entrance | Nos | 1 | 11475 | 11475
12 | Addressable fire control panel at Entrance | Nos | 1 | 291366 | 291366
|  |  |  | TOTAL | 771424
|  |  |  | GST @ 18% | 138856.32
|  |  |  | Total Amount can be claimed including GST | 910280.32

## Additionaal_Items
S.No | Item Description | QTY | UOM | Rate (Rs.) | Amount (Rs.) | Remarks
1 | Fowler Two Function Bed with ABS Panel in Pre and Post Operative wards and Semen Collection room | 5 | Nos | 39000 | 195000 | As Per IVF Gandhi
2 | Bed side Table with ABS Plastic body in Pre and Post Operative wards and Semen Collection room | 5 | Nos | 9000 | 45000 | As Per IVF Gandhi
3 | Corporate Deluxe Locker with SS 304 grade Top in Sample Collection and Injection Room | 1 | Nos | 8400 | 8400 | As Per IVF Gandhi
4 | Bed side stand with full SS 304 grade constructionof in C | 1 | Nos | 9300 | 9300 | As Per IVF Gandhi
5 | Bed side stand with full GI Powder coated constructionof in Semen Collection room | 1 | Nos | 4200 | 4200 | As Per IVF Gandhi
6 | Supply of a Sample collection chair in Sample Collection and Injection Room | 1 | Nos | 16200 | 16200 | As Per IVF Gandhi
7 | Sample collection bed in Sample Collection and Injection Room | 1 | Nos | 29000 | 29000 | As Per IVF Gandhi
8 | Cryo Can 11 Ltr without wheels in Cryo room | 1 | Nos | 32000 | 32000 | As Per IVF Gandhi
9 | Writing board in Counselling rooms | 1 | Nos | 2100 | 2100 | As Per IVF Gandhi
10 | MDF wooden table in Reception and Ultrasound room | 2 | Nos | 14500 | 29000 | As Per IVF Gandhi
11 | The Multipurpose Electro Hydraulic Mobile OT Table in Major OT | 1 | Nos | 210000 | 210000 | As Per IVF Gandhi
12 | Office table in Embryologist and Anesthetist room | 2 | Nos | 16000 | 32000 | As Per IVF Gandhi
13 | Window blinds (For semen collection room & Counselling room Windows) | 15 | Sqm | 2187 | 32805 | As Per IVF Gandhi
14 | Sofa | 2 | Nos | 24000 | 48000 | As Per IVF Gandhi
|  |  |  | Sub Total | 693005
|  |  |  | GST | 124740.9
|  |  |  | Sub Total | 817745.9
|  |  |  | TSMSIDC Charges, NAC & Labour Cess @ 5.1% | 41705.0409
|  |  |  | Grand Total | 859450.9409
Extra Items As Per Doctors Letter
1 | Consultant Chair in Embryologist and Anesthetist room | 3 | Nos | 20000 | 60000 | Extra Items
2 | Patient Chair Embryologist and Anesthetist room | 6 | Nos | 13500 | 81000 | Extra Items
3 | Lab Chairs Type I (DCA Price) in Andrology Lab & Embryology Lab | 10 | Nos | 15340 | 153400 | Extra Items
|  |  |  | Sub Total | 294400
|  |  |  | GST | 52992
|  |  |  | Sub Total | 347392
|  |  |  | TSMSIDC Charges, NAC & Labour Cess @ 5.1% | 17716.992
|  |  |  | Grand Total | 365108.992

## PBJ_Abstract
Name of the work: Design, fabrication, establishing & commissioning of In-Vitro Fertility Centers (IVFCs) along with allied services on Turnkey basis at Gandhi Hospital, Secunderabad, MGM Hospital, Warangal & MGMH Petlaburj, Hyd.
COMPARATIVE STATEMENT
S.No | Description |  | As per Agreement | As per workdone | Excess | Less | Net Difference
1 | Equipment |  | 26020475 | 26020475 | 0 | 0
2 | Civil Works |  | 5915529 | 7012631 | 1910379 | 813277
3 | Plumbing works |  | 215122 | 136973 | 7086 | 85235
4 | Electrical works |  | 3719411 | 5641335 | 2169638 | 247714
5 | ELV works |  | 689000 | 689000 | 0 | 0
6 | Fire Fighting works |  | 873880 | 873880 | 0 | 0
7 | Air Conditioning works |  | 3946060 | 2725391 | 374548 | 1595217
8 | MGPS works |  | 1025822 | 1141255 | 143424 | 27991
| Sub Total (Agreement Part-A) |  | 42405299 | 44240940 | 4605075 | 2769434
9 | Equipment supplimental |  | 0 | 221000 | 221000 | 0
10 | Civil supplimental works |  | 0 | 1156237 | 1156237 | 0
11 | Plumbing supplimental works |  | 0 | 8985 | 8985 | 0
12 | Electrical supplimental works |  | 0 | 496686 | 496686 | 0
14 | Air Conditioning supplimental works |  | 0 | 1749744 | 1749744 | 0
15 | MGPS supplimental works |  | 0 | 814670 | 814670 | 0
| Sub Total (Supplimental Part-B) |  | 0 | 4447322 | 4447322 | 0
| Total (Part-A+Part-B) |  | 42405299 | 48688262 | 9052397 | 2769434 | 6282963
16 | Provision towards Engineering Supervision Charges @ 4% on RE Value | 4% | 1696212 | 1947530 | 251318 | 0
| GST @ 18% |  | 7632953.82 | 8763887.16 | 1130933 | 0
|  |  | 51734465 | 59399679.16 | 10434648 | 2769434
17 | Labour Cess @ 1% on Basic Price of Revised Estimate | 1% |  | 486882.62 | 486883 | 0
18 | NAC @ 0.1% on Basic Price of Revised estimate | 0.1% |  | 48688.262 | 48688 | 0
19 | Provision towards Seniorage Charges on Civil Component |  |  | 448 | 448 | 0
20 | Provision towards DMF Charges 30% on Seniorage Charges | 30% |  | 134.4 | 134 | 0
21 | Provision towards SMFT Charges 2% on seniorage Charges | 2% |  | 8.96 | 9 | 0
22 | Provision towards Haritha Nidhi | 0.01% |  | 4868.8262 | 4869 | 0
23 | Sub total of S.No 17 to 22 |  |  | 541031 | 541031 | 0
24 | Provision towards GST 18% on Seniorage Charges | 18% |  | 97385.58 | 97386 | 0
25 | Provision towards Unforseen items and rounding off (LS) - |  | 3265535 | 910280 | 0 | 2355255
| Sub total of S.No 23 to 25 |  |  | 1548696.58 | 638417 | 2355255
|  |  | 55000000 | 60948375.74 | 11073065 | 5124689
26 | TSMSIDC Charges, NAC & Labour Cess @ 5.1% |  |  | 46424.28 | 46424 | 0
27 | New Additional Items As Per IVF Gandhi |  |  | 859451 | 859451 | 0
28 | Extra Items as per Enduser Letter |  |  | 365109 | 365109 | 0
| Sub Total (26 to 28) |  |  | 1270984.28 | 1270984 | 0
|  |  |  | 62219360.02 | 12344049 | 5124689
| As per Admn. Sanction |  |  | 55000000 | Excess | 12344049
| As per Work done |  |  | 62219360.02 | Less | 5124689
| Difference |  |  | 7219360.02 | Difference | 7219360