## Sheet1
Petlaburj ELV Work Schedule
| Description of Work | Start Date | Finish Date | Amount Required
Phase 1 | Fire Cabling | 2024-01-29 | 2024-02-03 | 250000
Fire Detectors (ASD)
LAN/Telephone/Access Control/CCTV
Phase 2 | Below Surface/Ceiling Detectors (BSD) | 3 days required after False Ceiling done |  | 250000
Network Panel
Telephone Panel
Phase 3 | Fire Panel | 4 days required after Painting work done |  | 250000
Cameras
Exit button for Acces Control
Patch Panel
Telephone
LAN
Phase 4 | NVR | 10 days |  | 335000
Wall Mics
Fire Extinguisher
Cleaning Agent
|  | Total Amount Required |  | 1085000