## Table 1
PETLABRUJ Work Progress
| S. No | DESCRIPTION |  |  | Quotations | PO | Delivery | Work Progress |  |  |  | Billing
[8 empty] | 25% | 50% | 75% | completed
MGMH Petlaburj Hospital
Equipment | 199 | Ovum Aspiration Pumps at Petlaburj Hospital | 2 | No
| 200 | IVF Test tube Warmers at Petlaburj Hospital | 2 | No
| 201 | DICOM compatible fully digital, compact, portable, Ultrasound Scan Machine Colour Doppler at Petlaburj Hospital | 2 | No
| 202 | Multipurpose Electro hydraulic with manual override mobile OT Table, with divided leg section suitable for all Gynaecological surgical procedures, complete with 5cm Mattress and corded handset at Petlaburj Hospital | 1 | No
| 203 | LED procedure Lights Double dome at Petlaburj Hospital | 1 | No
| 204 | LED procedure Lights Single dome at Petlaburj Hospital | 1 | No
| 205 | IVF Workstation with LAF at Petlaburj Hospital | 1 | No
| 206 | IVF Ant vibration Table for procedure at Petlaburj Hospital | 1 | No
| 207 | CO2 Incubators at Petlaburj Hospital | 2 | No
| 208 | Trigas bench Top Incubators for Human Embryo culture at Petlaburj Hospital | 1 | No
| 209 | Trinocular Stereozoom Microscope at Petlaburj Hospital | 1 | No
| 210 | ICSI Micro manipulator with Inverted Microscope at Petlaburj Hospital | 1 | No
| 211 | IVF Laser System at Petlaburj Hospital | 1 | No
| 212 | IVF Thermometer at Petlaburj Hospital | 1 | No
| 213 | CO2 Cylinder and Manifold at Petlaburj Hospital | 2 | No
| 214 | CO2 and O2 Analyzer at Petlaburj Hospital | 1 | No
| 215 | PH Meter at Petlaburj Hospital | 1 | No
| 216 | VOC Meter for ART Lab at Petlaburj Hospital | 1 | No
| 217 | Sperm Counting Makler Chamber at Petlaburj Hospital | 1 | No
| 218 | Binocular Microscope for Semen Analysis at Petlaburj Hospital | 1 | No
| 219 | Laminar flow cabinet with Andrology Work station at Petlaburj Hospital | 1 | No
| 220 | Clinical Centrifuge machine for Andrology at Petlaburj Hospital | 1 | No
| 221 | Dry Incubators at Petlaburj Hospital | 1 | No
| 222 | Pipetter and Denudation system at Petlaburj Hospital | 1 | No
| 223 | Pharmaceutical Refrigerator at Petlaburj Hospital | 1 | No
| 224 | Cryocans with wheels at Petlaburj Hospital | 2 | No
| 225 | Defibrillator at Petlaburj Hospital | 1 | No
| 226 | 7 Para Patient Monitor at Petlaburj Hospital | 2 | No
| 227 | Suction machine at Petlaburj Hospital | 1 | No
| 228 | Anaesthesia Work station at Petlaburj Hospital | 1 | No
| 229 | Autoclave at Petlaburj Hospital | 1 | No
| 230 | Operative Hysteroscopy and Resectoscope Set Machine at Petlaburj Hospital | 1 | No
| 231 | Operative Laparoscopy Set at Petlaburj Hospital | 1 | No
| 232 | Multifunctional Printer at Petlaburj Hospital | 1 | No
| 233 | Ultrasound Examination Couch at Petlaburj Hospital | 1 | No
| 234 | UPS 20KVA with battery backup at Petlaburj Hospital | 1 | No
| 235 | Laptop for Office usage at Petlaburj Hospital | 2 | No
| 236 | Reception Table at Petlaburj Hospital | 1 | No
| 237 | Reception chair at Petlaburj Hospital | 2 | No
| 238 | Filing Cabinet at Petlaburj Hospital | 2 | No
| 239 | Patient Seating 3 in 1 model at Petlaburj Hospital | 3 | No
| 240 | Consultant Chair at Petlaburj Hospital | 3 | No
| 241 | Patient Chair at Petlaburj Hospital | 6 | No
| 242 | Small Trolley at Petlaburj Hospital | 3 | No
| 243 | Big Trolley at Petlaburj Hospital | 3 | No
| 244 | Wall Storage Cabinets at Petlaburj Hospital | 8 | No
| 245 | Office Table at Petlaburj Hospital | 3 | No
| 246 | Consumables and Media for 100 Cycles at Petlaburj Hospital | 1 | Lot
CIVIL BALAJI | 247 | Dismantling Brick Masonry | 80 | Cum
| 248 | Dismantling clearing complete for Flooring | 400 | Sqm
| 249 | Dismantling doors, : Doors 1.00x2.60M | 16 | No | [5 empty] | 90%
| 250 | Dismantling doors, Doors1.50x2.60M | 5 | No
| 251 | Conveyance of Dismantled Brick masonry and existing flooring. | 120 | Cum
CIVIL SANDEEP | 252 | Brick masonry for panel walls width=230 mm | 10.5 | Cum
| 253 | Reinforced Masonry for partition walls 100 mm thick | 215 | Sqm
| 254 | Providing Mild steel MS steel bars Fe 250 For RBM walls 6mm dia | 0.9 | MT
| 255 | Plastering 20mm thick | 45 | Sqm
| 256 | Plastering 12mm thick in two coats | 430 | Sqm
| 257 | Providing and laying screed plain cement concrete | 20 | Sqm
| 263 | Flooring with soluble salt porcelain vitrified tiles | 360 | Sqm
| 264 | Flooring with non-skid full body ceramic floor tiles | 12 | Sqm
| 265 | Providing and fixing- Mineral Fiber sheet | 300 | Sqm
| 266 | Providing dadooing to walls with glazed full body porcelain wall tiles | 30 | Sqm
| 267 | Providing and applying Wall putty | 975 | Sqm
| 268 | Painting to new wood work and flush shutters | 80 | Sqm
| 269 | Supply and application of one coat water based cement primer | 975 | Sqm
| 270 | Painting to old walls with 2 coats of water proof cement paint | 100 | Sqm
| 290 | Providing, laying of scratch proof PVC/Vinyl flooring of 2mm | 140 | Sqm
NCL ABS DOORS | 258 | Supply and fixing powder coated aluminium fully glazed swing door | 5 | Sqm
| 259 | Supplying and fixing of UPVC 3 track sliding windows | 15 | Sqm | [5 empty] | 2 windows left
| 260 | Providing, supplying and fixing of Fixed Louvered Ventilator | 5 | Sqm
| 261 | Supply and fixing doors with medium teak wood 1000mm x 2100mm j | 35 | Sqm
| 262 | Supply and fixingdoors with medium teak wood 750mm x 2100mm | 10 | Sqm
| ADD | NCL ABS Doors |  | Sqm
PLUMBING | 272 | Supply and fixing CPVC Pipes 15.90mm OD pipe | 60 | Rmt
| 273 | Supply and fixing of CPVC Pipes 22.20mm OD pipe | 60 | Rmt
| 274 | Supplying and fixing of SWR PVC pipes - 75mm dia | 90 | Rmt
| 275 | Supplying and fixing of SWR PVC pipes - 110mm dia | 75 | Rmt
| 276 | Supplying and fixing Bronze Gate/ Globe valve 25mm Nominal bore | 6 | No
| 277 | Supplying and fixing of 4inches 101.6mm multi floor trap with jali - | 6 | No
SANITARY & CP FITTINGS | 271 | Supplying and fixing 15 mm brass body CP finish bib tap | 2 | No
| 278 | Supplying and fixing Indian make Flat Back Wash Hand Basin | 6 | No
| 279 | Supply, Installation of floor mounted Anglo Indian wash down EWC | 6 | No
| 280 | Supplying and fixing turn Bibcock cum Health Faucet | 6 | No
| 281 | Supplying and fixing CP finish brass soap dish | 6 | No
| 282 | Supplying and fixing TV shape mirror | 6 | No
| 283 | Supplying and fixing of CP finish brass wall mounted towel ring | 6 | No
| 284 | Supplying and fixing 15 mm brass body CP finish self closing tap | 6 | No
AHLADHA | 285 | Supply and installation of 80mm thick double skin modular wall Panel | 125 | sqm
| 286 | Supply and installation of 50mm thick double skin ceiling panel | 60 | sqm
| 287 | Double leaf clean room Doors : . Size 1500 X 2100 mm | 4 | No
| 288 | Single leaf clean room Doors : Size 900 X 2100 mm | 2 | No
| 289 | Supply and installation of Extruded Aluminium Coving at MGMH Petlaburj | 100 | Rmt
| 291 | Supply, installation, single person entry air shower | 1 | No
| 292 | Supply, installation, Testing and Commissioning of Static Pass Boxes | 3 | No
ELECTRICAL | 293 | Supply and laying of ISI 25mm outer dia rigid PVC pipe concealed in wall | 200 | Rmt
| 294 | Supply and laying of ISI 25mm outer dia rigid PVC pipe surface on wall | 450 | Rmt
| 295 | Wiring with 2 runs of 22/0.3mm 1.5 Sq.mm | 100 | Pts
| 296 | Supply and fixing of 6A ISI Mark 3/2 pin Modular socket with 6A 1way Modular switch, 3 Module box | 12 | No
| 297 | Supply and fixing of 16A switches - 1Nos and 6/16A 2 in one socket - 1Nos Modular type | 40 | No
| 298 | Supply and fixing of 16A/6A, 2 in one socket - 2 Nos with 16A switch control - 2 Nos modular type | 60 | No
| 299 | Supply and fixing of 16A/6A, 2 in one socket - 4 Nos with 16A switch control - 4 Nos modular type | 10 | No
| 300 | Supply and run of 1 of 22 /0.3mm 1.5 Sq.mm | 350 | Rmt
| 301 | Supply and run of 3 of 2.5 sq.mm 36/0.mm phase neutral and earth | 600 | Rmt
| 302 | Supply and 3 runs of 4.0 sq mm 56/0.3 mm phase neutral and earth | 1200 | Rmt
| 303 | Supply and run of 5 of 6.0 Sqmm 90/0.3 mm 3 phases, neutral | 60 | Rmt
| 304 | Supply and run of 5 of 10.0 Sqmm 140/0.3 mm 3 phases, neutral and earth | 40 | Rmt
| 305 | Supply and fixing of DP Metal Enclosure with IP 20 Protection DB Make | 5 | No
| 306 | Supply and fixing of 4 Way TPN DB Horizontal with IP 43 Protection | 3 | No
| 307 | Supply and fixing of 8 Way TPN DB Horizontal with IP 43 Protection | 2 | No
| 308 | Supply and fixing of 8 Way VTPN DB Horizontal with IP 43 Protection | 1 | No
| 309 | Providing and fixing of 125A 25KA TPN Thermal Magnetic Release MCCB | 1 | No
| 310 | Providing and fixing of 100A 10KA FP MCB and Terminal Spreaders | 2 | No
| 311 | Supply, transportation and fixing of 24W edge lit LED Down light Square | 50 | No
| 312 | Supply and Transportation 36W Edge lit, 2 feet x2 feet | 30 | No
| 313 | Supply and Transportation 42W Clean room Light fixture, | 12 | No
| 314 | Supply and fixing of ISI mark batten holder / slanting holder | 5 | No
| 315 | Supply, Transportation of energy efficient fan, 1200 mm sweep, | 12 | No
| 316 | Supply and fixing of Modular type Stepped electronic regulator for sweep AC ceiling fans of 1200mm / 1400mm | 12 | No
| 317 | Supply and installation of 225mm Light duty exhaust fan | 6 | No
| 318 | SITC of Hot dip galvanized perforated cable tray of 100 mm Wide | 70 | Rmt
| 319 | SITC of Hot dip galvanized perforated cable tray of 300 mm Wide | 80 | Rmt
| 323 | Providing and Fixing maintenance free earthing which consists of G.I. Earth station, with 600X600X3.15mm GI Plate | 2 | No
| 324 | Providing and Fixing maintenance free earthing which consists of copper. Earth station, with 600X600X3.15mm Copper Plate | 2 | No
| 325 | Supply and installation of 50x6 GI flat for body earthing of electrical,AC panel | 200 | Rmt
| 326 | Supply and installation of 25x3 GI flat for body earthing of DBs a | 100 | Rmt
| 327 | Supply and installation of 25x3 Copper flat for Neutral earthing of UPS and Equipment which is laid in 100mm cable tray at MGMH Petlaburj | 200 | Rmt
| 328 | Supply and installation of 4 sqmm Copper wire for Earthing of DBs | 80 | Rmt
| 329 | Supply, Lying and testing of 3.5Cx95 sqmm XLPE Insulated Cable 1100V | 120 | Rmt
| 330 | Supply, Lying and testing of 3.5CX50 sqmm XLPE Insulated Cable 1100V | 70 | Rmt
| 331 | Supply, Lying and testing of 4Cx16 sqmm PVC Insulated Cable | 100 | Rmt
| 332 | Supply, Lying and testing of 4Cx6 sqmm PVC Insulated Cable 1100V grade | 120 | Rmt
| 333 | Supply, Lying and testing of 4Cx4 sqmm PVC Insulated Cable 1100V grade | 80 | Rmt
| 334 | SITC of IVF Center Main Panel Indoor IP-42 wall for lighting,power DBs | 1 | No
| 335 | SITC of IVF center AC Panel outdoor IP-54 wall AHU’s stater with VFD by pass, Heater, ODU and VRF system | 1 | No
| 336 | Supply and installation of AHUs stater on/off push button station for Remote | 3 | No
UPS APS TECH | 320 | Supply and installation of 20KVA 3ph in and 3ph out on line UPS system | 1 | No
| 321 | Supply and fixing of 12V 65 AH SMF battery including wire leads. | 20 | No
| 322 | Supply and providing of UPS cum battery rack for 20 batteries | 1 | No
ELV | 337 | Supply, installation, testing and commissioning of 20nos LAN points | 1 | Job
| 338 | Supply, installation 1 no of Access control system | 1 | Job
| 339 | Supply, installation, of Automatic Fire Alarm System | 1 | Job
| 340 | Supply, installation, of 5nos IP Based CCTV cameras | 1 | Job
| 341 | Supply, installation of Audio and video recording of counseling rooms | 1 | Job
| 342 | Supply and installation of Fire Extinguishers of CO2 4.50 Kg | 5 | No
| 343 | Supply and installation of ceiling mounted Fire Extinguishers of ABC | 5 | No
| 344 | Supply and installation of 2.0 Kg clean agent HCFC 123 Fire Extinguishers | 5 | No
| 345 | Supply and fixing of Fire escape signage Boards at MGMH Petlaburj | 1 | Job
HVAC | 348 | Modular Double skin floor mounted EUROVENT Certified AHU | 1 | No
| 349 | SITC of filter module | 6 | No
| 350 | SITC of air cooled condensing units | 1 | No
| 351 | SITC of Flange type, Flame proof FLP duct heaters of 5 kW capacity | 1 | No
| 352 | SITC of 20/21 G hard drawn copper refrigerant piping . Liquid Line | 20 | Rmt
| 353 | SITC of 20/21 G hard drawn copper refrigerant piping . Suction Line | 20 | Rmt
| 354 | SITC of CPVC drain ping 32mm Dia | 50 | Rmt
| 355 | SITC of CPVC drain ping 25mm Dia | 50 | Rmt
| 356 | SITC of Factory fabricated and boxed ducting 20G - 1.0 mm Thick | 30 | Sqm
| 357 | SITC of Factory fabricated and boxed ducting 22G - 0.8 mm Thick | 250 | Sqm
| 358 | Aluminium low leakage aerofoil design volume control dampers | 2 | Sqm
| 359 | CBRI approved 16G GI Spring return actuated fire dampers | 2 | Sqm
| 360 | SITC of SS perforated return raiser grilles with 10 microns filters | 2 | Sqm
| 361 | Extruded Al. powder coated EXHAUST / RETURN discrete grilles | 1 | Sqm
| 362 | SITC of Collar Dampers made of Al. extrusions | 1 | Sqm
| 363 | SITC of Magnehelic gauges across pre and fine filter | 2 | No
| 364 | SITC of Magnehelic gauges to measure the room differential pressures | 2 | No
| 365 | SITC of Aluminium powder coated Fresh air and Exhaust Louvers | 1 | Sqm
| 366 | Supply, laying of Class O Nitrile rubber 32mm Thick | 130 | Sqm
| 367 | Supply, laying of Class O Nitrile rubber 25mm Thick for Exposed | 130 | Sqm
| 368 | Supply, laying of Class O Nitrile rubber 25mm Thick for Supply air duct | 40 | Sqm
| 369 | Supply, laying of Class O Nitrile rubber 19mm Thick for Return air | 40 | Sqm
VRV | 346 | Supply, transportation and installation of split AC unit 1.5 TR | 1 | No
| 347 | Supply, transportation and installation of split AC unit 1.0 TR | 1 | No
| 370 | Condensing units - VRF/VRV System : 16 HP | 1 | Set
| 371 | VRF Indoor Units : Hi wall Splits : 0.8 TR | 2 | No
| 372 | VRF Indoor Units : Hi wall Splits : 1.0 TR | 3 | No
| 373 | VRF Indoor Units : Hi wall Splits : . 1.5 TR | 4 | No
| 374 | Cassette Units : 3.0 TR – 4 way | 2 | No
| 375 | Supply, Installation, Hard copper REFRIGERANT PIPING o | 1 | Lot
| 376 | Supply, Installation , Testing and Commissioning of Refnet joints | 10 | Set
| 377 | Supply and Installation of control cum transmission wiring of size 3C x 1.5 | 150 | Rmt
| 378 | Supply and Installation of cabling of size 2C x 1 Sqmm copper wire to be | 100 | Rmt
MGPS | 379 | SITC of Oxygen Manifold Emergency for 1 plus 1 Cylinders, | 1 | Set
| 380 | SITC of Oxygen Outlets with matching probes, | 4 | each
| 381 | SITC of Oxygen Flowmeter with Humidifier, | 4 | each
| 382 | SITC of Nitrous Oxide Manifold Emergency for 1 Cylinder, | 1 | Set
| 383 | SITC of N20 Outlets with matching probes, | 4 | each
| 384 | SITC of C02 Manifold for 2 Cylinders, | 1 | Set
| 385 | SITC of C02 Outlets with matching probes, | 4 | each
| 386 | SITC of MEDICAL Grade BS EN: 13348 Kite Marked 12mm COPPER | 24 | Rmt
| 387 | SITC of MEDICAL Grade BS EN: 13348 Kite Marked 15mm COPPER | 114 | Rmt
| 388 | SITC of MEDICAL Grade BS EN: 13348 Kite Marked 22mm COPPER | 36 | Rmt
| 389 | SITC of MEDICAL Grade BS EN: 13348 Kite Marked 28mm COPPER | 18 | Rmt
| 390 | SITC of Touch type LCD Area Alarm and Zonal Valve box | 1 | each
| 391 | SITC of Touch type LCD Area Alarm and Zonal Valve box | 1 | each
| 392 | SITC of Medical Line Valve, 15mm 0D | 3 | each
| 393 | SITC of Medical Line Valve, 22mm 0D | 3 | each
| 394 | SITC of Medical Line Valve, 28mm 0D | 4 | each
| 395 | SITC of Bed Head Panel | 2 | each