## Measurements
DETAILED MEASUREMENTS
| Name of the work:Design, Fabriction, establishing and commissioning of In - Vitro ferility centers (IVFC) alongwith allied Services on Turnkey basis at Gandhi hospital secunderabad. | [8 empty] | Agency: M/s. Asta Sudha Consortium | [5 empty] | Agt.No:
Date Of Measurement | Discription Of Work etc., | Measurements Upto date | [5 empty] | Rate |  |  | Per | Total Volume |  | Deduct/previous Measurements |  | Since last measurement |  |  | Remarks
|  | No |  | L | B | D | Content | Units | Rs | Ps. |  | Rs. | Ps | P.No. | Qty. | Qty | Value
[17 empty] | Rs. | Ps.
Dismantling, clearing away and carefully stacking useful materials for re-use and disposal of unserviceable materials with 100m lead as directed by Executive Engineer duly taking actual premeasurements before dismantling including all labour charges , overheads & contractor profit etc., complete (Brick Masonary)
` | Step Down Room main Door | 1 | 1 | 1.7 | 0.23 | 3.05 | 1.1925
| Reception plat form | 1 | 4 | 1.72 | 0.15 | 0.92 | 0.94944
| do | 1 | 4 | 1.4 | 0.15 | 0.92 | 0.7728
| do | 1 | 4 | 0.6 | 0.15 | 0.92 | 0.3312
| Prepost Operative Room Partition Wall | 1 | 1 | 6.6 | 0.23 | 3.05 | 4.6299
| Toilet Walls | 1 | 1 | 3 | 0.15 | 3.45 | 1.5525
| Door Deduction(-) | -1 | 1 | 0.8 | 0.15 | 2.1 | -0.252
| Toilet Wall | 1 | 1 | 0.8 | 0.15 | 2.1 | 0.252
| Main Door Entry | 1 | 1 | 1.75 | 0.23 | 2.6 | 1.0465
| Door Deduction(-) | 1 | 1 | 1.5 | 0.23 | 2.6 | 0.897
| Auto Clave Room Partition Wall | 1 | 1 | 2.2 | 0.15 | 3.45 | 1.1385
| Counseling Room Partition Wall | 1 | 1 | 2.4 | 0.15 | 3.45 | 1.242
| Counseling Rooms Door Opening | 1 | 2 | 1.1 | 0.15 | 2.3 | 0.759
| Door Deduction(-) | -1 | 2 | 0.8 | 0.15 | 2.3 | -0.552
| Autoclave Room And Ultra Sound Room Door Opening | 1 | 2 | 1.2 | 0.15 | 2.3 | 0.828
| Door Deduction(-) | -1 | 2 | 0.8 | 0.15 | 2.3 | -0.552
| Doctors Room Main Door Entry | 1 | 1 | 1.4 | 0.23 | 3 | 0.966
| Counseling Room To Store Room Door Opening | 1 | 1 | 1.5 | 0.23 | 2.6 | 0.897
| Andrology Toilet Wall | 1 | 1 | 1.8 | 0.15 | 3.45 | 0.9315
| do | 1 | 1 | 3 | 0.15 | 3.45 | 1.5525
| do | 1 | 1 | 1.8 | 0.15 | 3.45 | 0.9315
| Door Deduction(-) | -1 | 2 | 0.8 | 0.15 | 2.1 | -0.504
| Andrology Room Door Entry Wall | 1 | 1 | 5.2 | 0.23 | 3 | 3.588
| Door Deduction(-) | -1 | 1 | 1.5 | 0.23 | 2.6 | -0.897
| Majot OT -1 Toilet Wall | 1 | 1 | 1.8 | 0.15 | 3.45 | 0.9315
| do | 1 | 1 | 3 | 0.15 | 3.45 | 1.5525
| Partition Wall | 1 | 1 | 1.8 | 0.15 | 3.45 | 0.9315
| Door Deduction(-) | -1 | 2 | 0.8 | 0.15 | 2.1 | -0.504
| Embrology Lab Main Door | 1 | 1 | 1.5 | 0.23 | 3 | 1.035
| Partition Walls | 1 | 1 | 4.3 | 0.15 | 3.45 | 2.2252
| do | 1 | 1 | 3 | 0.15 | 3.45 | 1.5525
| Entry Door | 1 | 1 | 1.8 | 0.23 | 3 | 1.242
| Selves Walls | 1 | 3 | 0.6 | 0.15 | 2 | 0.54
|  | Total |  |  |  |  | 31.2071 | Cum
Dismantling doors, windows and clear storey windows, Ventilators etc., (wood or steel) shutters including Chowkhats, architraves,hold fasts and other attachments etc., and stacking them within 100m lead including labour charge etc., and overheads & contractors profit complete for finished item of work.
| Prepost Operative Room Door | 1 | 2 |  |  |  | 2
| Access Control Door | 1 | 1 |  |  |  | 1
| Embrology Lab Main Door | 1 | 1 |  |  |  | 1
| Windows | 1 | 3 |  |  |  | 3
[7 empty] | 7 | No's
Dismantling, clearing away and carefully stacking useful materials for re-use and disposal of unserviceable materials with 100m lead as directed by Executive Engineer duly taking actual premeasurements before dismantling including all labour charges , overheads & contractor profit etc., complete (Unreinforcement Cement More Than 15cm Thick)
| Prepost operative toilet area | 1 | 1 | 1.8 | 1.2 | 0.3 | 0.648
| Andrology Lab Toilet area | 1 | 1 | 1.8 | 3 | 0.3 | 1.62
| Mojar OT-1 Toilet Area | 1 | 1 | 1.8 | 3 | 0.3 | 1.62
|  | Total |  |  |  |  | 3.888 | Cum
Dismantling, clearing away and carefully stacking useful materials for re-use and disposal of unserviceable materials with 100m lead as directed by Executive Engineer duly taking actual premeasurements before dismantling including all labour charges , overheads & contractor profit etc., complete(Old Cement Mortor Plaster)
| Toilet Inside Prepost Operative Room | 1 | 1 | 3 |  | 1.5 | 4.5
| do | 1 | 1 | 0.8 |  | 1.5 | 1.2
| Andrlogy Lab Toilet Wall | 1 | 1 | 1.8 |  | 1.5 | 2.7
| do | 1 | 1 | 3 |  | 1.5 | 4.5
| do | 1 | 1 | 1.8 |  | 1.5 | 2.7
| Andrology lab Partition wall | 1 | 1 | 5.2 |  | 1.5 | 7.8
| Door Deduction(-) | -1 | 1 | 1.5 |  | 1.5 | -2.25
| Major OT Toilet Wall | 1 | 1 | 1.8 |  | 1.5 | 2.7
| Major OT | 1 | 1 | 4.05 |  | 1.5 | 6.075
| do | 1 | 1 | 3 |  | 1.5 | 4.5
| partiton wall | 1 | 1 | 1.8 |  | 1.5 | 2.7
|  | Total |  |  |  |  | 37.125 | Sqm
Dismantling, clearing away and carefully stacking useful materials for re-use and disposal of unserviceable materials with 100m lead as directed by Executive Engineer duly taking actual premeasurements before dismantling including all labour charges , overheads & contractor profit etc., complete (Reinforcement Cement)
| Reception plat forms Slabs | 1 | 4 | 1.72 | 0.65 | 0.05 | 0.2236
|  | 1 | 4 | 0.8 | 0.65 | 0.05 | 0.104
| Embrology lab Shelves slabs | 1 | 4 | 3.1 | 0.6 | 0.05 | 0.372
|  | Total |  |  |  |  | 0.6996 | Cum
Masonry work 100 mm thick in CM (1:4) prop (cement: Screened sand) in super structure with Aerated (Cellular) Autoclaved Concrete Blocks conforming to IS:2185 (Part-3) - 1984 and IS:6441-1972 of Compressive strength 3 N/mm2 600x 200 x 100 mm from approved source having minimum crushing strength of 3 N/Sq.m including cost and conveyance of all materials like cement, sand, bricks, water etc., to site, including sales & other taxes on all materials, all operational, incidental and labour charges such as mixing cement mortar, constructing masonry, scaffolding charges, lift charges, curing, etc., complete but excluding seigniorage charges for finished item of work. (APSS No. 501 & 504).
| Record Room Main Door Wall | 1 | 1 | 3 |  | 3.5 | 10.5
| Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
| Partition Wall b/w Ultra Sound And Autoclave Room | 1 | 1 | 2.18 |  | 3.5 | 7.63
| Partition Wall b/w Counciling Room-2 And Counciling Room-1 | 1 | 1 | 2.452 |  | 3.5 | 8.582
| Doctors Toilet Room Wall | 1 | 1 | 4.7 |  | 3.45 | 16.215
| Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
| Partition Wall b/w Carridor and OT Room | 1 | 1 | 6.485 |  | 3.5 | 22.6975
| Partition Wall b/w OT Rooms | 1 | 1 | 6.485 |  | 3.5 | 22.6975
| P.Change Room Wall | 1 | 1 | 2.02 |  | 3.5 | 7.07
| Store Room | 1 | 1 | 2.582 |  | 3.5 | 9.037
| Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
| Partition Wall b/w Store Room And Blod Collection Room | 1 | 1 | 3.3 |  | 2.4 | 7.92
| Blod Collection Room Wall | 1 | 1 | 2.582 |  | 3.5 | 9.037
| Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
| partition Wall b/w Blod Collection Room And Sperm Collection Room | 1 | 1 | 3.3 |  | 2.4 | 7.92
| Sperm Collection Main Door Wall | 1 | 1 | 1.2 |  | 3.5 | 4.2
| Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
| partition Wall b/w Sperm Collection Room And Toilet Room | 1 | 1 | 3.3 |  | 3.5 | 11.55
| Door Deduction | -1 | 1 | 0.8 |  | 2.1 | -1.68
| Sperm Collection Toilet Wall | 1 | 1 | 1.1 |  | 3.5 | 3.85
| Partition Wall b/w Toilet And Cryo Room | 1 | 1 | 1.6 |  | 3.5 | 5.6
| Cryo Room Door Wall | 1 | 1 | 3 |  | 3.5 | 10.5
| Door Deduction | -1 | 1 | 1 |  | 2.1 | -2.1
| Manifold Room | 1 | 1 | 3.185 |  | 3.5 | 11.1475
|  | 1 | 1 | 1.45 |  | 3 | 4.35
|  | 1 | 1 | 2.13 |  | 3.5 | 7.455
|  | 1 | 1 | 2.505 |  | 3 | 7.515
| Wall Andrology Lab Scrub Area | 1 | 1 | 2.03 |  | 3.5 | 7.105
| Reciption Platform Wall | 1 | 1 | 1.73 |  | 0.9 | 1.557
| do | 1 | 3 | 0.5 |  | 0.9 | 1.35
|  | Total |  |  |  |  | 191.2055 | Sqm
Masonry work in CM (1:6) prop (cement: Screened sand) in super structure with Aerated (Cellular) Autoclaved Concrete Blocks conforming to IS:2185 (Part-3) - 1984 and IS:6441-1972 of Compressive strength 3 N/mm2 600x 230 x 200 mm from approved source having minimum crushing strength of 3 N/Sq.m including cost and conveyance of all materials like cement, sand, bricks, water etc., to site, including sales & other taxes on all materials, all operational, incidental and labour charges such as mixing cement mortar, constructing masonry, scaffolding charges, lift charges, curing, etc., complete but excluding seigniorage charges for finished item of work. (APSS No. 501 & 504).
| Step Down Room Door Replacing Brick Work | 1 | 1 | 1.5 | 0.23 | 2.6 | 0.897
| do | 1 | 1 | 1.7 | 0.23 | 0.4 | 0.1564
| Prepost operative room Door Replace Brick Work | 1 | 1 | 1 | 0.23 | 2.6 | 0.598
| Embryology Lab Door Replacing Brick Work | 1 | 1 | 1.16 | 0.23 | 2.9 | 0.77372
| do | 1 | 1 | 1.7 | 0.23 | 0.4 | 0.1564
| OT Room Window Replacing Brick Work | 1 | 3 | 1.5 | 0.23 | 1.5 | 1.5525
| Toilet Room Window Replacing Brick Work | 1 | 1 | 1.5 | 0.23 | 1.5 | 0.5175
| Embrology Lab Windows Replacing Brick Work | 1 | 3 | 1.5 | 0.23 | 1.5 | 1.5525
| Access Control Door Wall | 1 | 2 | 3 | 0.23 | 3 | 4.14
| Door Deduction(-) | -1 | 2 | 1.5 | 0.23 | 2.6 | -1.794
| Prepost operative Window Closing | 1 | 1 | 1.1 | 0.23 | 1.9 | 0.4807
[7 empty] | 9.0307 | Cum
Providing Thermo Mechanically Treated ( TMT) ( Fe-500/500D/550D from primery producer TATA, SAIL, VSP, JSW Steel, Goel steel, Jindal panther, X- Vega & balaji Shakthi as per IS 1786-2008) of Different Diameters RCC Works , including labour charges for straightening, cutting, bending to required sizes and shapes, placing in position with cover blocks of approved materials and sizes and typing and lap - spacing with binding wire of 18 SWG, Forming grills for reinforcement work as per approved design and drawings, including and conveyanace of steel bars, including all wastages such as overlaps, coupling, chairs, spacer bars including cost and conveyance of binding wire cover blocks and incidential, operational, labour charges such as cutting bending, placing in position, typing incliding sales and other taxes on all materials etc., and overheads & contractors profit completefor finished item of work
[8 empty] | 12mm | 10mm | 8mm
| Prepost Operative Room Top Bars | 1 | 2 | 1.8 |  |  |  | 3.6
| Bottom Bars | 1 | 2 | 1.8 |  |  |  | 3.6
| Stirrups | 1 | 15 | 0.8 | [5 empty] | 12
| Record Room Top Bars | 1 | 2 | 1.5 |  |  |  | 3
| Bottom Bars | 1 | 2 | 1.5 |  |  |  | 3
| Stirrups | 1 | 12 | 0.6 | [5 empty] | 7.2
| Dr Toilet Top Bars | 1 | 2 | 1.5 |  |  |  | 3
| Bottom Bars | 1 | 2 | 1.5 |  |  |  | 3
| Stirrups | 1 | 12 | 0.6 | [5 empty] | 7.2
| Store Room Top Bars | 1 | 2 | 1.5 |  |  |  | 3
| Bottom Bars | 1 | 2 | 1.5 |  |  |  | 3
| Stirrups | 1 | 12 | 0.6 | [5 empty] | 7.2
| Blood Collection Room Top Bars | 1 | 2 | 1.5 |  |  |  | 3
| Bottom Bars | 1 | 2 | 1.5 |  |  |  | 3
| Stirrups | 1 | 12 | 0.6 | [5 empty] | 7.2
| Sperm Collection Room Top Bars | 1 | 2 | 1.5 |  |  |  | 3
| Bottom Bars | 1 | 2 | 1.5 |  |  |  | 3
| Stirrups | 1 | 12 | 0.6 | [5 empty] | 7.2
| Toilet Top Bars | 1 | 2 | 1.3 |  |  |  | 2.6
| Bottom Bars | 1 | 2 | 1.3 |  |  |  | 2.6
| Stirrups | 1 | 10 | 0.6 | [5 empty] | 6
| Major OT Top bars | 1 | 2 | 2 |  |  |  | 4
| Bottom Bars | 1 | 2 | 2 |  |  |  | 4
| Stirrups | 1 | 17 | 0.8 | [5 empty] | 13.6
| Embrology Lab Top Bars | 1 | 2 | 2 |  |  |  | 4
| Bottom Bars | 1 | 2 | 2 |  |  |  | 4
| Stirrups | 1 | 17 | 0.8 | [5 empty] | 13.6
| Andrology Lab | 1 | 2 | 2 |  |  |  | 4
| Bottom Bars | 1 | 2 | 2 |  |  |  | 4
| Stirrups | 1 | 17 | 0.6 | [5 empty] | 10.2
| Cryo Room Top Bars | 1 | 2 | 1.5 |  |  |  | 3
| Bottom Bars | 1 | 2 | 1.5 |  |  |  | 3
| Stirrups | 1 | 15 | 0.6 | [5 empty] | 9
[8 empty] | 72.4 |  | 100.4
[8 empty] | 0.89 |  | 0.39
[8 empty] | 0.064436 |  | 0.039156
[10 empty] | 0.10359 | MT
Supply and placing of the Design Mix Concrete M 25 grade corresponding to IS 456 with minimum cement content of 380 kgs per 1 cum of concrete using Weight Batcher / Concrete mixer with 20mm size graded machine crushed hard granite metal (coarse aggregate - as per IS 383 - 1970 and IS 2386 Part 1 to Part 8) from approved quarry including cost and conveyance of all materials like cement, fine aggregate (sand) coarse aggregate, water etc., to site and sales & other taxes on all materials, centering using Casurina Ballies, Bamboos, Wooden Reapers, Runners, Wood Posts, Steel Plates etc., including all operational, incidental and labour charges such as weigh batching, machine mixing, lifting of concrete manually, laying concrete, curing , overheads & contractors profit etc., complete but excluding cost of steel and its fabrication charges for finished item of work (APSS No. 402) (For Lintels)
| Step Dow Room | 1 | 1 | 1.7 | 0.23 | 0.15 | 0.05865
| Record Room | 1 | 1 | 1.2 | 0.15 | 0.15 | 0.027
| Dr Toilet | 1 | 1 | 1.2 | 0.15 | 0.15 | 0.027
| Store Room | 1 | 1 | 1.2 | 0.15 | 0.15 | 0.027
| Blod Collection Room | 1 | 1 | 1.2 | 0.15 | 0.15 | 0.027
| Sperm Collection Room | 1 | 1 | 1.2 | 0.15 | 0.15 | 0.027
| Toilet | 1 | 1 | 1 | 0.15 | 0.15 | 0.0225
| Major OT | 1 | 1 | 1.7 | 0.23 | 0.15 | 0.05865
| Embrology Lab | 1 | 1 | 1.7 | 0.23 | 0.15 | 0.05865
| Andrology Lab | 1 | 1 | 1.7 | 0.15 | 0.15 | 0.03825
| Cryo Room | 1 | 1 | 1.2 | 0.15 | 0.15 | 0.027
[7 empty] | 0.3987 | Cum
Plastering 12mm thick in two coats using screened sand with base coat of 8mm thick in CM (1:6) and top coat of 4mm thick in CM (1:4) with dubara sponge finishing including cost and conveyance of all materials like cement, sand, water etc., to site, including sales & other taxes on all materials, and all operational, incidental charges on materials and including cost of all labour charges for mixing mortar, finishing, scaffolding, lift charges, curing, including cutting grooves as directed by Engineer-in-charge etc., and overheads & contractors profit complete for finished item of work. (SS 901,903 & 904).
| Step Down Room Door Replacing | 1 | 2 | 1.5 |  | 2.6 | 7.8
| do | 1 | 2 | 1.7 |  | 0.4 | 1.36
| Door Jam | 1 | 1 | 6.635 | 0.23 |  | 1.526
| Prepost operative room Door Replace | 1 | 2 | 1 |  | 2.6 | 5.2
| Embryology Lab Door Replacing | 1 | 2 | 1.16 |  | 2.9 | 6.728
| do | 1 | 2 | 1.7 |  | 0.4 | 1.36
| Door Jam | 1 | 1 | 6.7 | 0.23 |  | 1.541
| Major OT Door | 1 | 2 | 1.7 |  | 0.4 | 1.36
| Door Jam | 1 | 1 | 6.7 | 0.23 |  | 1.541
| OT Room Window Replacing | 3 | 2 | 1.5 |  | 1.5 | 13.5
| Toilet Room Window Replacing | 1 | 2 | 1.5 |  | 1.5 | 4.5
| Embrology Lab Windows Replacing | 3 | 2 | 1.5 |  | 1.5 | 13.5
| Access Control Door Wall | 2 | 2 | 3 |  | 3 | 36
| Door Deduction(-) | -2 | 2 | 1.5 |  | 2.6 | -15.6
| Door Jam | 1 | 2 | 6.7 | 0.23 |  | 3.082
| Prepost operative Window Closing | 1 | 2 | 1.1 |  | 1.9 | 4.18
| Record Room Wall | 1 | 2 | 3 |  | 3.45 | 20.7
| Door Deduction(-) | -1 | 2 | 1 |  | 2.1 | -4.2
| Door Jam | 1 | 1 | 5.2 | 0.15 |  | 0.78
| Partition Wall b/w Ultra Sound And Autoclave Room | 1 | 2 | 2.18 |  | 3.5 | 15.26
| Partition Wall b/w Counciling Room-2 And Counciling Room-1 | 1 | 2 | 2.452 |  | 3.5 | 17.164
| Doctors Toilet Room Wall | 1 | 2 | 4.7 |  | 3.5 | 32.9
| Door Deduction(-) | -1 | 2 | 1 |  | 2.1 | -4.2
| Door Jam | 1 | 1 | 5.2 | 0.15 |  | 0.78
| Partition Wall b/w Carridor and OT Room | 1 | 2 | 6.485 |  | 3.5 | 45.395
| Partition Wall b/w OT Rooms | 1 | 2 | 6.485 |  | 3.5 | 45.395
| P.Change Room Wall | 1 | 2 | 2.02 |  | 3.5 | 14.14
| Store Room | 1 | 2 | 2.582 |  | 3.5 | 18.074
| Door Jams | 1 | 1 | 5.2 | 0.15 |  | 0.78
| Door Deduction(-) | -1 | 2 | 1 |  | 2.1 | -4.2
| Partition Wall b/w Store Room And Blod Collection Room | 1 | 2 | 3.4 |  | 2.4 | 16.32
| Top | 1 | 2 | 3.4 | 0.15 |  | 1.02
| Blod Collection Room Wall | 1 | 2 | 2.582 |  | 3.5 | 18.074
| Door Jam | 1 | 1 | 5.2 | 0.15 |  | 0.78
| Door Deduction(-) | -1 | 2 | 1 |  | 2.1 | -4.2
| partition Wall b/w Blod Collection Room And Sperm Collection Room | 1 | 2 | 3.3 |  | 2.4 | 15.84
| Top | 1 | 1 | 3.4 | 0.15 |  | 0.51
| do | 1 | 2 | 1 |  | 1.2 | 2.4
| partition Wall b/w Sperm Collection Room And Toilet Room | 1 | 2 | 3.3 |  | 3.5 | 23.1
| Door Jam | 1 | 1 | 5 | 0.15 |  | 0.75
| Door Deduction(-) | -1 | 2 | 0.8 |  | 2.1 | -3.36
| Sperm Collection Toilet Wall | 1 | 2 | 2.05 |  | 3.5 | 14.35
| Partition Wall b/w Toilet And Cryo Room | 1 | 2 | 1.7 |  | 3.5 | 11.9
| Cryo Room Wall | 1 | 2 | 3 |  | 3.5 | 21
| Door Jams | 1 | 1 | 5.2 | 0.15 |  | 0.78
| Door Deduction | -1 | 2 | 1 |  | 2.1 | -4.2
| Manifold Room | 1 | 2 | 3.185 |  | 3.5 | 22.295
|  | 1 | 2 | 1.385 |  | 3 | 8.31
|  | 1 | 2 | 2.23 |  | 3.5 | 15.61
|  | 1 | 2 | 1.33 |  | 3 | 7.98
| Andrology Lab Scrub Area | 1 | 2 | 2.585 |  | 3.45 | 17.8365
| Doctors Corridor Door Jam | 1 | 1 | 8.1 | 0.23 |  | 1.863
| Corridor Change Room | 1 | 1 | 8.1 | 0.23 |  | 1.863
| Prepost Operative Room Wall Area | 1 | 1 | 12.6 | 0.23 |  | 2.898
| Toilet Wall | 1 | 1 | 4.65 | 0.15 |  | 0.6975
| Counseling Rooms Partition Wall Area | 1 | 1 | 9.3 | 0.15 |  | 1.395
| Andrology Lab Main Door wall area | 1 | 1 | 11.2 | 0.23 |  | 2.576
| Toilet Wall | 1 | 1 | 5.25 | 0.15 |  | 0.7875
| do | 1 | 1 | 6.45 | 0.15 |  | 0.9675
| partition Wall | 1 | 1 | 1.8 | 0.15 |  | 0.27
| Toilet Wall Major OT | 1 | 1 | 5.25 | 0.15 |  | 0.7875
| do | 1 | 1 | 6.45 | 0.15 |  | 0.9675
| partition Wall | 1 | 1 | 1.8 | 0.15 |  | 0.27
| Andrlogy Lab Wall plastring | 1 | 1 | 3.2 |  | 1.5 | 4.8
| Reciption Platform Wall | 1 | 2 | 1.5 |  | 0.9 | 2.7
| do | 3 | 2 | 0.5 |  | 0.9 | 2.7
| Toilet Inside Prepost Operative Room | 1 | 1 | 3 |  | 1.5 | 4.5
| do | 1 | 1 | 0.8 |  | 1.5 | 1.2
| Andrlogy Lab Toilet Wall | 1 | 1 | 1.8 |  | 1.5 | 2.7
| do | 1 | 1 | 3 |  | 1.5 | 4.5
| do | 1 | 1 | 1.8 |  | 1.5 | 2.7
| Andrology lab Partition wall | 1 | 1 | 5.2 |  | 1.5 | 7.8
| Door Deduction(-) | -1 | 1 | 1.5 |  | 1.5 | -2.25
| Major OT Toilet Wall | 1 | 1 | 1.8 |  | 1.5 | 2.7
| Major OT | 1 | 1 | 4.05 |  | 1.5 | 6.075
| do | 1 | 1 | 3 |  | 1.5 | 4.5
| partiton wall | 1 | 1 | 1.8 |  | 1.5 | 2.7
[7 empty] | 536.1091 | Sqm
Providing and applying Wall putty of White Cement or Polymer or Cement based of average 1 to 2 mm thickness over plastered surface to prepare the surface even and smooth after thoroughly brushing the surface to remove all dirt and remains of loose powdered materials, applying emery paper, Sand the surface, clean & wipe off loose dust, applying knifing paste filler by putty knife / muslin pad, air dry for 2 - 3 hrs, sand with 180 and 320 No., emery paper for the surface preparation including cost and conveyance of all materials to work site and all operational, incidental, labour charges, over heads and contractors profit etc., complete for finished item of work in all floors for Internal walls.
| Main Entry Corridor | 1 | 1 | 6.3 |  | 2 | 12.6
| main Entry Access Control Door | 1 | 1 | 3 |  | 2 | 6
| Door Deduction(-) | -1 | 1 | 1.5 |  | 2 | -3
| Corridor at Reception | 1 | 1 | 3 |  | 2 | 6
| Reception area | 1 | 2 | 3.4 |  | 2 | 13.6
| Record Room Main Door Wall | 1 | 1 | 3 |  | 2 | 6
| Door Jam | 1 | 1 | 5.2 | 0.15 |  | 0.78
| Door Deduction(-) | -1 | 1 | 1 |  | 2 | -2
| Record Room Inside | 1 | 2 | 3.2 |  | 2 | 12.8
| do | 1 | 1 | 3 |  | 2 | 6
| do | 1 | 1 | 3 |  | 3.5 | 10.5
| Door deductions(-) | -1 | 1 | 1 |  | 2.1 | -2.1
| Window Deduction(-) | 1 | 1 | 1.8 |  | 1.4 | 2.52
| Wndow Jam | 1 | 1 | 5.4 | 0.15 |  | 0.81
| Ultra Sound Room Inside Long Wall | 1 | 2 | 4.505 |  | 3.5 | 31.535
| Ultra Sound Room Inside Short Wall | 1 | 2 | 2.18 |  | 3.5 | 15.26
| Door Jam | 1 | 1 | 5.812 | 0.15 |  | 0.8718
| Door Deduction(-) | -1 | 1 | 1.215 |  | 2.3 | -2.7945
| Ventilator Deduction(-) | -1 | 1 | 0.45 |  | 0.45 | -0.2025
| Ventilator jam | 1 | 1 | 1.8 | 0.15 |  | 0.27
| Autoclave Room Inside Long Wall | 1 | 2 | 2.18 |  | 3.5 | 15.26
| Autoclave Room Inside Short Wall | 1 | 2 | 1.19 |  | 3.5 | 8.33
| Door deduction(-) | -1 | 1 | 1.21 |  | 2.37 | -2.8677
| Door Jam | 1 | 1 | 5.81 | 0.15 |  | 0.8715
| Toilet at Counseling Room 2 Inside Long Wall | 1 | 2 | 1.5 |  | 2 | 6
| Toilet at Counseling Room 2 Inside Short Wall Wall | 1 | 2 | 1.2 |  | 2 | 4.8
| Door Deduction(-) | -1 | 2 | 0.8 |  | 2 | -3.2
| Door Jam | 1 | 1 | 5 | 0.15 |  | 0.75
| Counseling Room 2 Inside Long Wall | 1 | 2 | 3.24 |  | 3.5 | 22.68
| Counseling Room 2 Inside Long Wall | 1 | 2 | 2.45 |  | 3.5 | 17.15
| Door jam | 1 | 1 | 5.47 | 0.15 |  | 0.8205
| Door Deduction(-) | -1 | 1 | 1.07 |  | 2.2 | -2.354
| Window Deduction(-) | -1 | 1 | 1.8 |  | 1.8 | -3.24
| Counseling Room 1 inside Long Wall | 1 | 2 | 3.24 |  | 3.5 | 22.68
| Counseling Room 1 inside Short Wall | 1 | 2 | 2.45 |  | 3.5 | 17.15
| Door Jam | 1 | 1 | 5.49 | 0.15 |  | 0.8235
| Door Deduction(-) | -1 | 1 | 1.09 |  | 2.2 | -2.398
| Corridor at Counseling Room 1 and 2 | 1 | 2 | 5.1 |  | 3.5 | 35.7
| do | 1 | 1 | 1.2 |  | 3.5 | 4.2
| Door Deductions(-) Counseling Room 2 | -1 | 1 | 1.09 |  | 2.2 | -2.398
| Door Deductions(-) Counseling Room 1 | -1 | 1 | 1.07 |  | 2.2 | -2.354
| Door Deductions(-) Auto Clave Room | -1 | 1 | 1.2 |  | 2.3 | -2.76
| Door Deductions(-) Altra Sound Room | -1 | 1 | 1.2 |  | 2.3 | -2.76
| Corridor at prepost Operative Wards | 1 | 2 | 6.3 |  | 2 | 25.2
| Door Deduction(-) | -1 | 1 | 1.49 |  | 2 | -2.98
| Corridor Deduction(-) | -1 | 1 | 1.2 |  | 2 | -2.4
| Prepost Operative Wards Inside Long Wall | 1 | 1 | 6.48 |  | 2 | 12.96
| Prepost Operative Wards Inside Long Wall | 1 | 1 | 4.38 |  | 2 | 8.76
| Prepost Operative Wards Inside Short Wall | 1 | 1 | 6 |  | 2 | 12
| Prepost Operative Wards Inside Short Wall | 1 | 1 | 4.8 |  | 2 | 9.6
| Door Deduction(-) | -1 | 1 | 1.49 |  | 2 | -2.98
| Door Jam | 1 | 1 | 6.49 | 0.23 |  | 1.4927
| Window Deduction(-) | -1 | 1 | 1.8 |  | 1.4 | -2.52
| Window Jam | 1 | 1 | 7.2 | 0.15 |  | 1.08
| Corridor At Semi Sterile Area | 1 | 2 | 6.45 |  | 2 | 25.8
| Corridor Opening Deductions(-) | -1 | 2 | 1.2 |  | 1.5 | -3.6
| Access Control Door at Semistearail Area | 1 | 2 | 3 |  | 3.5 | 21
| Door Deduction(-) | -1 | 2 | 1.5 |  | 2.6 | -7.8
| Door Jam | 1 | 1 | 6.7 | 0.23 |  | 1.541
| Corridor at Dr Change Room Long Wall | 1 | 2 | 4.7 |  | 3.5 | 32.9
| Corridor at Dr Change Room Short Wall | 1 | 2 | 4.68 |  | 3.5 | 32.76
| Corridor Opening Deductions(-) | 1 | 1 | 1.2 |  | 3 | 3.6
| Toilet Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
| Dr Toilet Inside | 1 | 2 | 4.68 |  | 2 | 18.72
| Dr Toilet Inside | 1 | 2 | 1.85 |  | 2 | 7.4
| Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
| Ventilator Deduction(-) | -1 | 1 | 0.45 |  | 0.45 | -0.2025
| Dr Change Room Partitions | 1 | 2 | 2.61 |  | 3.5 | 18.27
| Dr Change Room Partitions | 1 | 2 | 2.2 |  | 3.5 | 15.4
| Door Deductions(-) | -1 | 1 | 1 |  | 2.1 | -2.1
| Dr Change Room Partitions | 1 | 2 | 1.45 |  | 3.5 | 10.15
| Dr Change Room Partitions | 1 | 2 | 1.45 |  | 3.5 | 10.15
| Corridor at Manifold Room | 1 | 2 | 3.3 |  | 3.5 | 23.1
| Corridor at Manifold Room | 1 | 1 | 1.2 |  | 3.5 | 4.2
| Door Deductions(-) | -1 | 1 | 1.08 |  | 2.3 | -2.484
| Door Deductions(-) | -1 | 1 | 0.986 |  | 2.2 | -2.1692
| Manifold Room Inside Long Walls | 1 | 2 | 3.185 |  | 3.5 | 22.295
| Manifold Room Inside Short Walls | 1 | 2 | 2.13 |  | 3.5 | 14.91
| Door Deductions(-) | -1 | 1 | 1.01 |  | 2.3 | -2.323
| Door Jam | 1 | 1 | 5.61 | 0.15 |  | 0.8415
| Change Room walls | 3 | 2 | 1.87 |  | 3.5 | 39.27
| Change Room wall | 1 | 1 | 5.2 |  | 2 | 10.4
| Corridor at Blood Collection Room | 1 | 1 | 5.2 |  | 3.5 | 18.2
| Door Deductions(-) | -1 | 1 | 0.998 |  | 2.1 | -2.0958
| Door Deductions(-) | -1 | 1 | 0.999 |  | 2.1 | -2.0979
| Store Room Inside Long Wall | 1 | 1 | 3.3 |  | 3.5 | 11.55
| Store Room Inside Long Wall | 1 | 1 | 3.3 |  | 2.4 | 7.92
| Store Room Inside Short Wall | 1 | 2 | 2.5 |  | 3.5 | 17.5
| Door Deductions(-) | -1 | 1 | 1 |  | 2.1 | -2.1
| Partition Wall Top | 1 | 1 | 3.3 | 0.15 |  | 0.495
| Blood Collection Room Long Wall | 1 | 2 | 3.3 |  | 2.4 | 15.84
| Blood Collection Room Short Wall | 1 | 2 | 2.5 |  | 3.5 | 17.5
| Door Deductions(-) | -1 | 1 | 1 |  | 2.1 | -2.1
| Tartition Wall Top | 1 | 1 | 3.3 | 0.15 |  | 0.495
| Sperm Collection Inside Long Wall | 1 | 1 | 3.3 |  | 2.4 | 7.92
| Sperm Collection Inside Long Wall | 1 | 1 | 3.3 |  | 3.5 | 11.55
| Sperm Collection Inside Short Wall | 1 | 2 | 3.265 |  | 3.5 | 22.855
| Door Deductions(-) | -1 | 1 | 0.8 |  | 2.1 | -1.68
| Door Deductions(-) | -1 | 1 | 1 |  | 2.1 | -2.1
| Sperm Collection Toilet inside | 1 | 2 | 1.6 |  | 2 | 6.4
| Sperm Collection Toilet inside | 1 | 2 | 1.1 |  | 2 | 4.4
| Door Deductions(-) | -1 | 1 | 0.8 |  | 2.1 | -1.68
| Ventilator Deduction(-) | -1 | 1 | 0.45 |  | 0.45 | -0.2025
| Corridor at Sterile area | 1 | 2 | 6.3 |  | 2 | 25.2
| Corridor at Sterile area | 1 | 1 | 3 |  | 2 | 6
| Door Deductions(-) Minor OT | -1 | 1 | 1.5 |  | 2 | -3
| Door Deductions(-) Major OT | -1 | 1 | 1.5 |  | 2 | -3
| Door Deductions(-) Andrology Lab | -1 | 1 | 1.5 |  | 2 | -3
| Door Deductions(-) Emergency Exit | -1 | 1 | 1.8 |  | 2 | -3.6
| Minor OT Inside Long Walls | 1 | 2 | 6.4 |  | 3.5 | 44.8
| Minor OT Inside Short Walls | 1 | 2 | 4.2 |  | 3.5 | 29.4
| Door Deductions(-) | -1 | 1 | 1.5 |  | 2.6 | -3.9
| Pass box Opening (-) | -1 | 1 | 0.6 |  | 0.6 | -0.36
| Androlry Lab Long Walls Inside | 1 | 2 | 4.25 |  | 3.5 | 29.75
| Androlry Lab Short Walls Inside | 1 | 2 | 4.08 |  | 3.5 | 28.56
| Door Deductions(-) | -1 | 1 | 1.5 |  | 2.6 | -3.9
| Door Deductions(-) | -1 | 1 | 1 |  | 2.1 | -2.1
| Cryo Room Inside | 1 | 2 | 3 |  | 3.5 | 21
| do | 1 | 2 | 1.6 |  | 3.5 | 11.2
| Door Deductions | -1 | 1 | 1 |  | 2.1 | -2.1
| Staire Case area | 1 | 1 | 4.2 |  | 2 | 8.4
| Staire Case area | 1 | 2 | 4.2 |  | 2 | 16.8
| Window Deduction(-) | -1 | 1 | 1.8 |  | 1.8 | -3.24
[7 empty] | 917.8539 | Sqm
White washing two coats with white cement to ceiling to give an even shade after thouroughly brushing the surface to remove all dirt and remains of loose powdered materials including cost of all materials, labour charges and incidental such as scaffolding, lift charges etc., and overheads & contractors profit complete for finished item of work in all floors.
| Main Entry Corridor | 1 | 1 | 6.3 |  | 1.5 | 9.45
| main Entry Access Control Door | 1 | 1 | 3 |  | 1.5 | 4.5
| Door Deduction(-) | -1 | 1 | 1.5 |  | 2.6 | -3.9
| Corridor at Reception | 1 | 1 | 3 |  | 1.5 | 4.5
| Reception area | 1 | 2 | 3.4 |  | 1.5 | 10.2
| Record Room Main Door Wall | 1 | 2 | 3 |  | 3.05 | 18.3
| Door Jam | 1 | 1 | 5.2 | 0.15 |  | 0.78
| Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
| Record Room Inside | 1 | 2 | 3.2 |  | 1.5 | 9.6
| do | 1 | 1 | 3 |  | 1.5 | 4.5
| Window Deduction(-) | 1 | 1 | 1.8 |  | 1.4 | 2.52
| Wndow Jam | 1 | 1 | 5.4 | 0.15 |  | 0.81
| Ultra Sound Room Inside Long Wall | 1 | 2 | 4.505 |  | 3.05 | 27.4805
| Ultra Sound Room Inside Short Wall | 1 | 2 | 2.18 |  | 3.05 | 13.298
| Door Jam | 1 | 1 | 5.812 | 0.15 |  | 0.8718
| Door Deduction(-) | -1 | 1 | 1.215 |  | 2.3 | -2.7945
| Ventilator Deduction(-) | -1 | 1 | 0.45 |  | 0.45 | -0.2025
| Ventilator jam | 1 | 1 | 1.8 | 0.15 |  | 0.27
| Autoclave Room Inside Long Wall | 1 | 2 | 2.18 |  | 3.05 | 13.298
| Autoclave Room Inside Short Wall | 1 | 2 | 1.19 |  | 3.05 | 7.259
| Door deduction(-) | -1 | 1 | 1.21 |  | 2.37 | -2.8677
| Door Jam | 1 | 1 | 5.81 | 0.15 |  | 0.8715
| Toilet at Counseling Room 2 Inside Long Wall | 1 | 2 | 1.5 |  | 1.5 | 4.5
| Toilet at Counseling Room 2 Inside Short Wall Wall | 1 | 2 | 1.2 |  | 1.5 | 3.6
| Door Deduction(-) | 1 | 2 | 0.8 |  | 2.1 | 3.36
| Door Jam | 1 | 1 | 5 | 0.15 |  | 0.75
| Counseling Room 2 Inside Long Wall | 1 | 2 | 3.24 |  | 3.05 | 19.764
| Counseling Room 2 Inside Long Wall | 1 | 2 | 2.45 |  | 3.05 | 14.945
| Door jam | 1 | 1 | 5.47 | 0.15 |  | 0.8205
| Door Deduction(-) | -1 | 1 | 1.07 |  | 2.2 | -2.354
| Window Deduction(-) | -1 | 1 | 1.8 |  | 1.8 | -3.24
| Counseling Room 1 inside Long Wall | 1 | 2 | 3.24 |  | 3.05 | 19.764
| Counseling Room 1 inside Short Wall | 1 | 2 | 2.45 |  | 3.05 | 14.945
| Door Jam | 1 | 1 | 5.49 | 0.15 |  | 0.8235
| Door Deduction(-) | -1 | 1 | 1.09 |  | 2.2 | -2.398
| Corridor at Counseling Room 1 and 2 | 1 | 2 | 5.1 |  | 3.05 | 31.11
| do | 1 | 1 | 1.2 |  | 3.05 | 3.66
| Door Deductions(-) Counseling Room 2 | -1 | 1 | 1.09 |  | 2.2 | -2.398
| Door Deductions(-) Counseling Room 1 | -1 | 1 | 1.07 |  | 2.2 | -2.354
| Door Deductions(-) Auto Clave Room | -1 | 1 | 1.2 |  | 2.3 | -2.76
| Door Deductions(-) Altra Sound Room | -1 | 1 | 1.2 |  | 2.3 | -2.76
| Corridor at prepost Operative Wards | 1 | 2 | 6.3 |  | 1.5 | 18.9
| Door Deduction(-) | -1 | 1 | 1.49 |  | 1.5 | -2.235
| Corridor Deduction(-) | -1 | 1 | 1.2 |  | 2 | -2.4
| Prepost Operative Wards Inside Long Wall | 1 | 1 | 6.48 |  | 1.5 | 9.72
| Prepost Operative Wards Inside Long Wall | 1 | 1 | 4.38 |  | 1.5 | 6.57
| Prepost Operative Wards Inside Short Wall | 1 | 1 | 6 |  | 1.5 | 9
| Prepost Operative Wards Inside Short Wall | 1 | 1 | 4.8 |  | 1.5 | 7.2
| Door Deduction(-) | -1 | 1 | 1.49 |  | 2.5 | -3.725
| Door Jam | 1 | 1 | 6.49 | 0.23 |  | 1.4927
| Window Deduction(-) | -1 | 1 | 1.8 |  | 1.4 | -2.52
| Window Jam | 1 | 1 | 7.2 | 0.15 |  | 1.08
| Corridor At Semi Sterile Area | 1 | 2 | 6.45 |  | 2 | 25.8
| Corridor Opening Deductions(-) | -1 | 2 | 1.2 |  | 1.5 | -3.6
| Access Control Door at Semistearail Area | 1 | 2 | 3 |  | 3.05 | 18.3
| Door Deduction(-) | -1 | 2 | 1.5 |  | 2.6 | -7.8
| Door Jam | 1 | 1 | 6.7 | 0.23 |  | 1.541
| Corridor at Dr Change Room Long Wall | 1 | 2 | 4.7 |  | 3.05 | 28.67
| Corridor at Dr Change Room Short Wall | 1 | 2 | 4.68 |  | 3.05 | 28.548
| Corridor Opening Deductions(-) | 1 | 1 | 1.2 |  | 3 | 3.6
| Toilet Door Deduction(-) | -1 | 1 | 1 |  | 2.1 | -2.1
| Dr Toilet Inside | 1 | 2 | 4.68 |  | 1.5 | 14.04
| Dr Toilet Inside | 1 | 2 | 1.85 |  | 1.5 | 5.55
| Door Deduction(-) | -1 | 1 | 1 |  | 1.5 | -1.5
| Ventilator Deduction(-) | -1 | 1 | 0.45 |  | 0.45 | -0.2025
| Dr Change Room Partitions | 1 | 2 | 2.61 |  | 3.05 | 15.921
| Dr Change Room Partitions | 1 | 2 | 2.2 |  | 3.05 | 13.42
| Door Deductions(-) | -1 | 1 | 1 |  | 2.1 | -2.1
| Dr Change Room Partitions | 1 | 2 | 1.45 |  | 3.05 | 8.845
| Dr Change Room Partitions | 1 | 2 | 1.45 |  | 3.05 | 8.845
| Corridor at Manifold Room | 1 | 2 | 3.3 |  | 3.05 | 20.13
| Corridor at Manifold Room | 1 | 1 | 1.2 |  | 3.05 | 3.66
| Door Deductions(-) | -1 | 1 | 1.08 |  | 2.3 | -2.484
| Door Deductions(-) | -1 | 1 | 0.986 |  | 2.2 | -2.1692
| Manifold Room Inside Long Walls | 1 | 2 | 3.185 |  | 3.05 | 19.4285
| Manifold Room Inside Short Walls | 1 | 2 | 2.13 |  | 3.05 | 12.993
| Door Deductions(-) | -1 | 1 | 1.01 |  | 2.3 | -2.323
| Door Jam | 1 | 1 | 5.61 | 0.15 |  | 0.8415
| Change Room walls | 3 | 2 | 1.87 |  | 3.05 | 34.221
| Change Room wall | 1 | 1 | 5.2 |  | 1.5 | 7.8
| Corridor at Blood Collection Room | 1 | 1 | 5.2 |  | 3.05 | 15.86
| Door Deductions(-) | -1 | 1 | 0.998 |  | 2.1 | -2.0958
| Door Deductions(-) | -1 | 1 | 0.999 |  | 2.1 | -2.0979
| Store Room Inside Long Wall | 1 | 1 | 3.3 |  | 3.05 | 10.065
| Store Room Inside Long Wall | 1 | 1 | 3.3 |  | 2.4 | 7.92
| Store Room Inside Short Wall | 1 | 2 | 2.5 |  | 3.05 | 15.25
| Door Deductions(-) | -1 | 1 | 1 |  | 2.1 | -2.1
| Partition Wall Top | 1 | 1 | 3.3 | 0.15 |  | 0.495
| Blood Collection Room Long Wall | 1 | 2 | 3.3 |  | 2.4 | 15.84
| Blood Collection Room Short Wall | 1 | 2 | 2.5 |  | 3.05 | 15.25
| Door Deductions(-) | -1 | 1 | 1 |  | 2.1 | -2.1
| Tartition Wall Top | 1 | 1 | 3.3 | 0.15 |  | 0.495
| Sperm Collection Inside Long Wall | 1 | 1 | 3.3 |  | 2.4 | 7.92
| Sperm Collection Inside Long Wall | 1 | 1 | 3.3 |  | 3.05 | 10.065
| Sperm Collection Inside Short Wall | 1 | 2 | 3.265 |  | 3.05 | 19.9165
| Door Deductions(-) | -1 | 1 | 0.8 |  | 2.1 | -1.68
| Door Deductions(-) | -1 | 1 | 1 |  | 2.1 | -2.1
| Sperm Collection Toilet inside | 1 | 2 | 1.6 |  | 1.5 | 4.8
| Sperm Collection Toilet inside | 1 | 2 | 1.1 |  | 1.5 | 3.3
| Door Deductions(-) | -1 | 1 | 0.8 |  | 1.5 | -1.2
| Ventilator Deduction(-) | -1 | 1 | 0.45 |  | 0.45 | -0.2025
| Corridor at Sterile area | 1 | 2 | 6.3 |  | 1.5 | 18.9
| Corridor at Sterile area | 1 | 1 | 3 |  | 1.5 | 4.5
| Door Deductions(-) Minor OT | -1 | 1 | 1.5 |  | 1.5 | -2.25
| Door Deductions(-) Major OT | -1 | 1 | 1.5 |  | 1.5 | -2.25
| Door Deductions(-) Andrology Lab | -1 | 1 | 1.5 |  | 1.5 | -2.25
| Door Deductions(-) Emergency Exit | -1 | 1 | 1.8 |  | 1.5 | -2.7
| Minor OT Inside Long Walls | 1 | 2 | 6.4 |  | 3.05 | 39.04
| Minor OT Inside Short Walls | 1 | 2 | 4.2 |  | 3.05 | 25.62
| Door Deductions(-) | -1 | 1 | 1.5 |  | 2.6 | -3.9
| Pass box Opening (-) | -1 | 1 | 0.6 |  | 0.6 | -0.36
| Androlry Lab Long Walls Inside | 1 | 2 | 4.25 |  | 3.05 | 25.925
| Androlry Lab Short Walls Inside | 1 | 2 | 4.08 |  | 3.05 | 24.888
| Door Deductions(-) | -1 | 1 | 1.5 |  | 2.6 | -3.9
| Door Deductions(-) | -1 | 1 | 1 |  | 2.1 | -2.1
| Cryo Room Inside | 1 | 2 | 3 |  | 3.05 | 18.3
| do | 1 | 2 | 1.6 |  | 3.05 | 9.76
| Door Deductions | -1 | 1 | 1 |  | 2.1 | -2.1
| Staire Case area | 1 | 1 | 4.2 |  | 1.5 | 6.3
| Staire Case area | 1 | 2 | 4.2 |  | 1.5 | 12.6
| Window Deduction(-) | -1 | 1 | 1.8 |  | 1.5 | -2.7
[7 empty] | 782.3034 | Sqm
Flooring With 16 to 18 mm thick high polished granite stone slabs black color for platforms (s.s. 701 and specila)
| Reception Plot Form Sides Long | 1 | 1 | 1.73 |  | 0.9 | 1.557
| Reception Plot Form Sides Short | 1 | 1 | 0.7 |  | 0.9 | 0.63
| Top | 1 | 1 | 1.73 |  | 0.7 | 1.211
| Sides | 1 | 3 | 1 |  | 0.9 | 2.7
| Entry Access Control Door | 1 | 1 | 3 |  | 3 | 9
| Door Deductions(-) | -1 | 1 | 1.4 |  | 2.5 | -3.5
| Door Sides | 1 | 2 | 0.23 |  | 2.5 | 1.15
| Top | 1 | 1 | 1.4 |  | 0.23 | 0.322
[7 empty] | 13.07 | Sqm
Flooring with non- skid fully body ceramic floor tiles
| Main Entry Corridor | 1 | 1 | 6.3 | 3 |  | 18.9
| do | 1 | 1 | 1.4 | 0.23 |  | 0.322
| Corridor at Reception | 1 | 1 | 3 | 3 |  | 9
| Reception | 1 | 1 | 3.4 | 3 |  | 10.2
| Record Room | 1 | 1 | 3.2 | 3 |  | 9.6
| do | 1 | 1 | 0.98 | 0.15 |  | 0.147
| Corridor at Prepost Operative Wards | 1 | 1 | 6.3 | 3 |  | 18.9
| do | 1 | 1 | 1.5 | 0.23 |  | 0.345
| Corridor at Counseling Room 1 and 2 | 1 | 1 | 5.1 | 1.2 |  | 6.12
| Skerting | 1 | 1 | 5.8 | 0.1 |  | 0.58
| do | 1 | 1 | 0.4 | 0.1 |  | 0.04
| Toilet | 1 | 1 | 1.5 | 1.2 |  | 1.8
| Ultra Sound Room | 1 | 1 | 3.2 | 3 |  | 9.6
| do | 1 | 1 | 1.2 | 0.15 |  | 0.18
| Skerting | 1 | 1 | 12.16 | 0.1 |  | 1.216
| Auto Clave Room | 1 | 1 | 2.18 | 1.9 |  | 4.142
| do | 1 | 1 | 1.2 | 0.15 |  | 0.18
| Skerting | 1 | 1 | 6.8 | 0.1 |  | 0.68
| Counseling Room 2 | 1 | 1 | 3.24 | 2.4 |  | 7.776
| do | 1 | 1 | 1 | 0.15 |  | 0.15
| Skerting | 1 | 1 | 10.2 | 0.1 |  | 1.02
| Counseling Room 1 | 1 | 1 | 3.2 | 2.45 |  | 7.84
| do | 1 | 1 | 1 | 0.15 |  | 0.15
| Skerting | 1 | 1 | 10.2 | 0.1 |  | 1.02
| Prepost Operative Wards | 1 | 1 | 6.48 | 6 |  | 38.88
| do | 1 | 1 | 1.5 | 0.23 |  | 0.345
| Toilet Area Deduction | -1 | 1 | 2 | 2.1 |  | -4.2
| Column | -1 | 1 | 0.53 | 0.53 |  | -0.2809
| Toilet | 1 | 1 | 2 | 1.2 |  | 2.4
| Corridor At Semi Sterile Area | 1 | 1 | 6.45 | 3 |  | 19.35
| Dr Chganhe Room | 1 | 1 | 4.7 | 4.68 |  | 21.996
| Skerting | 1 | 2 | 4.7 | 0.1 |  | 0.94
| do | 1 | 1 | 4.8 | 0.1 |  | 0.48
| Dr Toilet | 1 | 1 | 4.68 | 1.85 |  | 8.658
| Change Room Area | 1 | 1 | 6.45 | 3.07 |  | 19.8015
| Store Room | 1 | 1 | 3.3 | 2.58 |  | 8.514
| do | 1 | 1 | 1 | 0.1 |  | 0.1
| Skerting | 1 | 1 | 10.76 | 0.1 |  | 1.076
| Blood Collection Room | 1 | 1 | 3.3 | 2.58 |  | 8.514
| do | 1 | 1 | 1 | 0.1 |  | 0.1
| Skerting | 1 | 1 | 10.76 | 0.1 |  | 1.076
| Sperm Collection Room | 1 | 1 | 3.3 | 3.27 |  | 10.791
| do | 1 | 1 | 1 | 0.1 |  | 0.1
| Skerting | 1 | 1 | 12.14 | 0.1 |  | 1.214
| Sterm Collection Toilet | 1 | 1 | 1.6 | 1.1 |  | 1.76
| Manifold Room | 1 | 1 | 3.185 | 2.13 |  | 6.784
| do | 1 | 1 | 1 | 0.1 |  | 0.1
| Deductions | -1 | 1 | 0.68 | 0.68 |  | -0.4624
| Skerting | 1 | 1 | 9.56 | 0.1 |  | 0.956
| Minor OT | 1 | 1 | 6.4 | 4.2 |  | 26.88
| do | 1 | 1 | 1.5 | 0.23 |  | 0.345
| Skerting | 1 | 1 | 19.7 | 0.1 |  | 1.97
| Corridor at Sterile area | 1 | 1 | 6.3 | 3 |  | 18.9
| Major OT | 1 | 1 | 6.48 | 4.05 |  | 26.244
| do | 1 | 1 | 1.5 | 0.23 |  | 0.345
| Skerting | 1 | 1 | 18.06 | 0.1 |  | 1.806
| Embrology Lab | 1 | 1 | 6.48 | 4.3 |  | 27.864
| do | 1 | 1 | 1.5 | 0.1 |  | 0.15
| Skerting | 1 | 1 | 20.06 | 0.1 |  | 2.006
| Scrub Area | 1 | 1 | 3.53 | 0.68 |  | 2.4004
| Andrology Lab | 1 | 1 | 4.13 | 4.1 |  | 16.933
| do | 1 | 1 | 1.5 | 0.1 |  | 0.15
| Skerting | 1 | 1 | 13.96 | 0.1 |  | 1.396
| Cryo room | 1 | 1 | 3 | 1.6 |  | 4.8
| do | 1 | 1 | 1 | 0.1 |  | 0.1
| Skerting | 1 | 1 | 8.2 | 0.1 |  | 0.82
| Staire Case area | 1 | 1 | 4.2 | 4.2 |  | 17.64
| Skerting | 1 | 1 | 10.8 | 0.1 |  | 1.08
[7 empty] | 410.7296 | Sqm
Dadooing to walls with glazed fully body porceiain wall tiles
| Prepost Operative Wards | 1 | 1 | 6.48 | 1.5 |  | 9.72
| do | 1 | 1 | 4 | 1.5 |  | 6
| do | 1 | 1 | 1.2 | 1.5 |  | 1.8
| do | 1 | 1 | 5.28 | 1.5 |  | 7.92
| do | 1 | 1 | 6 | 1.5 |  | 9
| Door Deductions(-) | -1 | 1 | 1.5 | 1.5 |  | -2.25
| Door Deductions(-) | -1 | 1 | 0.8 | 1.5 |  | -1.2
| Toilet | 1 | 2 | 2 | 1.5 |  | 6
| do | 1 | 2 | 1.2 | 1.5 |  | 3.6
| door deductions(-) | -1 | 1 | 0.8 | 1.5 |  | -1.2
| Toilet At Counseling Room | 1 | 2 | 1.2 | 1.5 |  | 3.6
| do | 1 | 2 | 1.5 | 1.5 |  | 4.5
| door deductions(-) | -1 | 1 | 0.8 | 1.5 |  | -1.2
| Sperm Collection Toilet | 1 | 2 | 1.6 | 1.5 |  | 4.8
| do | 1 | 2 | 1.1 | 1.5 |  | 3.3
| Door Deductions (-) | -1 | 1 | 0.8 | 1.5 |  | -1.2
| Dr Toilet | 1 | 2 | 4.6 | 1.5 |  | 13.8
| do | 1 | 2 | 1.85 | 1.5 |  | 5.55
| Door Deductions(-) | -1 | 1 | 1 | 1.5 |  | -1.5
| Mani Entry Corridor | 1 | 1 | 0.5 | 1.5 |  | 0.75
| do | 1 | 1 | 1.06 | 1.5 |  | 1.59
| do | 1 | 1 | 0.75 | 1.5 |  | 1.125
| Reception Corridor | 1 | 1 | 3 | 1.5 |  | 4.5
| do | 1 | 1 | 2.8 | 1.5 |  | 4.2
| do | 1 | 1 | 0.7 | 0.68 |  | 0.476
| Record Room | 1 | 1 | 1.7 | 1.5 |  | 2.55
| do | 1 | 1 | 0.65 | 1.5 |  | 0.975
| Prepost Operative Wards Corridor | 1 | 1 | 3.43 | 1.5 |  | 5.145
| Scrub | 1 | 1 | 4.33 | 1.5 |  | 6.495
| do | 1 | 1 | 0.68 | 1.5 |  | 1.02
| Access Control Door | 2 | 2 | 0.65 | 1.5 |  | 3.9
[7 empty] | 103.766 | Sqm
Flase Ceiling as per Technical Specification
| Main Entry Corridor | 1 | 1 | 6.3 | 3 |  | 18.9
| Corridor at Reception | 1 | 1 | 3 | 3 |  | 9
| Reception | 1 | 1 | 3.4 | 3 |  | 10.2
| Record Room | 1 | 1 | 3.2 | 3 |  | 9.6
| Corridor at Prepost Operative Wards | 1 | 1 | 6.3 | 3 |  | 18.9
| Corridor at Counseling Room 1 and 2 | 1 | 1 | 5.1 | 1.2 |  | 6.12
| do | 1 | 1 | 0.4 | 0.1 |  | 0.04
| Toilet | 1 | 1 | 1.5 | 1.2 |  | 1.8
| Ultra Sound Room | 1 | 1 | 3.2 | 3 |  | 9.6
| Auto Clave Room | 1 | 1 | 2.18 | 1.9 |  | 4.142
| Counseling Room 2 | 1 | 1 | 3.24 | 2.4 |  | 7.776
| Counseling Room 1 | 1 | 1 | 3.2 | 2.45 |  | 7.84
| Prepost Operative Wards | 1 | 1 | 6.48 | 6 |  | 38.88
| Toilet Area Deduction | -1 | 1 | 2 | 2.1 |  | -4.2
| Column | -1 | 1 | 0.53 | 0.53 |  | -0.2809
| Toilet | 1 | 1 | 2 | 1.2 |  | 2.4
| Corridor At Semi Sterile Area | 1 | 1 | 6.45 | 3 |  | 19.35
| Dr Chganhe Room | 1 | 1 | 4.7 | 4.68 |  | 21.996
| do | 1 | 1 | 4.8 | 0.1 |  | 0.48
| Dr Toilet | 1 | 1 | 4.68 | 1.85 |  | 8.658
| Change Room Area | 1 | 1 | 6.45 | 3.07 |  | 19.8015
| Store Room | 1 | 1 | 3.3 | 2.58 |  | 8.514
| Blood Collection Room | 1 | 1 | 3.3 | 2.58 |  | 8.514
| Sperm Collection Room | 1 | 1 | 3.3 | 3.27 |  | 10.791
| Sterm Collection Toilet | 1 | 1 | 1.6 | 1.1 |  | 1.76
| Manifold Room | 1 | 1 | 3.185 | 2.13 |  | 6.784
| Deductions Column | -1 | 1 | 0.68 | 0.68 |  | -0.4624
| Minor OT | 1 | 1 | 6.4 | 4.2 |  | 26.88
| Corridor at Sterile area | 1 | 1 | 6.3 | 3 |  | 18.9
| Major OT | 1 | 1 | 6.48 | 4.05 |  | 26.244
| Embrology Lab | 1 | 1 | 6.48 | 4.3 |  | 27.864
| Scrub Area | 1 | 1 | 3.53 | 0.68 |  | 2.4004
| Andrology Lab | 1 | 1 | 4.13 | 4.1 |  | 16.933
| Cryo room | 1 | 1 | 3 | 1.6 |  | 4.8
| Staire Case area | 1 | 1 | 4.2 | 4.2 |  | 17.64
[7 empty] | 388.5646 | Sqm

## Abstract
DETAILED MEASUREMENTS
| Name of the work:Design, Fabriction, establishing and commissioning of In - Vitro ferility centers (IVFC) alongwith allied Services on Turnkey basis at Gandhi hospital secunderabad. | [6 empty] | Agency: M/s. Asta Sudha Consortium | [5 empty] | Agt.No:
Date Of Measurement | Discription Of Work etc., | Measurements Upto date | [6 empty] | Per | Total Volume |  | Deduct/previous Measurements |  | Since last measurement |  |  | Remarks
|  | No | L | B | D | Content | Rs | Ps. |  | Rs. | Ps | P.No. | Qty. | Qty | Value
[15 empty] | Rs. | Ps.
Dismantling, clearing away and carefully stacking useful materials for re-use and disposal of unserviceable materials with 100m lead as directed by Executive Engineer duly taking actual premeasurements before dismantling including all labour charges , overheads & contractor profit etc., complete (Brick Masonary)
| V.P MB No 01 |  |  |  |  | 31.21 | 900 | Cum | 28089
Old Cement Morter
| V.P MB No 01 |  |  |  |  | 31.05 |  | Sqm
Unreinforcement Cement More Than 15cm
| V.P MB No 01 |  |  |  |  | 3.89 | 4500 | Cum | 17505
Reinforcement Cement
| V.P MB No 01 |  |  |  |  | 31.05 | 5400 | Cum | 167670
Dismantling doors, windows and clear storey windows, Ventilators etc., (wood or steel) shutters including Chowkhats, architraves,hold fasts and other attachments etc., and stacking them within 100m lead including labour charge etc., and overheads & contractors profit complete for finished item of work.
| V.P MB No 01 |  |  |  |  | 7 | 206 | Each | 1442
Masonry work in CM (1:6) prop (cement: Screened sand) in super structure with / lime solid blocks of size 290mmx225mmx140mm from approved source having minimum crushing strength of 50 Kg/Sqcm including cost and conveyance of all materials like cement, sand, bricks, water etc., to site, including sales & other taxes on all materials, all operational, incidental and labour charges such as mixing cement mortar, constructing masonry, scaffolding charges, lift charges, curing, etc., complete but excluding seigniorage charges for finished item of work. (APSS No. 501 & 504).
| V.P MB No 01 |  |  |  |  | 9.0307 | 15300 | Cum | 138170.016
Reinforced brick Masonry for Partition Walls (11.0 cm thick) in CM (1:4) prop (cement: Screened sand) in super structure with / lime solid blocks of size 290mmx225mmx140mm from approved source having minimum crushing strength of 50 Kg/Sqcm including cost and conveyance of all materials like cement, sand, bricks, water etc., to site, including sales & other taxes on all materials, all operational, incidental and labour charges such as mixing cement mortar, constructing masonry, scaffolding charges, lift charges, curing, etc., complete but excluding seigniorage charges for finished item of work. (APSS No. 501 & 504).
| V.P MB No 01 |  |  |  |  | 191.2055 | 2700 | Sqm | 516254.85
Providing Thermo Mechanically Treated ( TMT) ( Fe-500/500D/550D from primery producer TATA, SAIL, VSP, JSW Steel, Goel steel, Jindal panther, X- Vega & balaji Shakthi as per IS 1786-2008) of Different Diameters RCC Works , including labour charges for straightening, cutting, bending to required sizes and shapes, placing in position with cover blocks of approved materials and sizes and typing and lap - spacing with binding wire of 18 SWG, Forming grills for reinforcement work as per approved design and drawings, including and conveyanace of steel bars, including all wastages such as overlaps, coupling, chairs, spacer bars including cost and conveyance of binding wire cover blocks and incidential, operational, labour charges such as cutting bending, placing in position, typing incliding sales and other taxes on all materials etc., and overheads & contractors profit completefor finished item of work
| V.P MB No 01 |  |  |  |  | 0.10359 | 126000 | MT | 13052.592
Supply and placing of the Design Mix Concrete M 25 grade corresponding to IS 456 with minimum cement content of 380 kgs per 1 cum of concrete using Weight Batcher / Concrete mixer with 20mm size graded machine crushed hard granite metal (coarse aggregate - as per IS 383 - 1970 and IS 2386 Part 1 to Part 8) from approved quarry including cost and conveyance of all materials like cement, fine aggregate (sand) coarse aggregate, water etc., to site and sales & other taxes on all materials, centering using Casurina Ballies, Bamboos, Wooden Reapers, Runners, Wood Posts, Steel Plates etc., including all operational, incidental and labour charges such as weigh batching, machine mixing, lifting of concrete manually, laying concrete, curing , overheads & contractors profit etc., complete but excluding cost of steel and its fabrication charges for finished item of work (APSS No. 402) (For Lintels)
| V.P MB No 01 |  |  |  |  | 0.4 | 18900 | Cum | 7560
Plastering 12mm thick in two coats using screened sand with base coat of 8mm thick in CM (1:6) and top coat of 4mm thick in CM (1:4) with dubara sponge finishing including cost and conveyance of all materials like cement, sand, water etc., to site, including sales & other taxes on all materials, and all operational, incidental charges on materials and including cost of all labour charges for mixing mortar, finishing, scaffolding, lift charges, curing, including cutting grooves as directed by Engineer-in-charge etc., and overheads & contractors profit complete for finished item of work. (SS 901,903 & 904).
| V.P MB No 01 |  |  |  |  | 536.1091 | 1224 | Sqm | 656197.4772
Providing and applying Wall putty of White Cement or Polymer or Cement based of average 1 to 2 mm thickness over plastered surface to prepare the surface even and smooth after thoroughly brushing the surface to remove all dirt and remains of loose powdered materials, applying emery paper, Sand the surface, clean & wipe off loose dust, applying knifing paste filler by putty knife / muslin pad, air dry for 2 - 3 hrs, sand with 180 and 320 No., emery paper for the surface preparation including cost and conveyance of all materials to work site and all operational, incidental, labour charges, over heads and contractors profit etc., complete for finished item of work in all floors for Internal walls.
| V.P MB No 01 |  |  |  |  | 917.8539 | 270 | sqm | 247820.553
White washing two coats with white cement to ceiling to give an even shade after thouroughly brushing the surface to remove all dirt and remains of loose powdered materials including cost of all materials, labour charges and incidental such as scaffolding, lift charges etc., and overheads & contractors profit complete for finished item of work in all floors.
| V.P MB No 01 |  |  |  |  | 782.3034 | 250 | Sqm | 195575.85
Flooring With 16 to 18 mm thick high polished granite stone slabs black colour for plotforms (s.s. 701 and specila)
| V.P MB No 01 |  |  |  |  | 13.07 | 6300 | Sqm | 82341
Flooring with non- skid fully body ceramic floor tiles
| V.P MB No 01 |  |  |  |  | 410.7296 | 1710 | Sqm | 702347.7015
Dadooing to walls with glazed fully body porceiain wall tiles
| V.P MB No 01 |  |  |  |  | 103.766 | 1440 | Sqm | 149423.04
Flase Ceiling as per Technical Specification
| V.P MB No 01 |  |  |  |  | 388.5646 | 1800 | Sqm | 699416.37
[6 empty] | Grand Total |  |  | 3622865.4497
[6 empty] | Sub Total |  |  | 3622865.4497
[6 empty] | Add GST @ 18% |  |  | 652116
[6 empty] | Grand Total |  |  | 4274981.4497