## Sheet1
IVF - Warangal
S.No | Description of item | Quantity as per BOQ | Actual Quantity | Variation | Unit of Measurment
1 | Supplying and fixing 15 mm brass body CP finish bib tap of not less than 300 grams weight screw type full turn with internal / external threaded connection conforming to IS 8931 | 4 | 5 | 1 | Nos
2 | Supplying and fixing of 4inches 101.6mm multi floor trap with jali - UPVC/SWR pipe fittings as per site requirements with standard practice for all floors | 8 | 5 | -3 | Nos
3 | Supplying and fixing Indian make Flat Back Wash Hand Basin 1st quality conforming to IS:2556-Part-4:1972 of size 550mm x 400mm with 32 mm nominal size C.P. Fitting with parallel pipe thread conforming to IS:2963- 1979 and fitted with 15 mm nominal bore Chromium Plated Pillar Tap of 1st quality Indian make heavy duty complete with standard CI brackets including wooden blocks ,1 No.12.70mm PVC connection with brass union nuts CP coated , angle stop cock 12.70mm dia. first quality Indian make heavy duty, 30mm dia. PVC flexible waste pipe 914.4mm length of 1st quality | 4 | 5 | 1 | Nos
4 | Supply, Installation and commissioning approved make floor mounted Anglo Indian wash down EWC conforming to IS:2556 Part 8-2004 suit with P or S trap with dual flush porcelain cistern fixed on wash down EWC with all internal parts of dual flush cistern, ultra solid seat cover of approved make with rubber buffer and cap and 15 mm angle stop cock and 450 mm long PVC inter connection pipe wall flanges all of approved make etc. complete for finished item of work in all respects: TBSP-E.II-03 | 4 | 5 | 1 | Nos
5 | Supplying and fixing Chromium plated finish brass body quarter turn Bibcock cum Health Faucet with 1m long tube and wall hook with necessary fittings | 4 | 5 | 1 | Nos
6 | Supplying and fixing CP finish brass soap dish of approved make ISI quality | 4 | 5 | 1 | Nos
7 | Supplying and fixing TV shape mirror with plastic frame of size 609.6mm x 457.2mm, plywood back with NP screws 1st quality | 4 | 5 | 1 | Nos
8 | Supplying and fixing of CP finish brass wall mounted towel ring | 4 | 5 | 1 | Nos
9 | Supplying and fixing 15 mm brass body CP finish self closing tap push type conforming to IS 1711 | 4 | 5 | 1 | Nos