## IVF-Gandhi
PAYMENTS
S.No | Company Name | Equipment Category |  | Purchase Order Value |  |  |  | Payment 1 |  | Payment 2 |  | Payment 3 |  | Payment 4 |  | Net Amount Paid
[8 empty] | Advance |  | Readiness of Material |  | Delivey |  | Installation
|  |  |  | Actual Amount | GST % | GST Amount | Total Amount | Amount Paid | Date Of Payment | Amount Paid | Date Of Payment | Amount Paid | Date Of Payment | Amount Paid | Date of Pyment
1 | VJ Engineers | HVAC | High Side | 748451 | 28 | 209566.28 | 2503021.96 | 665000 | 2023-08-11 | [6 empty] | 665000
|  |  | Low Side | 1309326 | 18 | 235678.68
2 | VELIND | ELV | Acces Control System | 107900 | 18 | 19422 | 1387072.3 | 400000 | 2023-08-11 | [6 empty] | 400000
|  |  | CCTV | 139725 | 18 | 25150.5
|  |  | Counselling Room | 134730 | 18 | 24251.4
|  |  | DATA | 225000 | 18 | 40500
|  |  | Fire Extinguisher | 123150 | 18 | 22167
|  |  | Fire Detection & Alarm | 414405 | 18 | 74592.9
|  |  | Voice | 30575 | 18 | 5503.5
|  |  | Total | 1175485 |  | 211587.3
3 | Blue Space Medical Systems | Medical |  | 9496460 |  | 0 | 23135195 | 3500000 | 2023-07-20 | 2000000 | 2023-08-17 |  |  |  |  | 5500000
|  |  |  | 13638735 |  | 0
4 | Comfort Cool Care Systems | VRV | High Side | 686242 | 28 | 192147.76 | 1440482.76 | 574795 | 2023-08-05 | 356279 | 2023-08-17 |  |  |  |  | 931074
|  |  | Low Side | 476350 | 18 | 85743
5 | APS Tech | UPS | UPS | 312000 | 18 | 56160 | 576086.08 | 115404 | 2023-08-17 | [6 empty] | 115404
|  |  | MS Rack & Cables | 14000 | 18 | 2520
|  |  | Batteries | 149536 | 28 | 41870.08
6 | Wooden Doors
7 | HPL Partitions
8 | Electrical
9 | Civil
Delivey+T32Q14:Q41

## IVF_PBJ
PAYMENTS PETLABURJ
S.No | Company Name | Category |  | Purchase Order Value |  |  |  | Payment 1 |  | Payment 2 |  | Payment 3 |  | Payment 4 |  | Amount to be Paid (Pending Amount) | Net Amount Paid
[8 empty] | Advance |  | Readiness of Material |  | Delivey |  | Installation
|  |  |  | Basic Amount | GST % | GST Amount | Total Amount | Amount Paid | Date Of Payment | Amount Paid | Date Of Payment | Amount Paid | Date Of Payment | Amount Paid | Date of Pyment
1 | VJ ENGINEERS | HVAC | High Side | 1069354 | 28 | 299419.12 | 1368773.12 | 667920 | 2024-01-03 | [6 empty] | 700853.12 | 667920
|  |  | Low Side | 1225322 | 18 | 220557.96 | 1445879.96 | 300000 | 2024-01-03 | [6 empty] | 1145879.96 | 300000
2 | COMFORT COOL CARE SERVICES | VRV LG | High Side | 837034 |  | 227966 | 1065000 | 430000 | 2024-01-03 | [6 empty] | 635000 | 430000
|  |  | Low Side | 377120 | 18 | 67881.6 | 445001.6 | 133500 | 2023-12-06 | [6 empty] | 311501.6 | 133500
3 | AHLADHA CLEAN ROOM TECH | Paneling, Air Shower, SPB |  | 1665447 | 18 | 299780.46 | 1965227.46 | 400000 | 2024-01-03 | [6 empty] | 1565227.46 | 400000
4 | BHARGAVI ENTERPRISES | ABS DOORS |  | 406741 |  | 0 | 406741 | 160000 | 2024-01-03 | [6 empty] | 246741 | 160000
5 | APS TECH | UPS |  |  |  | 0 | 0 | [8 empty] | 0 | 0 | Delivey+T32Q14:Q41
6 | PRAKASH MARKETING | HINDWARE |  |  |  | 0 | 0 | [8 empty] | 0 | 0
7 | GAS TECH | MGPS |  |  |  | 0 | 0 | [8 empty] | 0 | 0
8 | VELIND VIRTUAL SYSTEMS | ELV |  | 1175485 | 18 | 211587.3 | 1387072.3 | [8 empty] | 1387072.3 | 0
[6 empty] | 0 | 0 | [8 empty] | 0 | 0
| SUM |  |  |  |  | 0 | 0 | 2091420 |  | 0 |  | 0 |  | 0 |  | 5992275.44 | 2091420

## IVF_PBJ-02
PAYMENTS PETLABURJ
S.No | Company Name | Category |  | Purchase Order Value |  |  |  | Payment Terms (%) |  |  |  | Payment 1 | Payment 2 | Payment 3 | Payment 4 | Total Amount
[12 empty] | Advance | Readiness of Material | Delivey | Installation
|  |  |  | Basic Amount | GST % | GST Amount | Total Amount | 1 | 2 | 3 | 4 | Amount to be Paid | Amount to be Paid | Amount to be Paid | Amount to be Paid
1 | VJ ENGINEERS | HVAC | High Side | 1069354 | 28 | 299419.12 | 1368773.12 | 25 | 30 | 35 | 10 | 342193.28 | 410631.936 | 479070.592 | 136877.312 | 2814653.08
|  |  | Low Side | 1225322 | 18 | 220557.96 | 1445879.96 | 25 | 30 | 35 | 10 | 361469.99 | 433763.988 | 506057.986 | 144587.996
2 | COMFORT COOL CARE SERVICES | VRV LG | High Side | 837034 |  | 227966 | 1065000 | 40 | 50 | 10 |  | 426000 | 532500 | 106500 | 0 | 1510001.6
|  |  | Low Side | 377120 | 18 | 67881.6 | 445001.6 | 30 | 60 | 10 |  | 133500.48 | 267000.96 | 44500.16 | 0
3 | AHLADHA CLEAN ROOM TECH | Paneling, Air Shower, SPB |  | 1665447 | 18 | 299780.46 | 1965227.46 | 20 | 70 | 10 |  | 393045.492 | 1375659.222 | 196522.746 | 0 | 1965227.46
4 | BHARGAVI ENTERPRISES | ABS DOORS |  | 406741 |  | 0 | 406741 | 40 | 50 | 10 |  | 162696.4 | 203370.5 | 40674.1 | 0 | 406741
5 | APS TECH | UPS |  |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | Delivey+T32Q14:Q41
6 | PRAKASH MARKETING | HINDWARE |  |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
7 | GAS TECH | MGPS |  |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
8 | VELIND VIRTUAL SYSTEMS | ELV |  | 1175485 | 18 | 211587.3 | 1387072.3 | 30 | 60 | 10 |  | 416121.69 | 832243.38 | 138707.23 | 0 | 1387072.3
[6 empty] | 0 | 0
| SUM |  |  |  |  | 0 | 0 |  |  |  |  | 2235027.332 | 4055169.986 | 1512032.814 | 281465.308 | 8083695.44

## Sheet3
PETLABURJ WORKS PROGRESS
1 | Sandeep | Vinyl Flooring
WPC Doors
False Ceiling
Pre Coat Painting
Post Coat Painting
2 | Velind | Pre False Ceiling Works
Post False Ceiling Works
3 | MGPS | Pre False Ceiling Works
Post False Ceiling Works
4 | HVAC | Ducting
Completion
5 | Comfort cool | VRV
6 | Ahladha | Paneling, Air Shower, Pass Box
7 | Bhargavi Enterprises | ABS doors
8 | Hardware
9 | Sanitary
10 | CP Fittings
11 | HPL Partitions
12 | APS Tech | UPS