## Gandhi hospital Hyderabad MOT
BAR CHART for Balance Works at SOTC 8th Floor, Gandhi Hospital, Hyderabad (Considering Additional 2 OTs) | [67 empty] | Date : | 2023-12-15
S.no | ITEM CATEGORY | ITEM DESCRIPTION | 2023-01-13 | To | 2023-02-08 | 2023-02-09 | To | 2023-03-06 | 2023-03-07 | To | 2023-04-01 | 2023-04-02 | To | 2023-04-27 | 2023-04-28 | To | 2023-05-23 | 2023-05-24 | To | 2023-06-18 | 2023-06-19 | To | 2023-07-14 | 2023-07-15 | To | 2023-08-09 | 2023-08-10 | To | 2023-09-04 | 2023-09-05 | To | 2023-09-30 | 2023-10-01 | To | 2023-10-26 | 2023-10-27 | To | 2023-11-21 | 2023-11-22 | To | 2023-12-20 | To | 2024-01-14 | 2024-01-15 | To | 2024-02-09 | 2024-02-11 | To | 2024-03-06 | MILESTONE 1 | 2024-03-07 | To | 2024-04-01 | 2024-04-02 | To | 2024-04-27 | 2024-04-28 | To | 2024-05-23 | MILESTONE 2 | 2024-05-24 | to | 2024-06-18 | 2024-06-19 | to | 2024-06-25 | COMPLETION | Start Date | Completion date
NOTIFICATION OF AWARD
AGREEMENT ON
SITE HANDOVER
| SHIFTING OF ELECTRICAL SOLAR PANELS ON TERRACE | Scope of TSMSIDC
TERRACE WATER PROOFING
SUBMISSSION OF PRILIMINARY LAYOUT DRAWINGS
LAYOUT APPROVAL
MOBILISATION
1 | DEMOLITION & REMOVAL | LINTELS | [65 empty] | 2023-12-20 | 2023-12-25
|  | BRICKWORK | [65 empty] | 2023-12-20 | 2023-12-25
2 | CIVIL WORKS | LINTELS | [65 empty] | 2023-12-20 | 2023-12-23
|  | BRICKWORK | [65 empty] | 2023-12-26 | 2024-01-15
|  | SPLIT AC's PIPING PROVISION | [65 empty] | 2023-12-24 | 2024-01-14
|  | PLASTERING | [65 empty] | 2024-01-15 | 2024-02-09
|  | DADOING | [65 empty] | 2024-02-11 | 2024-03-07
|  | WALL PUTTY | [65 empty] | 2024-02-20 | 2024-03-07
|  | SUPPLY &FIXING OF DOOR FRAMES & WINDOWS | [65 empty] | 2024-03-07 | 2024-03-31
|  | FALSE CEILING | [65 empty] | 2024-03-06 | 2024-04-27
|  | PCGI PANELING | [65 empty] | 2024-03-07 | 2024-04-27
|  | SCIENTIFIC DOORS & WOODEN DOORS | [65 empty] | 2024-04-02 | 2024-05-10
|  | FLOOR LEVELLING | [65 empty] | 2024-04-28 | 2024-05-23
|  | VINYL FLOORING | [65 empty] | 2024-05-24 | 2024-06-17
3 |  | CCTV CEILING CAMERA | [65 empty] | 2024-04-27 | 2024-05-23
4 | TOILETS | CP FITTINGS | [65 empty] | 2024-03-07 | 2024-03-31
|  | DOOR SHUTTERS | [65 empty] | 2024-04-02 | 2024-05-10
|  | EXHAUST FANS | [65 empty] | 2024-03-07 | 2024-03-31
5 | ELECTRICAL | DB's & MCB's | [65 empty] | 2023-12-20 | 2024-01-14
|  | POWER CABLES FOR DSU's | [65 empty] | 2024-01-15 | 2024-03-06
|  | DSU DUCTING | [65 empty] | 2024-12-25 | 2024-02-20
|  | ELECTRICAL PANELS | [65 empty] | 2024-04-02 | 2024-05-23
|  | A/C's & DSU's ODU | [65 empty] | 2023-12-25 | 2024-02-29
|  | ELECTRICAL SWITCH BOARDS | [65 empty] | 2024-03-06 | 2024-04-27
6 | UPS | SUPPLY OF UPS & RACKS | [65 empty] | 2024-04-02 | 2024-05-23
|  | SUPPLY OF BATTERIES | [65 empty] | 2024-04-28 | 2024-05-23
|  | INSTALLATION | [65 empty] | 2024-05-24 | 2024-06-17
7 | ELV | LAN | [65 empty] | 2024-02-09 | 2024-03-31
|  | VOICE | [65 empty] | 2024-02-11 | 2024-04-10
|  | ACCESS CONTROL | [65 empty] | 2024-06-17 | 2024-06-25
|  | FIRE SYSTEM | [65 empty] | 2024-05-24 | 2024-06-17
8 | TRANSFORMER | SUPPLY | [65 empty] | 2024-04-28 | 2024-05-23
|  | TRENCHING & CABLING | [65 empty] | 2024-03-07 | 2024-04-27
|  | CIRCUIT BRAKER | [65 empty] | 2024-05-23 | 2024-05-30
|  | COMISSIONING | [65 empty] | 2024-05-30 | 2024-06-10
9 | LIFT | FOUNDATION
|  | STRUCTURE ERECTION | [65 empty] | 2024-01-14 | 2024-03-31
|  | SUPPLY & INSTALLATION | [65 empty] | 2024-04-02 | 17-062024
10 |  | SITC of Aluminium Ducting | [65 empty] | 2023-12-25 | 2024-01-20
11 |  | SITC of Uni Directional Ceiling Laminar Airflow Systems & In TIR Corridor | [65 empty] | 2023-12-20 | 2024-03-30
12 |  | SITC of Stainless Steel Pre-fabricated Wall panels | [65 empty] | 2023-12-20 | 2024-03-30
13 |  | SITC of Stainless Steel Pre-fabricated Ceiling panels In MOTs & MOTs Corridor & in TIRs and TIR Corridor | [65 empty] | 2023-12-20 | 2024-03-30
14 |  | SITC of Storage Units | [65 empty] | 2024-01-14 | 2024-01-15
15 |  | SITC of Electrical Installations in MOTs & TIRs | [65 empty] | 2023-12-25 | 2024-01-30
16 |  | SITC of Dynamic Hatch Box | [65 empty] | 2023-02-15 | 2024-03-30
17 |  | SITC of Electro conductive Flooring inside MOTs & inside TIRs& TIR Corridor | [65 empty] | 2024-03-10 | 2024-04-15
18 |  | SITC of Flooring with Vinyl Sheets In MOT Corridor & In TIR Corridor | [65 empty] | 2024-03-10 | 2024-04-15
19 |  | SITC of Hermetically Sealed Doors | [65 empty] | 2024-04-30 | 2024-05-17
20 |  | SITC of Pressure Relief Dampers | [65 empty] | 2024-04-05 | 2024-04-15
21 |  | SITC of LED Peripheral Lights cum clean room (OT) luminaries | [65 empty] | 2024-04-05 | 2024-04-15
22 |  | SITC of View Window | [65 empty] | 2024-04-05 | 2024-04-15
23 |  | SITC of Writing Board | [65 empty] | 2024-04-05 | 2024-04-15
24 |  | SITC of X-Ray CT Scan LED viewing Screen | [65 empty] | 2024-04-05 | 2024-04-15
25 |  | SITC of Touch Screen Surgeon Control Panels | [65 empty] | 2024-04-05 | 2024-04-15
26 |  | SITC of 3-Bay Scrub Stations/Sinks | [65 empty] | 2024-04-05 | 2024-04-15
27 |  | SITC of Medical Gas pipeline Installation Inside MOT | [65 empty] | 2024-04-03 | 2024-04-30
28 |  | SITC of 12mm thick glazed Glass partition walls in TIRs | [65 empty] | 2024-04-01 | 2024-04-10
29 |  | SITC of Single & Double arm Anesthesia Pendants (Imported) | [65 empty] | 2024-05-25 | 2024-05-15
30 |  | SITC of Triple Dome Ceiling OT LED Lights (Imported) | [65 empty] | 2024-05-25 | 2024-05-15
31 |  | SITC of Double Dome Ceiling OT LED Lights (Imported) | [65 empty] | 2024-05-25 | 2024-05-15
32 |  | SITC of Detachable Hi Definition Cameras in Triple Dome Ceiling OT Lights | [65 empty] | 2024-05-25 | 2024-05-15
33 |  | SITC of Medical Grade Monitors 32 inch 4 K Resolution | [65 empty] | 2024-05-25 | 2024-05-15
34 |  | SITC of Air Handling Units (AHUs) | [65 empty] | 2024-04-29 | 2024-05-25
35 |  | SITC of Condensing Units | [65 empty] | 2024-04-29 | 2024-05-25
37 |  | SITC of Wall mounted large screen display 55 inch | [65 empty] | 2024-04-29 | 2024-05-15
38 |  | Supply of Wireless Microphones | [65 empty] | 2024-04-29 | 2024-05-15
39 |  | Supply of Digital Mixer Amplifier | [65 empty] | 2024-04-29 | 2024-05-15
40 |  | Supply of Ceiling Mounted Speakers | [65 empty] | 2024-04-29 | 2024-05-15
41 |  | Supply of Video Conferencing Systems | [65 empty] | 2024-04-29 | 2024-05-15
42 |  | Supply of Hifi Active Sub Woofer | [65 empty] | 2024-04-29 | 2024-05-15
43 |  | Supply of Equalization & Loud Speaker Control System | [65 empty] | 2024-04-29 | 2024-05-15
44 |  | Supply of Sound Analog Mixer | [65 empty] | 2024-04-29 | 2024-05-15
45 |  | Supply of Wall Mounted LED TV 43 Inches Full HD | [65 empty] | 2024-04-29 | 2024-05-15
46 |  | Supply of Home Theatre Power Conditioner, 230V | [65 empty] | 2024-04-29 | 2024-05-15
47 |  | Supply of Amplifier (8 Channel) | [65 empty] | 2024-04-29 | 2024-05-15
48 |  | Supply of Ceiling/Wall Mounted CCTV Room camera | [65 empty] | 2024-04-29 | 2024-05-15
49 |  | Testing & Commissioning | [65 empty] | 2024-05-24 | 2024-06-18
50 |  | Handover | [65 empty] | 2024-06-18 | 2024-06-25