## Gandhi hospital Hyderabad MOT
BAR CHART for Balance Works at SOTC 8th Floor, Gandhi Hospital, Hyderabad (Considering Additional 2 OTs) | [91 empty] | Date : | 2024-03-20
S.No | ITEM CATEGORY | ITEM DESCRIPTION | 2023-01-13 | To | 2023-02-08 | 2023-02-09 | To | 2023-03-06 | 2023-03-07 | To | 2023-04-01 | 2023-04-02 | To | 2023-04-27 | 2023-04-28 | To | 2023-05-23 | 2023-05-24 | To | 2023-06-18 | 2023-06-19 | To | 2023-07-14 | 2023-07-15 | To | 2023-08-09 | 2023-08-10 | To | 2023-09-04 | 2023-09-05 | To | 2023-09-30 | 2023-10-01 | To | 2023-10-26 | 2023-10-27 | To | 2023-11-21 | 2023-11-22 | To | 2023-12-20 | To | 2024-01-14 | 2024-01-15 | To | 2024-02-09 | 2024-02-11 | To | 2024-03-06 | 2024-03-07 | To | 2024-03-14 | MILESTONE 1 | 2024-03-15 | To | 2024-04-01 | 2024-04-02 | To | 2024-04-16 | 2024-04-17 | To | 2024-04-30 | 2024-05-01 | to | 2024-05-15 | 2024-05-16 | to | 2024-06-01 | 2024-06-02 | to | 2024-06-15 | MILESTONE 2 | 2024-06-16 | to | 2024-06-30 | 2024-07-01 | to | 2024-07-15 | 2024-07-16 | to | 2024-07-31 | 2024-08-01 | to | 2024-08-15 | 2024-08-16 | to | 2024-08-31 | 2024-09-01 | to | 2024-09-15 | COMPLETION | Start Date | Completion date
NOTIFICATION OF AWARD
AGREEMENT ON
SITE HANDOVER
| SHIFTING OF ELECTRICAL SOLAR PANELS ON TERRACE | Scope of TSMSIDC
TERRACE WATER PROOFING
SUBMISSSION OF PRILIMINARY LAYOUT DRAWINGS
LAYOUT APPROVAL
MOBILISATION
1 | DEMOLITION & REMOVAL | Lintels | [89 empty] | 2023-12-20 | 2023-12-25
|  | Brickwork | [89 empty] | 2023-12-20 | 2023-12-25
2 | CIVIL WORKS | Lintels | [89 empty] | 2023-12-20 | 2023-12-23
|  | Brickwork | [89 empty] | 2023-12-26 | 2024-01-15
|  | Split Ac's Piping Provision | [89 empty] | 2023-12-24 | 2024-01-14
|  | Plastering | [89 empty] | 2024-01-15 | 2024-02-09
|  | Dadoing | [89 empty] | 2024-02-11 | 2024-03-07
|  | Wall Putty | [89 empty] | 2024-02-20 | 2024-03-07
|  | Supply &Fixing of Door Frames & Windows | [89 empty] | 2024-03-07 | 2024-03-31
|  | False Ceiling | [89 empty] | 2024-03-06 | 2024-04-27
|  | PCGI Paneling | [89 empty] | 2024-03-07 | 2024-04-27
|  | Scientific Doors & Wooden Doors | [89 empty] | 2024-04-02 | 2024-05-10
|  | Floor Levelling | [89 empty] | 2024-04-28 | 2024-05-23
|  | Vinyl Flooring | [89 empty] | 2024-05-24 | 2024-06-17
3 | TOILETS | Cp Fittings | [89 empty] | 2024-03-07 | 2024-03-31
|  | Door Shutters | [89 empty] | 2024-04-02 | 2024-05-10
|  | Exhaust Fans | [89 empty] | 2024-03-07 | 2024-03-31
4 | ELECTRICAL | Point Wiring
|  | DB's & Mcb's | [89 empty] | 2023-12-20 | 2024-01-14
|  | Power Cables For Dsu's | [89 empty] | 2024-01-15 | 2024-03-06
|  | DSU's Ducting | [89 empty] | 2024-12-25 | 2024-02-20
|  | Electrical Panels | [89 empty] | 2024-04-02 | 2024-05-23
|  | A/C's & Dsu's Odu | [89 empty] | 2023-12-25 | 2024-02-29
|  | Electrical Switch Boards | [89 empty] | 2024-03-06 | 2024-04-27
5 | UPS | Supply Of Ups & Racks | [89 empty] | 2024-04-02 | 2024-05-23
|  | Supply Of Batteries | [89 empty] | 2024-04-28 | 2024-05-23
|  | Installation | [89 empty] | 2024-05-24 | 2024-06-17
6 | ELV | Lan | [89 empty] | 2024-02-09 | 2024-03-31
|  | Voice | [89 empty] | 2024-02-11 | 2024-04-10
|  | Access Control | [89 empty] | 2024-06-17 | 2024-06-25
|  | Cctv Ceiling Camera | [89 empty] | 2024-04-27 | 2024-05-23
|  | Fire System | [89 empty] | 2024-05-24 | 2024-06-17
7 | ELECTRICAL CONTROL ROOM | Main Cabel from Exisiting Transformer
Panels Fixing
Cabelling
Connections
Terminations
8 | TRANSFORMER | Supply | [89 empty] | 2024-04-28 | 2024-05-23
|  | Trenching & Cabling | [89 empty] | 2024-03-07 | 2024-04-27
|  | Circuit Braker | [89 empty] | 2024-05-23 | 2024-05-30
|  | Comissioning | [89 empty] | 2024-05-30 | 2024-06-10
9 | DG Set | Supply
Commissioning
10 | Acoustic Panelling | Wall Preparation
Erection of Panels
Installation
11 | Wooden Flooring | Self Levelling
Laying of Engineered wood
Finishing
12 | LIFT Structure | Foundation
|  | Structure Erection | [89 empty] | 2024-01-14 | 2024-03-31
|  | Supply & Installation | [89 empty] | 2024-04-02 | 17-062024
13 | RO Plant | Supply
Wall Chasing
Laying of PEX Pipe & drain lines
Installation of RO
15 | Water Proofing | Surface Preparation
Groving & Cleaning
Applying Chemical
Terrace Coving
External Walls Cleaning & Application Water Proof Paint
16 | Terrace AHU & RO Shed | Installation
17 |  | SITC of Aluminium Ducting | [89 empty] | 2023-12-25 | 2024-01-20
18 |  | SITC of Uni Directional Ceiling Laminar Airflow Systems & In TIR Corridor | [89 empty] | 2023-12-20 | 2024-03-30
19 |  | SITC of Stainless Steel Pre-fabricated Wall panels | [89 empty] | 2023-12-20 | 2024-03-30
20 |  | SITC of Stainless Steel Pre-fabricated Ceiling panels In MOTs & MOTs Corridor & in TIRs and TIR Corridor | [89 empty] | 2023-12-20 | 2024-03-30
21 |  | SITC of Storage Units | [89 empty] | 2024-01-14 | 2024-01-15
22 |  | SITC of Electrical Installations in MOTs & TIRs | [89 empty] | 2023-12-25 | 2024-01-30
23 |  | SITC of Dynamic Hatch Box | [89 empty] | 2023-02-15 | 2024-03-30
24 |  | SITC of Electro conductive Flooring inside MOTs & inside TIRs& TIR Corridor | [89 empty] | 2024-03-10 | 2024-04-15
25 |  | SITC of Flooring with Vinyl Sheets In MOT Corridor & In TIR Corridor | [89 empty] | 2024-03-10 | 2024-04-15
26 |  | SITC of Hermetically Sealed Doors | [89 empty] | 2024-04-30 | 2024-05-17
27 |  | SITC of Pressure Relief Dampers | [89 empty] | 2024-04-05 | 2024-04-15
28 |  | SITC of LED Peripheral Lights cum clean room (OT) luminaries | [89 empty] | 2024-04-05 | 2024-04-15
29 |  | SITC of View Window | [89 empty] | 2024-04-05 | 2024-04-15
30 |  | SITC of Writing Board | [89 empty] | 2024-04-05 | 2024-04-15
31 |  | SITC of X-Ray CT Scan LED viewing Screen | [89 empty] | 2024-04-05 | 2024-04-15
32 |  | SITC of Touch Screen Surgeon Control Panels | [89 empty] | 2024-04-05 | 2024-04-15
33 |  | SITC of 3-Bay Scrub Stations/Sinks | [89 empty] | 2024-04-05 | 2024-04-15
34 |  | SITC of Medical Gas pipeline Installation Inside MOT | [89 empty] | 2024-04-03 | 2024-04-30
35 |  | SITC of 12mm thick glazed Glass partition walls in TIRs | [89 empty] | 2024-04-01 | 2024-04-10
36 |  | SITC of Single & Double arm Anesthesia Pendants (Imported) | [89 empty] | 2024-05-25 | 2024-05-15
37 |  | SITC of Triple Dome Ceiling OT LED Lights (Imported) | [89 empty] | 2024-05-25 | 2024-05-15
38 |  | SITC of Double Dome Ceiling OT LED Lights (Imported) | [89 empty] | 2024-05-25 | 2024-05-15
39 |  | SITC of Detachable Hi Definition Cameras in Triple Dome Ceiling OT Lights | [89 empty] | 2024-05-25 | 2024-05-15
40 |  | SITC of Medical Grade Monitors 32 inch 4 K Resolution | [89 empty] | 2024-05-25 | 2024-05-15
41 |  | SITC of Air Handling Units (AHUs) | [89 empty] | 2024-04-29 | 2024-05-25
42 |  | SITC of Condensing Units | [89 empty] | 2024-04-29 | 2024-05-25
43 |  | SITC of Wall mounted large screen display 55 inch | [89 empty] | 2024-04-29 | 2024-05-15
44 |  | Supply of Wireless Microphones | [89 empty] | 2024-04-29 | 2024-05-15
45 |  | Supply of Digital Mixer Amplifier | [89 empty] | 2024-04-29 | 2024-05-15
46 |  | Supply of Ceiling Mounted Speakers | [89 empty] | 2024-04-29 | 2024-05-15
47 |  | Supply of Video Conferencing Systems | [89 empty] | 2024-04-29 | 2024-05-15
48 |  | Supply of Hifi Active Sub Woofer | [89 empty] | 2024-04-29 | 2024-05-15
49 |  | Supply of Equalization & Loud Speaker Control System | [89 empty] | 2024-04-29 | 2024-05-15
50 |  | Supply of Sound Analog Mixer | [89 empty] | 2024-04-29 | 2024-05-15
51 |  | Supply of Wall Mounted LED TV 43 Inches Full HD | [89 empty] | 2024-04-29 | 2024-05-15
52 |  | Supply of Home Theatre Power Conditioner, 230V | [89 empty] | 2024-04-29 | 2024-05-15
53 |  | Supply of Amplifier (8 Channel) | [89 empty] | 2024-04-29 | 2024-05-15
54 |  | Supply of Ceiling/Wall Mounted CCTV Room camera | [89 empty] | 2024-04-29 | 2024-05-15
55 |  | Testing & Commissioning | [89 empty] | 2024-05-24 | 2024-06-18
56 |  | Handover | [89 empty] | 2024-07-01 | 2024-07-15