## SOTC BAR CHART
BAR CHART for Balance Works at SOTC 8th Floor, Gandhi Hospital, Hyderabad (Considering Additional 2 OTs)
[82 empty] | MILE STONE -01 | [11 empty] | MILE STONE -02 | [11 empty] | MILESTONE -03 | [11 empty] | REVISED WORK SCHEDULE
S.no | ITEM CATEGORY | ITEM DESCRIPTION | 2023-01-13 | To | 2023-01-28 | 2023-01-29 | To | 2023-02-13 | 2023-02-14 | To | 2023-03-01 | 2023-03-02 | To | 2023-03-17 | 2023-03-18 | To | 2023-04-02 | 2023-04-03 | To | 2023-04-18 | 2023-04-19 | To | 2023-05-04 | 2023-05-05 | To | 2023-05-20 | 2023-05-21 | To | 2023-06-05 | 2023-06-06 | To | 2023-06-21 | 2023-06-22 | To | 2023-07-07 | 2023-07-08 | To | 2023-07-23 | 2023-07-24 | To | 2023-08-08 | 2023-08-09 | To | 2023-08-24 | 2023-08-25 | To | 2023-09-09 | 2023-09-10 | To | 2023-09-25 | 2023-09-26 | To | 2023-10-11 | 2023-10-12 | To | 2023-10-27 | 2023-10-28 | To | 2023-11-12 | 2023-11-13 | To | 2023-11-28 | 2023-11-29 | To | 2023-12-14 | 2023-12-15 | To | 2023-12-30 | To | 2024-01-15 | To | 2024-01-30 | 2024-01-31 | To | 2024-02-15 | 2024-02-16 | To | 2024-03-02 | 2024-03-03 | To | 2024-03-15 | 2024-03-16 | To | 2024-03-31 | 2024-04-01 | To | 2024-04-16 | 2024-04-17 | To | 2024-05-02 | 2024-05-03 | To | 2024-05-15 | 2024-05-16 | To | 2024-05-31 | 2024-06-01 | To | 2024-06-16 | 2024-06-17 | To | 2024-07-02 | 2024-07-03 | To | 2024-07-18 | 2024-07-19 | To | 2024-08-03 | 2024-08-04 | To | 2024-08-19 | 2024-08-20 | To | 2024-09-04 | 2024-09-05 | To | 2024-09-11 | Start Date | Completion date
Preparation & Approval of Terrace Drawing
|  | PLASTERING | [115 empty] | 2024-01-25 | 2024-02-15
|  | DADOING | [115 empty] | 2024-02-16 | 2024-03-15
|  | WALL PUTTY & PAINTING | [115 empty] | 2024-02-20 | 2024-03-15
|  | FALSE CEILING | [115 empty] | 2024-03-06 | 2024-04-27
|  | PCGI PANELING | [115 empty] | 2024-03-20 | 2024-04-25
|  | FLOOR SELF- LEVELLING | [115 empty] | 2024-04-16 | 2024-05-05
|  | SCIENTIFIC DOORS & WOODEN DOORS | [115 empty] | 2024-04-17 | 2024-05-15
|  | VINYL FLOORING | [115 empty] | 2024-05-16 | 2024-06-15
2 | TOILETS | CP & SANITARY FITTINGS | [115 empty] | 2024-03-31 | 2024-05-02
|  | WPC DOORS | [115 empty] | 2024-04-01 | 2024-04-25
GEYSER
|  | EXHAUST FANS | [115 empty] | 2024-03-16 | 2024-03-31
3 | ELECTRICAL | POINT WIRING | [115 empty] | 2024-03-16 | 2024-04-10
|  | DB's & MCB's | [115 empty] | 2024-01-15 | 2024-02-10
|  | POWER CABLES FOR DSU's | [115 empty] | 2024-01-31 | 2024-03-15
|  | DSU DUCTING | [115 empty] | 2024-01-20 | 2024-02-25
ELECTRICAL PANEL ROOM ON TERRACE
|  | ELECTRICAL PANELS | [115 empty] | 2024-04-01 | 2024-05-15
|  | A/C's & DSU's ODU | [115 empty] | 2024-01-25 | 2024-03-15
|  | ELECTRICAL SWITCH BOARDS | [115 empty] | 2024-03-16 | 2024-04-17
4 | UPS | SUPPLY OF UPS & RACKS | [115 empty] | 2024-04-01 | 2024-05-15
|  | SUPPLY OF BATTERIES | [115 empty] | 2024-04-17 | 2024-05-15
|  | INSTALLATION | [115 empty] | 2024-06-01 | 2024-06-20
5 | ELV | LAN | [115 empty] | 2024-03-16 | 2024-04-20
|  | VOICE | [115 empty] | 2024-03-16 | 2024-05-02
|  | ACCESS CONTROL | [115 empty] | 2024-06-17 | 2024-07-10
|  | CCTV CEILING CAMERA | [115 empty] | 2024-04-16 | 2024-05-15
|  | FIRE SYSTEM | [115 empty] | 2024-05-05 | 2024-07-02
6 | TRANSFORMER | SUPPLY | [115 empty] | 2024-04-05 | 2024-05-15
|  | TRENCHING & CABLING | [115 empty] | 2024-03-16 | 2024-04-16
|  | CIRCUIT BRAKER | [115 empty] | 2024-06-01 | 2024-06-30
|  | COMISSIONING | [115 empty] | 2024-06-30 | 2024-07-10
7 | DG SET | SUPPLY
CABLING
COMISSIONING
8 | ACCOUSTIC PANELING & WOODEN FLOORING | SURFACE PREPARATION
ACCOUSTIC WALL & CEILING PANELING
WOODEN FLOORIN
9 | LIFT | FOUNDATION | [115 empty] | 2024-06-20 | 2024-02-28
|  | STRUCTURE ERECTION | [115 empty] | 2024-03-16 | 2024-05-15
|  | INSTALLATION | [115 empty] | 2024-05-16 | 2024-06-20
10 | RO PLANT | SUPPLY
PEDASTALS ON TERRACE
LAYING OF SUPPLY & DRAIN LINES
INSTALLATION OF INLETS, DRAIN OUT LETS
ELECTRICAL CONNECTIONS TO RO
TESTING & COMMISSIONING
11 | WATER PROOFING | SURFACE PREPARATION
APPLICATION OF CHEMICAL
LAYING OF SCREED
GROOVING & TERRACE COVING
SUNSHADE REPAIR, EXTERNAL WALL CLEANING & APPLICATION OF WATERPROOF PAINT
12 | SHED FOR AHU & RO | PEDESTALS
STRUCTURE ERECTION
FIXING OF ROOFING SHEETS
13 | WORKS IN 6 MOT's & 3 TIR's | SITC of Aluminium Ducting | [115 empty] | 2024-01-15 | 2024-02-10
|  | SITC of Uni Directional Ceiling Laminar Airflow Systems & In TIR Corridor | [115 empty] | 2024-01-15 | 2024-02-25
|  | SITC of Stainless Steel Pre-fabricated Wall panels | [115 empty] | 2024-01-15 | 2024-03-15
|  | SITC of Stainless Steel Pre-fabricated Ceiling panels In MOTs & MOTs Corridor & in TIRs and TIR Corridor | [115 empty] | 2024-01-15 | 2024-03-15
|  | SITC of Storage Units | [115 empty] | 2024-01-30 | 2024-02-20
|  | SITC of Electrical Installations in MOTs & TIRs | [115 empty] | 2024-01-20 | 2024-02-20
LAYING OF SUPPLY & DRAIN LINES for RO Water
|  | SITC of Dynamic Hatch Box | [115 empty] | 2024-03-16 | 2024-04-10
|  | SITC of Electro conductive Flooring inside MOTs & inside TIRs& TIR Corridor | [115 empty] | 2024-03-20 | 2024-04-17
|  | SITC of Flooring with Vinyl Sheets In MOT Corridor & In TIR Corridor | [115 empty] | 2024-03-20 | 2024-04-17
|  | SITC of Hermetically Sealed Doors | [115 empty] | 2024-04-16 | 2024-05-15
|  | SITC of Pressure Relief Dampers | [115 empty] | 2024-04-05 | 2024-04-12
|  | SITC of LED Peripheral Lights cum clean room (OT) luminaries | [115 empty] | 2024-04-05 | 2024-04-12
|  | SITC of View Window | [115 empty] | 2024-04-05 | 2024-04-12
|  | SITC of Writing Board | [115 empty] | 2024-04-05 | 2024-04-12
|  | SITC of X-Ray CT Scan LED viewing Screen | [115 empty] | 2024-04-05 | 2024-04-12
|  | SITC of Touch Screen Surgeon Control Panels | [115 empty] | 2024-04-05 | 2024-04-12
|  | SITC of 3-Bay Scrub Stations/Sinks | [115 empty] | 2024-04-05 | 2024-04-12
|  | SITC of Medical Gas pipeline Installation Inside MOT | [115 empty] | 2024-04-03 | 2024-04-30
|  | SITC of 12mm thick glazed Glass partition walls in TIRs | [115 empty] | 2024-03-31 | 2024-05-02
|  | SITC of Air Handling Units (AHUs) | [115 empty] | 2024-04-05 | 2024-05-15
| WORKS IN 6 MOT's & 3 TIR's | SITC of Condensing Units | [115 empty] | 2024-04-05 | 2024-05-15
|  | SITC of Wall mounted large screen display 55 inch | [115 empty] | 2024-04-20 | 2024-05-10
|  | Supply of Wireless Microphones | [115 empty] | 2024-04-20 | 2024-05-10
|  | Supply of Digital Mixer Amplifier | [115 empty] | 2024-04-20 | 2024-05-10
|  | Supply of Ceiling Mounted Speakers | [115 empty] | 2024-04-20 | 2024-05-10
|  | Supply of Video Conferencing Systems | [115 empty] | 2024-04-20 | 2024-05-10
|  | Supply of Hifi Active Sub Woofer | [115 empty] | 2024-04-20 | 2024-05-10
|  | Supply of Equalization & Loud Speaker Control System | [115 empty] | 2024-04-20 | 2024-05-10
|  | Supply of Sound Analog Mixer | [115 empty] | 2024-04-20 | 2024-05-10
|  | Supply of Wall Mounted LED TV 43 Inches Full HD | [115 empty] | 2024-04-20 | 2024-05-10
|  | Supply of Home Theatre Power Conditioner, 230V | [115 empty] | 2024-04-20 | 2024-05-10
|  | Supply of Amplifier (8 Channel) | [115 empty] | 2024-04-20 | 2024-05-10
|  | Supply of Ceiling/Wall Mounted CCTV Room camera | [115 empty] | 2024-04-20 | 2024-05-10
|  | SITC of Single & Double arm Anesthesia Pendants (Imported) | [115 empty] | 2024-05-20 | 2024-06-16
|  | SITC of Triple Dome Ceiling OT LED Lights (Imported) | [115 empty] | 2024-05-20 | 2024-06-16
|  | SITC of Double Dome Ceiling OT LED Lights (Imported) | [115 empty] | 2024-05-20 | 2024-06-16
|  | SITC of Detachable Hi Definition Cameras in Triple Dome Ceiling OT Lights | [115 empty] | 2024-05-20 | 2024-06-16
|  | SITC of Medical Grade Monitors 32 inch 4 K Resolution | [115 empty] | 2024-05-20 | 2024-06-16
|  | Testing & Commissioning | [115 empty] | 2024-07-20 | 2024-07-02
|  | Handover | [115 empty] | 2024-07-02 | 2024-07-15

## MILE STONES
REVISED MILESTONES
MILE STONE | WORKS TO BE COMPLETED | STATUS
MILE STONE-1 15-05-2024 | LINTELS, BRICKWORK, SPLIT AC COPPER & DRAIN PIPING, PLASTERING | IN PROGRESS
| DADOING, WALL PUTTY, CP & SANITARY FITTINGS, WPC DOORS | IN PROGRESS
| ELECTRICAL DB'S AND MCB'S, POWER CABLES FOR DSU's, AC's & DSU's ODU FIXING | IN PROGRESS
| WIRING FOR LAN, VOICE | IN PROGRESS
| LIFT FOUNDATION | DRAWING APPROVAL PENDING
| DUCTING FOR MOT'S AND TIR'S& DSU UNITS, LAMINAR AIR FLOW SYSTEM | IN PROGRESS
| CONSTRUCTION OF PEDESTAL FOR RO PLANT, AHU, LAYING OF PEX PIPING, | IN PROGRESS
| SUPPLY OF RO MACHINE, 800 KVA TRANSFORMER, DG SET, UPS & UPS BATTERY RACKS, GEYSER | TO COMMENCE
| WATER PROOFING SURFACE PREPARATION & APPLICATION OF FIRST COAT | TO COMMENCE
| ELECTRICAL INSTALLATIONS IN MOT'S AND TIR'S | TO COMMENCE
MILE STONE-2 18-07-2024 | SUPPLYING AND FIXING OF DOORS & WINDOWS, FALSE CEILING, FLOOR LEVELLING, CP FITTINGS | TO COMMENCE
| ELECTRICAL POINT WIRING, ELECTRIC PANELS, SWITCH BOARDS, CONSTRUCTION OF PANEL ROOM | IN PROGRESS
| SS WALL & CEILING PANELING, STORAGE UNITS, ACs & DSU ODU FIXING, | IN PROGRESS
| TRANSFORMER TRENCHING & CABLING, INSTALLATION OF LAN & VOICE MODULAR BOXES | IN PROGRESS
| LIFT STRUCTURE ERECTION | TO COMMENCE
| ELECTRO CONDUCTIVE FLOORING INSIDE MOT'S & TIR'S, DYNAMIC HATCH BOX INSTALLATION | TO COMMENCE
| INSTALLATIONS IN MOTs, VINYL FLOORING IN STERILE CORRIDOR, 3-BAY SCRUB STATION, AHU's, CONDENSING UNITS | TO COMMENCE
| MEDICAL GAS PIPELINE INSTALLATION INSIDE MOTS | TO COMMENCE
| INSTALLATIONS IN MOTs INTEGRATION ROOM, CCTV ROOM CAMERA | TO COMMENCE
| WATER PROOFING SCREED, FINAL COAT, COVING, EXTERNAL WALL & SUNSHADE REPAIR | TO COMMENCE
| RO INLET & OUTLET FIXING, STRUCTURE ERECTION FOR AHU & RO SHED | TO COMMENCE
MILE STONE-3 11-09-2024 | VINYL FLOORING IN CORRIDORS & ALL ROOMS IN STERILE & SEMI-STERILE AREA, PCGI PANELING | TO COMMENCE
| UPS INSTALLATION, ACCESS CONTROL, FIRE SYSTEM | TO COMMENCE
| DG CABLING & COMISSIONING, ELECTRICAL CONNECTIONS TO RO, TESTING & COMISSIONING | TO COMMENCE
| TRANSFORMER CIRCUIT BRAKER, COMMISSIONING OF TRANSFORMER | TO COMMENCE
| ACCOUSTIC PANELING & WOODEN FLOORING | TO COMMENCE
| LIFT INSTALLATION | TO COMMENCE
| FIXING OF PENDANTS, TRIPLE DOME & DOUBLE DOME OT LIGHTS, HIGH DEFINITION CAMERA, MEDICAL GRADE MONITOR | TO COMMENCE
| TESTING & COMISSIONING | TO COMMENCE
| HANDOVER | TO COMMENCE

## MILE STONES (2)
REVISED MILESTONES
MILE STONE
MILE STONE-1 15-05-2024 | DADOING, WALL PUTTY, CP & SANITARY FITTINGS, WPC DOORS
ELECTRICAL DB'S AND MCB'S, POWER CABLES FOR DSU's, AC's & DSU's ODU FIXING
WIRING FOR LAN, VOICE
LIFT FOUNDATION
DUCTING FOR MOT'S AND TIR'S& DSU UNITS, LAMINAR AIR FLOW SYSTEM
CONSTRUCTION OF PEDESTAL FOR RO PLANT, AHU, LAYING OF PEX PIPING,
SUPPLY OF RO MACHINE, 800 KVA TRANSFORMER, DG SET, UPS & UPS BATTERY RACKS, GEYSER
WATER PROOFING SURFACE PREPARATION & APPLICATION OF FIRST COAT
ELECTRICAL INSTALLATIONS IN MOT'S AND TIR'S
MILE STONE-2 18-07-2024 | SUPPLYING AND FIXING OF DOORS & WINDOWS, FALSE CEILING, FLOOR LEVELLING, CP FITTINGS
ELECTRICAL POINT WIRING, ELECTRIC PANELS, SWITCH BOARDS, CONSTRUCTION OF PANEL ROOM
SS WALL & CEILING PANELING, STORAGE UNITS, ACs & DSU ODU FIXING,
TRANSFORMER TRENCHING & CABLING, INSTALLATION OF LAN & VOICE MODULAR BOXES
LIFT STRUCTURE ERECTION
ELECTRO CONDUCTIVE FLOORING INSIDE MOT'S & TIR'S, DYNAMIC HATCH BOX INSTALLATION
INSTALLATIONS IN MOTs, VINYL FLOORING IN STERILE CORRIDOR, 3-BAY SCRUB STATION, AHU's, CONDENSING UNITS
MEDICAL GAS PIPELINE INSTALLATION INSIDE MOTS
INSTALLATIONS IN MOTs INTEGRATION ROOM, CCTV ROOM CAMERA
WATER PROOFING SCREED, FINAL COAT, COVING, EXTERNAL WALL & SUNSHADE REPAIR
RO INLET & OUTLET FIXING, STRUCTURE ERECTION FOR AHU & RO SHED
MILE STONE-3 11-09-2024 | VINYL FLOORING IN CORRIDORS & ALL ROOMS IN STERILE & SEMI-STERILE AREA, PCGI PANELING
UPS INSTALLATION, ACCESS CONTROL, FIRE SYSTEM
DG CABLING & COMISSIONING, ELECTRICAL CONNECTIONS TO RO, TESTING & COMISSIONING
TRANSFORMER CIRCUIT BRAKER, COMMISSIONING OF TRANSFORMER
ACCOUSTIC PANELING & WOODEN FLOORING
LIFT INSTALLATION
FIXING OF PENDANTS, TRIPLE DOME & DOUBLE DOME OT LIGHTS, HIGH DEFINITION CAMERA, MEDICAL GRADE MONITOR
ALL OTHER MISCELLANEOUS WORKS
HANDOVER