## MILE STONES
REVISED MILESTONES
MILE STONE
MILE STONE-1 15-05-2024 | DADOING, WALL PUTTY, CP & SANITARY FITTINGS, WPC DOORS
ELECTRICAL DB'S AND MCB'S, POWER CABLES FOR DSU's, AC's & DSU's ODU FIXING
WIRING FOR LAN, VOICE
LIFT FOUNDATION
DUCTING FOR MOT'S AND TIR'S& DSU UNITS, LAMINAR AIR FLOW SYSTEM
CONSTRUCTION OF PEDESTAL FOR RO PLANT, AHU, LAYING OF PEX PIPING,
SUPPLY OF RO MACHINE, 800 KVA TRANSFORMER, DG SET, UPS & UPS BATTERY RACKS, GEYSER
WATER PROOFING SURFACE PREPARATION & APPLICATION OF FIRST COAT
ELECTRICAL INSTALLATIONS IN MOT'S AND TIR'S
MILE STONE-2 18-07-2024 | SUPPLYING AND FIXING OF DOORS & WINDOWS, FALSE CEILING, FLOOR LEVELLING, CP FITTINGS
ELECTRICAL POINT WIRING, ELECTRIC PANELS, SWITCH BOARDS, CONSTRUCTION OF PANEL ROOM
SS WALL & CEILING PANELING, STORAGE UNITS, ACs & DSU ODU FIXING,
TRANSFORMER TRENCHING & CABLING, INSTALLATION OF LAN & VOICE MODULAR BOXES
LIFT STRUCTURE ERECTION
ELECTRO CONDUCTIVE FLOORING INSIDE MOT'S & TIR'S, DYNAMIC HATCH BOX INSTALLATION
INSTALLATIONS IN MOTs, VINYL FLOORING IN STERILE CORRIDOR, 3-BAY SCRUB STATION, AHU's, CONDENSING UNITS
MEDICAL GAS PIPELINE INSTALLATION INSIDE MOTS
INSTALLATIONS IN MOTs INTEGRATION ROOM, CCTV ROOM CAMERA
WATER PROOFING SCREED, FINAL COAT, COVING, EXTERNAL WALL & SUNSHADE REPAIR
RO INLET & OUTLET FIXING, STRUCTURE ERECTION FOR AHU & RO SHED
MILE STONE-3 11-09-2024 | VINYL FLOORING IN CORRIDORS & ALL ROOMS IN STERILE & SEMI-STERILE AREA, PCGI PANELING
UPS INSTALLATION, ACCESS CONTROL, FIRE SYSTEM
DG CABLING & COMISSIONING, ELECTRICAL CONNECTIONS TO RO, TESTING & COMISSIONING
TRANSFORMER CIRCUIT BRAKER, COMMISSIONING OF TRANSFORMER
ACCOUSTIC PANELING & WOODEN FLOORING
LIFT INSTALLATION
FIXING OF PENDANTS, TRIPLE DOME & DOUBLE DOME OT LIGHTS, HIGH DEFINITION CAMERA, MEDICAL GRADE MONITOR
ALL OTHER MISCELLANEOUS WORKS
HANDOVER

## SOTC BAR CHART
BAR CHART for Balance Works at SOTC 8th Floor, Gandhi Hospital, Hyderabad (Considering Additional 2 OTs)
[82 empty] | MILESTONE -01 | [45 empty] | MILESTONE -02 | [10 empty] | MILESTONE -03
S.no | ITEM CATEGORY | ITEM DESCRIPTION | 2023-01-13 | To | 2023-01-28 | 2023-01-29 | To | 2023-02-13 | 2023-02-14 | To | 2023-03-01 | 2023-03-02 | To | 2023-03-17 | 2023-03-18 | To | 2023-04-02 | 2023-04-03 | To | 2023-04-18 | 2023-04-19 | To | 2023-05-04 | 2023-05-05 | To | 2023-05-20 | 2023-05-21 | To | 2023-06-05 | 2023-06-06 | To | 2023-06-21 | 2023-06-22 | To | 2023-07-07 | 2023-07-08 | To | 2023-07-23 | 2023-07-24 | To | 2023-08-08 | 2023-08-09 | To | 2023-08-24 | 2023-08-25 | To | 2023-09-09 | 2023-09-10 | To | 2023-09-25 | 2023-09-26 | To | 2023-10-11 | 2023-10-12 | To | 2023-10-27 | 2023-10-28 | To | 2023-11-12 | 2023-11-13 | To | 2023-11-28 | 2023-11-29 | To | 2023-12-14 | 2023-12-15 | To | 2023-12-30 | To | 2024-01-15 | To | 2024-01-30 | 2024-01-31 | To | 2024-02-15 | 2024-02-16 | To | 2024-03-02 | 2024-03-03 | To | 2024-03-15 | 2024-03-16 | To | 2024-03-31 | 2024-04-01 | To | 2024-04-16 | 2024-04-17 | To | 2024-05-02 | 2024-05-03 | To | 2024-05-15 | 2024-05-16 | To | 2024-05-31 | 2024-06-01 | To | 2024-06-16 | 2024-06-17 | To | 2024-07-02 | 2024-07-03 | To | 2024-07-18 | 2024-07-19 | To | 2024-08-03 | 2024-08-04 | To | 2024-08-19 | 2024-08-20 | To | 2024-09-04 | 2024-09-05 | To | 2024-09-11 | 2024-09-12 | To | 2024-09-27 | 2024-09-28 | To | 2024-10-13 | 2024-10-14 | To | 2024-10-29 | 2024-10-30 | To | 2024-11-14 | 2024-11-15 | To | 2024-11-30 | 2024-12-01 | To | 2024-12-16 | 2024-12-17 | To | 2025-01-01 | 2025-01-02 | To | 2025-01-17 | 2025-01-18 | To | 2025-02-02 | 2025-02-03 | To | 2025-02-18 | 2025-02-19 | To | 2025-02-28
Preparation & Approval of Terrace Drawing
PLASTERING
DADOING
WALL PUTTY & PAINTING
FALSE CEILING
PCGI PANELING
FLOOR SELF- LEVELLING
SCIENTIFIC DOORS & WOODEN DOORS
VINYL FLOORING
2 | TOILETS | CP & SANITARY FITTINGS
WPC DOORS
GEYSER
EXHAUST FANS
3 | ELECTRICAL | POINT WIRING
DB's & MCB's
POWER CABLES FOR DSU's
DSU DUCTING
ELECTRICAL PANELS
A/C's & DSU's ODU
ELECTRICAL SWITCH BOARDS
4 | UPS | SUPPLY OF UPS & RACKS
SUPPLY OF BATTERIES
INSTALLATION
5 | ELV | LAN
VOICE
ACCESS CONTROL
CCTV CEILING CAMERA
FIRE SYSTEM
6 | TRANSFORMER | SUPPLY
TRENCHING & CABLING
CIRCUIT BRAKER
COMISSIONING
7 | DG SET | SUPPLY
CABLING
COMISSIONING
8 | ACCOUSTIC PANELING & WOODEN FLOORING | SURFACE PREPARATION
ACCOUSTIC WALL & CEILING PANELING
WOODEN FLOORIN
9 | LIFT | FOUNDATION
STRUCTURE ERECTION
INSTALLATION
10 | RO PLANT | SUPPLY
PEDASTALS ON TERRACE
LAYING OF SUPPLY LINES
INSTALLATION OF INLETS
ELECTRICAL CONNECTIONS TO RO
TESTING & COMMISSIONING
11 | WATER PROOFING | SURFACE PREPARATION
APPLICATION OF CHEMICAL
LAYING OF SCREED
GROOVING & TERRACE COVING
SUNSHADE REPAIR, EXTERNAL WALL CLEANING & APPLICATION OF WATERPROOF PAINT
12 | SHED FOR AHU & RO | PEDESTALS
STRUCTURE ERECTION
FIXING OF ROOFING SHEETS
13 | WORKS IN 6 MOT's & 3 TIR's | SITC of Aluminium Ducting
SITC of Uni Directional Ceiling Laminar Airflow Systems & In TIR Corridor
SITC of Stainless Steel Pre-fabricated Wall panels
SITC of Stainless Steel Pre-fabricated Ceiling panels In MOTs & MOTs Corridor & in TIRs and TIR Corridor
SITC of Storage Units
SITC of Electrical Installations in MOTs & TIRs
LAYING OF SUPPLY & DRAIN LINES for RO Water
SITC of Dynamic Hatch Box
SITC of Electro conductive Flooring inside MOTs & inside TIRs& TIR Corridor
SITC of Flooring with Vinyl Sheets In MOT Corridor & In TIR Corridor
SITC of Hermetically Sealed Doors
SITC of Pressure Relief Dampers
SITC of LED Peripheral Lights cum clean room (OT) luminaries
SITC of View Window
SITC of Writing Board
SITC of X-Ray CT Scan LED viewing Screen
SITC of Touch Screen Surgeon Control Panels
SITC of 3-Bay Scrub Stations/Sinks
SITC of Medical Gas pipeline Installation Inside MOT
SITC of 12mm thick glazed Glass partition walls in TIRs
SITC of Air Handling Units (AHUs)
| WORKS IN 6 MOT's & 3 TIR's | SITC of Condensing Units
SITC of Wall mounted large screen display 55 inch
Supply of Wireless Microphones
Supply of Digital Mixer Amplifier
Supply of Ceiling Mounted Speakers
Supply of Video Conferencing Systems
Supply of Hifi Active Sub Woofer
Supply of Equalization & Loud Speaker Control System
Supply of Sound Analog Mixer
Supply of Wall Mounted LED TV 43 Inches Full HD
Supply of Home Theatre Power Conditioner, 230V
Supply of Amplifier (8 Channel)
Supply of Ceiling/Wall Mounted CCTV Room camera
SITC of Single & Double arm Anesthesia Pendants (Imported)
SITC of Triple Dome Ceiling OT LED Lights (Imported)
SITC of Double Dome Ceiling OT LED Lights (Imported)
SITC of Detachable Hi Definition Cameras in Triple Dome Ceiling OT Lights
SITC of Medical Grade Monitors 32 inch 4 K Resolution
Testing & Commissioning
Handover