## Table 2
ABSTRACT - STATE ORGAN TRANSPLANT CENTRE AT GANDHI HOSPITAL, SECUNDERABAD
Administrative Sanction details
S. No | Admn. Sanction Details | Description | Admn. Sanction Amount (incl. 18% GST) | Remarks
1 | GO Rt No. 519, HM&FW (A1) Dept. 06.09.2018 (Original sanction) | Civil Works | 10,00,00,000
2 |  | Surgical Gastroenterology Dept (incl c/o 5- MOTs, equipments) | 17,45,37,842
3 |  | Medical Gastroenterology Dept (incl equipments) | 7,01,35,352
4 |  | TSMSIDC Supervision charges & LS | 53,26,806
|  | Total | 35,00,00,000
1 | GO Rt No. 358, HM&FW (C2) Dept. 24.06.2023 (Additional sanction) | Addl. Sanction accorded for 2-MOTs | 4,66,59,536 | Separate admn. sanction accorded for removal & relocation of rooftop solar panels for Rs. 11,39,602/- vide GO Rt. No. 269 HM&FW (C2) Dept. 15.05.2023
2 |  | Removal & Relocation of Roof top solar panels | 14,00,000
3 |  | TSMSIDC Supervision charges & LS | 19,40,464
|  | Total | 5,00,00,000
|  | Grand Total | 40,00,00,000
Work entrustment details
| Details of work entrustment | Description | Amount (incl. 18% GST) | Remarks
1 | Lr. No. 507/SOTC/Spl. Proj/TSMSIDC/2022, Dt. 13.01.2023 (NoA) | Turnkey works entrusted to M/s MPS Asta Consortium | 17,57,73,221 | Work entrusted through open tenders floated in e-procurement platform
2 | Addl. Work entrusted to the subsisting agency vide Govt. Memo. No. 6168/C2/2023, HM&FW (C2) Dept., Dt. 21.08.2023 | Construction of additional 2- MOTs | 4,80,59,536 | including Rs.14.00 lakhs sanctioned for removal & relocation of rooftop solar panels
|  | Total | 22,38,32,757
Work done/to be done details
| Description |  | Amount (incl. 18% GST) | Excess amount (Rs.)
1 | Amount of work done/to be done as Per the Revised Estimate including Supplemental Items |  | 278541319
2 | Removal & Relocation of Roof top solar panels |  | 1400000
3 | Sanctioned Amount |  | 400000000
4 | Balance Available |  | 120058681

## Table 3
Details of supplemental items to be taken up (including 5- year unconditional warranty & excl. 5-year CAMC charges)
| Description of item | Amount required | Remarks
1 | Terrace & exterior walls waterproofing | 12611958 | As per the lowest quotations obtained by the Executive Engineer, Hyd Div-I. Approval requested.
2 | Double pass Reverse Osmosis (RO) plant 1500 Ltr/hr with recirculation loop including 5- year unconditional warranty & excl. 5-year CAMC charges | 6240000
3 | 750 KVA DG Set with AMF panel including 5- year unconditional warranty & excl. 5-year CAMC charges | 9540000
4 | 4 & 6- Gas Digital Alarm Systems incl Valve boxes | 488750
5 | O2 Manifold & Automatic Control System | 270116
6 | Supply, Transportation and installation of 20KVA / 312V DC on line UPS system (2 Nos) | 1258716
7 | N2O Emg Manifold & Automatic Control System | 239414
8 | Recording Counselling Room & Local Area Network (LAN) | 615620
9 | Monitor Stand beside Bed in ICUs & TIRs (31 Nos) | 191456
10 | Glass Sliding Door in TIR-2 & TIR-3 (2 Nos) | 540552
11 | Providing dadooing to walls with glazed full body ceramic wall tiles of size 800 x 1600 mm with any type of design texture such as marble finish, wooden, bamboo, stone finishes etc., (For entrance Lobby) | 556931
12 | Miscellaneous works such as Under-deck Thermocol insulation, Plain Cement Concrete of M 25 grade, Supply and Laying of Floor leveller compund (self smoothing mortar) & V-Board Partitions on top of false ceiling for partitioning of sterile corridor and non-sterile corridor etc | 1941858
13 | GI Powder Coated Sliding Doors (0.8mm shutter sheet thk & 1.2mm & 4 + 4 size of N2O manifold system | 132236
14 | 800 KVA Transformer OLTC for transformers with RTCC | 4814994
15 | Flooring & Skirting with Double Charged Vitrified Tiles (600X600) | 902100
| Excess amount required to take up the above supplemental works | 40344701
| Excess amount as per workdone /to be done | 5650287 |  | 1080
| Additional amount required for completion of turnkey works | 45994988 | (Say) Rs. 4.60 crores
| PCGI Wall and Ceiling paneling in corridor infront of POST ICU to Fire exit door & Point of Care Lab to Clean Utility. | 3431470
| Accoustic wall and ceiling paneling using Accoustic Panels and Flooring with Engineered Wood Panels in MOT's Integration Room. | 1598400
| Provision for Labour cess, NAC, Seinorage, DMF, SMFT charges (including GST) | 2957111
| Supervision Charges TSMSIDC | 9244148
| Deducting Previous Value (72,67,270) | -7267270
|  | 63226117 | (Say) Rs. 6.33 crores
Labour Cess
NAC
Sch
DMF
SMEF
Harita Nidhi