## RE
REVISED ESTIMATE OF SOTC AT 8TH FLOOR, SOUTH-WEST BLOCK, GANDHI HOSPITAL
S.No | Item Code | Item Name |  |  | As Per Agmt. (4- OTs & 3-TIRs) |  |  | Actual Quantities for agreement items (with 4 Ots) |  | Variation |  | Addl. Sanction (2- OTs) |  | Actual QTY for Additional 2 OTs |  | Variation |  | Total |  | As Per Work Done/To Be Done |  | Variation |  | As Per Work Done /To Be Done |  | Variation |  | As per price bid CAMC unit rate | As per Agmt. - CAMC | Revised CAMC
|  |  | UOM | Unit Rate (Rs.) | QTY |  | Amount (Rs.) | QTY | Amount (Rs.) | Excess | Less | QTY | Amount (Rs.) | QTY | Amount (Rs.) | Excess | Less | QTY | Amount (Rs.) | QTY | Amount (Rs.) | Excess | Less | QTY | Amount (Rs.) | Excess | Less
1 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27
1 | SOTC001 | Stainless Steel Pre-fabricated Wall panels in MOTs1) Make: SS 304 medical grade JINDAL certified by a notified body NABL Lab.2) Not less than 50mm thick (0.80mm thick sheet on both sides).3) 41Kg/Cum density PUF, fine grain surface, treated with anti bacterial/anti fungal paint, shall be made with single sheet without any joints/welding, should be covered with a protective sheet. Certified by a notified body NABL Lab. | Sqm | 15010 | 400 | 12720.339 | 6004000 | 294.28 | 4417142.8 | 0 | 1586857.2 | 350 | 5253500 | 183.34 | 2751933.4 | 0 | 2501566.6 | 750 | 11257500 | 477.62 | 7169076.2 | 0 | 4088423.8 | 491.9486 | 7384148.486 | 0 | 3873351.514 | 5253.5 | 2101400 | 2584451.9701
2 | SOTC002 | Stainless Steel Pre-fabricated Ceiling panels In MOTs & MOTs Corridor | Sqm | 15010 | 385 | 12720.339 | 5778850 | 157.13 | 2358521.3 | 0 | 3420328.7 | 78 | 1170780 | 98.37 | 1476533.7 | 305753.7 | 0 | 463 | 6949630 | 255.5 | 3835055 | 0 | 3114575 | 263.165 | 3950106.65 | 0 | 2999523.35 | 5253.5 | 2022597.5 | 1382537.3275
3 | SOTC003 | Dynamic Hatch Box | Nos | 295000 | 2 | 250000 | 590000 | 0 | 0 | 0 | 590000 | 1 | 295000 | 0 | 0 | 0 | 295000 | 3 | 885000 | 0 | 0 | 0 | 885000 | 0 | 0 | 0 | 885000 | 103250 | 206500 | 0
4 | SOTC004 | Electro conductive Flooring inside MOTs | Sqm | 4035 | 160 | 3419.4915 | 645600 | 139.94 | 564657.9 | 0 | 80942.1 | 80 | 322800 | 73.57 | 296854.95 | 0 | 25945.05 | 240 | 968400 | 213.51 | 861512.85 | 0 | 106887.15 | 217.7802 | 878743.107 | 0 | 89656.893 | 1412.25 | 225960 | 307560.0874
5 | SOTC005 | Flooring with Vinyl Sheets In MOT Corridor | Sqm | 3750 | 175 | 3177.9661 | 656250 | 44.828 | 168105 | 0 | 488145 | 50 | 187500 | 39.67 | 148762.5 | 0 | 38737.5 | 225 | 843750 | 84.498 | 316867.5 | 0 | 526882.5 | 87.0329 | 326373.525 | 0 | 517376.475 | 1312.5 | 229687.5 | 114230.7338
6 | SOTC006 | Uni Directional Ceiling Laminar Airflow Systems | Nos | 465000 | 4 | 394067.7966 | 1860000 | 4 | 1860000 | 0 | 0 | 2 | 930000 | 2 | 930000 | 0 | 0 | 6 | 2790000 | 6 | 2790000 | 0 | 0 | 6 | 2790000 | 0 | 0 | 162750 | 651000 | 976500
7 | SOTC007 | Air Handling Units (AHUs) 11 TR | Nos | 1495000 | 4 | 1266949.1525 | 5980000 | 4 | 5980000 | 0 | 0 | 2 | 2990000 | 2 | 2990000 | 0 | 0 | 6 | 8970000 | 6 | 8970000 | 0 | 0 | 6 | 8970000 | 0 | 0 | 523250 | 2093000 | 3139500
8 | SOTC008 | Condensing Units | Nos | 345000 | 4 | 292372.8814 | 1380000 | 4 | 1380000 | 0 | 0 | 2 | 690000 | 2 | 690000 | 0 | 0 | 6 | 2070000 | 6 | 2070000 | 0 | 0 | 10 | 3450000 | 1380000 | 0 | 120750 | 483000 | 1207500
9 | SOTC009 | Pressure Relief Dampers | Nos | 22500 | 4 | 19067.7966 | 90000 | 4 | 90000 | 0 | 0 | 2 | 45000 | 2 | 45000 | 0 | 0 | 6 | 135000 | 6 | 135000 | 0 | 0 | 6 | 135000 | 0 | 0 | 7875 | 31500 | 47250
10 | SOTC010 | Single arm Anesthesia Pendants (Imported) | Nos | 1195000 | 4 | 1012711.8644 | 4780000 | 4 | 4780000 | 0 | 0 | 2 | 2390000 | 2 | 2390000 | 0 | 0 | 6 | 7170000 | 6 | 7170000 | 0 | 0 | 6 | 7170000 | 0 | 0 | 418250 | 1673000 | 2509500
11 | SOTC011 | Triple Dome Ceiling OT LED Lights (Imported) | Nos | 4750000 | 2 | 4025423.7288 | 9500000 | 2 | 9500000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2 | 9500000 | 2 | 9500000 | 0 | 0 | 3 | 14250000 | 4750000 | 0 | 1662500 | 3325000 | 4987500
12 | SOTC012 | Double Dome Ceiling OT LED Lights (Imported) | Nos | 3550000 | 2 | 3008474.5763 | 7100000 | 2 | 7100000 | 0 | 0 | 2 | 7100000 | 2 | 7100000 | 0 | 0 | 4 | 14200000 | 4 | 14200000 | 0 | 0 | 3 | 10650000 | 0 | 3550000 | 1242500 | 2485000 | 3727500
13 | SOTC013 | Detachable Hi Definition Cameras in Triple Dome Ceiling OT Lights | Nos | 995000 | 2 | 843220.339 | 1990000 | 2 | 1990000 | 0 | 0 | 1 | 995000 | 0 | 0 | 0 | 995000 | 3 | 2985000 | 2 | 1990000 | 0 | 995000 | 2 | 1990000 | 0 | 995000 | 348250 | 696500 | 696500
14 | SOTC014 | Ceiling/Wall mounted CCTV Room Camera | Nos | 22500 | 4 | 19067.7966 | 90000 | 4 | 90000 | 0 | 0 | 2 | 45000 | 2 | 45000 | 0 | 0 | 6 | 135000 | 6 | 135000 | 0 | 0 | 6 | 135000 | 0 | 0 | 7875 | 31500 | 47250
15 | SOTC015 | LED Peripheral Lights cum clean room (OT) luminaries | Nos | 18750 | 62 | 15889.8305 | 1162500 | 62 | 1162500 | 0 | 0 | 40 | 750000 | 40 | 750000 | 0 | 0 | 102 | 1912500 | 102 | 1912500 | 0 | 0 | 107 | 2006250 | 93750 | 0 | 6562.5 | 406875 | 702187.5
16 | SOTC016 | View Window with Motorised Blinds of 1 Mt Length & 1 Mt Height | Nos | 115000 | 7 | 97457.6271 | 805000 | 10 | 1150000 | 345000 | 0 | 2 | 230000 | 4 | 460000 | 230000 | 0 | 9 | 1035000 | 14 | 1610000 | 575000 | 0 | 14 | 1610000 | 575000 | 0 | 40250 | 281750 | 563500
17 | SOTC017 | Hermetically Sealed Doors (1.80mt x 2.10 mt) | Nos | 115000 | 4 | 97457.6271 | 460000 | 4 | 460000 | 0 | 0 | 2 | 230000 | 2 | 230000 | 0 | 0 | 6 | 690000 | 6 | 690000 | 0 | 0 | 6 | 690000 | 0 | 0 | 40250 | 161000 | 241500
18 | SOTC018 | (1.50mt x 2.10 mt) Sliding Automatic Sliding Doors with View Window of 1 Mt x 1 Mt | Nos | 525000 | 2 | 444915.2542 | 1050000 | 2 | 1050000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2 | 1050000 | 2 | 1050000 | 0 | 0 | 3 | 1575000 | 525000 | 0 | 183750 | 367500 | 551250
19 | SOTC019 | Storage Units | Nos | 75000 | 4 | 63559.322 | 300000 | 4 | 300000 | 0 | 0 | 2 | 150000 | 2 | 150000 | 0 | 0 | 6 | 450000 | 6 | 450000 | 0 | 0 | 6 | 450000 | 0 | 0 | 26250 | 105000 | 157500
20 | SOTC020 | Writing Board (List Board) | Nos | 18750 | 4 | 15889.8305 | 75000 | 4 | 75000 | 0 | 0 | 2 | 37500 | 2 | 37500 | 0 | 0 | 6 | 112500 | 6 | 112500 | 0 | 0 | 6 | 112500 | 0 | 0 | 6562.5 | 26250 | 39375
21 | SOTC021 | X-Ray CT Scan LED viewing Screen | Nos | 37500 | 4 | 31779.661 | 150000 | 4 | 150000 | 0 | 0 | 2 | 75000 | 2 | 75000 | 0 | 0 | 6 | 225000 | 6 | 225000 | 0 | 0 | 6 | 225000 | 0 | 0 | 13125 | 52500 | 78750
22 | SOTC022 | Touch Screen Surgeon Control Panels | Nos | 385000 | 4 | 326271.1864 | 1540000 | 4 | 1540000 | 0 | 0 | 2 | 770000 | 2 | 770000 | 0 | 0 | 6 | 2310000 | 6 | 2310000 | 0 | 0 | 9 | 3465000 | 1155000 | 0 | 134750 | 539000 | 1212750
23 | SOTC023 | 3-Bay Scrub Stations/Sinks | Nos | 368750 | 2 | 312500 | 737500 | 3 | 1106250 | 368750 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2 | 737500 | 3 | 1106250 | 368750 | 0 | 3 | 1106250 | 368750 | 0 | 129062.5 | 258125 | 387187.5
24 | SOTC024 | Video and Image Management system | Nos | 8000000 | 1 | 6779661.0169 | 8000000 | 1 | 8000000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 8000000 | 1 | 8000000 | 0 | 0 | 1 | 8000000 | 0 | 0 | 2800000 | 2800000 | 2800000
25 | SOTC025 | Medical Grade Monitors 32 inch 4 K Resolution | Nos | 1295000 | 4 | 1097457.6271 | 5180000 | 4 | 5180000 | 0 | 0 | 2 | 2590000 | 2 | 2590000 | 0 | 0 | 6 | 7770000 | 6 | 7770000 | 0 | 0 | 6 | 7770000 | 0 | 0 | 453250 | 1813000 | 2719500
26 | SOTC026 | Wall mounted large screen display 55 inch (Commercial Grade) | Nos | 495000 | 2 | 419491.5254 | 990000 | 2 | 990000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 2 | 990000 | 2 | 990000 | 0 | 0 | 2 | 990000 | 0 | 0 | 173250 | 346500 | 346500
27 | SOTC027 | Cable connections for integration within MOTs and with Workshop Projector Hall, Networks with OFC Cable | Job | 997500 | 4 | 845338.9831 | 3990000 | 4 | 3990000 | 0 | 0 | 2 | 1995000 | 2 | 1995000 | 0 | 0 | 6 | 5985000 | 6 | 5985000 | 0 | 0 | 6 | 5985000 | 0 | 0 | 349125 | 1396500 | 2094750
28 | SOTC028 | Wireless Microphone | Nos | 255000 | 1 | 216101.6949 | 255000 | 1 | 255000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 255000 | 1 | 255000 | 0 | 0 | 1 | 255000 | 0 | 0 | 89250 | 89250 | 89250
29 | SOTC029 | Digital mixer Amplifier | Nos | 245000 | 1 | 207627.1186 | 245000 | 1 | 245000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 245000 | 1 | 245000 | 0 | 0 | 1 | 245000 | 0 | 0 | 85750 | 85750 | 85750
30 | SOTC030 | Ceiling Mounted Speakers | Nos | 15000 | 4 | 12711.8644 | 60000 | 4 | 60000 | 0 | 0 | 2 | 30000 | 2 | 30000 | 0 | 0 | 6 | 90000 | 6 | 90000 | 0 | 0 | 6 | 90000 | 0 | 0 | 5250 | 21000 | 31500
31 | SOTC031 | Video Conferencing System | Nos | 1195000 | 1 | 1012711.8644 | 1195000 | 1 | 1195000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 1195000 | 1 | 1195000 | 0 | 0 | 1 | 1195000 | 0 | 0 | 418250 | 418250 | 418250
32 | SOTC032 | Home Theatre Power Conditioner, 230 V | Nos | 145000 | 1 | 122881.3559 | 145000 | 1 | 145000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 145000 | 1 | 145000 | 0 | 0 | 1 | 145000 | 0 | 0 | 50750 | 50750 | 50750
33 | SOTC033 | Amplifier (8 Channel) | Nos | 245000 | 1 | 207627.1186 | 245000 | 1 | 245000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 245000 | 1 | 245000 | 0 | 0 | 1 | 245000 | 0 | 0 | 85750 | 85750 | 85750
34 | SOTC034 | HiFi Active Sub Woofer | Nos | 50000 | 1 | 42372.8814 | 50000 | 1 | 50000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 50000 | 1 | 50000 | 0 | 0 | 1 | 50000 | 0 | 0 | 17500 | 17500 | 17500
35 | SOTC035 | 4K Laser Projection TV | Nos | 1495000 | 1 | 1266949.1525 | 1495000 | 1 | 1495000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 1495000 | 1 | 1495000 | 0 | 0 | 1 | 1495000 | 0 | 0 | 523250 | 523250 | 523250
36 | SOTC036 | Equalization & Loud Speaker Control System | Nos | 40000 | 1 | 33898.3051 | 40000 | 1 | 40000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 40000 | 1 | 40000 | 0 | 0 | 1 | 40000 | 0 | 0 | 14000 | 14000 | 14000
37 | SOTC037 | Sound Analog Mixer | Nos | 245000 | 1 | 207627.1186 | 245000 | 1 | 245000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 245000 | 1 | 245000 | 0 | 0 | 1 | 245000 | 0 | 0 | 85750 | 85750 | 85750
38 | SOTC038 | Electrical Installations in MOTs & TIRs | Job | 195000 | 7 | 165254.2373 | 1365000 | 7 | 1365000 | 0 | 0 | 2 | 390000 | 2 | 390000 | 0 | 0 | 9 | 1755000 | 9 | 1755000 | 0 | 0 | 9 | 1755000 | 0 | 0 | 68250 | 477750 | 614250
39 | SOTC039 | Stainless Steel Pre-fabricated Wall panels in TIRs | Sqm | 15010 | 202 | 12720.339 | 3032020 | 329.06 | 4939190.6 | 1907170.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 202 | 3032020 | 329.06 | 4939190.6 | 1907170.6 | 0 | 338.9318 | 5087366.318 | 2055346.318 | 0 | 5253.5 | 1061207 | 1780578.2113
40 | SOTC040 | Stainless Steel Pre-fabricated Ceiling panels in TIRs and TIR Corridor | Sqm | 15010 | 146 | 12720.339 | 2191460 | 174 | 2611740 | 420280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 146 | 2191460 | 174 | 2611740 | 420280 | 0 | 179.22 | 2690092.2 | 498632.2 | 0 | 5253.5 | 767011 | 941532.27
41 | SOTC041 | Electro conductive Flooring inside TIRs | Sqm | 4035 | 146 | 3419.4915 | 589110 | 72.22 | 291407.7 | 0 | 297702.3 |  | 0 |  | 0 | 0 | 0 | 146 | 589110 | 72.22 | 291407.7 | 0 | 297702.3 | 73.6644 | 297235.854 | 0 | 291874.146 | 1412.25 | 206188.5 | 104032.5489
42 | SOTC042 | Flooring with Vinyl Sheets In TIR Corridor | Sqm | 3750 | 61 | 3177.9661 | 228750 | 127.58 | 478425 | 249675 | 0 |  | 0 |  | 0 | 0 | 0 | 61 | 228750 | 127.58 | 478425 | 249675 | 0 | 131.4074 | 492777.75 | 264027.75 | 0 | 1312.5 | 80062.5 | 172472.2125
43 | SOTC043 | Uni Directional Ceiling Laminar Airflow Systems | Nos | 395000 | 3 | 334745.7627 | 1185000 | 3 | 1185000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 3 | 1185000 | 3 | 1185000 | 0 | 0 | 3 | 1185000 | 0 | 0 | 138250 | 414750 | 414750
44 | SOTC044 | Air Handling Units (AHUs) 11 TR | Nos | 1495000 | 2 | 1266949.1525 | 2990000 | 2 | 2990000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 2 | 2990000 | 2 | 2990000 | 0 | 0 | 2 | 2990000 | 0 | 0 | 523250 | 1046500 | 1046500
45 | SOTC045 | Air Handling Units (AHUs) 8.5 TR | Nos | 1195000 | 1 | 1012711.8644 | 1195000 | 1 | 1195000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 1195000 | 1 | 1195000 | 0 | 0 | 1 | 1195000 | 0 | 0 | 418250 | 418250 | 418250
46 | SOTC046 | Condensing Units | Nos | 345000 | 3 | 292372.8814 | 1035000 | 3 | 1035000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 3 | 1035000 | 3 | 1035000 | 0 | 0 | 6 | 2070000 | 1035000 | 0 | 120750 | 362250 | 724500
47 | SOTC047 | Pressure Relief Dampers | Nos | 22500 | 3 | 19067.7966 | 67500 | 3 | 67500 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 3 | 67500 | 3 | 67500 | 0 | 0 | 3 | 67500 | 0 | 0 | 7875 | 23625 | 23625
48 | SOTC049 | Hermetically Sealed Doors (1.80mt x 2.10 mt) | Nos | 525000 | 3 | 444915.2542 | 1575000 | 3 | 1575000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 3 | 1575000 | 3 | 1575000 | 0 | 0 | 3 | 1575000 | 0 | 0 | 183750 | 551250 | 551250
49 | SOTC050 | 12mm thick glazed Glass partition walls in TIRs | Sqm | 650 | 40 | 550.8475 | 26000 | 40 | 26000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 40 | 26000 | 40 | 26000 | 0 | 0 | 40 | 26000 | 0 | 0 | 227.5 | 9100 | 9100
50 | SOTC051 | Wall mounted LED TV43 inchesFull HD | Nos | 165000 | 3 | 139830.5085 | 495000 | 3 | 495000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 3 | 495000 | 3 | 495000 | 0 | 0 | 3 | 495000 | 0 | 0 | 57750 | 173250 | 173250
51 | SOTC052 | Ceiling/Wall mounted CCTV Room Camera | Nos | 12000 | 3 | 10169.4915 | 36000 | 3 | 36000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 3 | 36000 | 3 | 36000 | 0 | 0 | 3 | 36000 | 0 | 0 | 4200 | 12600 | 12600
52 | SOTC053 | BED HEAD PANEL FOR TIR WITH DOUBLE OUTLETS AND ELECTRICAL OUTLETS | Nos | 49500 | 3 | 41949.1525 | 148500 | 6 | 297000 | 148500 | 0 |  | 0 |  | 0 | 0 | 0 | 3 | 148500 | 6 | 297000 | 148500 | 0 | 3 | 148500 | 0 | 0 | 17325 | 51975 | 51975
5 | SOTC054 | X-RAY VIEWERS FOR ALL ICUS AND PRE OPP AREAS AND DOCTORS ROOMS | Nos | 37500 | 5 | 31779.661 | 187500 | 5 | 187500 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 5 | 187500 | 5 | 187500 | 0 | 0 | 6 | 225000 | 37500 | 0 | 13125 | 65625 | 78750
54 | SOTC055 | WRITING BOARDS FOR ICUS, PRE OPP | Nos | 18750 | 5 | 15889.8305 | 93750 | 5 | 93750 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 5 | 93750 | 5 | 93750 | 0 | 0 | 6 | 112500 | 18750 | 0 | 6562.5 | 32812.5 | 39375
55 | SOTC056 | CCTV CEILING CAMERA | Nos | 9500 | 10 | 8050.8475 | 95000 | 10 | 95000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 10 | 95000 | 10 | 95000 | 0 | 0 | 10 | 95000 | 0 | 0 | 3325 | 33250 | 33250
56 | SOTC057 | Supply and Fixing of 25mm dia Conduit Pipes surface on wall. | Rmt | 110 | 10000 | 93.2203 | 1100000 | 10000 | 1100000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 10000 | 1100000 | 10000 | 1100000 | 0 | 0 | 10000 | 1100000 | 0 | 0 | 38.5 | 385000 | 385000
57 | SOTC058 | Supply and Fixing of 25mm dia Conduit Pipes Concealed on wall. | Rmt | 115 | 4000 | 97.4576 | 460000 | 4000 | 460000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 4000 | 460000 | 4000 | 460000 | 0 | 0 | 4000 | 460000 | 0 | 0 | 40.25 | 161000 | 161000
58 | SOTC059 | Wiring with run of 2 of 1.5 Sqmm Copper cable for points wiring. | Pts | 1525 | 570 | 1292.3729 | 869250 | 570 | 869250 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 570 | 869250 | 570 | 869250 | 0 | 0 | 570 | 869250 | 0 | 0 | 533.75 | 304237.5 | 304237.5
59 | SOTC060 | Wiring with run of 2 of 1.5 Sqmm Copper cable for stairecase points wiring. | Pts | 1100 | 10 | 932.2034 | 11000 | 10 | 11000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 10 | 11000 | 10 | 11000 | 0 | 0 | 10 | 11000 | 0 | 0 | 385 | 3850 | 3850
60 | SOTC061 | Supply and fixing of 6A/10A ISI Mark 3/2 pin Modular socket Common switch board | Pts | 900 | 25 | 762.7119 | 22500 | 25 | 22500 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 25 | 22500 | 25 | 22500 | 0 | 0 | 25 | 22500 | 0 | 0 | 315 | 7875 | 7875
61 | SOTC062 | Wiring with 3 of 1.5 sq.mm with 6A switch and 6A, 3/2 pin socket Modular type with 6A switch control fixing on separate board. | Pts | 2800 | 50 | 2372.8814 | 140000 | 50 | 140000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 50 | 140000 | 50 | 140000 | 0 | 0 | 50 | 140000 | 0 | 0 | 190.75 | 9537.5 | 9537.5
62 | SOTC063 | Supply and fixing of 6A switchs - 2 Nos and 6A 3/2 pin socket - 3 Nos Modular type with cover plate | Pts | 1400 | 200 | 1186.4407 | 280000 | 200 | 280000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 200 | 280000 | 200 | 280000 | 0 | 0 | 200 | 280000 | 0 | 0 | 490 | 98000 | 98000
63 | SOTC064 | Supply & fixing of 16A/6A, 2 in one socket with 16A switch control modular type | Nos | 900 | 200 | 762.7119 | 180000 | 200 | 180000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 200 | 180000 | 200 | 180000 | 0 | 0 | 200 | 180000 | 0 | 0 | 315 | 63000 | 63000
64 | SOTC065 | Supply & fixing of 32A, socket with switch control modular | Nos | 1600 | 18 | 1355.9322 | 28800 | 18 | 28800 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 18 | 28800 | 18 | 28800 | 0 | 0 | 18 | 28800 | 0 | 0 | 560 | 10080 | 10080
65 | SOTC066 | Supply & fixing of 64A, socket with 64A switch control modular type | Nos | 18000 | 4 | 15254.2373 | 72000 | 4 | 72000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 4 | 72000 | 4 | 72000 | 0 | 0 | 4 | 72000 | 0 | 0 | 6300 | 25200 | 25200
66 | SOTC067 | Supply and Run of 1 of 1.5 sq.mm (phase, neutral and earth) FRLSH / HFFR PVC insulated 1100V grade as per IS:694/1990, IS 17048 specifications for Copper cable. | Rmt | 36 | 2000 | 30.5085 | 72000 | 2000 | 72000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 2000 | 72000 | 2000 | 72000 | 0 | 0 | 2000 | 72000 | 0 | 0 | 12.6 | 25200 | 25200
67 | SOTC068 | Supply and Run of 3 of 1.5 sq.mm (phase, neutral and earth) FRLSH / HFFR PVC insulated 1100V grade as per IS:694/1990, IS 17048 specifications for Copper cable . | Rmt | 100 | 2000 | 84.7458 | 200000 | 2000 | 200000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 2000 | 200000 | 2000 | 200000 | 0 | 0 | 2000 | 200000 | 0 | 0 | 35 | 70000 | 70000
68 | SOTC069 | Supply and Run of 3 of 2.5 sq.mm (phase, neutral and earth) FRLSH / HFFR PVC insulated 1100V grade as per IS:694/1990, IS 17048 specifications for Copper cable. | Rmt | 145 | 8000 | 122.8814 | 1160000 | 8000 | 1160000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 8000 | 1160000 | 8000 | 1160000 | 0 | 0 | 8000 | 1160000 | 0 | 0 | 50.75 | 406000 | 406000
69 | SOTC070 | Supply and Run of 3 runs of 4.0 sq mm (phase neutral and earth) FRLSH / HFFR PVC insulated 1100V grade as per IS:694/1990, IS 17048 specifications for Copper cable. | Rmt | 230 | 5000 | 194.9153 | 1150000 | 5000 | 1150000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 5000 | 1150000 | 5000 | 1150000 | 0 | 0 | 5000 | 1150000 | 0 | 0 | 80.5 | 402500 | 402500
70 | SOTC071 | Supply and Run of 3 of 6.0 Sq.mm FRLSH / HFFR PVC insulated 1100V grade as per IS:694/1990, IS 17048 specifications for Copper cable. | Rmt | 325 | 300 | 275.4237 | 97500 | 300 | 97500 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 300 | 97500 | 300 | 97500 | 0 | 0 | 300 | 97500 | 0 | 0 | 113.75 | 34125 | 34125
71 | SOTC072 | Supply and Run of 5 of 6.0 Sq.mm FRLSH / HFFR PVC insulated 1100V grade as per IS:694/1990, IS 17048 specifications for Copper cable. | Rmt | 545 | 300 | 461.8644 | 163500 | 300 | 163500 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 300 | 163500 | 300 | 163500 | 0 | 0 | 300 | 163500 | 0 | 0 | 190.75 | 57225 | 57225
72 | SOTC073 | Supply and Run of 5 of 10.0 Sq.mm FRLSH / HFFR PVC insulated 1100V grade as per IS:694/1990, IS 17048 specifications for Copper cable. | Rmt | 850 | 500 | 720.339 | 425000 | 500 | 425000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 500 | 425000 | 500 | 425000 | 0 | 0 | 500 | 425000 | 0 | 0 | 297.5 | 148750 | 148750
73 | SOTC074 | Supply and fixing of DP Metal Enclosure with IP 20 Protection DB Make with 1 No 20A, 10 KA DP MCB | Nos | 1800 | 8 | 1525.4237 | 14400 | 8 | 14400 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 8 | 14400 | 8 | 14400 | 0 | 0 | 8 | 14400 | 0 | 0 | 630 | 5040 | 5040
74 | SOTC075 | Supply and fixing of 4 Way TPN DB Horizontal with IP 43 Protection as per IS:13032 (For Lighting DBs) | Nos | 13000 | 10 | 11016.9492 | 130000 | 10 | 130000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 10 | 130000 | 10 | 130000 | 0 | 0 | 10 | 130000 | 0 | 0 | 4550 | 45500 | 45500
75 | SOTC076 | Supply and fixing of 4 Way TPN DB Horizontal with IP 43 Protection as per IS:13032 (For Power DB's) | Nos | 13000 | 14 | 11016.9492 | 182000 | 14 | 182000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 14 | 182000 | 14 | 182000 | 0 | 0 | 14 | 182000 | 0 | 0 | 4550 | 63700 | 63700
76 | SOTC077 | Supply and fixing of 8 Way VTPN DB with IP 43 Protection as per IS:13032 | Nos | 50000 | 5 | 42372.8814 | 250000 | 5 | 250000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 5 | 250000 | 5 | 250000 | 0 | 0 | 5 | 250000 | 0 | 0 | 17500 | 87500 | 87500
77 | SOTC078 | Supply and fixing of cable adopteres box with cover for DBs including, massanory work etc., complete., | Nos | 6000 | 10 | 5084.7458 | 60000 | 10 | 60000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 10 | 60000 | 10 | 60000 | 0 | 0 | 10 | 60000 | 0 | 0 | 2100 | 21000 | 21000
78 | SOTC079 | Providing independent earthing for Important equipment with 40mm dia 'B' class 2.5m long G.I pipe (GI Earthing) | Nos | 22500 | 18 | 19067.7966 | 405000 | 18 | 405000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 18 | 405000 | 18 | 405000 | 0 | 0 | 18 | 405000 | 0 | 0 | 7875 | 141750 | 141750
79 | SOTC080 | Providing independent earthing by exacavating a pit to a depth of 2.25Mtr in all soils as per size specified in the data for Sophisticated Electronic equipment (Copper Earthing) | Nos | 54000 | 18 | 45762.7119 | 972000 | 18 | 972000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 18 | 972000 | 18 | 972000 | 0 | 0 | 18 | 972000 | 0 | 0 | 18900 | 340200 | 340200
80 | SOTC081 | Providing independent earthing for Important equipment with 100mm dia Heavy gauge C.I Earthing | Nos | 25000 | 6 | 21186.4407 | 150000 | 6 | 150000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 6 | 150000 | 6 | 150000 | 0 | 0 | 6 | 150000 | 0 | 0 | 8750 | 52500 | 52500
81 | SOTC082 | Supply and Run of 50mm x 6mm G.I Strip | Rmt | 450 | 400 | 381.3559 | 180000 | 400 | 180000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 400 | 180000 | 400 | 180000 | 0 | 0 | 400 | 180000 | 0 | 0 | 157.5 | 63000 | 63000
82 | SOTC083 | Supply and Run of 25mm x 3mm copper strip | Rmt | 300 | 400 | 254.2373 | 120000 | 400 | 120000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 400 | 120000 | 400 | 120000 | 0 | 0 | 400 | 120000 | 0 | 0 | 105 | 42000 | 42000
83 | SOTC084 | Supply, transportation and fixing of 22W +/ 10% , >/ 2300 lumens, 1200mm length LED light | Nos | 4800 | 20 | 4067.7966 | 96000 | 20 | 96000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 20 | 96000 | 20 | 96000 | 0 | 0 | 20 | 96000 | 0 | 0 | 1680 | 33600 | 33600
84 | SOTC085 | Supply, transportation and fixing 32-36W (>=3600 Lumens), 2' x2' (600mm x 600mm) slim panel LED luminaire | Nos | 4000 | 60 | 3389.8305 | 240000 | 60 | 240000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 60 | 240000 | 60 | 240000 | 0 | 0 | 60 | 240000 | 0 | 0 | 1400 | 84000 | 84000
85 | SOTC086 | Supply, transportation and fixing 12 W +/-10% (>= 1200 Lumens) Down lighter back lit LED Down Light Recessed / Surface | Nos | 1400 | 215 | 1186.4407 | 301000 | 215 | 301000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 215 | 301000 | 215 | 301000 | 0 | 0 | 215 | 301000 | 0 | 0 | 490 | 105350 | 105350
86 | SOTC087 | Supply, transportation and fixing 18 W +/-10% (>= 1800 Lumens) Down lighter back lit LED Down Light | Nos | 1800 | 95 | 1525.4237 | 171000 | 95 | 171000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 95 | 171000 | 95 | 171000 | 0 | 0 | 95 | 171000 | 0 | 0 | 630 | 59850 | 59850
87 | SOTC088 | Supply, transportation and fixing ISI mark batten holder / slanting holder | Nos | 160 | 8 | 135.5932 | 1280 | 8 | 1280 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 8 | 1280 | 8 | 1280 | 0 | 0 | 8 | 1280 | 0 | 0 | 56 | 448 | 448
88 | SOTC089 | Supply, Transportation of energy efficient fan, 1200 mm sweep, aluminium body, consuming 28 W, BEE 5 star rated, ceiling fan | Nos | 3700 | 40 | 3135.5932 | 148000 | 40 | 148000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 40 | 148000 | 40 | 148000 | 0 | 0 | 40 | 148000 | 0 | 0 | 1295 | 51800 | 51800
89 | SOTC090 | Supply and fixing of Modular type Stepped electronic regulator. | Nos | 1000 | 40 | 847.4576 | 40000 | 40 | 40000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 40 | 40000 | 40 | 40000 | 0 | 0 | 40 | 40000 | 0 | 0 | 350 | 14000 | 14000
90 | SOTC091 | Labour charges for fixing of ceiling fan and regulator | Nos | 210 | 40 | 177.9661 | 8400 | 40 | 8400 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 40 | 8400 | 40 | 8400 | 0 | 0 | 40 | 8400 | 0 | 0 | 73.5 | 2940 | 2940
91 | SOTC092 | Supply and erecting 19/20mm steel tube down rod of one meter length | Nos | 600 | 40 | 508.4746 | 24000 | 40 | 24000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 40 | 24000 | 40 | 24000 | 0 | 0 | 40 | 24000 | 0 | 0 | 210 | 8400 | 8400
92 | SOTC093 | Supply of 12" (300mm) Light duty exhaust fan | Nos | 3000 | 5 | 2542.3729 | 15000 | 5 | 15000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 5 | 15000 | 5 | 15000 | 0 | 0 | 5 | 15000 | 0 | 0 | 1050 | 5250 | 5250
93 | SOTC094 | Supply,Transportation of 12" (300mm) ISI, 900 RPM Heavy duty exhaust fan | Nos | 4900 | 10 | 4152.5424 | 49000 | 10 | 49000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 10 | 49000 | 10 | 49000 | 0 | 0 | 10 | 49000 | 0 | 0 | 1715 | 17150 | 17150
94 | SOTC095 | Labour charges for fixing the exhaust fan in wall with necessary connections | Nos | 900 | 15 | 762.7119 | 13500 | 15 | 13500 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 15 | 13500 | 15 | 13500 | 0 | 0 | 15 | 13500 | 0 | 0 | 315 | 4725 | 4725
95 | SOTC096 | Supply and fixing of GI louver shutter including GI mesh | Nos | 3200 | 15 | 2711.8644 | 48000 | 15 | 48000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 15 | 48000 | 15 | 48000 | 0 | 0 | 15 | 48000 | 0 | 0 | 1120 | 16800 | 16800
96 | SOTC097 | Main Power Panel with 1000A 4 Pole ACB as incomer - 1 No and out goings 800 A 4P MCCB - 1 No., 630 A 4P MCCB - 1 No., 400A 4P MCCB - 4 Nos & 250A 4P MCCB - 3 No's with required Digital Ammeter and Voltmer, LED Indicators | Nos | 1315000 | 1 | 1114406.7797 | 1315000 | 1 | 1315000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 1315000 | 1 | 1315000 | 0 | 0 | 1 | 1315000 | 0 | 0 | 460250 | 460250 | 460250
97 | SOTC098 | Floor Power Panel : Incomer: 630A 4 Pole MCCB,- 1 No Outgoings 250 A 4P MCCB - 4 No's 125 A 4P MCCB - 10 No's, 63 A 4P MCCB - 4 No's with required Digital Ammeter and Voltmer, LED Indicators | Nos | 875000 | 1 | 741525.4237 | 875000 | 1 | 875000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 875000 | 1 | 875000 | 0 | 0 | 1 | 875000 | 0 | 0 | 306250 | 306250 | 306250
98 | SOTC099 | Electrical Lighting Panels : Incomer: 250 A 4 Pole MCCB - 1 No, Out Goings 125 A 4P MCCB - 4 No's 63 A 4P MCCB - 3 No's with required Digital Ammeter and Voltmer, LED Indicators | Nos | 370000 | 2 | 313559.322 | 740000 | 2 | 740000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 2 | 740000 | 2 | 740000 | 0 | 0 | 2 | 740000 | 0 | 0 | 129500 | 259000 | 259000
99 | SOTC100 | 130KVAR Out Door Capacitor panel : Incomer: 250A FP MCCB - 1 No, 63A 10KA TP MCB - 9 Nos. 20 KVAR Capacitor Duty contactors - 5 Nos., 10 KVAR Capacitor Duty contactors - 2 Nos, .5 KVAR Capacitor Duty contactors - 2 Nos. 12 stage APFC Relay - 1 No | Nos | 450000 | 1 | 381355.9322 | 450000 | 1 | 450000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 450000 | 1 | 450000 | 0 | 0 | 1 | 450000 | 0 | 0 | 157500 | 157500 | 157500
100 | SOTC101 | 630 KVA Transformer OLTC for transformers with RTCC: Supply, Transportation, Installation, Testing and Commissioning of 630 KVA TRANSFORMER with all test reports. The Transformer shall be designed and manufactured as per IS:1180 OLTC with level-II with initial filling of oil as per IS 335-1993. 1000 A LT Breaker Kiosk - 01 No.The basic details of the Transformer are as under. Makes: Kirloskar / PETE / Esennar / Voltamp / Crompton / ABB / Schneider. | Nos | 4000000 | 1 | 3389830.5085 | 4000000 | 0 | 0 | 0 | 4000000 |  | 0 |  | 0 | 0 | 0 | 1 | 4000000 | 0 | 0 | 0 | 4000000 | 1 | 4814994 | 814994 | 0 | 1400000 | 1400000 | 1400000
101 | SOTC102 | Supply of 25 Sqmm 3.5 Core XLPE insulated UG Cable. | Rmt | 300 | 200 | 254.2373 | 60000 | 200 | 60000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 200 | 60000 | 200 | 60000 | 0 | 0 | 200 | 60000 | 0 | 0 | 105 | 21000 | 21000
102 | SOTC103 | Supply of 50 Sqmm 3.5 Core XLPE insulated UG Cable. | Rmt | 560 | 200 | 474.5763 | 112000 | 200 | 112000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 200 | 112000 | 200 | 112000 | 0 | 0 | 200 | 112000 | 0 | 0 | 196 | 39200 | 39200
103 | SOTC104 | Supply of 70 Sqmm 3.5 Core XLPE insulated UG Cable. | Rmt | 750 | 75 | 635.5932 | 56250 | 75 | 56250 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 75 | 56250 | 75 | 56250 | 0 | 0 | 75 | 56250 | 0 | 0 | 262.5 | 19687.5 | 19687.5
104 | SOTC105 | Supply of 120 Sqmm 3.5 Core XLPE insulated UG Cable. | Rmt | 1050 | 50 | 889.8305 | 52500 | 50 | 52500 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 50 | 52500 | 50 | 52500 | 0 | 0 | 50 | 52500 | 0 | 0 | 367.5 | 18375 | 18375
105 | SOTC106 | Supply of 185 Sqmm 3.5 Core XLPE insulated UG Cable. | Rmt | 1500 | 50 | 1271.1864 | 75000 | 50 | 75000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 50 | 75000 | 50 | 75000 | 0 | 0 | 50 | 75000 | 0 | 0 | 525 | 26250 | 26250
106 | SOTC107 | Supply of 240 Sqmm 3.5 Core XLPE insulated UG Cable. | Rmt | 1900 | 100 | 1610.1695 | 190000 | 100 | 190000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 100 | 190000 | 100 | 190000 | 0 | 0 | 100 | 190000 | 0 | 0 | 665 | 66500 | 66500
107 | SOTC108 | Supply of 300 Sqmm 3.5 Core XLPE insulated UG Cable. | Rmt | 2400 | 500 | 2033.8983 | 1200000 | 500 | 1200000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 500 | 1200000 | 500 | 1200000 | 0 | 0 | 500 | 1200000 | 0 | 0 | 840 | 420000 | 420000
108 | SOTC109 | Termination of UG cables of 3.5 core 25 Sq.mm | Nos | 850 | 8 | 720.339 | 6800 | 8 | 6800 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 8 | 6800 | 8 | 6800 | 0 | 0 | 8 | 6800 | 0 | 0 | 297.5 | 2380 | 2380
109 | SOTC110 | Termination of UG cables of 3.5 core 50 Sq.mm | Nos | 1200 | 8 | 1016.9492 | 9600 | 8 | 9600 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 8 | 9600 | 8 | 9600 | 0 | 0 | 8 | 9600 | 0 | 0 | 420 | 3360 | 3360
110 | SOTC111 | Termination of UG cables of 3.5 core 70 Sq.mm | Nos | 1500 | 8 | 1271.1864 | 12000 | 8 | 12000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 8 | 12000 | 8 | 12000 | 0 | 0 | 8 | 12000 | 0 | 0 | 525 | 4200 | 4200
111 | SOTC112 | Termination of UG cables of 3.5 core 120 Sq.mm | Nos | 1900 | 4 | 1610.1695 | 7600 | 4 | 7600 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 4 | 7600 | 4 | 7600 | 0 | 0 | 4 | 7600 | 0 | 0 | 665 | 2660 | 2660
112 | SOTC113 | Termination of UG cables of 3.5 core 185 Sq.mm | Nos | 2500 | 4 | 2118.6441 | 10000 | 4 | 10000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 4 | 10000 | 4 | 10000 | 0 | 0 | 4 | 10000 | 0 | 0 | 875 | 3500 | 3500
113 | SOTC114 | Termination of UG cables of 3.5 core 240 Sq.mm | Nos | 3500 | 4 | 2966.1017 | 14000 | 4 | 14000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 4 | 14000 | 4 | 14000 | 0 | 0 | 4 | 14000 | 0 | 0 | 1225 | 4900 | 4900
114 | SOTC115 | Termination of UG cables of 3.5 core 300 Sq.mm | Nos | 4000 | 12 | 3389.8305 | 48000 | 12 | 48000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 12 | 48000 | 12 | 48000 | 0 | 0 | 12 | 48000 | 0 | 0 | 1400 | 16800 | 16800
115 | SOTC116 | Earth work excavation of Trench laying of U.G cables up to 70 sqmm | Rmt | 1100 | 100 | 932.2034 | 110000 | 100 | 110000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 100 | 110000 | 100 | 110000 | 0 | 0 | 100 | 110000 | 0 | 0 | 385 | 38500 | 38500
116 | SOTC117 | Earth work excavation of Trench laying of U.G cables from 95 Sqmm | Rmt | 1150 | 100 | 974.5763 | 115000 | 100 | 115000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 100 | 115000 | 100 | 115000 | 0 | 0 | 100 | 115000 | 0 | 0 | 402.5 | 40250 | 40250
117 | SOTC118 | Laying of PVC armoured under ground cable up to 95 Sqmm on wall | Rmt | 125 | 200 | 105.9322 | 25000 | 200 | 25000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 200 | 25000 | 200 | 25000 | 0 | 0 | 200 | 25000 | 0 | 0 | 43.75 | 8750 | 8750
118 | SOTC119 | Laying of PVC armoured under ground cable from 120 Sq.mm to 400 Sqmm saddles on wall | Rmt | 270 | 700 | 228.8136 | 189000 | 700 | 189000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 700 | 189000 | 700 | 189000 | 0 | 0 | 700 | 189000 | 0 | 0 | 94.5 | 66150 | 66150
119 | SOTC120 | Supply, Transportation and Installation of 150mm x 50mm x 2mm thick hot dip GI perforated cable tray | Rmt | 1295 | 200 | 1097.4576 | 259000 | 200 | 259000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 200 | 259000 | 200 | 259000 | 0 | 0 | 200 | 259000 | 0 | 0 | 453.25 | 90650 | 90650
120 | SOTC121 | Supply, Transportation and Installation of 300mm x 50mm x 2mm thick thick hot dip GI perforated cable tray | Rmt | 4500 | 100 | 3813.5593 | 450000 | 100 | 450000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 100 | 450000 | 100 | 450000 | 0 | 0 | 100 | 450000 | 0 | 0 | 1575 | 157500 | 157500
121 | SOTC122 | Supply, Transportation and installation of 10KVA / 312V DC on line UPS system | Nos | 400000 | 7 | 338983.0508 | 2800000 | 11 | 4400000 | 1600000 | 0 | 2 | 800000 | 2 | 800000 | 0 | 0 | 9 | 3600000 | 13 | 5200000 | 1600000 | 0 | 10 | 4000000 | 400000 | 0 | 140000 | 980000 | 1400000
122 | SOTC123 | Supply and fixing of 12V, 150 AH MF battery | Nos | 25000 | 182 | 21186.4407 | 4550000 | 286 | 7150000 | 2600000 | 0 | 52 | 1300000 | 52 | 1300000 | 0 | 0 | 234 | 5850000 | 338 | 8450000 | 2600000 | 0 | 384 | 9600000 | 3750000 | 0 | 8750 | 1592500 | 3360000
123 | SOTC124 | Supply and providing of UPS cum battery rack 20 batteries | Nos | 30000 | 7 | 25423.7288 | 210000 | 11 | 330000 | 120000 | 0 | 2 | 60000 | 2 | 60000 | 0 | 0 | 9 | 270000 | 13 | 390000 | 120000 | 0 | 12 | 360000 | 90000 | 0 | 10500 | 73500 | 126000
124 | SOTC125 | Supply, Transportation, Installation, Testing and commissioning of storage / Pressure type 5 Star rated water heater with ABS plastic body of 15 Ltrs | Nos | 16000 | 7 | 13559.322 | 112000 | 12 | 192000 | 80000 | 0 |  | 0 |  | 0 | 0 | 0 | 7 | 112000 | 11 | 176000 | 64000 | 0 | 11 | 176000 | 64000 | 0 | 5600 | 39200 | 61600
125 | SOTC126 | 26 persons ICU bed cum passenger lift (1768 Kgs) G+8 Floors, 9 stops,9 Openings (Cost Includes amount for Construction of Shaft / Cladding from Ground to 8th Floor) | Nos | 10495000 | 1 | 8894067.7966 | 10495000 | 1 | 10495000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 10495000 | 1 | 10495000 | 0 | 0 | 1 | 10495000 | 0 | 0 | 3673250 | 3673250 | 3673250
126 | SOTC127 | 1.50 TR with , 18000 BTU/Hr High Wall mount Split Air Conditioners | Nos | 150000 | 6 | 127118.6441 | 900000 | 6 | 900000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 6 | 900000 | 6 | 900000 | 0 | 0 | 7 | 1050000 | 150000 | 0 | 52500 | 315000 | 367500
127 | SOTC128 | 2.0 TR with , 24000 BTU/Hr High Wall mount Split Air Conditioners | Nos | 210000 | 2 | 177966.1017 | 420000 | 6 | 1260000 | 840000 | 0 |  | 0 |  | 0 | 0 | 0 | 2 | 420000 | 6 | 1260000 | 840000 | 0 | 6 | 1260000 | 840000 | 0 | 73500 | 147000 | 441000
128 | SOTC129 | Voltage stabilizer for 4 KVA maximum load | Nos | 7000 | 6 | 5932.2034 | 42000 | 6 | 42000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 6 | 42000 | 6 | 42000 | 0 | 0 | 7 | 49000 | 7000 | 0 | 2450 | 14700 | 17150
129 | SOTC130 | Voltage stabilizer for 5 KVA maximum load | Nos | 8500 | 2 | 7203.3898 | 17000 | 6 | 51000 | 34000 | 0 |  | 0 |  | 0 | 0 | 0 | 2 | 17000 | 6 | 51000 | 34000 | 0 | 6 | 51000 | 34000 | 0 | 2975 | 5950 | 17850
130 | SOTC131 | Ductable Air Conditioners 11.0 TR with ISEER ≥ 4 | Nos | 1200000 | 1 | 1016949.1525 | 1200000 | 1 | 1200000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 1200000 | 1 | 1200000 | 0 | 0 | 1 | 1200000 | 0 | 0 | 420000 | 420000 | 420000
131 | SOTC132 | Ductable Air Conditioners 8.5 TR with ISEER ≥ 4 | Nos | 1000000 | 2 | 847457.6271 | 2000000 | 2 | 2000000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 2 | 2000000 | 2 | 2000000 | 0 | 0 | 4 | 4000000 | 2000000 | 0 | 350000 | 700000 | 1400000
132 | SOTC133 | Ductable Air Conditioners 5.5 TR with ISEER ≥ 4 | Nos | 900000 | 1 | 762711.8644 | 900000 | 3 | 2700000 | 1800000 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 900000 | 3 | 2700000 | 1800000 | 0 | 3 | 2700000 | 1800000 | 0 | 315000 | 315000 | 945000
133 | SOTC134 | Automatic Smoke Detection System | Job | 1425000 | 1 | 1207627.1186 | 1425000 | 1 | 1425000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 1425000 | 1 | 1425000 | 0 | 0 | 1 | 1425000 | 0 | 0 | 498750 | 498750 | 498750
134 | SOTC135 | Automatic Fire Alarm System | Job | 1400000 | 1 | 1186440.678 | 1400000 | 1 | 1400000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 1400000 | 1 | 1400000 | 0 | 0 | 1 | 1400000 | 0 | 0 | 490000 | 490000 | 490000
135 | SOTC136 | Supply & Fixing of 4.5Kg, CO2 Type Fire Extinguisher. | Nos | 27000 | 6 | 22881.3559 | 162000 | 6 | 162000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 6 | 162000 | 6 | 162000 | 0 | 0 | 6 | 162000 | 0 | 0 | 9450 | 56700 | 56700
136 | SOTC137 | Supply and fixing of ABC stored pressure squeeze grip type fire extinguishers, 9 kg capacity. | Nos | 16000 | 6 | 13559.322 | 96000 | 6 | 96000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 6 | 96000 | 6 | 96000 | 0 | 0 | 6 | 96000 | 0 | 0 | 5600 | 33600 | 33600
137 | SOTC138 | Supply and fixing of ABC Powder MAP 4 Kg Fire extinguisher | Nos | 11000 | 10 | 9322.0339 | 110000 | 10 | 110000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 10 | 110000 | 10 | 110000 | 0 | 0 | 10 | 110000 | 0 | 0 | 3850 | 38500 | 38500
138 | SOTC139 | Supply and fixing of 2 Kg Fire extinguisher Clean Agent | Nos | 22500 | 10 | 19067.7966 | 225000 | 10 | 225000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 10 | 225000 | 10 | 225000 | 0 | 0 | 10 | 225000 | 0 | 0 | 7875 | 78750 | 78750
139 | SOTC140 | Supply and fixing of Escape signage boards in Rigid Photo luminescent based glow | Nos | 2000 | 150 | 1694.9153 | 300000 | 150 | 300000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 150 | 300000 | 150 | 300000 | 0 | 0 | 150 | 300000 | 0 | 0 | 700 | 105000 | 105000
140 | SOTC141 | Supply & Fixing of Powder Coated Fire Rated doors. | Sqm | 29000 | 6 | 24576.2712 | 174000 | 3 | 87000 | 0 | 87000 |  | 0 |  | 0 | 0 | 0 | 6 | 174000 | 3 | 87000 | 0 | 87000 | 13.8 | 400200 | 226200 | 0 | 10150 | 60900 | 140070
141 | SOTC142 | Telephone & EPABX System | Job | 1000000 | 1 | 847457.6271 | 1000000 | 1 | 1000000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 1000000 | 1 | 1000000 | 0 | 0 | 1 | 1000000 | 0 | 0 | 350000 | 350000 | 350000
142 | SOTC143 | Local Area Network (LAN) System | Job | 1250000 | 1 | 1059322.0339 | 1250000 | 1 | 1250000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 1250000 | 1 | 1250000 | 0 | 0 | 1 | 1250000 | 0 | 0 | 437500 | 437500 | 437500
143 | SOTC144 | Biometric Access Control System | Nos | 300000 | 2 | 254237.2881 | 600000 | 3 | 900000 | 300000 | 0 |  | 0 |  | 0 | 0 | 0 | 2 | 600000 | 3 | 900000 | 300000 | 0 | 3 | 900000 | 300000 | 0 | 105000 | 210000 | 315000
144 | SOTC145 | Dismantling, clearing away and carefully stacking useful materials for re-use and disposal of unserviceable materials with 100m lead as directed by Engineer-in-Charge duly taking actual premeasurements before dismantling including all charges complete (Reinforced cement concrete) | Cum | 5400 | 10 | 4576.2712 | 54000 | 5.95 | 32130 | 0 | 21870 |  | 0 |  | 0 | 0 | 0 | 10 | 54000 | 5.95 | 32130 | 0 | 21870 | 10 | 54000 | 0 | 0 | 1890 | 18900 | 18900
145 | SOTC146 | Dismantling, clearing away and carefully stacking useful materials for re-use and disposal of unserviceable materials with 100m lead as directed by Engineer-in-Charge duly taking actual premeasurements before dismantling including all charges complete (Unreinforced cement concrete) | Cum | 4500 | 1.5 | 3813.5593 | 6750 | 49.43 | 222435 | 215685 | 0 |  | 0 |  | 0 | 0 | 0 | 1.5 | 6750 | 49.43 | 222435 | 215685 | 0 | 51.9015 | 233556.75 | 226806.75 | 0 | 1575 | 2362.5 | 81744.8625
146 | SOTC147 | Dismantling, clearing away and carefully stacking useful materials for re-use and disposal of unserviceable materials with 100m lead as directed by Engineer-in-Charge duly taking actual premeasurements before dismantling including all charges complete (Brick Masonary) | Cum | 900 | 118 | 762.7119 | 106200 | 145.42 | 130878 | 24678 | 0 |  | 0 |  | 0 | 0 | 0 | 118 | 106200 | 145.42 | 130878 | 24678 | 0 | 152.691 | 137421.9 | 31221.9 | 0 | 315 | 37170 | 48097.665
147 | SOTC148 | Dismantling, clearing away and carefully stacking useful materials for re-use and disposal of unserviceable materials with 100m lead as directed by Engineer-in-Charge duly taking actual premeasurements before dismantling including all charges complete (Kadapa slabs or shahabad stone slabs on sand bed) | Sqm | 630 | 25 | 533.8983 | 15750 | 659.93 | 415755.9 | 400005.9 | 0 |  | 0 |  | 0 | 0 | 0 | 25 | 15750 | 659.93 | 415755.9 | 400005.9 | 0 | 692.9265 | 436543.695 | 420793.695 | 0 | 220.5 | 5512.5 | 152790.2933
148 | SOTC149 | Dismantling doors, windows and clear storey windows, Ventilators etc., (wood or steel) shutters including Chowkhats, architraves,hold fasts and other attachments etc., and stacking them within 100m lead including charge etc., complete for finished item of work. (Not exceeding 3 sqm in area) | Nos | 1800 | 57 | 1525.4237 | 102600 | 203 | 365400 | 262800 | 0 |  | 0 |  | 0 | 0 | 0 | 57 | 102600 | 203 | 365400 | 262800 | 0 | 203 | 365400 | 262800 | 0 | 630 | 35910 | 127890
149 | SOTC150 | Conveyance of un-useful excavated earth to a distance of 16 KM for disposal including hire charges of T and P, labour charges etc., complete for finished item of work. | Cum | 900 | 250 | 762.7119 | 225000 | 299.78 | 269802 | 44802 | 0 |  | 0 |  | 0 | 0 | 0 | 250 | 225000 | 299.78 | 269802 | 44802 | 0 | 314.769 | 283292.1 | 58292.1 | 0 | 315 | 78750 | 99152.235
150 | SOTC151 | RCC M 25 grade design mix (For lintels) | Cum | 18900 | 3 | 16016.9492 | 56700 | 3.02 | 57078 | 378 | 0 |  | 0 |  | 0 | 0 | 0 | 3 | 56700 | 3.02 | 57078 | 378 | 0 | 3.171 | 59931.9 | 3231.9 | 0 | 6615 | 19845 | 20976.165
151 | SOTC152 | RCC M 20 grade design mix (50mm thick platforms) | Sqm | 1170 | 12 | 991.5254 | 14040 | 0 | 0 | 0 | 14040 |  | 0 |  | 0 | 0 | 0 | 12 | 14040 | 0 | 0 | 0 | 14040 | 0 | 0 | 0 | 14040 | 409.5 | 4914 | 0
152 | SOTC153 | RCC M 20 grade design mix (25 mm thick Shelves) | Sqm | 900 | 12 | 762.7119 | 10800 | 0 | 0 | 0 | 10800 |  | 0 |  | 0 | 0 | 0 | 12 | 10800 | 0 | 0 | 0 | 10800 | 0 | 0 | 0 | 10800 | 315 | 3780 | 0
153 | SOTC154 | Brick Masonry work in CM (1:6) prop in superstructure | Cum | 15300 | 3 | 12966.1017 | 45900 | 106.62 | 1631286 | 1585386 | 0 |  | 0 |  | 0 | 0 | 0 | 3 | 45900 | 106.62 | 1631286 | 1585386 | 0 | 111.951 | 1712850.3 | 1666950.3 | 0 | 5355 | 16065 | 599497.605
154 | SOTC155 | Reinforced Masonry for partition walls (100 mm thick) in CM (1:4) | Sqm | 2700 | 500 | 2288.1356 | 1350000 | 385.65 | 1041255 | 0 | 308745 |  | 0 |  | 0 | 0 | 0 | 500 | 1350000 | 385.65 | 1041255 | 0 | 308745 | 404.9325 | 1093317.75 | 0 | 256682.25 | 945 | 472500 | 382661.2125
155 | SOTC156 | PCC (1:3:6) nominal mix using 20mm size graded m/c (For bed blocks and hold fasts) (OTs screed) | Cum | 9000 | 1.5 | 7627.1186 | 13500 | 0 | 0 | 0 | 13500 |  | 0 |  | 0 | 0 | 0 | 1.5 | 13500 | 0 | 0 | 0 | 13500 | 0 | 0 | 0 | 13500 | 3150 | 4725 | 0
156 | SOTC157 | Filling with light weight concrete in Cement Concrete (1:5:10) proportion using brick jelly for low roofs | Cum | 7200 | 23 | 6101.6949 | 165600 | 16.062 | 115646.4 | 0 | 49953.6 |  | 0 |  | 0 | 0 | 0 | 23 | 165600 | 16.062 | 115646.4 | 0 | 49953.6 | 16.8651 | 121428.72 | 0 | 44171.28 | 2520 | 57960 | 42500.052
157 | SOTC158 | Thermo Mechanically Treated (Fe -500/500D/550D) for RCC works | MT | 126000 | 1.25 | 106779.661 | 157500 | 0.732 | 92232 | 0 | 65268 |  | 0 |  | 0 | 0 | 0 | 1.25 | 157500 | 0.732 | 92232 | 0 | 65268 | 0.7686 | 96843.6 | 0 | 60656.4 | 44100 | 55125 | 33895.26
158 | SOTC159 | Plastering 12mm thick in two coats with base coat of 8mm thick in CM (1:6) and top coat of 4mm thick in CM (1:4). for Internal walls. | Sqm | 1224 | 1600 | 1037.2881 | 1958400 | 2046.48 | 2504891.52 | 546491.52 | 0 |  | 0 |  | 0 | 0 | 0 | 1600 | 1958400 | 2046.48 | 2504891.52 | 546491.52 | 0 | 2148.804 | 2630136.096 | 671736.096 | 0 | 428.4 | 685440 | 920547.6336
159 | SOTC160 | Impervious coat to exposed RCC roof slab surfaces (APSS No. 901 and 903) For Toilets | Sqm | 360 | 77.78 | 305.0847 | 28000.8 | 41 | 14760 | 0 | 13240.8 |  | 0 |  | 0 | 0 | 0 | 77.78 | 28000.8 | 41 | 14760 | 0 | 13240.8 | 43.05 | 15498 | 0 | 12502.8 | 126 | 9800.28 | 5424.3
160 | SOTC161 | Providing and applying Wall putty of White Cement or Polymer or Cement based of average 1 to 2 mm thickness over plastered surface to prepare the surface even and smooth after thoroughly brushing the surface to remove all dirt and remains of loose powdered materials, applying emery paper, Sand the surface, clean & wipe off loose dust, applying knifing paste filler by putty knife / muslin pad, air dry for 2 - 3 | Sqm | 270 | 4447 | 228.8136 | 1200690 | 1725.27 | 465822.9 | 0 | 734867.1 |  | 0 |  | 0 | 0 | 0 | 4447 | 1200690 | 1725.27 | 465822.9 | 0 | 734867.1 | 1811.5335 | 489114.045 | 0 | 711575.955 | 94.5 | 420241.5 | 171189.9158
161 | SOTC162 | Flooring with non-skid full body ceramic floor tiles | Sqm | 1710 | 85 | 1449.1525 | 145350 | 93.41 | 159731.1 | 14381.1 | 0 |  | 0 |  | 0 | 0 | 0 | 85 | 145350 | 93.41 | 159731.1 | 14381.1 | 0 | 98.0805 | 167717.655 | 22367.655 | 0 | 598.5 | 50872.5 | 58701.1793
162 | SOTC163 | Dadooing to walls with glazed full body Porcelain wall tiles | Sqm | 1440 | 225 | 1220.339 | 324000 | 372.89 | 536961.6 | 212961.6 | 0 |  | 0 |  | 0 | 0 | 0 | 225 | 324000 | 372.89 | 536961.6 | 212961.6 | 0 | 391.5345 | 563809.68 | 239809.68 | 0 | 504 | 113400 | 197333.388
163 | SOTC164 | Dadooing to walls with glazed full body Ceramic tiles | Sqm | 1440 | 350 | 1220.339 | 504000 | 257.35 | 370584 | 0 | 133416 |  | 0 |  | 0 | 0 | 0 | 350 | 504000 | 257.35 | 370584 | 0 | 133416 | 270.2175 | 389113.2 | 0 | 114886.8 | 504 | 176400 | 136189.62
164 | SOTC165 | Painting one coat water based cement primer of interior grade I and two coats of acrylic emulsion paint for ceiling and Walls | Sqm | 360 | 4447 | 305.0847 | 1600920 | 1306.68 | 470404.8 | 0 | 1130515.2 |  | 0 |  | 0 | 0 | 0 | 4447 | 1600920 | 1306.68 | 470404.8 | 0 | 1130515.2 | 1372.014 | 493925.04 | 0 | 1106994.96 | 126 | 560322 | 172873.764
165 | SOTC166 | Painting to new wood work | Sqm | 360 | 313 | 305.0847 | 112680 | 60 | 21600 | 0 | 91080 |  | 0 |  | 0 | 0 | 0 | 313 | 112680 | 60 | 21600 | 0 | 91080 | 75 | 27000 | 0 | 85680 | 126 | 39438 | 9450
166 | SOTC167 | Painting to new iron work | Sqm | 270 | 88 | 228.8136 | 23760 | 120.4 | 32508 | 8748 | 0 |  | 0 |  | 0 | 0 | 0 | 88 | 23760 | 120.4 | 32508 | 8748 | 0 | 126.42 | 34133.4 | 10373.4 | 0 | 94.5 | 8316 | 11946.69
167 | SOTC168 | Two shutter cupboards | Sqm | 9000 | 100 | 7627.1186 | 900000 | 0 | 0 | 0 | 900000 |  | 0 |  | 0 | 0 | 0 | 100 | 900000 | 0 | 0 | 0 | 900000 | 0 | 0 | 0 | 900000 | 3150 | 315000 | 0
168 | SOTC169 | UPVC Fixed Louvered Ventilator | Sqm | 12000 | 7 | 10169.4915 | 84000 | 15.73 | 188760 | 104760 | 0 |  | 0 |  | 0 | 0 | 0 | 7 | 84000 | 15.73 | 188760 | 104760 | 0 | 16.5165 | 198198 | 114198 | 0 | 4200 | 29400 | 69369.3
169 | SOTC170 | UPVC 3 track Sliding Windows | Sqm | 9000 | 15 | 7627.1186 | 135000 | 43.12 | 388080 | 253080 | 0 |  | 0 |  | 0 | 0 | 0 | 15 | 135000 | 43.12 | 388080 | 253080 | 0 | 45.276 | 407484 | 272484 | 0 | 3150 | 47250 | 142619.4
170 | SOTC171 | MS Grills to Windows | Sqm | 1800 | 150 | 1525.4237 | 270000 | 120.4 | 216720 | 0 | 53280 |  | 0 |  | 0 | 0 | 0 | 150 | 270000 | 120.4 | 216720 | 0 | 53280 | 126.42 | 227556 | 0 | 42444 | 630 | 94500 | 79644.6
171 | SOTC172 | Flooring with 16 to 18 mm thick high polished granite stone slabs black colour for platforms (S.S.701 and special) | Sqm | 6300 | 50 | 5338.9831 | 315000 | 402.07 | 2533041 | 2218041 | 0 |  | 0 |  | 0 | 0 | 0 | 50 | 315000 | 402.07 | 2533041 | 2218041 | 0 | 422.1735 | 2659693.05 | 2344693.05 | 0 | 2205 | 110250 | 930892.5675
172 | SOTC173 | Doors as per approved drawings with medium teak wood frame (1500mm x 2600mm) | Sqm | 6300 | 50 | 5338.9831 | 315000 | 14.16 | 89208 | 0 | 225792 |  | 0 |  | 0 | 0 | 0 | 50 | 315000 | 14.16 | 89208 | 0 | 225792 | 15.4 | 97020 | 0 | 217980 | 2205 | 110250 | 33957
173 | SOTC174 | Doors as per approved drawings with medium teak wood frame (1000mm x 2100mm) | Sqm | 7400 | 45 | 6271.1864 | 333000 | 8.98 | 66452 | 0 | 266548 |  | 0 |  | 0 | 0 | 0 | 45 | 333000 | 8.98 | 66452 | 0 | 266548 | 17.2 | 127280 | 0 | 205720 | 2590 | 116550 | 44548
174 | SOTC175 | Doors Shutters WPC(800mm x 2100mm) | Sqm | 5400 | 40 | 4576.2712 | 216000 | 31.79 | 171666 | 0 | 44334 |  | 0 |  | 0 | 0 | 0 | 40 | 216000 | 31.79 | 171666 | 0 | 44334 | 33.3795 | 180249.3 | 0 | 35750.7 | 1890 | 75600 | 63087.255
175 | SOTC176 | Scientific Doors with metal door frames and door shutters made of galvanize steel | Sqm | 18000 | 45 | 15254.2373 | 810000 | 78.72 | 1416960 | 606960 | 0 |  | 0 |  | 0 | 0 | 0 | 45 | 810000 | 78.72 | 1416960 | 606960 | 0 | 77.65 | 1397700 | 587700 | 0 | 6300 | 283500 | 489195
176 | SOTC177 | False ceiling as per Technical specification | Sqm | 1800 | 1400 | 1525.4237 | 2520000 | 825.4 | 1485720 | 0 | 1034280 |  | 0 |  | 0 | 0 | 0 | 1400 | 2520000 | 825.4 | 1485720 | 0 | 1034280 | 866.67 | 1560006 | 0 | 959994 | 630 | 882000 | 546002.1
177 | SOTC178 | Vinyl flooring | Sqm | 3000 | 500 | 2542.3729 | 1500000 | 691 | 2073000 | 573000 | 0 |  | 0 |  | 0 | 0 | 0 | 500 | 1500000 | 691 | 2073000 | 573000 | 0 | 725.55 | 2176650 | 676650 | 0 | 1050 | 525000 | 761827.5
178 | SOTC179 | Impervious coat to exposed RCC roof slab surfacesof 20mm thick (APSS No. 901 and 903) | Sqm | 1260 | 350 | 1067.7966 | 441000 | 0 | 0 | 0 | 441000 |  | 0 |  | 0 | 0 | 0 | 350 | 441000 | 0 | 0 | 0 | 441000 | 0 | 0 | 0 | 441000 | 441 | 154350 | 0
179 | SOTC180 | Fixed Glass Window – 1200 x 1200 | Sqm | 5400 | 53.55 | 4576.2712 | 289170 | 60.51 | 326754 | 37584 | 0 |  | 0 |  | 0 | 0 | 0 | 53.55 | 289170 | 60.51 | 326754 | 37584 | 0 | 61.01 | 329454 | 40284 | 0 | 1890 | 101209.5 | 115308.9
180 | SOTC181 | Grouting the holes with neat cement slurry of 20mm dia with all required accessories of all materials etc., including cost & Conveyance of all labour Charges etc., complete finished item of work (*As per SSR2021-22 of S.NO:-8) | Nos | 180 | 500 | 152.5424 | 90000 | 0 | 0 | 0 | 90000 |  | 0 |  | 0 | 0 | 0 | 500 | 90000 | 0 | 0 | 0 | 90000 | 0 | 0 | 0 | 90000 | 63 | 31500 | 0
181 | SOTC182 | Pressure grouting the drilled holes with neat cement slurry or with approved grout admixture using pump - excluding cost of drilling holes after fixing nozzles as technical specification approved by the department etc., including cost & Conveyance of all labour charges etc., complete finished item of work | Nos | 630 | 500 | 533.8983 | 315000 | 1084 | 682920 | 367920 | 0 |  | 0 |  | 0 | 0 | 0 | 500 | 315000 | 1084 | 682920 | 367920 | 0 | 1132 | 713160 | 398160 | 0 | 220.5 | 110250 | 249606
182 | SOTC183 | Supply and fabricating,erecting and fixing inposition trusses of approved design with structural steel other than MS. | Kgs | 180 | 6500 | 152.5424 | 1170000 | 6500 | 1170000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 6500 | 1170000 | 6500 | 1170000 | 0 | 0 | 6500 | 1170000 | 0 | 0 | 63 | 409500 | 409500
183 | SOTC184 | Supply and fixing of pre painted Galvalume Trapezoidal Profile Roofing with 0.50mm Thickness. | Sqm | 1080 | 65 | 915.2542 | 70200 | 65 | 70200 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 65 | 70200 | 65 | 70200 | 0 | 0 | 65 | 70200 | 0 | 0 | 378 | 24570 | 24570
184 | SOTC185 | 4" (101.6mm) multi floor trap with jali - UPVC/SWR | Nos | 270 | 25 | 228.8136 | 6750 | 44 | 11880 | 5130 | 0 |  | 0 |  | 0 | 0 | 0 | 25 | 6750 | 44 | 11880 | 5130 | 0 | 44 | 11880 | 5130 | 0 | 94.5 | 2362.5 | 4158
185 | SOTC186 | 580mm x 440mm long Orissa pan white glazed Water Closet | Nos | 5400 | 4 | 4576.2712 | 21600 | 4 | 21600 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 4 | 21600 | 4 | 21600 | 0 | 0 | 4 | 21600 | 0 | 0 | 1890 | 7560 | 7560
186 | SOTC187 | European Water Closet of 1st quality | Nos | 6300 | 9 | 5338.9831 | 56700 | 9 | 56700 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 9 | 56700 | 9 | 56700 | 0 | 0 | 9 | 56700 | 0 | 0 | 2205 | 19845 | 19845
187 | SOTC188 | Indian make Flat Back Wash Hand Basin 1st quality | Nos | 3600 | 16 | 3050.8475 | 57600 | 15 | 54000 | 0 | 3600 |  | 0 |  | 0 | 0 | 0 | 16 | 57600 | 15 | 54000 | 0 | 3600 | 15 | 54000 | 0 | 3600 | 1260 | 20160 | 18900
188 | SOTC189 | CP finish brass soap dish | Nos | 1100 | 21 | 932.2034 | 23100 | 21 | 23100 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 21 | 23100 | 21 | 23100 | 0 | 0 | 21 | 23100 | 0 | 0 | 385 | 8085 | 8085
189 | SOTC190 | TV shape mirror with plastic frame of size 609.6mm x 457.2mm | Nos | 630 | 25 | 533.8983 | 15750 | 15 | 9450 | 0 | 6300 |  | 0 |  | 0 | 0 | 0 | 25 | 15750 | 15 | 9450 | 0 | 6300 | 15 | 9450 | 0 | 6300 | 220.5 | 5512.5 | 3307.5
190 | SOTC191 | 25.4mm dia , 609.6mm long aluminium anodized towel rods | Nos | 540 | 36 | 457.6271 | 19440 | 21 | 11340 | 0 | 8100 |  | 0 |  | 0 | 0 | 0 | 36 | 19440 | 21 | 11340 | 0 | 8100 | 21 | 11340 | 0 | 8100 | 189 | 6804 | 3969
191 | SOTC192 | 15 mm brass body CP finish bib tap of not less than 300 grams weight | Nos | 540 | 25 | 457.6271 | 13500 | 14 | 7560 | 0 | 5940 |  | 0 |  | 0 | 0 | 0 | 25 | 13500 | 14 | 7560 | 0 | 5940 | 14 | 7560 | 0 | 5940 | 189 | 4725 | 2646
192 | SOTC193 | Self Closing Tap - Push Type | Nos | 720 | 25 | 610.1695 | 18000 | 15 | 10800 | 0 | 7200 |  | 0 |  | 0 | 0 | 0 | 25 | 18000 | 15 | 10800 | 0 | 7200 | 15 | 10800 | 0 | 7200 | 252 | 6300 | 3780
193 | SOTC194 | Chromium plated finish brass body quarter turn Bibcock cum Health Faucet | Nos | 3600 | 12 | 3050.8475 | 43200 | 24 | 86400 | 43200 | 0 |  | 0 |  | 0 | 0 | 0 | 12 | 43200 | 24 | 86400 | 43200 | 0 | 24 | 86400 | 43200 | 0 | 1260 | 15120 | 30240
194 | SOTC195 | Ashirvad/ Ajay/ Astral Flowguard or equivalent CPVC Pipes and Fittings - 15.90mm OD pipe | Rmt | 270 | 55 | 228.8136 | 14850 | 103.08 | 27831.6 | 12981.6 | 0 |  | 0 |  | 0 | 0 | 0 | 55 | 14850 | 103.08 | 27831.6 | 12981.6 | 0 | 108.234 | 29223.18 | 14373.18 | 0 | 94.5 | 5197.5 | 10228.113
195 | SOTC196 | Ashirvad/Ajay/Astral Flowguard or equivalent CPVC Pipes and Fittings - 22.20mm OD pipe | Rmt | 360 | 115 | 305.0847 | 41400 | 123.53 | 44470.8 | 3070.8 | 0 |  | 0 |  | 0 | 0 | 0 | 115 | 41400 | 123.53 | 44470.8 | 3070.8 | 0 | 129.7065 | 46694.34 | 5294.34 | 0 | 126 | 14490 | 16343.019
196 | SOTC197 | Ashirvad/ Ajay/ Astral Flowguard or equivalent CPVC Pipes and Fittings -28.60mm OD pipe | Rmt | 450 | 143 | 381.3559 | 64350 | 110 | 49500 | 0 | 14850 |  | 0 |  | 0 | 0 | 0 | 143 | 64350 | 110 | 49500 | 0 | 14850 | 115.5 | 51975 | 0 | 12375 | 157.5 | 22522.5 | 18191.25
197 | SOTC198 | Bronze Gate/ Globe valve - 25mm Nominal bore | Nos | 1440 | 15 | 1220.339 | 21600 | 20 | 28800 | 7200 | 0 |  | 0 |  | 0 | 0 | 0 | 15 | 21600 | 20 | 28800 | 7200 | 0 | 20 | 28800 | 7200 | 0 | 504 | 7560 | 10080
198 | SOTC199 | SWR PVC pipes (Prince/ Sudhakar/ Kisan/ Supreme or any ISI brand) 4 Kg/Sq.cm. - 75mmdia | Rmt | 450 | 145 | 381.3559 | 65250 | 80 | 36000 | 0 | 29250 |  | 0 |  | 0 | 0 | 0 | 145 | 65250 | 80 | 36000 | 0 | 29250 | 84 | 37800 | 0 | 27450 | 157.5 | 22837.5 | 13230
199 | SOTC200 | SWR PVC pipes (Prince/ Sudhakar/ Kisan/ Supreme or any ISI brand) 4 Kg/Sq.cm. -110mmdia | Rmt | 540 | 145 | 457.6271 | 78300 | 65 | 35100 | 0 | 43200 |  | 0 |  | 0 | 0 | 0 | 145 | 78300 | 65 | 35100 | 0 | 43200 | 68.25 | 36855 | 0 | 41445 | 189 | 27405 | 12899.25
200 | SOTC201 | Supplying and fixing15 mm nominal size 152.0 mm CP finish iron body shower rose 1st quality including cost and conveyance of all materials, labour charges , overheads & contractors profit for finished item of work in all floors. | Nos | 630 | 5 | 533.8983 | 3150 | 6 | 3780 | 630 | 0 |  | 0 |  | 0 | 0 | 0 | 5 | 3150 | 6 | 3780 | 630 | 0 | 630 | 396900 | 393750 | 0 | 220.5 | 1102.5 | 138915
201 | SOTC202 | Supply and Fixing of white glazed flat back bowl urinals | Nos | 2700 | 4 | 2288.1356 | 10800 | 0 | 0 | 0 | 10800 |  | 0 |  | 0 | 0 | 0 | 4 | 10800 | 0 | 0 | 0 | 10800 | 0 | 0 | 0 | 10800 | 945 | 3780 | 0
202 | SOTC203 | Supply and fixing of 16mm to 20 mm thick ploished marbles slab partitions of size 4'0"*2'0" | Nos | 3600 | 10 | 3050.8475 | 36000 | 0 | 0 | 0 | 36000 |  | 0 |  | 0 | 0 | 0 | 10 | 36000 | 0 | 0 | 0 | 36000 | 0 | 0 | 0 | 36000 | 1260 | 12600 | 0
203 | SOTC204 | 28 mm dia. and 0.90 mm thick Copper Pipe Lines for Main lines | Rmt | 1750 | 700 | 1483.0508 | 1225000 | 832 | 1456000 | 231000 | 0 |  | 0 |  | 0 | 0 | 0 | 700 | 1225000 | 832 | 1456000 | 231000 | 0 | 833 | 1457750 | 232750 | 0 | 612.5 | 428750 | 510212.5
204 | SOTC205 | 42 mm dia. and 1.20 mm thick Copper Pipe Lines for Main lines | Rmt | 2250 | 200 | 1906.7797 | 450000 | 226 | 508500 | 58500 | 0 |  | 0 |  | 0 | 0 | 0 | 200 | 450000 | 226 | 508500 | 58500 | 0 | 227 | 510750 | 60750 | 0 | 787.5 | 157500 | 178762.5
205 | SOTC206 | 54 mm dia. and 1.20 mm thick Copper Pipe Lines for Main lines | Rmt | 2950 | 550 | 2500 | 1622500 | 550 | 1622500 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 550 | 1622500 | 550 | 1622500 | 0 | 0 | 564 | 1663800 | 41300 | 0 | 1032.5 | 567875 | 582330
206 | SOTC207 | 12 mm dia. and 0.70 mm thick Copper Pipe Lines for distribution lines | Rmt | 650 | 320 | 550.8475 | 208000 | 591 | 384150 | 176150 | 0 |  | 0 |  | 0 | 0 | 0 | 320 | 208000 | 591 | 384150 | 176150 | 0 | 544 | 353600 | 145600 | 0 | 227.5 | 72800 | 123760
207 | SOTC208 | 15 mm dia. and 0.90 mm thick Copper Pipe Lines for distribution lines | Rmt | 950 | 525 | 805.0847 | 498750 | 838 | 796100 | 297350 | 0 |  | 0 |  | 0 | 0 | 0 | 525 | 498750 | 838 | 796100 | 297350 | 0 | 757 | 719150 | 220400 | 0 | 332.5 | 174562.5 | 251702.5
208 | SOTC209 | 22 mm dia. and 0.90 mm thick Copper Pipe Lines for distribution lines | Rmt | 1450 | 530 | 1228.8136 | 768500 | 636 | 922200 | 153700 | 0 |  | 0 |  | 0 | 0 | 0 | 530 | 768500 | 636 | 922200 | 153700 | 0 | 595 | 862750 | 94250 | 0 | 507.5 | 268975 | 301962.5
209 | SOTC210 | 15 mm (1/2") Isolation Valves | Nos | 1500 | 40 | 1271.1864 | 60000 | 35 | 52500 | 0 | 7500 |  | 0 |  | 0 | 0 | 0 | 40 | 60000 | 35 | 52500 | 0 | 7500 | 31 | 46500 | 0 | 13500 | 525 | 21000 | 16275
210 | SOTC211 | 22 mm (3/4") Isolation Valves | Nos | 2500 | 15 | 2118.6441 | 37500 | 13 | 32500 | 0 | 5000 |  | 0 |  | 0 | 0 | 0 | 15 | 37500 | 13 | 32500 | 0 | 5000 | 14 | 35000 | 0 | 2500 | 875 | 13125 | 12250
211 | SOTC212 | 28 mm Isolation Valves | Nos | 3500 | 3 | 2966.1017 | 10500 | 7 | 24500 | 14000 | 0 | 2 | 7000 | 2 | 7000 | 0 | 0 | 5 | 17500 | 9 | 31500 | 14000 | 0 | 9 | 31500 | 14000 | 0 | 1225 | 3675 | 11025
212 | SOTC213 | 42 mm Isolation Valves | Nos | 4500 | 2 | 3813.5593 | 9000 | 2 | 9000 | 0 | 0 | 3 | 13500 | 2 | 9000 | 0 | 4500 | 5 | 22500 | 4 | 18000 | 0 | 4500 | 4 | 18000 | 0 | 4500 | 1575 | 3150 | 6300
213 | SOTC214 | 54 mm Isolation Valves | Nos | 5500 | 2 | 4661.0169 | 11000 | 5 | 27500 | 16500 | 0 | 1 | 5500 | 1 | 5500 | 0 | 0 | 3 | 16500 | 6 | 33000 | 16500 | 0 | 10 | 55000 | 38500 | 0 | 1925 | 3850 | 19250
214 | SOTC215 | Gas Outlet Points with probes for Oxygen with S Brackets | Nos | 2850 | 189 | 2415.2542 | 538650 | 231 | 658350 | 119700 | 0 |  | 0 |  | 0 | 0 | 0 | 189 | 538650 | 231 | 658350 | 119700 | 0 | 206 | 587100 | 48450 | 0 | 997.5 | 188527.5 | 205485
215 | SOTC216 | 2 Gas Digital Area Alarm Panels | Nos | 25000 | 2 | 21186.4407 | 50000 | 0 | 0 | 0 | 50000 |  | 0 |  | 0 | 0 | 0 | 2 | 50000 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 50000 | 8750 | 17500 | 0
216 | SOTC217 | 3 Gas Digital Area Alarm Panels | Nos | 30000 | 4 | 25423.7288 | 120000 | 5 | 150000 | 30000 | 0 |  | 0 |  | 0 | 0 | 0 | 4 | 120000 | 5 | 150000 | 30000 | 0 | 5 | 150000 | 30000 | 0 | 10500 | 42000 | 52500
217 | SOTC218 | 5 Gas Digital Area Alarm Panels | Nos | 40000 | 5 | 33898.3051 | 200000 | 0 | 0 | 0 | 200000 | 1 | 40000 | 0 | 0 | 0 | 40000 | 6 | 240000 | 0 | 0 | 0 | 240000 | 0 | 0 | 0 | 240000 | 14000 | 70000 | 0
218 | SOTC219 | Master Digital Alarm Panels | Nos | 50000 | 1 | 42372.8814 | 50000 | 1 | 50000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 50000 | 1 | 50000 | 0 | 0 | 1 | 50000 | 0 | 0 | 17500 | 17500 | 17500
219 | SOTC220 | BPC Flow meter with Humidifier bottle and L adapter | Nos | 2250 | 27 | 1906.7797 | 60750 | 43 | 96750 | 36000 | 0 |  | 0 |  | 0 | 0 | 0 | 27 | 60750 | 43 | 96750 | 36000 | 0 | 43 | 96750 | 36000 | 0 | 787.5 | 21262.5 | 33862.5
220 | SOTC221 | L Type Adapter for Oxygen Flow meters | Nos | 1250 | 27 | 1059.322 | 33750 | 27 | 33750 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 27 | 33750 | 27 | 33750 | 0 | 0 | 27 | 33750 | 0 | 0 | 437.5 | 11812.5 | 11812.5
221 | SOTC222 | Kit for conversion of Oxygen | Nos | 1650 | 27 | 1398.3051 | 44550 | 18 | 29700 | 0 | 14850 |  | 0 |  | 0 | 0 | 0 | 27 | 44550 | 18 | 29700 | 0 | 14850 | 18 | 29700 | 0 | 14850 | 577.5 | 15592.5 | 10395
222 | SOTC223 | Suction Jars of 600 ml capacity | Nos | 3450 | 27 | 2923.7288 | 93150 | 37 | 127650 | 34500 | 0 |  | 0 |  | 0 | 0 | 0 | 27 | 93150 | 37 | 127650 | 34500 | 0 | 46 | 158700 | 65550 | 0 | 1027.5 | 27742.5 | 47265
223 | SOTC224 | Adapters for Vacuum | Nos | 750 | 27 | 635.5932 | 20250 | 27 | 20250 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 27 | 20250 | 27 | 20250 | 0 | 0 | 27 | 20250 | 0 | 0 | 262.5 | 7087.5 | 7087.5
224 | SOTC225 | Adapters for Air | Nos | 750 | 27 | 635.5932 | 20250 | 27 | 20250 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 27 | 20250 | 27 | 20250 | 0 | 0 | 27 | 20250 | 0 | 0 | 262.5 | 7087.5 | 7087.5
225 | SOTC226 | Adapters for Nitrous Oxide | Nos | 750 | 15 | 635.5932 | 11250 | 15 | 11250 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 15 | 11250 | 15 | 11250 | 0 | 0 | 15 | 11250 | 0 | 0 | 262.5 | 3937.5 | 3937.5
226 | SOTC227 | Vacuum Tube | Nos | 550 | 27 | 466.1017 | 14850 | 32 | 17600 | 2750 | 0 | 58 | 31900 | 5 | 2750 | 0 | 29150 | 85 | 46750 | 37 | 20350 | 0 | 26400 | 115 | 63250 | 16500 | 0 | 192.5 | 5197.5 | 22137.5
227 | SOTC228 | Bed Head wall panel horizontal 1500 mm long single railing | Nos | 35000 | 27 | 29661.0169 | 945000 | 31 | 1085000 | 140000 | 0 |  | 0 |  | 0 | 0 | 0 | 27 | 945000 | 31 | 1085000 | 140000 | 0 | 31 | 1085000 | 140000 | 0 | 12250 | 330750 | 379750
228 | SOTC229 | Valve box -2 services | Nos | 9500 | 1 | 8050.8475 | 9500 | 0 | 0 | 0 | 9500 |  | 0 |  | 0 | 0 | 0 | 1 | 9500 | 0 | 0 | 0 | 9500 | 0 | 0 | 0 | 9500 | 3325 | 3325 | 0
229 | SOTC230 | Valve box -3 services | Nos | 14500 | 3 | 12288.1356 | 43500 | 5 | 72500 | 29000 | 0 |  | 0 |  | 0 | 0 | 0 | 3 | 43500 | 5 | 72500 | 29000 | 0 | 5 | 72500 | 29000 | 0 | 5075 | 15225 | 25375
230 | SOTC231 | Valve box -6 services | Nos | 22500 | 1 | 19067.7966 | 22500 | 2 | 45000 | 22500 | 0 | 5 | 112500 | 5 | 112500 | 0 | 0 | 6 | 135000 | 7 | 157500 | 22500 | 0 | 6 | 135000 | 0 | 0 | 7875 | 7875 | 47250
231 | SOTC232 | 4 + 4 size of CO2 manifold System | Job | 40000 | 1 | 33898.3051 | 40000 | 1 | 40000 | 0 | 0 | 1 | 40000 | 1 | 40000 | 0 | 0 | 2 | 80000 | 2 | 80000 | 0 | 0 | 3 | 120000 | 40000 | 0 | 14000 | 14000 | 42000
232 | SOTC233 | 2 cylinder emergency manifold | Job | 14500 | 1 | 12288.1356 | 14500 | 1 | 14500 | 0 | 0 | 1 | 14500 | 1 | 14500 | 0 | 0 | 2 | 29000 | 2 | 29000 | 0 | 0 | 2 | 29000 | 0 | 0 | 5075 | 5075 | 10150
233 | SOTC234 | Fully Automatic CO2 Control System | Job | 185000 | 1 | 156779.661 | 185000 | 1 | 185000 | 0 | 0 | 1 | 185000 | 1 | 185000 | 0 | 0 | 2 | 370000 | 2 | 370000 | 0 | 0 | 2 | 370000 | 0 | 0 | 64750 | 64750 | 129500
234 | SOTC235 | Aneste Iwata Make TFS 150 C9 Model, Compresso Two stage, Motor 15 HP & 57.18 CFM, 60 CFM Air Dryer with 2000 Ltrs Receiver Twin System (For Air4, Air7) | Job | 1895000 | 1 | 1605932.2034 | 1895000 | 1 | 1895000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 1895000 | 1 | 1895000 | 0 | 0 | 1 | 1895000 | 0 | 0 | 663250 | 663250 | 663250
235 | SOTC236 | Supporting structure for MGPS lines with Ismb Columns, beams, MS angles, Flats and square rods | Job | 795000 | 1 | 673728.8136 | 795000 | 1 | 795000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 795000 | 1 | 795000 | 0 | 0 | 1 | 795000 | 0 | 0 | 278250 | 278250 | 278250
236 | SOTC237 | 2x20 Oxygen Main manifold System | Job | 95000 | 1 | 80508.4746 | 95000 | 1 | 95000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 95000 | 1 | 95000 | 0 | 0 | 1 | 95000 | 0 | 0 | 33250 | 33250 | 33250
237 | SOTC238 | Electrical Control Panel for MGPS | Job | 145000 | 1 | 122881.3559 | 145000 | 1 | 145000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 145000 | 1 | 145000 | 0 | 0 | 1 | 145000 | 0 | 0 | 50750 | 50750 | 50750
238 | SOTC239 | Vaccum system Ingersoll Rand Make Model 15V x 10 Model with 5 HP Motor with 1000 Liters Reciever, Filters, Electricals, Etc Secretion Trap and Bacteria Filter | Job | 1495000 | 2 | 1266949.1525 | 2990000 | 2 | 2990000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 2 | 2990000 | 2 | 2990000 | 0 | 0 | 2 | 2990000 | 0 | 0 | 523250 | 1046500 | 1046500
239 | SOTC240 | Validation By Third Party Agency Charges per Each MOT | Each | 100000 | 4 | 84745.7627 | 400000 | 4 | 400000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 4 | 400000 | 4 | 400000 | 0 | 0 | 9 | 900000 | 500000 | 0 | 35000 | 140000 | 315000
240 | SOTC241 | Anesthetic Gas Scavenging System (AGSS) | Job | 1213000 | 1 | 1027966.1017 | 1213000 | 1 | 1213000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 1213000 | 1 | 1213000 | 0 | 0 | 1 | 1213000 | 0 | 0 | 424550 | 424550 | 424550
241 | New item | Double Arm Surgical Pendants (Imported) | Nos | 1195000 | 0 |  | 0 | 0 | 0 | 0 | 0 | 6 | 7170000 | 6 | 7170000 | 0 | 0 | 6 | 7170000 | 6 | 7170000 | 0 | 0 | 6 | 7170000 | 0 | 0
|  | GRAND TOTAL |  |  |  |  | 175773220.8 |  | 178852525.92 | 19724900.12 | 16645595 |  | 39441980 |  | 36047834.55 | 535753.7 | 3929899.15 |  | 215215200.8 | 62753.552 | 214884360.47 | 19936150.12 | 20266990.45 |  | 229698479.591 | 33503500.314 | 19020221.523 |  | 61476304.78 | 77551977.4568
SUPPLEMENTAL ITEMS
S.No |  | Item Description | UOM | Unit Rate (Rs.) |  |  |  | QTY | Amount (Rs.) | [10 empty] | QTY | Amount (Rs.) |  |  | QTY | Amount (Rs.)
1 |  | Supply and installation of Under-deck insulation sheets of 40 mm thick having more than 30 Kg/m3 density to ceiling by brush application of bituminous adhesive to the sheets and secured with screw along with washer at the centre of the sheet supported with GI wire running diagonally to the sheet of 2mm dia. | Sqm | 744 |  |  |  | 262.74 | 195478.56 | [10 empty] | 262.74 | 195478.56 |  |  | 262.74 | 195478.56
2 |  | PCC (1:3:6) nominal mix using 20mm size graded m/c (OTs screed) | Cum | 8000 |  |  |  | 28.01 | 224080 | [10 empty] | 28.01 | 224080 |  |  | 28.01 | 224080
3 |  | Supply and Laying of Floor leveller compund (self smoothing mortar) to level the surface, having bulk density not less than 2 Kg/l for a fresh mortor, compressive strength not less than 20 N/mm2, initial setting time not more than 40 minutes and offer a 25 minutes working time, The surface should be walkabe after 30 min of laying. | Sqm | 1070 |  |  | 51 | 636.23 | 680766.1 | [10 empty] | 636.23 | 680766.1 |  |  | 725.55 | 776338.5
4 |  | 800 KVA Transformer OLTC for transformers with RTCC: Supply, Transportation, Installation, Testing and Commissioning of 800 KVA TRANSFORMER with all test reports. The Transformer shall be designed and manufactured as per IS:1180 OLTC with level-II with initial filling of oil as per IS 335-1993. 1000 A LT Breaker Kiosk - 01 No.The basic details of the Transformer are as under. Makes: Kirloskar / PETE / Esennar / Voltamp / Crompton / ABB / Schneider. | Nos | 5000000 |  |  |  | 1 | 5000000 | [10 empty] | 1 | 5000000 |  |  | 1 | 5000000
5 |  | 4 Gas Digital Alarm Panels | Nos | 30000 |  |  |  | 1 | 30000 | [10 empty] | 1 | 30000 |  |  | 1 | 30000
6 |  | 6 Gas Digital Alarm Panels | Nos | 40000 |  |  |  | 7 | 280000 | [10 empty] | 7 | 280000 |  |  | 7 | 280000
7 |  | Valve box 4 series | Nos | 14500 |  |  |  | 1 | 14500 | [10 empty] | 1 | 14500 |  |  | 1 | 14500
8 |  | 4 + 4 O2 manifold system | Job | 40000 |  |  |  | 1 | 40000 | [10 empty] | 1 | 40000 |  |  | 1 | 40000
9 |  | Fully automatic O2 control system | Job | 185000 |  |  |  | 1 | 185000 | [10 empty] | 1 | 185000 |  |  | 1 | 185000
10 |  | Supply and installation of 80mm thick double skin modular wall Panels made of 0.8 mm thick powder coated GI on both the sides, with 40 plus or minus 2 kg/m3 density PUF as infill, GI profiles all along the periphery, flush on both sides with maximum allowable gap of 3- 4mm filled with food grade silicon sealant and placed on cold rolled galvanised bottom tracks with a recess to provide floor to wall coving flush with the wall panel. This includes all required harware for completion Panels to be covered with a protective film to avoid any damages during transportation and installation | Sqm | 7801.8824 |  |  |  | 297.52 | 2321216.0376 | [10 empty] | 297.52 | 2321216.0376 |  |  | 312.396 | 2437276.8395
11 |  | Supply and installation of 50mm thick double skin ceiling system made of 0.8 mm thick Powder Coated GI sheets on both sides, 40 plus or minus 2 kg/m3 density PUF as infill, GI profiles all along the periphery, panels flush towards room side with maximum allowable gap of 3-4mm at panel to panel joints filled with silicon sealant. Ceiling panels are suspended from the RCC slab by using concealed AL ceiling grid with tie rod and adjustable turn buckle arrangement etc. This includes all required hardware for completion. Panels to be covered with a protective film to avoid any damages during transportation and installation | Sqm | 7114.7059 |  |  |  | 163.08 | 1160266.2353 | [10 empty] | 163.08 | 1160266.2353 |  |  | 171.234 | 1218279.5471
12 |  | Providing dadooing to walls with glazed full body ceramic wall tiles of size 800 x 1600 mm with any type of design texture such as marble finish, wooden, bamboo, stone finishes etc., scratch less, stain free and thickness between 6-8 mm 1st quality conforming to IS:13711, IS:13712, IS:13630 Parts 1 to 15 of any colour and finish in all shades and designs with borders as approved by Engineer-in-Charge set over base coat of CM1:5 12 mm thick using screened sand with cement slurry of honey like consistency spread at the rate of 3.30 kgs per sqm and jointing with white cement paste mixed with pigment of matching shade to full depth, including cost of all materials like tiles, cement, sand and water etc., complete for finished item of work. | Sqm | 3422 | [15 empty] | 113.7 | 389081.4 |  |  | 119.385 | 408535.47
13 |  | Supply and installation of double pass RO system with raw water tank capacity of 5000 ltr plastic tank having 2 nos feed pumps of 1.5 HP with max flow of 9000 ltr/hr including construction of sand filter of dimensions (H=1665 mm, D=325 mm) with filter media as Quartz sand of SS vessel construction and Activated Carbon filter of dimensions (H= 1665mm) with filter media as Activated carbon (IV-600) of SS vessel construction, with 4 nos of spiral wound RO membrane of size 8 inch dia x 1 m length of make G.E OSMONICS (or) HYDRAUNAUTICS, 4 nos UV system with service flow of 1000 ltr/hr (Before Snd filter and after SS tank out-let) for supply for 10 beds in Post ICU, 4 beds in Transplant ICU and 1 for each TIR with drinage system for used water.) | Nos | 5500000 | [15 empty] | 1 | 5500000 |  |  | 1 | 5500000
14 |  | Glass Sliding Doors in TIR-2 & TIR-3 | Sqm | 25000 | [15 empty] | 20 | 500000 |  |  | 6.5 | 162500
15 |  | Supply and installation of 4-shelf shoe rack made of Grade 202 stainless steel, featuring an open design, perfectly upright frame, shelves fitted parallel at right angles, dimensions 900mm W x 325mm D x 900mm H, welded with MIG welding, buffed surface, and packaged in five ply corrugated board with 12mm HDPE strapping | Nos | 20000 | [15 empty] | 1 | 20000 |  |  | 1 | 20000
16 |  | Monitor Stand beside Bed in ICUs & TIRs | Nos | 0 | [15 empty] | 31 | 0 |  |  | 31 | 0
17 |  | 2 way AV communictaion in counselling room | Job | 175000 | [15 empty] | 1 | 175000 |  |  | 1 | 175000
18 |  | Removal of old Cement Mortor of Wall cladding | Sqm | 15 | [15 empty] | 543.3 | 8149.5 |  |  | 543.3 | 8149.5
19 |  | Local Area Network (LAN) System | Job | 385000 | [19 empty] | 1 | 385000
20 |  | Supply, Transportation and installation of 20KVA / 312V DC on line UPS system | Nos | [20 empty] | 2
21 |  | Water Proofing of roof and peripheral walls of south west block, 8th floor, Gandhi Hospital which includes Dismantling of existing screed and lifting of debris to ground floor, Surface preparation and cracks treatment, Providing Angle fillet/taper of 75mm X 75mm with polymer modified mortor in the ratio of cement:sand:admixture (1:1.5:1.5) (Forsoc Nitobond SBR/M-Crete PC Bond @ 10% by weight of cement), Applying 1 coat of Forsoc Nitoproof WB Primer, Application of 2 coats of pitch free based liquid applied single component elastomeric waterproofing membrane (Forsoc Nito proof 600PF/BASF HLM5000), Laying 200 GSM Geotextile Fabric, Laying of 125mm Fiber Reinforced M20 grade protective concrete screed on terrace, Control joints treatment and External walls repair with window Frame-walls joints/Gaps treatment. (Considered 7th floor peripheral walls also for water proofing) | Job
17060138.4166
[19 empty] | 39441980 | [5 empty] | 53925258.791 |  |  |  | 44122.22
80
24.1
827.13
1
7
1
1
1
1
1
1
1
470
88.5
61.5
147
534.3
[20 empty] | 0 | 0

## Sheet1
61520427 | #REF!
#REF! | #REF!

## RE (2)
REVISED ESTIMATE OF SOTC AT 8TH FLOOR, SOUTH-WEST BLOCK, GANDHI HOSPITAL
S.No | Item Code | Item Name |  |  | As Per Agmt. (4- OTs & 3-TIRs) |  |  | Actual Quantities for agreement items (with 4 Ots) |  | Variation |  | Addl. Sanction (2- OTs) |  | Actual QTY for Additional 2 OTs |  | Variation |  | Total |  | As Per Work Done/To Be Done |  | Variation |  | As Per Work Done /To Be Done |  | Variation |  | As per price bid CAMC unit rate | As per Agmt. - CAMC | Revised CAMC
|  |  | UOM | Unit Rate (Rs.) | QTY |  | Amount (Rs.) | QTY | Amount (Rs.) | Excess | Less | QTY | Amount (Rs.) | QTY | Amount (Rs.) | Excess | Less | QTY | Amount (Rs.) | QTY | Amount (Rs.) | Excess | Less | QTY | Amount (Rs.) | Excess | Less
1 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27
1 | SOTC001 | Stainless Steel Pre-fabricated Wall panels in MOTs1) Make: SS 304 medical grade JINDAL certified by a notified body NABL Lab.2) Not less than 50mm thick (0.80mm thick sheet on both sides).3) 41Kg/Cum density PUF, fine grain surface, treated with anti bacterial/anti fungal paint, shall be made with single sheet without any joints/welding, should be covered with a protective sheet. Certified by a notified body NABL Lab. | Sqm | 15010 | 400 | 12720.339 | 6004000 | 294.28 | 4417142.8 | 0 | 1586857.2 | 350 | 5253500 | 183.34 | 2751933.4 | 0 | 2501566.6 | 750 | 11257500 | 477.62 | 7169076.2 | 0 | 4088423.8 | 491.9486 | 7384148.486 | 0 | 3873351.514 | 5253.5 | 2101400 | 2584451.9701
2 | SOTC002 | Stainless Steel Pre-fabricated Ceiling panels In MOTs & MOTs Corridor | Sqm | 15010 | 385 | 12720.339 | 5778850 | 157.13 | 2358521.3 | 0 | 3420328.7 | 78 | 1170780 | 98.37 | 1476533.7 | 305753.7 | 0 | 463 | 6949630 | 255.5 | 3835055 | 0 | 3114575 | 263.165 | 3950106.65 | 0 | 2999523.35 | 5253.5 | 2022597.5 | 1382537.3275
3 | SOTC003 | Dynamic Hatch Box | Nos | 295000 | 2 | 250000 | 590000 | 0 | 0 | 0 | 590000 | 1 | 295000 | 0 | 0 | 0 | 295000 | 3 | 885000 | 0 | 0 | 0 | 885000 | 0 | 0 | 0 | 885000 | 103250 | 206500 | 0
4 | SOTC004 | Electro conductive Flooring inside MOTs | Sqm | 4035 | 160 | 3419.4915 | 645600 | 139.94 | 564657.9 | 0 | 80942.1 | 80 | 322800 | 73.57 | 296854.95 | 0 | 25945.05 | 240 | 968400 | 213.51 | 861512.85 | 0 | 106887.15 | 217.7802 | 878743.107 | 0 | 89656.893 | 1412.25 | 225960 | 307560.0874
5 | SOTC005 | Flooring with Vinyl Sheets In MOT Corridor | Sqm | 3750 | 175 | 3177.9661 | 656250 | 44.828 | 168105 | 0 | 488145 | 50 | 187500 | 39.67 | 148762.5 | 0 | 38737.5 | 225 | 843750 | 84.498 | 316867.5 | 0 | 526882.5 | 87.0329 | 326373.525 | 0 | 517376.475 | 1312.5 | 229687.5 | 114230.7338
6 | SOTC006 | Uni Directional Ceiling Laminar Airflow Systems | Nos | 465000 | 4 | 394067.7966 | 1860000 | 4 | 1860000 | 0 | 0 | 2 | 930000 | 2 | 930000 | 0 | 0 | 6 | 2790000 | 6 | 2790000 | 0 | 0 | 6 | 2790000 | 0 | 0 | 162750 | 651000 | 976500
7 | SOTC007 | Air Handling Units (AHUs) 11 TR | Nos | 1495000 | 4 | 1266949.1525 | 5980000 | 4 | 5980000 | 0 | 0 | 2 | 2990000 | 2 | 2990000 | 0 | 0 | 6 | 8970000 | 6 | 8970000 | 0 | 0 | 6 | 8970000 | 0 | 0 | 523250 | 2093000 | 3139500
8 | SOTC008 | Condensing Units | Nos | 345000 | 4 | 292372.8814 | 1380000 | 4 | 1380000 | 0 | 0 | 2 | 690000 | 2 | 690000 | 0 | 0 | 6 | 2070000 | 6 | 2070000 | 0 | 0 | 10 | 3450000 | 1380000 | 0 | 120750 | 483000 | 1207500
9 | SOTC009 | Pressure Relief Dampers | Nos | 22500 | 4 | 19067.7966 | 90000 | 4 | 90000 | 0 | 0 | 2 | 45000 | 2 | 45000 | 0 | 0 | 6 | 135000 | 6 | 135000 | 0 | 0 | 6 | 135000 | 0 | 0 | 7875 | 31500 | 47250
10 | SOTC010 | Single arm Anesthesia Pendants (Imported) | Nos | 1195000 | 4 | 1012711.8644 | 4780000 | 4 | 4780000 | 0 | 0 | 2 | 2390000 | 2 | 2390000 | 0 | 0 | 6 | 7170000 | 6 | 7170000 | 0 | 0 | 6 | 7170000 | 0 | 0 | 418250 | 1673000 | 2509500
11 | SOTC011 | Triple Dome Ceiling OT LED Lights (Imported) | Nos | 4750000 | 2 | 4025423.7288 | 9500000 | 2 | 9500000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2 | 9500000 | 2 | 9500000 | 0 | 0 | 2 | 9500000 | 0 | 0 | 1662500 | 3325000 | 3325000
12 | SOTC012 | Double Dome Ceiling OT LED Lights (Imported) | Nos | 3550000 | 2 | 3008474.5763 | 7100000 | 2 | 7100000 | 0 | 0 | 2 | 7100000 | 2 | 7100000 | 0 | 0 | 4 | 14200000 | 4 | 14200000 | 0 | 0 | 4 | 14200000 | 0 | 0 | 1242500 | 2485000 | 4970000
13 | SOTC013 | Detachable Hi Definition Cameras in Triple Dome Ceiling OT Lights | Nos | 995000 | 2 | 843220.339 | 1990000 | 2 | 1990000 | 0 | 0 | 1 | 995000 | 0 | 0 | 0 | 995000 | 3 | 2985000 | 2 | 1990000 | 0 | 995000 | 2 | 1990000 | 0 | 995000 | 348250 | 696500 | 696500
14 | SOTC014 | Ceiling/Wall mounted CCTV Room Camera | Nos | 22500 | 4 | 19067.7966 | 90000 | 4 | 90000 | 0 | 0 | 2 | 45000 | 2 | 45000 | 0 | 0 | 6 | 135000 | 6 | 135000 | 0 | 0 | 6 | 135000 | 0 | 0 | 7875 | 31500 | 47250
15 | SOTC015 | LED Peripheral Lights cum clean room (OT) luminaries | Nos | 18750 | 62 | 15889.8305 | 1162500 | 62 | 1162500 | 0 | 0 | 40 | 750000 | 40 | 750000 | 0 | 0 | 102 | 1912500 | 102 | 1912500 | 0 | 0 | 107 | 2006250 | 93750 | 0 | 6562.5 | 406875 | 702187.5
16 | SOTC016 | View Window with Motorised Blinds of 1 Mt Length & 1 Mt Height | Nos | 115000 | 7 | 97457.6271 | 805000 | 10 | 1150000 | 345000 | 0 | 2 | 230000 | 4 | 460000 | 230000 | 0 | 9 | 1035000 | 14 | 1610000 | 575000 | 0 | 14 | 1610000 | 575000 | 0 | 40250 | 281750 | 563500
17 | SOTC017 | Hermetically Sealed Doors (1.80mt x 2.10 mt) | Nos | 115000 | 4 | 97457.6271 | 460000 | 4 | 460000 | 0 | 0 | 2 | 230000 | 2 | 230000 | 0 | 0 | 6 | 690000 | 6 | 690000 | 0 | 0 | 7 | 805000 | 115000 | 0 | 40250 | 161000 | 281750
18 | SOTC018 | (1.50mt x 2.10 mt) Sliding Automatic Sliding Doors with View Window of 1 Mt x 1 Mt | Nos | 525000 | 2 | 444915.2542 | 1050000 | 2 | 1050000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2 | 1050000 | 2 | 1050000 | 0 | 0 | 2 | 1050000 | 0 | 0 | 183750 | 367500 | 367500
19 | SOTC019 | Storage Units | Nos | 75000 | 4 | 63559.322 | 300000 | 4 | 300000 | 0 | 0 | 2 | 150000 | 2 | 150000 | 0 | 0 | 6 | 450000 | 6 | 450000 | 0 | 0 | 6 | 450000 | 0 | 0 | 26250 | 105000 | 157500
20 | SOTC020 | Writing Board (List Board) | Nos | 18750 | 4 | 15889.8305 | 75000 | 4 | 75000 | 0 | 0 | 2 | 37500 | 2 | 37500 | 0 | 0 | 6 | 112500 | 6 | 112500 | 0 | 0 | 6 | 112500 | 0 | 0 | 6562.5 | 26250 | 39375
21 | SOTC021 | X-Ray CT Scan LED viewing Screen | Nos | 37500 | 4 | 31779.661 | 150000 | 4 | 150000 | 0 | 0 | 2 | 75000 | 2 | 75000 | 0 | 0 | 6 | 225000 | 6 | 225000 | 0 | 0 | 6 | 225000 | 0 | 0 | 13125 | 52500 | 78750
22 | SOTC022 | Touch Screen Surgeon Control Panels | Nos | 385000 | 4 | 326271.1864 | 1540000 | 4 | 1540000 | 0 | 0 | 2 | 770000 | 2 | 770000 | 0 | 0 | 6 | 2310000 | 6 | 2310000 | 0 | 0 | 6 | 2310000 | 0 | 0 | 134750 | 539000 | 808500
23 | SOTC023 | 3-Bay Scrub Stations/Sinks | Nos | 368750 | 2 | 312500 | 737500 | 3 | 1106250 | 368750 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2 | 737500 | 3 | 1106250 | 368750 | 0 | 3 | 1106250 | 368750 | 0 | 129062.5 | 258125 | 387187.5
24 | SOTC024 | Video and Image Management system | Nos | 8000000 | 1 | 6779661.0169 | 8000000 | 1 | 8000000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 8000000 | 1 | 8000000 | 0 | 0 | 1 | 8000000 | 0 | 0 | 2800000 | 2800000 | 2800000
25 | SOTC025 | Medical Grade Monitors 32 inch 4 K Resolution | Nos | 1295000 | 4 | 1097457.6271 | 5180000 | 4 | 5180000 | 0 | 0 | 2 | 2590000 | 2 | 2590000 | 0 | 0 | 6 | 7770000 | 6 | 7770000 | 0 | 0 | 6 | 7770000 | 0 | 0 | 453250 | 1813000 | 2719500
26 | SOTC026 | Wall mounted large screen display 55 inch (Commercial Grade) | Nos | 495000 | 2 | 419491.5254 | 990000 | 2 | 990000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 2 | 990000 | 2 | 990000 | 0 | 0 | 2 | 990000 | 0 | 0 | 173250 | 346500 | 346500
27 | SOTC027 | Cable connections for integration within MOTs and with Workshop Projector Hall, Networks with OFC Cable | Job | 997500 | 4 | 845338.9831 | 3990000 | 4 | 3990000 | 0 | 0 | 2 | 1995000 | 2 | 1995000 | 0 | 0 | 6 | 5985000 | 6 | 5985000 | 0 | 0 | 6 | 5985000 | 0 | 0 | 349125 | 1396500 | 2094750
28 | SOTC028 | Wireless Microphone | Nos | 255000 | 1 | 216101.6949 | 255000 | 1 | 255000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 255000 | 1 | 255000 | 0 | 0 | 1 | 255000 | 0 | 0 | 89250 | 89250 | 89250
29 | SOTC029 | Digital mixer Amplifier | Nos | 245000 | 1 | 207627.1186 | 245000 | 1 | 245000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 245000 | 1 | 245000 | 0 | 0 | 1 | 245000 | 0 | 0 | 85750 | 85750 | 85750
30 | SOTC030 | Ceiling Mounted Speakers | Nos | 15000 | 4 | 12711.8644 | 60000 | 4 | 60000 | 0 | 0 | 2 | 30000 | 2 | 30000 | 0 | 0 | 6 | 90000 | 6 | 90000 | 0 | 0 | 6 | 90000 | 0 | 0 | 5250 | 21000 | 31500
31 | SOTC031 | Video Conferencing System | Nos | 1195000 | 1 | 1012711.8644 | 1195000 | 1 | 1195000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 1195000 | 1 | 1195000 | 0 | 0 | 1 | 1195000 | 0 | 0 | 418250 | 418250 | 418250
32 | SOTC032 | Home Theatre Power Conditioner, 230 V | Nos | 145000 | 1 | 122881.3559 | 145000 | 1 | 145000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 145000 | 1 | 145000 | 0 | 0 | 1 | 145000 | 0 | 0 | 50750 | 50750 | 50750
33 | SOTC033 | Amplifier (8 Channel) | Nos | 245000 | 1 | 207627.1186 | 245000 | 1 | 245000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 245000 | 1 | 245000 | 0 | 0 | 1 | 245000 | 0 | 0 | 85750 | 85750 | 85750
34 | SOTC034 | HiFi Active Sub Woofer | Nos | 50000 | 1 | 42372.8814 | 50000 | 1 | 50000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 50000 | 1 | 50000 | 0 | 0 | 1 | 50000 | 0 | 0 | 17500 | 17500 | 17500
35 | SOTC035 | 4K Laser Projection TV | Nos | 1495000 | 1 | 1266949.1525 | 1495000 | 1 | 1495000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 1495000 | 1 | 1495000 | 0 | 0 | 1 | 1495000 | 0 | 0 | 523250 | 523250 | 523250
36 | SOTC036 | Equalization & Loud Speaker Control System | Nos | 40000 | 1 | 33898.3051 | 40000 | 1 | 40000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 40000 | 1 | 40000 | 0 | 0 | 1 | 40000 | 0 | 0 | 14000 | 14000 | 14000
37 | SOTC037 | Sound Analog Mixer | Nos | 245000 | 1 | 207627.1186 | 245000 | 1 | 245000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 245000 | 1 | 245000 | 0 | 0 | 1 | 245000 | 0 | 0 | 85750 | 85750 | 85750
38 | SOTC038 | Electrical Installations in MOTs & TIRs | Job | 195000 | 7 | 165254.2373 | 1365000 | 7 | 1365000 | 0 | 0 | 2 | 390000 | 2 | 390000 | 0 | 0 | 9 | 1755000 | 9 | 1755000 | 0 | 0 | 9 | 1755000 | 0 | 0 | 68250 | 477750 | 614250
39 | SOTC039 | Stainless Steel Pre-fabricated Wall panels in TIRs | Sqm | 15010 | 202 | 12720.339 | 3032020 | 329.06 | 4939190.6 | 1907170.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 202 | 3032020 | 329.06 | 4939190.6 | 1907170.6 | 0 | 338.9318 | 5087366.318 | 2055346.318 | 0 | 5253.5 | 1061207 | 1780578.2113
40 | SOTC040 | Stainless Steel Pre-fabricated Ceiling panels in TIRs and TIR Corridor | Sqm | 15010 | 146 | 12720.339 | 2191460 | 174 | 2611740 | 420280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 146 | 2191460 | 174 | 2611740 | 420280 | 0 | 179.22 | 2690092.2 | 498632.2 | 0 | 5253.5 | 767011 | 941532.27
41 | SOTC041 | Electro conductive Flooring inside TIRs | Sqm | 4035 | 146 | 3419.4915 | 589110 | 72.22 | 291407.7 | 0 | 297702.3 |  | 0 |  | 0 | 0 | 0 | 146 | 589110 | 72.22 | 291407.7 | 0 | 297702.3 | 73.6644 | 297235.854 | 0 | 291874.146 | 1412.25 | 206188.5 | 104032.5489
42 | SOTC042 | Flooring with Vinyl Sheets In TIR Corridor | Sqm | 3750 | 61 | 3177.9661 | 228750 | 127.58 | 478425 | 249675 | 0 |  | 0 |  | 0 | 0 | 0 | 61 | 228750 | 127.58 | 478425 | 249675 | 0 | 131.4074 | 492777.75 | 264027.75 | 0 | 1312.5 | 80062.5 | 172472.2125
43 | SOTC043 | Uni Directional Ceiling Laminar Airflow Systems | Nos | 395000 | 3 | 334745.7627 | 1185000 | 3 | 1185000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 3 | 1185000 | 3 | 1185000 | 0 | 0 | 3 | 1185000 | 0 | 0 | 138250 | 414750 | 414750
44 | SOTC044 | Air Handling Units (AHUs) 11 TR | Nos | 1495000 | 2 | 1266949.1525 | 2990000 | 2 | 2990000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 2 | 2990000 | 2 | 2990000 | 0 | 0 | 2 | 2990000 | 0 | 0 | 523250 | 1046500 | 1046500
45 | SOTC045 | Air Handling Units (AHUs) 8.5 TR | Nos | 1195000 | 1 | 1012711.8644 | 1195000 | 1 | 1195000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 1195000 | 1 | 1195000 | 0 | 0 | 1 | 1195000 | 0 | 0 | 418250 | 418250 | 418250
46 | SOTC046 | Condensing Units | Nos | 345000 | 3 | 292372.8814 | 1035000 | 3 | 1035000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 3 | 1035000 | 3 | 1035000 | 0 | 0 | 6 | 2070000 | 1035000 | 0 | 120750 | 362250 | 724500
47 | SOTC047 | Pressure Relief Dampers | Nos | 22500 | 3 | 19067.7966 | 67500 | 3 | 67500 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 3 | 67500 | 3 | 67500 | 0 | 0 | 3 | 67500 | 0 | 0 | 7875 | 23625 | 23625
48 | SOTC049 | Hermetically Sealed Doors (1.80mt x 2.10 mt) | Nos | 525000 | 3 | 444915.2542 | 1575000 | 3 | 1575000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 3 | 1575000 | 3 | 1575000 | 0 | 0 | 3 | 1575000 | 0 | 0 | 183750 | 551250 | 551250
| SOTC050 | 12mm thick glazed Glass partition walls in TIRs | Sqm | 650 | 40 | 550.8475 | 26000 | 40 | 26000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 40 | 26000 | 40 | 26000 | 0 | 0 | 40 | 26000 | 0 | 0 | 227.5 | 9100 | 9100
50 | SOTC051 | Wall mounted LED TV43 inchesFull HD | Nos | 165000 | 3 | 139830.5085 | 495000 | 3 | 495000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 3 | 495000 | 3 | 495000 | 0 | 0 | 3 | 495000 | 0 | 0 | 57750 | 173250 | 173250
51 | SOTC052 | Ceiling/Wall mounted CCTV Room Camera | Nos | 12000 | 3 | 10169.4915 | 36000 | 3 | 36000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 3 | 36000 | 3 | 36000 | 0 | 0 | 3 | 36000 | 0 | 0 | 4200 | 12600 | 12600
52 | SOTC053 | BED HEAD PANEL FOR TIR WITH DOUBLE OUTLETS AND ELECTRICAL OUTLETS | Nos | 49500 | 3 | 41949.1525 | 148500 | 6 | 297000 | 148500 | 0 |  | 0 |  | 0 | 0 | 0 | 3 | 148500 | 6 | 297000 | 148500 | 0 | 3 | 148500 | 0 | 0 | 17325 | 51975 | 51975
5 | SOTC054 | X-RAY VIEWERS FOR ALL ICUS AND PRE OPP AREAS AND DOCTORS ROOMS | Nos | 37500 | 5 | 31779.661 | 187500 | 5 | 187500 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 5 | 187500 | 5 | 187500 | 0 | 0 | 6 | 225000 | 37500 | 0 | 13125 | 65625 | 78750
54 | SOTC055 | WRITING BOARDS FOR ICUS, PRE OPP | Nos | 18750 | 5 | 15889.8305 | 93750 | 5 | 93750 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 5 | 93750 | 5 | 93750 | 0 | 0 | 6 | 112500 | 18750 | 0 | 6562.5 | 32812.5 | 39375
55 | SOTC056 | CCTV CEILING CAMERA | Nos | 9500 | 10 | 8050.8475 | 95000 | 10 | 95000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 10 | 95000 | 10 | 95000 | 0 | 0 | 10 | 95000 | 0 | 0 | 3325 | 33250 | 33250
56 | SOTC057 | Supply and Fixing of 25mm dia Conduit Pipes surface on wall. | Rmt | 110 | 10000 | 93.2203 | 1100000 | 10000 | 1100000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 10000 | 1100000 | 10000 | 1100000 | 0 | 0 | 10000 | 1100000 | 0 | 0 | 38.5 | 385000 | 385000
57 | SOTC058 | Supply and Fixing of 25mm dia Conduit Pipes Concealed on wall. | Rmt | 115 | 4000 | 97.4576 | 460000 | 4000 | 460000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 4000 | 460000 | 4000 | 460000 | 0 | 0 | 4000 | 460000 | 0 | 0 | 40.25 | 161000 | 161000
58 | SOTC059 | Wiring with run of 2 of 1.5 Sqmm Copper cable for points wiring. | Pts | 1525 | 570 | 1292.3729 | 869250 | 570 | 869250 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 570 | 869250 | 570 | 869250 | 0 | 0 | 570 | 869250 | 0 | 0 | 533.75 | 304237.5 | 304237.5
59 | SOTC060 | Wiring with run of 2 of 1.5 Sqmm Copper cable for stairecase points wiring. | Pts | 1100 | 10 | 932.2034 | 11000 | 10 | 11000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 10 | 11000 | 10 | 11000 | 0 | 0 | 10 | 11000 | 0 | 0 | 385 | 3850 | 3850
60 | SOTC061 | Supply and fixing of 6A/10A ISI Mark 3/2 pin Modular socket Common switch board | Pts | 900 | 25 | 762.7119 | 22500 | 25 | 22500 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 25 | 22500 | 25 | 22500 | 0 | 0 | 25 | 22500 | 0 | 0 | 315 | 7875 | 7875
61 | SOTC062 | Wiring with 3 of 1.5 sq.mm with 6A switch and 6A, 3/2 pin socket Modular type with 6A switch control fixing on separate board. | Pts | 2800 | 50 | 2372.8814 | 140000 | 50 | 140000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 50 | 140000 | 50 | 140000 | 0 | 0 | 50 | 140000 | 0 | 0 | 190.75 | 9537.5 | 9537.5
62 | SOTC063 | Supply and fixing of 6A switchs - 2 Nos and 6A 3/2 pin socket - 3 Nos Modular type with cover plate | Pts | 1400 | 200 | 1186.4407 | 280000 | 200 | 280000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 200 | 280000 | 200 | 280000 | 0 | 0 | 200 | 280000 | 0 | 0 | 490 | 98000 | 98000
63 | SOTC064 | Supply & fixing of 16A/6A, 2 in one socket with 16A switch control modular type | Nos | 900 | 200 | 762.7119 | 180000 | 200 | 180000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 200 | 180000 | 200 | 180000 | 0 | 0 | 200 | 180000 | 0 | 0 | 315 | 63000 | 63000
64 | SOTC065 | Supply & fixing of 32A, socket with switch control modular | Nos | 1600 | 18 | 1355.9322 | 28800 | 18 | 28800 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 18 | 28800 | 18 | 28800 | 0 | 0 | 18 | 28800 | 0 | 0 | 560 | 10080 | 10080
65 | SOTC066 | Supply & fixing of 64A, socket with 64A switch control modular type | Nos | 18000 | 4 | 15254.2373 | 72000 | 4 | 72000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 4 | 72000 | 4 | 72000 | 0 | 0 | 4 | 72000 | 0 | 0 | 6300 | 25200 | 25200
66 | SOTC067 | Supply and Run of 1 of 1.5 sq.mm (phase, neutral and earth) FRLSH / HFFR PVC insulated 1100V grade as per IS:694/1990, IS 17048 specifications for Copper cable. | Rmt | 36 | 2000 | 30.5085 | 72000 | 2000 | 72000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 2000 | 72000 | 2000 | 72000 | 0 | 0 | 2000 | 72000 | 0 | 0 | 12.6 | 25200 | 25200
67 | SOTC068 | Supply and Run of 3 of 1.5 sq.mm (phase, neutral and earth) FRLSH / HFFR PVC insulated 1100V grade as per IS:694/1990, IS 17048 specifications for Copper cable . | Rmt | 100 | 2000 | 84.7458 | 200000 | 2000 | 200000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 2000 | 200000 | 2000 | 200000 | 0 | 0 | 2000 | 200000 | 0 | 0 | 35 | 70000 | 70000
68 | SOTC069 | Supply and Run of 3 of 2.5 sq.mm (phase, neutral and earth) FRLSH / HFFR PVC insulated 1100V grade as per IS:694/1990, IS 17048 specifications for Copper cable. | Rmt | 145 | 8000 | 122.8814 | 1160000 | 8000 | 1160000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 8000 | 1160000 | 8000 | 1160000 | 0 | 0 | 8000 | 1160000 | 0 | 0 | 50.75 | 406000 | 406000
69 | SOTC070 | Supply and Run of 3 runs of 4.0 sq mm (phase neutral and earth) FRLSH / HFFR PVC insulated 1100V grade as per IS:694/1990, IS 17048 specifications for Copper cable. | Rmt | 230 | 5000 | 194.9153 | 1150000 | 5000 | 1150000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 5000 | 1150000 | 5000 | 1150000 | 0 | 0 | 5000 | 1150000 | 0 | 0 | 80.5 | 402500 | 402500
70 | SOTC071 | Supply and Run of 3 of 6.0 Sq.mm FRLSH / HFFR PVC insulated 1100V grade as per IS:694/1990, IS 17048 specifications for Copper cable. | Rmt | 325 | 300 | 275.4237 | 97500 | 300 | 97500 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 300 | 97500 | 300 | 97500 | 0 | 0 | 300 | 97500 | 0 | 0 | 113.75 | 34125 | 34125
71 | SOTC072 | Supply and Run of 5 of 6.0 Sq.mm FRLSH / HFFR PVC insulated 1100V grade as per IS:694/1990, IS 17048 specifications for Copper cable. | Rmt | 545 | 300 | 461.8644 | 163500 | 300 | 163500 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 300 | 163500 | 300 | 163500 | 0 | 0 | 300 | 163500 | 0 | 0 | 190.75 | 57225 | 57225
72 | SOTC073 | Supply and Run of 5 of 10.0 Sq.mm FRLSH / HFFR PVC insulated 1100V grade as per IS:694/1990, IS 17048 specifications for Copper cable. | Rmt | 850 | 500 | 720.339 | 425000 | 500 | 425000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 500 | 425000 | 500 | 425000 | 0 | 0 | 500 | 425000 | 0 | 0 | 297.5 | 148750 | 148750
73 | SOTC074 | Supply and fixing of DP Metal Enclosure with IP 20 Protection DB Make with 1 No 20A, 10 KA DP MCB | Nos | 1800 | 8 | 1525.4237 | 14400 | 8 | 14400 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 8 | 14400 | 8 | 14400 | 0 | 0 | 8 | 14400 | 0 | 0 | 630 | 5040 | 5040
74 | SOTC075 | Supply and fixing of 4 Way TPN DB Horizontal with IP 43 Protection as per IS:13032 (For Lighting DBs) | Nos | 13000 | 10 | 11016.9492 | 130000 | 10 | 130000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 10 | 130000 | 10 | 130000 | 0 | 0 | 10 | 130000 | 0 | 0 | 4550 | 45500 | 45500
75 | SOTC076 | Supply and fixing of 4 Way TPN DB Horizontal with IP 43 Protection as per IS:13032 (For Power DB's) | Nos | 13000 | 14 | 11016.9492 | 182000 | 14 | 182000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 14 | 182000 | 14 | 182000 | 0 | 0 | 14 | 182000 | 0 | 0 | 4550 | 63700 | 63700
76 | SOTC077 | Supply and fixing of 8 Way VTPN DB with IP 43 Protection as per IS:13032 | Nos | 50000 | 5 | 42372.8814 | 250000 | 5 | 250000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 5 | 250000 | 5 | 250000 | 0 | 0 | 5 | 250000 | 0 | 0 | 17500 | 87500 | 87500
77 | SOTC078 | Supply and fixing of cable adopteres box with cover for DBs including, massanory work etc., complete., | Nos | 6000 | 10 | 5084.7458 | 60000 | 10 | 60000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 10 | 60000 | 10 | 60000 | 0 | 0 | 10 | 60000 | 0 | 0 | 2100 | 21000 | 21000
78 | SOTC079 | Providing independent earthing for Important equipment with 40mm dia 'B' class 2.5m long G.I pipe (GI Earthing) | Nos | 22500 | 18 | 19067.7966 | 405000 | 18 | 405000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 18 | 405000 | 18 | 405000 | 0 | 0 | 18 | 405000 | 0 | 0 | 7875 | 141750 | 141750
79 | SOTC080 | Providing independent earthing by exacavating a pit to a depth of 2.25Mtr in all soils as per size specified in the data for Sophisticated Electronic equipment (Copper Earthing) | Nos | 54000 | 18 | 45762.7119 | 972000 | 18 | 972000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 18 | 972000 | 18 | 972000 | 0 | 0 | 18 | 972000 | 0 | 0 | 18900 | 340200 | 340200
80 | SOTC081 | Providing independent earthing for Important equipment with 100mm dia Heavy gauge C.I Earthing | Nos | 25000 | 6 | 21186.4407 | 150000 | 6 | 150000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 6 | 150000 | 6 | 150000 | 0 | 0 | 6 | 150000 | 0 | 0 | 8750 | 52500 | 52500
81 | SOTC082 | Supply and Run of 50mm x 6mm G.I Strip | Rmt | 450 | 400 | 381.3559 | 180000 | 400 | 180000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 400 | 180000 | 400 | 180000 | 0 | 0 | 400 | 180000 | 0 | 0 | 157.5 | 63000 | 63000
82 | SOTC083 | Supply and Run of 25mm x 3mm copper strip | Rmt | 300 | 400 | 254.2373 | 120000 | 400 | 120000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 400 | 120000 | 400 | 120000 | 0 | 0 | 400 | 120000 | 0 | 0 | 105 | 42000 | 42000
83 | SOTC084 | Supply, transportation and fixing of 22W +/ 10% , >/ 2300 lumens, 1200mm length LED light | Nos | 4800 | 20 | 4067.7966 | 96000 | 20 | 96000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 20 | 96000 | 20 | 96000 | 0 | 0 | 20 | 96000 | 0 | 0 | 1680 | 33600 | 33600
84 | SOTC085 | Supply, transportation and fixing 32-36W (>=3600 Lumens), 2' x2' (600mm x 600mm) slim panel LED luminaire | Nos | 4000 | 60 | 3389.8305 | 240000 | 60 | 240000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 60 | 240000 | 60 | 240000 | 0 | 0 | 60 | 240000 | 0 | 0 | 1400 | 84000 | 84000
85 | SOTC086 | Supply, transportation and fixing 12 W +/-10% (>= 1200 Lumens) Down lighter back lit LED Down Light Recessed / Surface | Nos | 1400 | 215 | 1186.4407 | 301000 | 215 | 301000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 215 | 301000 | 215 | 301000 | 0 | 0 | 215 | 301000 | 0 | 0 | 490 | 105350 | 105350
86 | SOTC087 | Supply, transportation and fixing 18 W +/-10% (>= 1800 Lumens) Down lighter back lit LED Down Light | Nos | 1800 | 95 | 1525.4237 | 171000 | 95 | 171000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 95 | 171000 | 95 | 171000 | 0 | 0 | 95 | 171000 | 0 | 0 | 630 | 59850 | 59850
87 | SOTC088 | Supply, transportation and fixing ISI mark batten holder / slanting holder | Nos | 160 | 8 | 135.5932 | 1280 | 8 | 1280 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 8 | 1280 | 8 | 1280 | 0 | 0 | 8 | 1280 | 0 | 0 | 56 | 448 | 448
88 | SOTC089 | Supply, Transportation of energy efficient fan, 1200 mm sweep, aluminium body, consuming 28 W, BEE 5 star rated, ceiling fan | Nos | 3700 | 40 | 3135.5932 | 148000 | 40 | 148000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 40 | 148000 | 40 | 148000 | 0 | 0 | 40 | 148000 | 0 | 0 | 1295 | 51800 | 51800
89 | SOTC090 | Supply and fixing of Modular type Stepped electronic regulator. | Nos | 1000 | 40 | 847.4576 | 40000 | 40 | 40000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 40 | 40000 | 40 | 40000 | 0 | 0 | 40 | 40000 | 0 | 0 | 350 | 14000 | 14000
90 | SOTC091 | Labour charges for fixing of ceiling fan and regulator | Nos | 210 | 40 | 177.9661 | 8400 | 40 | 8400 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 40 | 8400 | 40 | 8400 | 0 | 0 | 40 | 8400 | 0 | 0 | 73.5 | 2940 | 2940
91 | SOTC092 | Supply and erecting 19/20mm steel tube down rod of one meter length | Nos | 600 | 40 | 508.4746 | 24000 | 40 | 24000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 40 | 24000 | 40 | 24000 | 0 | 0 | 40 | 24000 | 0 | 0 | 210 | 8400 | 8400
92 | SOTC093 | Supply of 12" (300mm) Light duty exhaust fan | Nos | 3000 | 5 | 2542.3729 | 15000 | 5 | 15000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 5 | 15000 | 5 | 15000 | 0 | 0 | 5 | 15000 | 0 | 0 | 1050 | 5250 | 5250
93 | SOTC094 | Supply,Transportation of 12" (300mm) ISI, 900 RPM Heavy duty exhaust fan | Nos | 4900 | 10 | 4152.5424 | 49000 | 10 | 49000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 10 | 49000 | 10 | 49000 | 0 | 0 | 10 | 49000 | 0 | 0 | 1715 | 17150 | 17150
94 | SOTC095 | Labour charges for fixing the exhaust fan in wall with necessary connections | Nos | 900 | 15 | 762.7119 | 13500 | 15 | 13500 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 15 | 13500 | 15 | 13500 | 0 | 0 | 15 | 13500 | 0 | 0 | 315 | 4725 | 4725
95 | SOTC096 | Supply and fixing of GI louver shutter including GI mesh | Nos | 3200 | 15 | 2711.8644 | 48000 | 15 | 48000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 15 | 48000 | 15 | 48000 | 0 | 0 | 15 | 48000 | 0 | 0 | 1120 | 16800 | 16800
96 | SOTC097 | Main Power Panel with 1000A 4 Pole ACB as incomer - 1 No and out goings 800 A 4P MCCB - 1 No., 630 A 4P MCCB - 1 No., 400A 4P MCCB - 4 Nos & 250A 4P MCCB - 3 No's with required Digital Ammeter and Voltmer, LED Indicators | Nos | 1315000 | 1 | 1114406.7797 | 1315000 | 1 | 1315000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 1315000 | 1 | 1315000 | 0 | 0 | 1 | 1315000 | 0 | 0 | 460250 | 460250 | 460250
97 | SOTC098 | Floor Power Panel : Incomer: 630A 4 Pole MCCB,- 1 No Outgoings 250 A 4P MCCB - 4 No's 125 A 4P MCCB - 10 No's, 63 A 4P MCCB - 4 No's with required Digital Ammeter and Voltmer, LED Indicators | Nos | 875000 | 1 | 741525.4237 | 875000 | 1 | 875000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 875000 | 1 | 875000 | 0 | 0 | 1 | 875000 | 0 | 0 | 306250 | 306250 | 306250
98 | SOTC099 | Electrical Lighting Panels : Incomer: 250 A 4 Pole MCCB - 1 No, Out Goings 125 A 4P MCCB - 4 No's 63 A 4P MCCB - 3 No's with required Digital Ammeter and Voltmer, LED Indicators | Nos | 370000 | 2 | 313559.322 | 740000 | 2 | 740000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 2 | 740000 | 2 | 740000 | 0 | 0 | 2 | 740000 | 0 | 0 | 129500 | 259000 | 259000
99 | SOTC100 | 130KVAR Out Door Capacitor panel : Incomer: 250A FP MCCB - 1 No, 63A 10KA TP MCB - 9 Nos. 20 KVAR Capacitor Duty contactors - 5 Nos., 10 KVAR Capacitor Duty contactors - 2 Nos, .5 KVAR Capacitor Duty contactors - 2 Nos. 12 stage APFC Relay - 1 No | Nos | 450000 | 1 | 381355.9322 | 450000 | 1 | 450000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 450000 | 1 | 450000 | 0 | 0 | 1 | 450000 | 0 | 0 | 157500 | 157500 | 157500
100 | SOTC101 | 630 KVA Transformer OLTC for transformers with RTCC: Supply, Transportation, Installation, Testing and Commissioning of 630 KVA TRANSFORMER with all test reports. The Transformer shall be designed and manufactured as per IS:1180 OLTC with level-II with initial filling of oil as per IS 335-1993. 1000 A LT Breaker Kiosk - 01 No.The basic details of the Transformer are as under. Makes: Kirloskar / PETE / Esennar / Voltamp / Crompton / ABB / Schneider. | Nos | 4000000 | 1 | 3389830.5085 | 4000000 | 0 | 0 | 0 | 4000000 |  | 0 |  | 0 | 0 | 0 | 1 | 4000000 | 0 | 0 | 0 | 4000000 | 1 | 4700000 | 700000 | 0 | 1400000 | 1400000 | 1400000
101 | SOTC102 | Supply of 25 Sqmm 3.5 Core XLPE insulated UG Cable. | Rmt | 300 | 200 | 254.2373 | 60000 | 200 | 60000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 200 | 60000 | 200 | 60000 | 0 | 0 | 200 | 60000 | 0 | 0 | 105 | 21000 | 21000
102 | SOTC103 | Supply of 50 Sqmm 3.5 Core XLPE insulated UG Cable. | Rmt | 560 | 200 | 474.5763 | 112000 | 200 | 112000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 200 | 112000 | 200 | 112000 | 0 | 0 | 200 | 112000 | 0 | 0 | 196 | 39200 | 39200
103 | SOTC104 | Supply of 70 Sqmm 3.5 Core XLPE insulated UG Cable. | Rmt | 750 | 75 | 635.5932 | 56250 | 75 | 56250 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 75 | 56250 | 75 | 56250 | 0 | 0 | 75 | 56250 | 0 | 0 | 262.5 | 19687.5 | 19687.5
104 | SOTC105 | Supply of 120 Sqmm 3.5 Core XLPE insulated UG Cable. | Rmt | 1050 | 50 | 889.8305 | 52500 | 50 | 52500 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 50 | 52500 | 50 | 52500 | 0 | 0 | 50 | 52500 | 0 | 0 | 367.5 | 18375 | 18375
105 | SOTC106 | Supply of 185 Sqmm 3.5 Core XLPE insulated UG Cable. | Rmt | 1500 | 50 | 1271.1864 | 75000 | 50 | 75000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 50 | 75000 | 50 | 75000 | 0 | 0 | 50 | 75000 | 0 | 0 | 525 | 26250 | 26250
106 | SOTC107 | Supply of 240 Sqmm 3.5 Core XLPE insulated UG Cable. | Rmt | 1900 | 100 | 1610.1695 | 190000 | 100 | 190000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 100 | 190000 | 100 | 190000 | 0 | 0 | 100 | 190000 | 0 | 0 | 665 | 66500 | 66500
107 | SOTC108 | Supply of 300 Sqmm 3.5 Core XLPE insulated UG Cable. | Rmt | 2400 | 500 | 2033.8983 | 1200000 | 500 | 1200000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 500 | 1200000 | 500 | 1200000 | 0 | 0 | 500 | 1200000 | 0 | 0 | 840 | 420000 | 420000
108 | SOTC109 | Termination of UG cables of 3.5 core 25 Sq.mm | Nos | 850 | 8 | 720.339 | 6800 | 8 | 6800 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 8 | 6800 | 8 | 6800 | 0 | 0 | 8 | 6800 | 0 | 0 | 297.5 | 2380 | 2380
109 | SOTC110 | Termination of UG cables of 3.5 core 50 Sq.mm | Nos | 1200 | 8 | 1016.9492 | 9600 | 8 | 9600 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 8 | 9600 | 8 | 9600 | 0 | 0 | 8 | 9600 | 0 | 0 | 420 | 3360 | 3360
110 | SOTC111 | Termination of UG cables of 3.5 core 70 Sq.mm | Nos | 1500 | 8 | 1271.1864 | 12000 | 8 | 12000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 8 | 12000 | 8 | 12000 | 0 | 0 | 8 | 12000 | 0 | 0 | 525 | 4200 | 4200
111 | SOTC112 | Termination of UG cables of 3.5 core 120 Sq.mm | Nos | 1900 | 4 | 1610.1695 | 7600 | 4 | 7600 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 4 | 7600 | 4 | 7600 | 0 | 0 | 4 | 7600 | 0 | 0 | 665 | 2660 | 2660
112 | SOTC113 | Termination of UG cables of 3.5 core 185 Sq.mm | Nos | 2500 | 4 | 2118.6441 | 10000 | 4 | 10000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 4 | 10000 | 4 | 10000 | 0 | 0 | 4 | 10000 | 0 | 0 | 875 | 3500 | 3500
113 | SOTC114 | Termination of UG cables of 3.5 core 240 Sq.mm | Nos | 3500 | 4 | 2966.1017 | 14000 | 4 | 14000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 4 | 14000 | 4 | 14000 | 0 | 0 | 4 | 14000 | 0 | 0 | 1225 | 4900 | 4900
114 | SOTC115 | Termination of UG cables of 3.5 core 300 Sq.mm | Nos | 4000 | 12 | 3389.8305 | 48000 | 12 | 48000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 12 | 48000 | 12 | 48000 | 0 | 0 | 12 | 48000 | 0 | 0 | 1400 | 16800 | 16800
115 | SOTC116 | Earth work excavation of Trench laying of U.G cables up to 70 sqmm | Rmt | 1100 | 100 | 932.2034 | 110000 | 100 | 110000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 100 | 110000 | 100 | 110000 | 0 | 0 | 100 | 110000 | 0 | 0 | 385 | 38500 | 38500
116 | SOTC117 | Earth work excavation of Trench laying of U.G cables from 95 Sqmm | Rmt | 1150 | 100 | 974.5763 | 115000 | 100 | 115000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 100 | 115000 | 100 | 115000 | 0 | 0 | 100 | 115000 | 0 | 0 | 402.5 | 40250 | 40250
117 | SOTC118 | Laying of PVC armoured under ground cable up to 95 Sqmm on wall | Rmt | 125 | 200 | 105.9322 | 25000 | 200 | 25000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 200 | 25000 | 200 | 25000 | 0 | 0 | 200 | 25000 | 0 | 0 | 43.75 | 8750 | 8750
118 | SOTC119 | Laying of PVC armoured under ground cable from 120 Sq.mm to 400 Sqmm saddles on wall | Rmt | 270 | 700 | 228.8136 | 189000 | 700 | 189000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 700 | 189000 | 700 | 189000 | 0 | 0 | 700 | 189000 | 0 | 0 | 94.5 | 66150 | 66150
119 | SOTC120 | Supply, Transportation and Installation of 150mm x 50mm x 2mm thick hot dip GI perforated cable tray | Rmt | 1295 | 200 | 1097.4576 | 259000 | 200 | 259000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 200 | 259000 | 200 | 259000 | 0 | 0 | 200 | 259000 | 0 | 0 | 453.25 | 90650 | 90650
120 | SOTC121 | Supply, Transportation and Installation of 300mm x 50mm x 2mm thick thick hot dip GI perforated cable tray | Rmt | 4500 | 100 | 3813.5593 | 450000 | 100 | 450000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 100 | 450000 | 100 | 450000 | 0 | 0 | 100 | 450000 | 0 | 0 | 1575 | 157500 | 157500
121 | SOTC122 | Supply, Transportation and installation of 10KVA / 312V DC on line UPS system | Nos | 400000 | 7 | 338983.0508 | 2800000 | 11 | 4400000 | 1600000 | 0 | 2 | 800000 | 2 | 800000 | 0 | 0 | 9 | 3600000 | 13 | 5200000 | 1600000 | 0 | 10 | 4000000 | 400000 | 0 | 140000 | 980000 | 1400000
122 | SOTC123 | Supply and fixing of 12V, 150 AH MF battery | Nos | 25000 | 182 | 21186.4407 | 4550000 | 286 | 7150000 | 2600000 | 0 | 52 | 1300000 | 52 | 1300000 | 0 | 0 | 234 | 5850000 | 338 | 8450000 | 2600000 | 0 | 384 | 9600000 | 3750000 | 0 | 8750 | 1592500 | 3360000
123 | SOTC124 | Supply and providing of UPS cum battery rack 20 batteries | Nos | 30000 | 7 | 25423.7288 | 210000 | 11 | 330000 | 120000 | 0 | 2 | 60000 | 2 | 60000 | 0 | 0 | 9 | 270000 | 13 | 390000 | 120000 | 0 | 12 | 360000 | 90000 | 0 | 10500 | 73500 | 126000
124 | SOTC125 | Supply, Transportation, Installation, Testing and commissioning of storage / Pressure type 5 Star rated water heater with ABS plastic body of 15 Ltrs | Nos | 16000 | 7 | 13559.322 | 112000 | 12 | 192000 | 80000 | 0 |  | 0 |  | 0 | 0 | 0 | 7 | 112000 | 11 | 176000 | 64000 | 0 | 11 | 176000 | 64000 | 0 | 5600 | 39200 | 61600
125 | SOTC126 | 26 persons ICU bed cum passenger lift (1768 Kgs) G+8 Floors, 9 stops,9 Openings (Cost Includes amount for Construction of Shaft / Cladding from Ground to 8th Floor) | Nos | 10495000 | 1 | 8894067.7966 | 10495000 | 1 | 10495000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 10495000 | 1 | 10495000 | 0 | 0 | 1 | 10495000 | 0 | 0 | 3673250 | 3673250 | 3673250
126 | SOTC127 | 1.50 TR with , 18000 BTU/Hr High Wall mount Split Air Conditioners | Nos | 150000 | 6 | 127118.6441 | 900000 | 6 | 900000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 6 | 900000 | 6 | 900000 | 0 | 0 | 7 | 1050000 | 150000 | 0 | 52500 | 315000 | 367500
127 | SOTC128 | 2.0 TR with , 24000 BTU/Hr High Wall mount Split Air Conditioners | Nos | 210000 | 2 | 177966.1017 | 420000 | 6 | 1260000 | 840000 | 0 |  | 0 |  | 0 | 0 | 0 | 2 | 420000 | 6 | 1260000 | 840000 | 0 | 6 | 1260000 | 840000 | 0 | 73500 | 147000 | 441000
128 | SOTC129 | Voltage stabilizer for 4 KVA maximum load | Nos | 7000 | 6 | 5932.2034 | 42000 | 6 | 42000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 6 | 42000 | 6 | 42000 | 0 | 0 | 7 | 49000 | 7000 | 0 | 2450 | 14700 | 17150
129 | SOTC130 | Voltage stabilizer for 5 KVA maximum load | Nos | 8500 | 2 | 7203.3898 | 17000 | 6 | 51000 | 34000 | 0 |  | 0 |  | 0 | 0 | 0 | 2 | 17000 | 6 | 51000 | 34000 | 0 | 6 | 51000 | 34000 | 0 | 2975 | 5950 | 17850
130 | SOTC131 | Ductable Air Conditioners 11.0 TR with ISEER ≥ 4 | Nos | 1200000 | 1 | 1016949.1525 | 1200000 | 1 | 1200000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 1200000 | 1 | 1200000 | 0 | 0 | 1 | 1200000 | 0 | 0 | 420000 | 420000 | 420000
131 | SOTC132 | Ductable Air Conditioners 8.5 TR with ISEER ≥ 4 | Nos | 1000000 | 2 | 847457.6271 | 2000000 | 2 | 2000000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 2 | 2000000 | 2 | 2000000 | 0 | 0 | 4 | 4000000 | 2000000 | 0 | 350000 | 700000 | 1400000
132 | SOTC133 | Ductable Air Conditioners 5.5 TR with ISEER ≥ 4 | Nos | 900000 | 1 | 762711.8644 | 900000 | 3 | 2700000 | 1800000 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 900000 | 3 | 2700000 | 1800000 | 0 | 3 | 2700000 | 1800000 | 0 | 315000 | 315000 | 945000
133 | SOTC134 | Automatic Smoke Detection System | Job | 1425000 | 1 | 1207627.1186 | 1425000 | 1 | 1425000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 1425000 | 1 | 1425000 | 0 | 0 | 1 | 1425000 | 0 | 0 | 498750 | 498750 | 498750
134 | SOTC135 | Automatic Fire Alarm System | Job | 1400000 | 1 | 1186440.678 | 1400000 | 1 | 1400000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 1400000 | 1 | 1400000 | 0 | 0 | 1 | 1400000 | 0 | 0 | 490000 | 490000 | 490000
135 | SOTC136 | Supply & Fixing of 4.5Kg, CO2 Type Fire Extinguisher. | Nos | 27000 | 6 | 22881.3559 | 162000 | 6 | 162000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 6 | 162000 | 6 | 162000 | 0 | 0 | 6 | 162000 | 0 | 0 | 9450 | 56700 | 56700
136 | SOTC137 | Supply and fixing of ABC stored pressure squeeze grip type fire extinguishers, 9 kg capacity. | Nos | 16000 | 6 | 13559.322 | 96000 | 6 | 96000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 6 | 96000 | 6 | 96000 | 0 | 0 | 6 | 96000 | 0 | 0 | 5600 | 33600 | 33600
137 | SOTC138 | Supply and fixing of ABC Powder MAP 4 Kg Fire extinguisher | Nos | 11000 | 10 | 9322.0339 | 110000 | 10 | 110000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 10 | 110000 | 10 | 110000 | 0 | 0 | 10 | 110000 | 0 | 0 | 3850 | 38500 | 38500
138 | SOTC139 | Supply and fixing of 2 Kg Fire extinguisher Clean Agent | Nos | 22500 | 10 | 19067.7966 | 225000 | 10 | 225000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 10 | 225000 | 10 | 225000 | 0 | 0 | 10 | 225000 | 0 | 0 | 7875 | 78750 | 78750
139 | SOTC140 | Supply and fixing of Escape signage boards in Rigid Photo luminescent based glow | Nos | 2000 | 150 | 1694.9153 | 300000 | 150 | 300000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 150 | 300000 | 150 | 300000 | 0 | 0 | 150 | 300000 | 0 | 0 | 700 | 105000 | 105000
140 | SOTC141 | Supply & Fixing of Powder Coated Fire Rated doors. | Sqm | 29000 | 6 | 24576.2712 | 174000 | 3 | 87000 | 0 | 87000 |  | 0 |  | 0 | 0 | 0 | 6 | 174000 | 3 | 87000 | 0 | 87000 | 13.8 | 400200 | 226200 | 0 | 10150 | 60900 | 140070
141 | SOTC142 | Telephone & EPABX System | Job | 1000000 | 1 | 847457.6271 | 1000000 | 1 | 1000000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 1000000 | 1 | 1000000 | 0 | 0 | 1 | 1000000 | 0 | 0 | 350000 | 350000 | 350000
142 | SOTC143 | Local Area Network (LAN) System | Job | 1250000 | 1 | 1059322.0339 | 1250000 | 1 | 1250000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 1250000 | 1 | 1250000 | 0 | 0 | 1 | 1250000 | 0 | 0 | 437500 | 437500 | 437500
143 | SOTC144 | Biometric Access Control System | Nos | 300000 | 2 | 254237.2881 | 600000 | 3 | 900000 | 300000 | 0 |  | 0 |  | 0 | 0 | 0 | 2 | 600000 | 3 | 900000 | 300000 | 0 | 3 | 900000 | 300000 | 0 | 105000 | 210000 | 315000
144 | SOTC145 | Dismantling, clearing away and carefully stacking useful materials for re-use and disposal of unserviceable materials with 100m lead as directed by Engineer-in-Charge duly taking actual premeasurements before dismantling including all charges complete (Reinforced cement concrete) | Cum | 5400 | 10 | 4576.2712 | 54000 | 5.95 | 32130 | 0 | 21870 |  | 0 |  | 0 | 0 | 0 | 10 | 54000 | 5.95 | 32130 | 0 | 21870 | 10 | 54000 | 0 | 0 | 1890 | 18900 | 0
145 | SOTC146 | Dismantling, clearing away and carefully stacking useful materials for re-use and disposal of unserviceable materials with 100m lead as directed by Engineer-in-Charge duly taking actual premeasurements before dismantling including all charges complete (Unreinforced cement concrete) | Cum | 4500 | 1.5 | 3813.5593 | 6750 | 49.43 | 222435 | 215685 | 0 |  | 0 |  | 0 | 0 | 0 | 1.5 | 6750 | 49.43 | 222435 | 215685 | 0 | 51.9015 | 233556.75 | 226806.75 | 0 | 1575 | 2362.5 | 0
146 | SOTC147 | Dismantling, clearing away and carefully stacking useful materials for re-use and disposal of unserviceable materials with 100m lead as directed by Engineer-in-Charge duly taking actual premeasurements before dismantling including all charges complete (Brick Masonary) | Cum | 900 | 118 | 762.7119 | 106200 | 145.42 | 130878 | 24678 | 0 |  | 0 |  | 0 | 0 | 0 | 118 | 106200 | 145.42 | 130878 | 24678 | 0 | 152.691 | 137421.9 | 31221.9 | 0 | 315 | 37170 | 0
147 | SOTC148 | Dismantling, clearing away and carefully stacking useful materials for re-use and disposal of unserviceable materials with 100m lead as directed by Engineer-in-Charge duly taking actual premeasurements before dismantling including all charges complete (Kadapa slabs or shahabad stone slabs on sand bed) | Sqm | 630 | 25 | 533.8983 | 15750 | 659.93 | 415755.9 | 400005.9 | 0 |  | 0 |  | 0 | 0 | 0 | 25 | 15750 | 659.93 | 415755.9 | 400005.9 | 0 | 692.9265 | 436543.695 | 420793.695 | 0 | 220.5 | 5512.5 | 0
148 | SOTC149 | Dismantling doors, windows and clear storey windows, Ventilators etc., (wood or steel) shutters including Chowkhats, architraves,hold fasts and other attachments etc., and stacking them within 100m lead including charge etc., complete for finished item of work. (Not exceeding 3 sqm in area) | Nos | 1800 | 57 | 1525.4237 | 102600 | 203 | 365400 | 262800 | 0 |  | 0 |  | 0 | 0 | 0 | 57 | 102600 | 203 | 365400 | 262800 | 0 | 203 | 365400 | 262800 | 0 | 630 | 35910 | 0
149 | SOTC150 | Conveyance of un-useful excavated earth to a distance of 16 KM for disposal including hire charges of T and P, labour charges etc., complete for finished item of work. | Cum | 900 | 250 | 762.7119 | 225000 | 299.78 | 269802 | 44802 | 0 |  | 0 |  | 0 | 0 | 0 | 250 | 225000 | 299.78 | 269802 | 44802 | 0 | 314.769 | 283292.1 | 58292.1 | 0 | 315 | 78750 | 0
150 | SOTC151 | RCC M 25 grade design mix (For lintels) | Cum | 18900 | 3 | 16016.9492 | 56700 | 3.02 | 57078 | 378 | 0 |  | 0 |  | 0 | 0 | 0 | 3 | 56700 | 3.02 | 57078 | 378 | 0 | 3.171 | 59931.9 | 3231.9 | 0 | 6615 | 19845 | 20976.165
151 | SOTC152 | RCC M 20 grade design mix (50mm thick platforms) | Sqm | 1170 | 12 | 991.5254 | 14040 | 0 | 0 | 0 | 14040 |  | 0 |  | 0 | 0 | 0 | 12 | 14040 | 0 | 0 | 0 | 14040 | 0 | 0 | 0 | 14040 | 409.5 | 4914 | 0
152 | SOTC153 | RCC M 20 grade design mix (25 mm thick Shelves) | Sqm | 900 | 12 | 762.7119 | 10800 | 0 | 0 | 0 | 10800 |  | 0 |  | 0 | 0 | 0 | 12 | 10800 | 0 | 0 | 0 | 10800 | 0 | 0 | 0 | 10800 | 315 | 3780 | 0
153 | SOTC154 | Brick Masonry work in CM (1:6) prop in superstructure | Cum | 15300 | 3 | 12966.1017 | 45900 | 106.62 | 1631286 | 1585386 | 0 |  | 0 |  | 0 | 0 | 0 | 3 | 45900 | 106.62 | 1631286 | 1585386 | 0 | 111.951 | 1712850.3 | 1666950.3 | 0 | 5355 | 16065 | 599497.605
154 | SOTC155 | Reinforced Masonry for partition walls (100 mm thick) in CM (1:4) | Sqm | 2700 | 500 | 2288.1356 | 1350000 | 385.65 | 1041255 | 0 | 308745 |  | 0 |  | 0 | 0 | 0 | 500 | 1350000 | 385.65 | 1041255 | 0 | 308745 | 404.9325 | 1093317.75 | 0 | 256682.25 | 945 | 472500 | 382661.2125
155 | SOTC156 | PCC (1:3:6) nominal mix using 20mm size graded m/c (For bed blocks and hold fasts) (OTs screed) | Cum | 9000 | 1.5 | 7627.1186 | 13500 | 0 | 0 | 0 | 13500 |  | 0 |  | 0 | 0 | 0 | 1.5 | 13500 | 0 | 0 | 0 | 13500 | 0 | 0 | 0 | 13500 | 3150 | 4725 | 0
156 | SOTC157 | Filling with light weight concrete in Cement Concrete (1:5:10) proportion using brick jelly for low roofs | Cum | 7200 | 23 | 6101.6949 | 165600 | 16.062 | 115646.4 | 0 | 49953.6 |  | 0 |  | 0 | 0 | 0 | 23 | 165600 | 16.062 | 115646.4 | 0 | 49953.6 | 16.8651 | 121428.72 | 0 | 44171.28 | 2520 | 57960 | 42500.052
157 | SOTC158 | Thermo Mechanically Treated (Fe -500/500D/550D) for RCC works | MT | 126000 | 1.25 | 106779.661 | 157500 | 0.732 | 92232 | 0 | 65268 |  | 0 |  | 0 | 0 | 0 | 1.25 | 157500 | 0.732 | 92232 | 0 | 65268 | 0.7686 | 96843.6 | 0 | 60656.4 | 44100 | 55125 | 33895.26
158 | SOTC159 | Plastering 12mm thick in two coats with base coat of 8mm thick in CM (1:6) and top coat of 4mm thick in CM (1:4). for Internal walls. | Sqm | 1224 | 1600 | 1037.2881 | 1958400 | 2046.48 | 2504891.52 | 546491.52 | 0 |  | 0 |  | 0 | 0 | 0 | 1600 | 1958400 | 2046.48 | 2504891.52 | 546491.52 | 0 | 2148.804 | 2630136.096 | 671736.096 | 0 | 428.4 | 685440 | 920547.6336
159 | SOTC160 | Impervious coat to exposed RCC roof slab surfaces (APSS No. 901 and 903) For Toilets | Sqm | 360 | 77.78 | 305.0847 | 28000.8 | 41 | 14760 | 0 | 13240.8 |  | 0 |  | 0 | 0 | 0 | 77.78 | 28000.8 | 41 | 14760 | 0 | 13240.8 | 43.05 | 15498 | 0 | 12502.8 | 126 | 9800.28 | 5424.3
160 | SOTC161 | Providing and applying Wall putty of White Cement or Polymer or Cement based of average 1 to 2 mm thickness over plastered surface to prepare the surface even and smooth after thoroughly brushing the surface to remove all dirt and remains of loose powdered materials, applying emery paper, Sand the surface, clean & wipe off loose dust, applying knifing paste filler by putty knife / muslin pad, air dry for 2 - 3 | Sqm | 270 | 4447 | 228.8136 | 1200690 | 1725.27 | 465822.9 | 0 | 734867.1 |  | 0 |  | 0 | 0 | 0 | 4447 | 1200690 | 1725.27 | 465822.9 | 0 | 734867.1 | 1811.5335 | 489114.045 | 0 | 711575.955 | 94.5 | 420241.5 | 171189.9158
161 | SOTC162 | Flooring with non-skid full body ceramic floor tiles | Sqm | 1710 | 85 | 1449.1525 | 145350 | 93.41 | 159731.1 | 14381.1 | 0 |  | 0 |  | 0 | 0 | 0 | 85 | 145350 | 93.41 | 159731.1 | 14381.1 | 0 | 98.0805 | 167717.655 | 22367.655 | 0 | 598.5 | 50872.5 | 58701.1793
162 | SOTC163 | Dadooing to walls with glazed full body Porcelain wall tiles | Sqm | 1440 | 225 | 1220.339 | 324000 | 372.89 | 536961.6 | 212961.6 | 0 |  | 0 |  | 0 | 0 | 0 | 225 | 324000 | 372.89 | 536961.6 | 212961.6 | 0 | 391.5345 | 563809.68 | 239809.68 | 0 | 504 | 113400 | 197333.388
163 | SOTC164 | Dadooing to walls with glazed full body Ceramic tiles | Sqm | 1440 | 350 | 1220.339 | 504000 | 257.35 | 370584 | 0 | 133416 |  | 0 |  | 0 | 0 | 0 | 350 | 504000 | 257.35 | 370584 | 0 | 133416 | 270.2175 | 389113.2 | 0 | 114886.8 | 504 | 176400 | 136189.62
164 | SOTC165 | Painting one coat water based cement primer of interior grade I and two coats of acrylic emulsion paint for ceiling and Walls | Sqm | 360 | 4447 | 305.0847 | 1600920 | 1306.68 | 470404.8 | 0 | 1130515.2 |  | 0 |  | 0 | 0 | 0 | 4447 | 1600920 | 1306.68 | 470404.8 | 0 | 1130515.2 | 1372.014 | 493925.04 | 0 | 1106994.96 | 126 | 560322 | 172873.764
165 | SOTC166 | Painting to new wood work | Sqm | 360 | 313 | 305.0847 | 112680 | 60 | 21600 | 0 | 91080 |  | 0 |  | 0 | 0 | 0 | 313 | 112680 | 60 | 21600 | 0 | 91080 | 75 | 27000 | 0 | 85680 | 126 | 39438 | 9450
166 | SOTC167 | Painting to new iron work | Sqm | 270 | 88 | 228.8136 | 23760 | 120.4 | 32508 | 8748 | 0 |  | 0 |  | 0 | 0 | 0 | 88 | 23760 | 120.4 | 32508 | 8748 | 0 | 126.42 | 34133.4 | 10373.4 | 0 | 94.5 | 8316 | 11946.69
167 | SOTC168 | Two shutter cupboards | Sqm | 9000 | 100 | 7627.1186 | 900000 | 0 | 0 | 0 | 900000 |  | 0 |  | 0 | 0 | 0 | 100 | 900000 | 0 | 0 | 0 | 900000 | 0 | 0 | 0 | 900000 | 3150 | 315000 | 0
168 | SOTC169 | UPVC Fixed Louvered Ventilator | Sqm | 12000 | 7 | 10169.4915 | 84000 | 15.73 | 188760 | 104760 | 0 |  | 0 |  | 0 | 0 | 0 | 7 | 84000 | 15.73 | 188760 | 104760 | 0 | 16.5165 | 198198 | 114198 | 0 | 4200 | 29400 | 69369.3
169 | SOTC170 | UPVC 3 track Sliding Windows | Sqm | 9000 | 15 | 7627.1186 | 135000 | 43.12 | 388080 | 253080 | 0 |  | 0 |  | 0 | 0 | 0 | 15 | 135000 | 43.12 | 388080 | 253080 | 0 | 45.276 | 407484 | 272484 | 0 | 3150 | 47250 | 142619.4
170 | SOTC171 | MS Grills to Windows | Sqm | 1800 | 150 | 1525.4237 | 270000 | 120.4 | 216720 | 0 | 53280 |  | 0 |  | 0 | 0 | 0 | 150 | 270000 | 120.4 | 216720 | 0 | 53280 | 126.42 | 227556 | 0 | 42444 | 630 | 94500 | 79644.6
171 | SOTC172 | Flooring with 16 to 18 mm thick high polished granite stone slabs black colour for platforms (S.S.701 and special) | Sqm | 6300 | 50 | 5338.9831 | 315000 | 402.07 | 2533041 | 2218041 | 0 |  | 0 |  | 0 | 0 | 0 | 50 | 315000 | 402.07 | 2533041 | 2218041 | 0 | 422.1735 | 2659693.05 | 2344693.05 | 0 | 2205 | 110250 | 930892.5675
172 | SOTC173 | Doors as per approved drawings with medium teak wood frame (1500mm x 2600mm) | Sqm | 6300 | 50 | 5338.9831 | 315000 | 14.16 | 89208 | 0 | 225792 |  | 0 |  | 0 | 0 | 0 | 50 | 315000 | 14.16 | 89208 | 0 | 225792 | 15.4 | 97020 | 0 | 217980 | 2205 | 110250 | 33957
173 | SOTC174 | Doors as per approved drawings with medium teak wood frame (1000mm x 2100mm) | Sqm | 7400 | 45 | 6271.1864 | 333000 | 8.98 | 66452 | 0 | 266548 |  | 0 |  | 0 | 0 | 0 | 45 | 333000 | 8.98 | 66452 | 0 | 266548 | 17.2 | 127280 | 0 | 205720 | 2590 | 116550 | 44548
174 | SOTC175 | Doors Shutters WPC(800mm x 2100mm) | Sqm | 5400 | 40 | 4576.2712 | 216000 | 31.79 | 171666 | 0 | 44334 |  | 0 |  | 0 | 0 | 0 | 40 | 216000 | 31.79 | 171666 | 0 | 44334 | 33.3795 | 180249.3 | 0 | 35750.7 | 1890 | 75600 | 63087.255
175 | SOTC176 | Scientific Doors with metal door frames and door shutters made of galvanize steel | Sqm | 18000 | 45 | 15254.2373 | 810000 | 78.72 | 1416960 | 606960 | 0 |  | 0 |  | 0 | 0 | 0 | 45 | 810000 | 78.72 | 1416960 | 606960 | 0 | 77.65 | 1397700 | 587700 | 0 | 6300 | 283500 | 489195
176 | SOTC177 | False ceiling as per Technical specification | Sqm | 1800 | 1400 | 1525.4237 | 2520000 | 825.4 | 1485720 | 0 | 1034280 |  | 0 |  | 0 | 0 | 0 | 1400 | 2520000 | 825.4 | 1485720 | 0 | 1034280 | 866.67 | 1560006 | 0 | 959994 | 630 | 882000 | 546002.1
177 | SOTC178 | Vinyl flooring | Sqm | 3000 | 500 | 2542.3729 | 1500000 | 691 | 2073000 | 573000 | 0 |  | 0 |  | 0 | 0 | 0 | 500 | 1500000 | 691 | 2073000 | 573000 | 0 | 725.55 | 2176650 | 676650 | 0 | 1050 | 525000 | 761827.5
178 | SOTC179 | Impervious coat to exposed RCC roof slab surfaces of 20mm thick (APSS No. 901 and 903) | Sqm | 1260 | 350 | 1067.7966 | 441000 | 0 | 0 | 0 | 441000 |  | 0 |  | 0 | 0 | 0 | 350 | 441000 | 0 | 0 | 0 | 441000 | 0 | 0 | 0 | 441000 | 441 | 154350 | 0
179 | SOTC180 | Fixed Glass Window – 1200 x 1200 | Sqm | 5400 | 53.55 | 4576.2712 | 289170 | 60.51 | 326754 | 37584 | 0 |  | 0 |  | 0 | 0 | 0 | 53.55 | 289170 | 60.51 | 326754 | 37584 | 0 | 61.01 | 329454 | 40284 | 0 | 1890 | 101209.5 | 115308.9
180 | SOTC181 | Grouting the holes with neat cement slurry of 20mm dia with all required accessories of all materials etc., including cost & Conveyance of all labour Charges etc., complete finished item of work (*As per SSR2021-22 of S.NO:-8) | Nos | 180 | 500 | 152.5424 | 90000 | 0 | 0 | 0 | 90000 |  | 0 |  | 0 | 0 | 0 | 500 | 90000 | 0 | 0 | 0 | 90000 | 0 | 0 | 0 | 90000 | 63 | 31500 | 0
181 | SOTC182 | Pressure grouting the drilled holes with neat cement slurry or with approved grout admixture using pump - excluding cost of drilling holes after fixing nozzles as technical specification approved by the department etc., including cost & Conveyance of all labour charges etc., complete finished item of work | Nos | 630 | 500 | 533.8983 | 315000 | 1084 | 682920 | 367920 | 0 |  | 0 |  | 0 | 0 | 0 | 500 | 315000 | 1084 | 682920 | 367920 | 0 | 1132 | 713160 | 398160 | 0 | 220.5 | 110250 | 0
182 | SOTC183 | Supply and fabricating,erecting and fixing inposition trusses of approved design with structural steel other than MS. | Kgs | 180 | 6500 | 152.5424 | 1170000 | 6500 | 1170000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 6500 | 1170000 | 6500 | 1170000 | 0 | 0 | 6500 | 1170000 | 0 | 0 | 63 | 409500 | 0
183 | SOTC184 | Supply and fixing of pre painted Galvalume Trapezoidal Profile Roofing with 0.50mm Thickness. | Sqm | 1080 | 65 | 915.2542 | 70200 | 65 | 70200 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 65 | 70200 | 65 | 70200 | 0 | 0 | 65 | 70200 | 0 | 0 | 378 | 24570 | 24570
184 | SOTC185 | 4" (101.6mm) multi floor trap with jali - UPVC/SWR | Nos | 270 | 25 | 228.8136 | 6750 | 44 | 11880 | 5130 | 0 |  | 0 |  | 0 | 0 | 0 | 25 | 6750 | 44 | 11880 | 5130 | 0 | 44 | 11880 | 5130 | 0 | 94.5 | 2362.5 | 4158
185 | SOTC186 | 580mm x 440mm long Orissa pan white glazed Water Closet | Nos | 5400 | 4 | 4576.2712 | 21600 | 4 | 21600 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 4 | 21600 | 4 | 21600 | 0 | 0 | 4 | 21600 | 0 | 0 | 1890 | 7560 | 7560
186 | SOTC187 | European Water Closet of 1st quality | Nos | 6300 | 9 | 5338.9831 | 56700 | 9 | 56700 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 9 | 56700 | 9 | 56700 | 0 | 0 | 9 | 56700 | 0 | 0 | 2205 | 19845 | 19845
187 | SOTC188 | Indian make Flat Back Wash Hand Basin 1st quality | Nos | 3600 | 16 | 3050.8475 | 57600 | 15 | 54000 | 0 | 3600 |  | 0 |  | 0 | 0 | 0 | 16 | 57600 | 15 | 54000 | 0 | 3600 | 15 | 54000 | 0 | 3600 | 1260 | 20160 | 18900
188 | SOTC189 | CP finish brass soap dish | Nos | 1100 | 21 | 932.2034 | 23100 | 21 | 23100 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 21 | 23100 | 21 | 23100 | 0 | 0 | 21 | 23100 | 0 | 0 | 385 | 8085 | 8085
189 | SOTC190 | TV shape mirror with plastic frame of size 609.6mm x 457.2mm | Nos | 630 | 25 | 533.8983 | 15750 | 15 | 9450 | 0 | 6300 |  | 0 |  | 0 | 0 | 0 | 25 | 15750 | 15 | 9450 | 0 | 6300 | 15 | 9450 | 0 | 6300 | 220.5 | 5512.5 | 3307.5
190 | SOTC191 | 25.4mm dia , 609.6mm long aluminium anodized towel rods | Nos | 540 | 36 | 457.6271 | 19440 | 21 | 11340 | 0 | 8100 |  | 0 |  | 0 | 0 | 0 | 36 | 19440 | 21 | 11340 | 0 | 8100 | 21 | 11340 | 0 | 8100 | 189 | 6804 | 3969
191 | SOTC192 | 15 mm brass body CP finish bib tap of not less than 300 grams weight | Nos | 540 | 25 | 457.6271 | 13500 | 14 | 7560 | 0 | 5940 |  | 0 |  | 0 | 0 | 0 | 25 | 13500 | 14 | 7560 | 0 | 5940 | 14 | 7560 | 0 | 5940 | 189 | 4725 | 2646
192 | SOTC193 | Self Closing Tap - Push Type | Nos | 720 | 25 | 610.1695 | 18000 | 15 | 10800 | 0 | 7200 |  | 0 |  | 0 | 0 | 0 | 25 | 18000 | 15 | 10800 | 0 | 7200 | 15 | 10800 | 0 | 7200 | 252 | 6300 | 3780
193 | SOTC194 | Chromium plated finish brass body quarter turn Bibcock cum Health Faucet | Nos | 3600 | 12 | 3050.8475 | 43200 | 24 | 86400 | 43200 | 0 |  | 0 |  | 0 | 0 | 0 | 12 | 43200 | 24 | 86400 | 43200 | 0 | 24 | 86400 | 43200 | 0 | 1260 | 15120 | 30240
194 | SOTC195 | Ashirvad/ Ajay/ Astral Flowguard or equivalent CPVC Pipes and Fittings - 15.90mm OD pipe | Rmt | 270 | 55 | 228.8136 | 14850 | 103.08 | 27831.6 | 12981.6 | 0 |  | 0 |  | 0 | 0 | 0 | 55 | 14850 | 103.08 | 27831.6 | 12981.6 | 0 | 108.234 | 29223.18 | 14373.18 | 0 | 94.5 | 5197.5 | 10228.113
195 | SOTC196 | Ashirvad/Ajay/Astral Flowguard or equivalent CPVC Pipes and Fittings - 22.20mm OD pipe | Rmt | 360 | 115 | 305.0847 | 41400 | 123.53 | 44470.8 | 3070.8 | 0 |  | 0 |  | 0 | 0 | 0 | 115 | 41400 | 123.53 | 44470.8 | 3070.8 | 0 | 129.7065 | 46694.34 | 5294.34 | 0 | 126 | 14490 | 16343.019
196 | SOTC197 | Ashirvad/ Ajay/ Astral Flowguard or equivalent CPVC Pipes and Fittings -28.60mm OD pipe | Rmt | 450 | 143 | 381.3559 | 64350 | 110 | 49500 | 0 | 14850 |  | 0 |  | 0 | 0 | 0 | 143 | 64350 | 110 | 49500 | 0 | 14850 | 115.5 | 51975 | 0 | 12375 | 157.5 | 22522.5 | 18191.25
197 | SOTC198 | Bronze Gate/ Globe valve - 25mm Nominal bore | Nos | 1440 | 15 | 1220.339 | 21600 | 20 | 28800 | 7200 | 0 |  | 0 |  | 0 | 0 | 0 | 15 | 21600 | 20 | 28800 | 7200 | 0 | 20 | 28800 | 7200 | 0 | 504 | 7560 | 10080
198 | SOTC199 | SWR PVC pipes (Prince/ Sudhakar/ Kisan/ Supreme or any ISI brand) 4 Kg/Sq.cm. - 75mmdia | Rmt | 450 | 145 | 381.3559 | 65250 | 80 | 36000 | 0 | 29250 |  | 0 |  | 0 | 0 | 0 | 145 | 65250 | 80 | 36000 | 0 | 29250 | 84 | 37800 | 0 | 27450 | 157.5 | 22837.5 | 13230
199 | SOTC200 | SWR PVC pipes (Prince/ Sudhakar/ Kisan/ Supreme or any ISI brand) 4 Kg/Sq.cm. -110mmdia | Rmt | 540 | 145 | 457.6271 | 78300 | 65 | 35100 | 0 | 43200 |  | 0 |  | 0 | 0 | 0 | 145 | 78300 | 65 | 35100 | 0 | 43200 | 68.25 | 36855 | 0 | 41445 | 189 | 27405 | 12899.25
200 | SOTC201 | Supplying and fixing15 mm nominal size 152.0 mm CP finish iron body shower rose 1st quality including cost and conveyance of all materials, labour charges , overheads & contractors profit for finished item of work in all floors. | Nos | 630 | 5 | 533.8983 | 3150 | 6 | 3780 | 630 | 0 |  | 0 |  | 0 | 0 | 0 | 5 | 3150 | 6 | 3780 | 630 | 0 | 630 | 396900 | 393750 | 0 | 220.5 | 1102.5 | 138915
201 | SOTC202 | Supply and Fixing of white glazed flat back bowl urinals | Nos | 2700 | 4 | 2288.1356 | 10800 | 0 | 0 | 0 | 10800 |  | 0 |  | 0 | 0 | 0 | 4 | 10800 | 0 | 0 | 0 | 10800 | 0 | 0 | 0 | 10800 | 945 | 3780 | 0
202 | SOTC203 | Supply and fixing of 16mm to 20 mm thick ploished marbles slab partitions of size 4'0"*2'0" | Nos | 3600 | 10 | 3050.8475 | 36000 | 0 | 0 | 0 | 36000 |  | 0 |  | 0 | 0 | 0 | 10 | 36000 | 0 | 0 | 0 | 36000 | 0 | 0 | 0 | 36000 | 1260 | 12600 | 0
203 | SOTC204 | 28 mm dia. and 0.90 mm thick Copper Pipe Lines for Main lines | Rmt | 1750 | 700 | 1483.0508 | 1225000 | 832 | 1456000 | 231000 | 0 |  | 0 |  | 0 | 0 | 0 | 700 | 1225000 | 832 | 1456000 | 231000 | 0 | 833 | 1457750 | 232750 | 0 | 612.5 | 428750 | 510212.5
204 | SOTC205 | 42 mm dia. and 1.20 mm thick Copper Pipe Lines for Main lines | Rmt | 2250 | 200 | 1906.7797 | 450000 | 226 | 508500 | 58500 | 0 |  | 0 |  | 0 | 0 | 0 | 200 | 450000 | 226 | 508500 | 58500 | 0 | 227 | 510750 | 60750 | 0 | 787.5 | 157500 | 178762.5
205 | SOTC206 | 54 mm dia. and 1.20 mm thick Copper Pipe Lines for Main lines | Rmt | 2950 | 550 | 2500 | 1622500 | 550 | 1622500 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 550 | 1622500 | 550 | 1622500 | 0 | 0 | 564 | 1663800 | 41300 | 0 | 1032.5 | 567875 | 582330
206 | SOTC207 | 12 mm dia. and 0.70 mm thick Copper Pipe Lines for distribution lines | Rmt | 650 | 320 | 550.8475 | 208000 | 591 | 384150 | 176150 | 0 |  | 0 |  | 0 | 0 | 0 | 320 | 208000 | 591 | 384150 | 176150 | 0 | 544 | 353600 | 145600 | 0 | 227.5 | 72800 | 123760
207 | SOTC208 | 15 mm dia. and 0.90 mm thick Copper Pipe Lines for distribution lines | Rmt | 950 | 525 | 805.0847 | 498750 | 838 | 796100 | 297350 | 0 |  | 0 |  | 0 | 0 | 0 | 525 | 498750 | 838 | 796100 | 297350 | 0 | 757 | 719150 | 220400 | 0 | 332.5 | 174562.5 | 251702.5
208 | SOTC209 | 22 mm dia. and 0.90 mm thick Copper Pipe Lines for distribution lines | Rmt | 1450 | 530 | 1228.8136 | 768500 | 636 | 922200 | 153700 | 0 |  | 0 |  | 0 | 0 | 0 | 530 | 768500 | 636 | 922200 | 153700 | 0 | 595 | 862750 | 94250 | 0 | 507.5 | 268975 | 301962.5
209 | SOTC210 | 15 mm (1/2") Isolation Valves | Nos | 1500 | 40 | 1271.1864 | 60000 | 35 | 52500 | 0 | 7500 |  | 0 |  | 0 | 0 | 0 | 40 | 60000 | 35 | 52500 | 0 | 7500 | 31 | 46500 | 0 | 13500 | 525 | 21000 | 16275
210 | SOTC211 | 22 mm (3/4") Isolation Valves | Nos | 2500 | 15 | 2118.6441 | 37500 | 13 | 32500 | 0 | 5000 |  | 0 |  | 0 | 0 | 0 | 15 | 37500 | 13 | 32500 | 0 | 5000 | 14 | 35000 | 0 | 2500 | 875 | 13125 | 12250
211 | SOTC212 | 28 mm Isolation Valves | Nos | 3500 | 3 | 2966.1017 | 10500 | 7 | 24500 | 14000 | 0 | 2 | 7000 | 2 | 7000 | 0 | 0 | 5 | 17500 | 9 | 31500 | 14000 | 0 | 9 | 31500 | 14000 | 0 | 1225 | 3675 | 11025
212 | SOTC213 | 42 mm Isolation Valves | Nos | 4500 | 2 | 3813.5593 | 9000 | 2 | 9000 | 0 | 0 | 3 | 13500 | 2 | 9000 | 0 | 4500 | 5 | 22500 | 4 | 18000 | 0 | 4500 | 4 | 18000 | 0 | 4500 | 1575 | 3150 | 6300
213 | SOTC214 | 54 mm Isolation Valves | Nos | 5500 | 2 | 4661.0169 | 11000 | 5 | 27500 | 16500 | 0 | 1 | 5500 | 1 | 5500 | 0 | 0 | 3 | 16500 | 6 | 33000 | 16500 | 0 | 10 | 55000 | 38500 | 0 | 1925 | 3850 | 19250
214 | SOTC215 | Gas Outlet Points with probes for Oxygen with S Brackets | Nos | 2850 | 189 | 2415.2542 | 538650 | 231 | 658350 | 119700 | 0 |  | 0 |  | 0 | 0 | 0 | 189 | 538650 | 231 | 658350 | 119700 | 0 | 206 | 587100 | 48450 | 0 | 997.5 | 188527.5 | 205485
215 | SOTC216 | 2 Gas Digital Area Alarm Panels | Nos | 25000 | 2 | 21186.4407 | 50000 | 0 | 0 | 0 | 50000 |  | 0 |  | 0 | 0 | 0 | 2 | 50000 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 50000 | 8750 | 17500 | 0
216 | SOTC217 | 3 Gas Digital Area Alarm Panels | Nos | 30000 | 4 | 25423.7288 | 120000 | 5 | 150000 | 30000 | 0 |  | 0 |  | 0 | 0 | 0 | 4 | 120000 | 5 | 150000 | 30000 | 0 | 5 | 150000 | 30000 | 0 | 10500 | 42000 | 52500
217 | SOTC218 | 5 Gas Digital Area Alarm Panels | Nos | 40000 | 5 | 33898.3051 | 200000 | 0 | 0 | 0 | 200000 | 1 | 40000 | 0 | 0 | 0 | 40000 | 6 | 240000 | 0 | 0 | 0 | 240000 | 0 | 0 | 0 | 240000 | 14000 | 70000 | 0
218 | SOTC219 | Master Digital Alarm Panels | Nos | 50000 | 1 | 42372.8814 | 50000 | 1 | 50000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 50000 | 1 | 50000 | 0 | 0 | 1 | 50000 | 0 | 0 | 17500 | 17500 | 17500
219 | SOTC220 | BPC Flow meter with Humidifier bottle and L adapter | Nos | 2250 | 27 | 1906.7797 | 60750 | 43 | 96750 | 36000 | 0 |  | 0 |  | 0 | 0 | 0 | 27 | 60750 | 43 | 96750 | 36000 | 0 | 43 | 96750 | 36000 | 0 | 787.5 | 21262.5 | 33862.5
220 | SOTC221 | L Type Adapter for Oxygen Flow meters | Nos | 1250 | 27 | 1059.322 | 33750 | 27 | 33750 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 27 | 33750 | 27 | 33750 | 0 | 0 | 27 | 33750 | 0 | 0 | 437.5 | 11812.5 | 11812.5
221 | SOTC222 | Kit for conversion of Oxygen | Nos | 1650 | 27 | 1398.3051 | 44550 | 18 | 29700 | 0 | 14850 |  | 0 |  | 0 | 0 | 0 | 27 | 44550 | 18 | 29700 | 0 | 14850 | 18 | 29700 | 0 | 14850 | 577.5 | 15592.5 | 10395
222 | SOTC223 | Suction Jars of 600 ml capacity | Nos | 3450 | 27 | 2923.7288 | 93150 | 37 | 127650 | 34500 | 0 |  | 0 |  | 0 | 0 | 0 | 27 | 93150 | 37 | 127650 | 34500 | 0 | 46 | 158700 | 65550 | 0 | 1027.5 | 27742.5 | 47265
223 | SOTC224 | Adapters for Vacuum | Nos | 750 | 27 | 635.5932 | 20250 | 27 | 20250 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 27 | 20250 | 27 | 20250 | 0 | 0 | 27 | 20250 | 0 | 0 | 262.5 | 7087.5 | 7087.5
224 | SOTC225 | Adapters for Air | Nos | 750 | 27 | 635.5932 | 20250 | 27 | 20250 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 27 | 20250 | 27 | 20250 | 0 | 0 | 27 | 20250 | 0 | 0 | 262.5 | 7087.5 | 7087.5
225 | SOTC226 | Adapters for Nitrous Oxide | Nos | 750 | 15 | 635.5932 | 11250 | 15 | 11250 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 15 | 11250 | 15 | 11250 | 0 | 0 | 15 | 11250 | 0 | 0 | 262.5 | 3937.5 | 3937.5
226 | SOTC227 | Vacuum Tube | Nos | 550 | 27 | 466.1017 | 14850 | 32 | 17600 | 2750 | 0 | 58 | 31900 | 5 | 2750 | 0 | 29150 | 85 | 46750 | 37 | 20350 | 0 | 26400 | 115 | 63250 | 16500 | 0 | 192.5 | 5197.5 | 22137.5
227 | SOTC228 | Bed Head wall panel horizontal 1500 mm long single railing | Nos | 35000 | 27 | 29661.0169 | 945000 | 31 | 1085000 | 140000 | 0 |  | 0 |  | 0 | 0 | 0 | 27 | 945000 | 31 | 1085000 | 140000 | 0 | 31 | 1085000 | 140000 | 0 | 12250 | 330750 | 379750
228 | SOTC229 | Valve box -2 services | Nos | 9500 | 1 | 8050.8475 | 9500 | 0 | 0 | 0 | 9500 |  | 0 |  | 0 | 0 | 0 | 1 | 9500 | 0 | 0 | 0 | 9500 | 0 | 0 | 0 | 9500 | 3325 | 3325 | 0
229 | SOTC230 | Valve box -3 services | Nos | 14500 | 3 | 12288.1356 | 43500 | 5 | 72500 | 29000 | 0 |  | 0 |  | 0 | 0 | 0 | 3 | 43500 | 5 | 72500 | 29000 | 0 | 5 | 72500 | 29000 | 0 | 5075 | 15225 | 25375
230 | SOTC231 | Valve box -6 services | Nos | 22500 | 1 | 19067.7966 | 22500 | 2 | 45000 | 22500 | 0 | 5 | 112500 | 5 | 112500 | 0 | 0 | 6 | 135000 | 7 | 157500 | 22500 | 0 | 6 | 135000 | 0 | 0 | 7875 | 7875 | 47250
231 | SOTC232 | 4 + 4 size of CO2 manifold System | Job | 40000 | 1 | 33898.3051 | 40000 | 1 | 40000 | 0 | 0 | 1 | 40000 | 1 | 40000 | 0 | 0 | 2 | 80000 | 2 | 80000 | 0 | 0 | 3 | 120000 | 40000 | 0 | 14000 | 14000 | 42000
232 | SOTC233 | 2 cylinder emergency manifold | Job | 14500 | 1 | 12288.1356 | 14500 | 1 | 14500 | 0 | 0 | 1 | 14500 | 1 | 14500 | 0 | 0 | 2 | 29000 | 2 | 29000 | 0 | 0 | 2 | 29000 | 0 | 0 | 5075 | 5075 | 10150
233 | SOTC234 | Fully Automatic CO2 Control System | Job | 185000 | 1 | 156779.661 | 185000 | 1 | 185000 | 0 | 0 | 1 | 185000 | 1 | 185000 | 0 | 0 | 2 | 370000 | 2 | 370000 | 0 | 0 | 2 | 370000 | 0 | 0 | 64750 | 64750 | 129500
234 | SOTC235 | Aneste Iwata Make TFS 150 C9 Model, Compresso Two stage, Motor 15 HP & 57.18 CFM, 60 CFM Air Dryer with 2000 Ltrs Receiver Twin System (For Air4, Air7) | Job | 1895000 | 1 | 1605932.2034 | 1895000 | 1 | 1895000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 1895000 | 1 | 1895000 | 0 | 0 | 1 | 1895000 | 0 | 0 | 663250 | 663250 | 663250
235 | SOTC236 | Supporting structure for MGPS lines with Ismb Columns, beams, MS angles, Flats and square rods | Job | 795000 | 1 | 673728.8136 | 795000 | 1 | 795000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 795000 | 1 | 795000 | 0 | 0 | 1 | 795000 | 0 | 0 | 278250 | 278250 | 278250
236 | SOTC237 | 2x20 Oxygen Main manifold System | Job | 95000 | 1 | 80508.4746 | 95000 | 1 | 95000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 95000 | 1 | 95000 | 0 | 0 | 1 | 95000 | 0 | 0 | 33250 | 33250 | 33250
237 | SOTC238 | Electrical Control Panel for MGPS | Job | 145000 | 1 | 122881.3559 | 145000 | 1 | 145000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 145000 | 1 | 145000 | 0 | 0 | 1 | 145000 | 0 | 0 | 50750 | 50750 | 50750
238 | SOTC239 | Vaccum system Ingersoll Rand Make Model 15V x 10 Model with 5 HP Motor with 1000 Liters Reciever, Filters, Electricals, Etc Secretion Trap and Bacteria Filter | Job | 1495000 | 2 | 1266949.1525 | 2990000 | 2 | 2990000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 2 | 2990000 | 2 | 2990000 | 0 | 0 | 2 | 2990000 | 0 | 0 | 523250 | 1046500 | 1046500
239 | SOTC240 | Validation By Third Party Agency Charges per Each MOT | Each | 100000 | 4 | 84745.7627 | 400000 | 4 | 400000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 4 | 400000 | 4 | 400000 | 0 | 0 | 9 | 900000 | 500000 | 0 | 35000 | 140000 | 315000
240 | SOTC241 | Anesthetic Gas Scavenging System (AGSS) | Job | 1213000 | 1 | 1027966.1017 | 1213000 | 1 | 1213000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 1213000 | 1 | 1213000 | 0 | 0 | 1 | 1213000 | 0 | 0 | 424550 | 424550 | 424550
241 | New item | Double Arm Surgical Pendants (Imported) | Nos | 1195000 | 0 |  | 0 | 0 | 0 | 0 | 0 | 6 | 7170000 | 6 | 7170000 | 0 | 0 | 6 | 7170000 | 6 | 7170000 | 0 | 0 | 6 | 7170000 | 0 | 0
|  | GRAND TOTAL |  |  |  |  | 175773220.8 |  | 178852525.92 | 19724900.12 | 16645595 |  | 39441980 |  | 36047834.55 | 535753.7 | 3929899.15 |  | 215215200.8 | 62753.552 | 214884360.47 | 19936150.12 | 20266990.45 |  | 226818485.591 | 27073506.314 | 15470221.523 |  | 61476304.78 | 75396546.4011
SUPPLEMENTAL ITEMS | [30 empty] | 11603284.791
S. No | Item Code | Item Name | UOM | Unit Rate (Rs.) | [19 empty] | QTY | Amount (Rs.)
1 |  | Supply and installation of Under-deck Thermocol insulation sheets of 40 mm thick having more than 30 Kg/m3 density to ceiling by brush application of bituminous adhesive to the sheets and secured with screw along with washer at the centre of the sheet supported with GI wire running diagonally to the sheet of 2mm dia. | Sqm | 1013.54 | [19 empty] | 262.74 | 266297.4996
2 |  | Supply and placing of the Design Mix Plain Cement Concrete of M 25 grade corresponding to IS 456 with minimum cement content of 380 kgs per 1 cum of concrete using Concrete Batching Plant with 20mm size graded machine crushed hard granite metal (coarse aggregate - as per IS 383 - 1970 and IS 2386 Part 1 to Part 8) including cost and conveyance of all materials like cement, fine aggregate (sand) coarse aggregate, water etc., to site and sales & other taxes on all materials. | Cum | 11740 | [19 empty] | 28.01 | 328837.4
3 |  | Supply and Laying of Floor leveller compund (self smoothing mortar) to level the surface, having bulk density not less than 2 Kg/l for a fresh mortor, compressive strength not less than 20 N/mm2, initial setting time not more than 40 minutes and offer a 25 minutes working time, The surface should be walkabe after 30 min of laying. (ICUs) | Sqm | 1460 | [19 empty] | 725.55 | 1059303
4 |  | 800 KVA Transformer OLTC for transformers with RTCC: Supply, Transportation, Installation, Testing and Commissioning of 800 KVA TRANSFORMER with all test reports. The Transformer shall be designed and manufactured as per IS:1180 OLTC with level-II with initial filling of oil as per IS 335-1993. 1000 A LT Breaker Kiosk - 01 No.The basic details of the Transformer are as under. Makes: Kirloskar / PETE / Esennar / Voltamp / Crompton / ABB / Schneider. | Nos | 5086347.01 | [19 empty] | 1
5 |  | 4 Gas Digital Alarm Panels : 4 Gas Digital Alarm Panel consisting of atl necessary accessories ie Pressure sensors,reguIators,hand valves ,pressure gauges ecL(Oxygen, Nitrous oxide, Medical Air, Vacuum) | Nos | 42150 | [19 empty] | 1 | 42150
6 |  | 6 Gas Digital Alarm Panele : 6 Gas Digital Alarm Panel(Oxygen, Nitrous oxide, Medical Air, Surgical Air, Vacuum, Carbon dieoxide) consisting of all necessary accessories ie pressure sensors, regulators, hand vatves, pressure gauges etc. | Nos | 60008 | [19 empty] | 6 | 360048
7 |  | Valve box -4 services : Valve box - 4 Service consisting of Isolation valve 15 mm OD - 04 Nos. and isolation valve 22 mm OD - 01 Nos. accessories ie Pressure gauge connection in a powder coated box The box consisting of lock & key and a brakable glass for emergency. | Nos | 22201 | [19 empty] | 1 | 22201
8 |  | 4 + 4 size of O2 manifold system : 4+4 Oxygen Main mannifold with 19mm ODx12mm I.D .Copper pipe mounted on top frame, Middle frmae and Bottom frame along with brass blocks, NRVs/ cylinder valves and pigtail pipes of 1m long of 8mm OD x 3mm I.D. duly tested at250Kg/Cum 2 pressure & Fully automatic control panel for Oxygen. | Job | 48103 | [19 empty] | 1 | 48103
9 |  | Fully Automatic O2 Control System ”Manufactured under an ISO 9001: 2015 certified works. ”Control Panel cover made of M.S. duly powder coated. “Compact and fully automatic manifold control system far Oxygen services. *Easy to maintain and use. “Designed with both safety and continuity of flow supply at a constant pressure via to/o banks of bottled gas cylinders with following status monitoring. ”A-Bank in use (Green indication). ”B-Bank ready for use (Yelk›w indication). ”C-Empty Bank (Red indication). ”Control Panel has build in LED display to indicate Normal. High & Low line Pressure. ”It has facility to test all above indicators working perfectly. the Control Panel indudes Pressure gauge (63 mm) to indicate the gas pressure of each header and pipe line diistribution pressure. ”Capable to provide a distribution distribution flow rate of 2IXI0 LPM or more for O2. the control panel incorporte safety puncture system in case pressure exceeds 100 Psi. ”In ease of failure of electronic pneumatics system, control can be used manually through by pass system. * CE CERTIFIED. | Job | 222013 | [19 empty] | 1 | 222013
10 |  | Supply and installation of 50mm thick double skin modular wall Panels made of 0.8 mm thick powder coated GI on both the sides, with 40 plus or minus 2 kg/m3 density PUF as infill, GI profiles all along the periphery, flush on both sides with maximum allowable gap of 3- 4mm filled with food grade silicon sealant and placed on cold rolled galvanised bottom tracks with a recess to provide floor to wall coving flush with the wall panel. This includes all required harware for completion Panels to be covered with a protective film to avoid any damages during transportation and installation | Sqm | 7450 | [19 empty] | 0 | 0
11 |  | Supply and installation of 50mm thick double skin ceiling system made of 0.8 mm thick Powder Coated GI sheets on both sides, 40 plus or minus 2 kg/m3 density PUF as infill, GI profiles all along the periphery, panels flush towards room side with maximum allowable gap of 3-4mm at panel to panel joints filled with silicon sealant. Ceiling panels are suspended from the RCC slab by using concealed AL ceiling grid with tie rod and adjustable turn buckle arrangement etc. This includes all required hardware for completion. Panels to be covered with a protective film to avoid any damages during transportation and installation | Sqm | 7450 | [19 empty] | 0 | 0
12 |  | Providing dadooing to walls with glazed full body ceramic wall tiles of size 800 x 1600 mm with any type of design texture such as marble finish, wooden, bamboo, stone finishes etc., scratch less, stain free and thickness between 6-8 mm 1st quality conforming to IS:13711, IS:13712, IS:13630 Parts 1 to 15 of any colour and finish in all shades and designs with borders as approved by Engineer-in-Charge set over base coat of CM1:5 12 mm thick using screened sand with cement slurry of honey like consistency spread at the rate of 3.30 kgs per sqm and jointing with white cement paste mixed with pigment of matching shade to full depth, including cost of all materials like tiles, cement, sand and water etc., complete for finished item of work. | Sqm | 4665 | [19 empty] | 120 | 559800
13 |  | Glass Sliding Door in TIR-2 & TIR-3 *Size 1.8mt x 2.1mt. *The door will be sliding. ”The material of door will be Glass. *The door will be operate by sensor. *The door movement will be easy and smooth. | Nos | 270276 | [19 empty] | 2 | 540552
14 |  | Monitor Stand beside Bed in ICUs & TIRs | Nos | 6176 | [19 empty] | 31 | 191456
15 |  | Recording in counselling room | Job | 155378 | [19 empty] | 1 | 155378
17 |  | Local Area Network (LAN) System | Job | 460242 | [19 empty] | 1 | 460242
18 |  | Supply, Transportation and installation of 20KVA / 312V DC on line UPS system | Nos | 629358 | [19 empty] | 2 | 1258716
19 |  | V-Board Partitions on top of false ceiling for partitioning of sterile corridor and non-sterile corridor | Sqm | 3640 | [19 empty] | 16 | 58240
20 |  | Manual Hermetically Sealed Sliding Doors (1.20mt x 2.10 mt) the door shall be a hermetically sealed, single sliding. ”The track shall be of stainless stœl/Aluminum and the running surface for the top rollers shall be suitably angled to reduce resistanœ to movement ”Door opening handle tower bolt 2 Nos. of 100mm x 10mm, 2 Nos of handles 100mm Iong and Heavy duty and shall be strong and sturdy. h4aterial shall be of SS (gloss/Matt finish). Shall be provided withhigh quality cylindrical/ESPG lock. “The door material shall be of HPL Color shall match me interior and care shall be taken to make the leaf strong and light weight “One shall be able to open and Öose the door effortlessly manually Operated. “Door opening handle shall be strong and sturdy. Matenal shall be of SS (gloss/Matt finish). Shall be provided with high quality cylindrical/ESPG lock. “Door leaf shall have high quality synthetic rubber gasket with kmg life to ensure hermetic sealing (to maintain air pressure differential). Air tightriess99.99% at a pressure of 75Pa. the finished floor on either side of the door shall be perfectly level (maximum permissible difference +1mm). “The overall thickness of the fînished door shall be 55 to 60mm. The inner part of the door shall be filled with CFC free polyurethane foam thickness of48mm or nearby.(SeaIed airtight to prevent fui1her ingress of any microbial organism). The door and controls shall œmply with IEE regulation. Æl motors used shall be DC brushless / PMDC motors with essenôal isolaüon from mains. Door shall be with vision window 300 mm x 300 mm with doubte glazed Smm thick panels and hermetically sealed with lead line protection. Door movement shall have minimum noise. | Nos | [20 empty] | 1 | 0
21 |  | 4 + 4 size of N2O manifold system : 4+4 Nitrous oxide Main mannifold with 19mm ODx12mm I.D .Copper pipe mounted on top frame, Middle frmae and Bottom frame along with brass blocks, NRVs/ cylinder valves and pigtail pipes of 1m long of 8mm OD x 3mm I.D. duly tested at 250Kg/Cum 2 pressure & Fully automatic control panel for Nitrous Oxide. | Job | 48103 | [19 empty] | 1 | 48103
22 |  | 2 cylinder emergency maniféld - N2O : 2 Cylinder Nftmus oxide Emergency mannifold with 19mm ODx12mm I.D .Copper pipe mounted on top frame, Middle frmae and Bottom frame along with brass blocks, NRVs/ cytinder valves and pigtail pipes of 1m long of 8mm OD x 3mm I.D. duly tested at 250Kg/Cum 2 pressure & Fully automatic control panel for Nitrous Oxide. | Job | 17401 | [19 empty] | 1 | 17401
23 |  | Fully Automate N2O Combat System ”Manufactured under an ISO 9001: 2015 certified works. ”Control Panel cover made of M.S. duly powder coated. “Compact and fully automatic manifold control system for N2O services. ”Easy to maintain and use. ”Designed with both safety and continuity of flow supply at a constant pressure via two banks of bottled gas cylinders with following status monitoring. A-Bank in use (Green indication). “B-Bank ready for use (Yetlow indication). “C-Empty Bank (Red indication). “Control Panel has build in LED display to indicate Normal. High & Lou line Pressure. ”It has facility to test all above indicators working perfectly. the Control Panel includes Pressure gauge (63 mm) to indicate the gas pressure of each header and pipe line diistribution pressure. Capable to provide a distribution flow rate of 5tXl LPM or more for N2O. The control panel incorporte safety puncture system in case pressure exceeds 100 Psi. “In ease of failure of electronic pneumatics system, contrbl can be used manually through by pass system. ” CE CERTIFIED. | Job | 222013 | [19 empty] | 1 | 222013
5860853.8996
80
24.1
827.13
1
7
1
1
1
1
1
1
1
470
88.5
61.5
147
534.3
[20 empty] | 0 | 0