## RE
REVISED ESTIMATE OF SOTC 8TH FLOOR, SOUTH-WEST BLOCK, GANDHI HOSPITAL
S.No | Item S.No | Item Code | Item Name |  |  | As Per Agreement (with 4 Ots) |  |  | Actual Quantities for agreement items (with 4 Ots) |  | Variation |  | Additional Sanction fot 2 Ots |  | Actual QTY for Additional 2 OTs |  | Variation |  | Total (6 Ots) |  | As Per Work Done/To Be Done |  | Variation |  | As Per Work Done/To Be Done |  | Variation |  | Remarks
|  |  |  | UOM | Unit Rate (Rs.) | QTY |  | Amount (Rs.) | QTY | Amount (Rs.) | Excess | Less | QTY | Amount (Rs.) | QTY | Amount (Rs.) | Excess | Less | QTY | Amount (Rs.) | QTY | Amount (Rs.) | Excess | Less | QTY | Amount (Rs.) | Excess | Less
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27
1 | 1 | SOTC001 | Stainless Steel Pre-fabricated Wall panels. (MOTs & MOT Corridor) - Wall panels | Sqm | 15010 | 400 | 12720.339 | 6004000 | 294.28 | 4417142.8 | 0 | 1586857.2 | 350 | 5253500 | 183.34 | 2751933.4 | 0 | 2501566.6 | 750 | 11257500 | 477.62 | 7169076.2 | 0 | 4088423.8 | 491.9486 | 7384148.486 | 0 | 3873351.514
2 | 199 | SOTC002 | Stainless Steel Pre-fabricated Ceiling panels In MOTs & MOTs Corridor | Sqm | 15010 | 385 | 12720.339 | 5778850 | 157.13 | 2358521.3 | 0 | 3420328.7 | 78 | 1170780 | 98.37 | 1476533.7 | 305753.7 | 0 | 463 | 6949630 | 255.5 | 3835055 | 0 | 3114575 | 263.165 | 3950106.65 | 0 | 2999523.35
3 | 2 | SOTC003 | Dynamic Hatch Box | Nos | 295000 | 2 | 250000 | 590000 | 0 | 0 | 0 | 590000 | 1 | 295000 | 0 | 0 | 0 | 295000 | 3 | 885000 | 0 | 0 | 0 | 885000 | 0 | 0 | 0 | 885000
4 | 3 | SOTC004 | Electro conductive Flooring inside MOTs | Sqm | 4035 | 160 | 3419.4915 | 645600 | 139.94 | 564657.9 | 0 | 80942.1 | 80 | 322800 | 73.57 | 296854.95 | 0 | 25945.05 | 240 | 968400 | 213.51 | 861512.85 | 0 | 106887.15 | 217.7802 | 878743.107 | 0 | 89656.893
5 | 4 | SOTC005 | Flooring with Vinyl Sheets In MOT Corridor | Sqm | 3750 | 175 | 3177.9661 | 656250 | 44.828 | 168105 | 0 | 488145 | 50 | 187500 | 39.67 | 148762.5 | 0 | 38737.5 | 225 | 843750 | 84.498 | 316867.5 | 0 | 526882.5 | 87.0329 | 326373.525 | 0 | 517376.475
6 | 5 | SOTC006 | Uni Directional Ceiling Laminar Airflow Systems | Nos | 465000 | 4 | 394067.7966 | 1860000 | 4 | 1860000 | 0 | 0 | 2 | 930000 | 2 | 930000 | 0 | 0 | 6 | 2790000 | 6 | 2790000 | 0 | 0 | 6 | 2790000 | 0 | 0
7 | 6 | SOTC007 | Air Handling Units (AHUs) 11 TR | Nos | 1495000 | 4 | 1266949.1525 | 5980000 | 4 | 5980000 | 0 | 0 | 2 | 2990000 | 2 | 2990000 | 0 | 0 | 6 | 8970000 | 6 | 8970000 | 0 | 0 | 6 | 8970000 | 0 | 0
8 | 7 | SOTC008 | Condensing Units | Nos | 345000 | 4 | 292372.8814 | 1380000 | 4 | 1380000 | 0 | 0 | 2 | 690000 | 2 | 690000 | 0 | 0 | 6 | 2070000 | 6 | 2070000 | 0 | 0 | 6 | 2070000 | 0 | 0
9 | 8 | SOTC009 | Pressure Relief Dampers | Nos | 22500 | 4 | 19067.7966 | 90000 | 4 | 90000 | 0 | 0 | 2 | 45000 | 2 | 45000 | 0 | 0 | 6 | 135000 | 6 | 135000 | 0 | 0 | 6 | 135000 | 0 | 0
10 | 9 | SOTC010 | Single arm Anesthesia Pendants (Imported) | Nos | 1195000 | 4 | 1012711.8644 | 4780000 | 4 | 4780000 | 0 | 0 | 2 | 2390000 | 2 | 2390000 | 0 | 0 | 6 | 7170000 | 6 | 7170000 | 0 | 0 | 6 | 7170000 | 0 | 0
11 | 10 | SOTC011 | Triple Dome Ceiling OT LED Lights (Imported) | Nos | 4750000 | 2 | 4025423.7288 | 9500000 | 2 | 9500000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2 | 9500000 | 2 | 9500000 | 0 | 0 | 2 | 9500000 | 0 | 0
12 | 11 | SOTC012 | Double Dome Ceiling OT LED Lights (Imported) | Nos | 3550000 | 2 | 3008474.5763 | 7100000 | 2 | 7100000 | 0 | 0 | 2 | 7100000 | 2 | 7100000 | 0 | 0 | 4 | 14200000 | 4 | 14200000 | 0 | 0 | 4 | 14200000 | 0 | 0
13 | 12 | SOTC013 | Detachable Hi Definition Cameras in Triple Dome Ceiling OT Lights | Nos | 995000 | 2 | 843220.339 | 1990000 | 2 | 1990000 | 0 | 0 | 1 | 995000 | 0 | 0 | 0 | 995000 | 3 | 2985000 | 2 | 1990000 | 0 | 995000 | 2 | 1990000 | 0 | 995000
14 | 13 | SOTC014 | Ceiling/Wall mounted CCTV Room Camera | Nos | 22500 | 4 | 19067.7966 | 90000 | 4 | 90000 | 0 | 0 | 2 | 45000 | 2 | 45000 | 0 | 0 | 6 | 135000 | 6 | 135000 | 0 | 0 | 6 | 135000 | 0 | 0
15 | 14 | SOTC015 | LED Peripheral Lights cum clean room (OT) luminaries | Nos | 18750 | 62 | 15889.8305 | 1162500 | 62 | 1162500 | 0 | 0 | 40 | 750000 | 40 | 750000 | 0 | 0 | 102 | 1912500 | 102 | 1912500 | 0 | 0 | 87 | 1631250 | 0 | 281250
16 | 239 | SOTC016 | View Window with Motorised Blinds of 1 Mt Length & 1 Mt Height | Nos | 115000 | 7 | 97457.6271 | 805000 | 10 | 1150000 | 345000 | 0 | 2 | 230000 | 4 | 460000 | 230000 | 0 | 9 | 1035000 | 14 | 1610000 | 575000 | 0 | 14 | 1610000 | 575000 | 0
17 | 15 | SOTC017 | Hermetically Sealed Doors (1.80mt x 2.10 mt) | Nos | 115000 | 4 | 97457.6271 | 460000 | 4 | 460000 | 0 | 0 | 2 | 230000 | 2 | 230000 | 0 | 0 | 6 | 690000 | 6 | 690000 | 0 | 0 | 6 | 690000 | 0 | 0
18 | 240 | SOTC018 | (1.50mt x 2.10 mt) Sliding Automatic Sliding Doors with View Windoy of 1 Mt x 1 Mt | Nos | 525000 | 2 | 444915.2542 | 1050000 | 2 | 1050000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2 | 1050000 | 2 | 1050000 | 0 | 0 | 3 | 1575000 | 525000 | 0
19 | 16 | SOTC019 | Storage Units | Nos | 75000 | 4 | 63559.322 | 300000 | 4 | 300000 | 0 | 0 | 2 | 150000 | 2 | 150000 | 0 | 0 | 6 | 450000 | 6 | 450000 | 0 | 0 | 6 | 450000 | 0 | 0
20 | 17 | SOTC020 | Writing Board (List Board) | Nos | 18750 | 4 | 15889.8305 | 75000 | 4 | 75000 | 0 | 0 | 2 | 37500 | 2 | 37500 | 0 | 0 | 6 | 112500 | 6 | 112500 | 0 | 0 | 6 | 112500 | 0 | 0
21 | 18 | SOTC021 | X-Ray CT Scan LED viewing Screen | Nos | 37500 | 4 | 31779.661 | 150000 | 4 | 150000 | 0 | 0 | 2 | 75000 | 2 | 75000 | 0 | 0 | 6 | 225000 | 6 | 225000 | 0 | 0 | 6 | 225000 | 0 | 0
22 | 19 | SOTC022 | Touch Screen Surgeon Control Panels | Nos | 385000 | 4 | 326271.1864 | 1540000 | 4 | 1540000 | 0 | 0 | 2 | 770000 | 2 | 770000 | 0 | 0 | 6 | 2310000 | 6 | 2310000 | 0 | 0 | 6 | 2310000 | 0 | 0
23 | 20 | SOTC023 | 3-Bay Scrub Stations/Sinks | Nos | 368750 | 2 | 312500 | 737500 | 3 | 1106250 | 368750 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2 | 737500 | 3 | 1106250 | 368750 | 0 | 3 | 1106250 | 368750 | 0
24 | 21 | SOTC024 | Video and Image Management system | Nos | 8000000 | 1 | 6779661.0169 | 8000000 | 1 | 8000000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 8000000 | 1 | 8000000 | 0 | 0 | 1 | 8000000 | 0 | 0
25 | 22 | SOTC025 | Medical Grade Monitors 32 inch 4 K Resolution | Nos | 1295000 | 4 | 1097457.6271 | 5180000 | 4 | 5180000 | 0 | 0 | 2 | 2590000 | 2 | 2590000 | 0 | 0 | 6 | 7770000 | 6 | 7770000 | 0 | 0 | 6 | 7770000 | 0 | 0
26 | 23 | SOTC026 | Wall mounted large screen display 55 inch (Commercial Grade) | Nos | 495000 | 2 | 419491.5254 | 990000 | 2 | 990000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 2 | 990000 | 2 | 990000 | 0 | 0 | 2 | 990000 | 0 | 0
27 | 24 | SOTC027 | Cable connections for integration within MOTs and with Workshop Projector Hall, Networks with OFC Cable | Job | 997500 | 4 | 845338.9831 | 3990000 | 4 | 3990000 | 0 | 0 | 2 | 1995000 | 2 | 1995000 | 0 | 0 | 6 | 5985000 | 6 | 5985000 | 0 | 0 | 6 | 5985000 | 0 | 0
28 | 25 | SOTC028 | Wireless Microphone | Nos | 255000 | 1 | 216101.6949 | 255000 | 1 | 255000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 255000 | 1 | 255000 | 0 | 0 | 1 | 255000 | 0 | 0
29 | 26 | SOTC029 | Digital mixer Amplifier | Nos | 245000 | 1 | 207627.1186 | 245000 | 1 | 245000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 245000 | 1 | 245000 | 0 | 0 | 1 | 245000 | 0 | 0
30 | 27 | SOTC030 | Ceiling Mounted Speakers | Nos | 15000 | 4 | 12711.8644 | 60000 | 4 | 60000 | 0 | 0 | 2 | 30000 | 2 | 30000 | 0 | 0 | 6 | 90000 | 6 | 90000 | 0 | 0 | 6 | 90000 | 0 | 0
31 | 28 | SOTC031 | Video Conferencing System | Nos | 1195000 | 1 | 1012711.8644 | 1195000 | 1 | 1195000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 1195000 | 1 | 1195000 | 0 | 0 | 1 | 1195000 | 0 | 0
32 | 29 | SOTC032 | Home Theatre Power Conditioner, 230 V | Nos | 145000 | 1 | 122881.3559 | 145000 | 1 | 145000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 145000 | 1 | 145000 | 0 | 0 | 1 | 145000 | 0 | 0
33 | 30 | SOTC033 | Amplifier (8 Channel) | Nos | 245000 | 1 | 207627.1186 | 245000 | 1 | 245000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 245000 | 1 | 245000 | 0 | 0 | 1 | 245000 | 0 | 0
34 | 31 | SOTC034 | HiFi Active Sub Woofer | Nos | 50000 | 1 | 42372.8814 | 50000 | 1 | 50000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 50000 | 1 | 50000 | 0 | 0 | 1 | 50000 | 0 | 0
35 | 32 | SOTC035 | 4K Laser Projection TV | Nos | 1495000 | 1 | 1266949.1525 | 1495000 | 1 | 1495000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 1495000 | 1 | 1495000 | 0 | 0 | 1 | 1495000 | 0 | 0
36 | 200 | SOTC036 | Equalization & Loud Speaker Control System | Nos | 40000 | 1 | 33898.3051 | 40000 | 1 | 40000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 40000 | 1 | 40000 | 0 | 0 | 1 | 40000 | 0 | 0
37 | 33 | SOTC037 | Sound Analog Mixer | Nos | 245000 | 1 | 207627.1186 | 245000 | 1 | 245000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 245000 | 1 | 245000 | 0 | 0 | 1 | 245000 | 0 | 0
38 | 201 | SOTC038 | Electrical Installations in MOTs & TIRs | Job | 195000 | 7 | 165254.2373 | 1365000 | 7 | 1365000 | 0 | 0 | 2 | 390000 | 2 | 390000 | 0 | 0 | 9 | 1755000 | 9 | 1755000 | 0 | 0 | 9 | 1755000 | 0 | 0
39 | 34 | SOTC039 | Stainless Steel Pre-fabricated Wall panels in TIRs & TIR Corridor | Sqm | 15010 | 202 | 12720.339 | 3032020 | 329.06 | 4939190.6 | 1907170.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 202 | 3032020 | 329.06 | 4939190.6 | 1907170.6 | 0 | 338.9318 | 5087366.318 | 2055346.318 | 0
40 | 35 | SOTC040 | Stainless Steel Pre-fabricated Ceiling panels in TIRs and TIR Corridor | Sqm | 15010 | 146 | 12720.339 | 2191460 | 174 | 2611740 | 420280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 146 | 2191460 | 174 | 2611740 | 420280 | 0 | 179.22 | 2690092.2 | 498632.2 | 0
41 | 202 | SOTC041 | Electro conductive Flooring inside TIRs | Sqm | 4035 | 146 | 3419.4915 | 589110 | 72.22 | 291407.7 | 0 | 297702.3 |  | 0 |  | 0 | 0 | 0 | 146 | 589110 | 72.22 | 291407.7 | 0 | 297702.3 | 73.6644 | 297235.854 | 0 | 291874.146
42 | 36 | SOTC042 | Flooring with Vinyl Sheets In TIR Corridor | Sqm | 3750 | 61 | 3177.9661 | 228750 | 127.58 | 478425 | 249675 | 0 |  | 0 |  | 0 | 0 | 0 | 61 | 228750 | 127.58 | 478425 | 249675 | 0 | 131.4074 | 492777.75 | 264027.75 | 0
43 | 37 | SOTC043 | Uni Directional Ceiling Laminar Airflow Systems | Nos | 395000 | 3 | 334745.7627 | 1185000 | 3 | 1185000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 3 | 1185000 | 3 | 1185000 | 0 | 0 | 3 | 1185000 | 0 | 0
44 | 38 | SOTC044 | Air Handling Units (AHUs) 11 TR | Nos | 1495000 | 2 | 1266949.1525 | 2990000 | 2 | 2990000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 2 | 2990000 | 2 | 2990000 | 0 | 0 | 2 | 2990000 | 0 | 0
45 | 39 | SOTC045 | Air Handling Units (AHUs) 8.5 TR | Nos | 1195000 | 1 | 1012711.8644 | 1195000 | 1 | 1195000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 1195000 | 1 | 1195000 | 0 | 0 | 1 | 1195000 | 0 | 0
46 | 40 | SOTC046 | Condensing Units | Nos | 345000 | 3 | 292372.8814 | 1035000 | 3 | 1035000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 3 | 1035000 | 3 | 1035000 | 0 | 0 | 3 | 1035000 | 0 | 0
47 | 41 | SOTC047 | Pressure Relief Dampers | Nos | 22500 | 3 | 19067.7966 | 67500 | 3 | 67500 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 3 | 67500 | 3 | 67500 | 0 | 0 | 3 | 67500 | 0 | 0
48 | 42 | SOTC049 | Hermetically Sealed Doors (1.80mt x 2.10 mt) | Nos | 525000 | 3 | 444915.2542 | 1575000 | 3 | 1575000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 3 | 1575000 | 3 | 1575000 | 0 | 0 | 3 | 1575000 | 0 | 0
49 | 43 | SOTC050 | 12mm thick glazed Glass partition walls in TIRs | Sqm | 650 | 40 | 550.8475 | 26000 | 40 | 26000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 40 | 26000 | 40 | 26000 | 0 | 0 | 40 | 26000 | 0 | 0
50 | 44 | SOTC051 | Wall mounted LED TV43 inchesFull HD | Nos | 165000 | 3 | 139830.5085 | 495000 | 3 | 495000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 3 | 495000 | 3 | 495000 | 0 | 0 | 3 | 495000 | 0 | 0
51 | 45 | SOTC052 | Ceiling/Wall mounted CCTV Room Camera | Nos | 12000 | 3 | 10169.4915 | 36000 | 3 | 36000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 3 | 36000 | 3 | 36000 | 0 | 0 | 3 | 36000 | 0 | 0
52 | 46 | SOTC053 | BED HEAD PANEL FOR TIR WITH DOUBLE OUTLETS AND ELECTRICAL OUTLETS | Nos | 49500 | 3 | 41949.1525 | 148500 | 6 | 297000 | 148500 | 0 |  | 0 |  | 0 | 0 | 0 | 3 | 148500 | 6 | 297000 | 148500 | 0 | 3 | 148500 | 0 | 0
5 | 47 | SOTC054 | X-RAY VIEWERS FOR ALL ICUS AND PRE OPP AREAS AND DOCTORS ROOMS | Nos | 37500 | 5 | 31779.661 | 187500 | 5 | 187500 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 5 | 187500 | 5 | 187500 | 0 | 0 | 6 | 225000 | 37500 | 0
54 | 48 | SOTC055 | WRITING BOARDS FOR ICUS, PRE OPP | Nos | 18750 | 5 | 15889.8305 | 93750 | 5 | 93750 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 5 | 93750 | 5 | 93750 | 0 | 0 | 6 | 112500 | 18750 | 0
55 | 49 | SOTC056 | CCTV CEILING CAMERA | Nos | 9500 | 10 | 8050.8475 | 95000 | 10 | 95000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 10 | 95000 | 10 | 95000 | 0 | 0 | 10 | 95000 | 0 | 0
56 | 50 | SOTC057 | Supply and Fixing of 25mm dia Conduit Pipes surface on wall. | Rmt | 110 | 10000 | 93.2203 | 1100000 | 10000 | 1100000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 10000 | 1100000 | 10000 | 1100000 | 0 | 0 | 10000 | 1100000 | 0 | 0
57 | 51 | SOTC058 | Supply and Fixing of 25mm dia Conduit Pipes Concealed on wall. | Rmt | 115 | 4000 | 97.4576 | 460000 | 4000 | 460000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 4000 | 460000 | 4000 | 460000 | 0 | 0 | 4000 | 460000 | 0 | 0
58 | 52 | SOTC059 | Wiring with run of 2 of 1.5 Sqmm Copper cable for points wiring. | Pts | 1525 | 570 | 1292.3729 | 869250 | 570 | 869250 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 570 | 869250 | 570 | 869250 | 0 | 0 | 570 | 869250 | 0 | 0
59 | 53 | SOTC060 | Wiring with run of 2 of 1.5 Sqmm Copper cable for stairecase points wiring. | Pts | 1100 | 10 | 932.2034 | 11000 | 10 | 11000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 10 | 11000 | 10 | 11000 | 0 | 0 | 10 | 11000 | 0 | 0
60 | 54 | SOTC061 | Supply and fixing of 6A/10A ISI Mark 3/2 pin Modular socket Common switch board | Pts | 900 | 25 | 762.7119 | 22500 | 25 | 22500 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 25 | 22500 | 25 | 22500 | 0 | 0 | 25 | 22500 | 0 | 0
61 | 55 | SOTC062 | Wiring with 3 of 1.5 sq.mm with 6A switch and 6A, 3/2 pin socket Modular type with 6A switch control fixing on separate board. | Pts | 2800 | 50 | 2372.8814 | 140000 | 50 | 140000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 50 | 140000 | 50 | 140000 | 0 | 0 | 50 | 140000 | 0 | 0
62 | 56 | SOTC063 | Supply and fixing of 6A switchs - 2 Nos and 6A 3/2 pin socket - 3 Nos Modular type with cover plate | Pts | 1400 | 200 | 1186.4407 | 280000 | 200 | 280000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 200 | 280000 | 200 | 280000 | 0 | 0 | 200 | 280000 | 0 | 0
63 | 203 | SOTC064 | Supply & fixing of 16A/6A, 2 in one socket with 16A switch control modular type | Nos | 900 | 200 | 762.7119 | 180000 | 200 | 180000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 200 | 180000 | 200 | 180000 | 0 | 0 | 200 | 180000 | 0 | 0
64 | 204 | SOTC065 | Supply & fixing of 32A, socket with switch control modular | Nos | 1600 | 18 | 1355.9322 | 28800 | 18 | 28800 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 18 | 28800 | 18 | 28800 | 0 | 0 | 18 | 28800 | 0 | 0
65 | 205 | SOTC066 | Supply & fixing of 64A, socket with 64A switch control modular type | Nos | 18000 | 4 | 15254.2373 | 72000 | 4 | 72000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 4 | 72000 | 4 | 72000 | 0 | 0 | 4 | 72000 | 0 | 0
66 | 57 | SOTC067 | Supply and Run of 1 of 1.5 sq.mm (phase, neutral and earth) FRLSH / HFFR PVC insulated 1100V grade as per IS:694/1990, IS 17048 specifications for Copper cable. | Rmt | 36 | 2000 | 30.5085 | 72000 | 2000 | 72000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 2000 | 72000 | 2000 | 72000 | 0 | 0 | 2000 | 72000 | 0 | 0
67 | 58 | SOTC068 | Supply and Run of 3 of 1.5 sq.mm (phase, neutral and earth) FRLSH / HFFR PVC insulated 1100V grade as per IS:694/1990, IS 17048 specifications for Copper cable . | Rmt | 100 | 2000 | 84.7458 | 200000 | 2000 | 200000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 2000 | 200000 | 2000 | 200000 | 0 | 0 | 2000 | 200000 | 0 | 0
68 | 59 | SOTC069 | Supply and Run of 3 of 2.5 sq.mm (phase, neutral and earth) FRLSH / HFFR PVC insulated 1100V grade as per IS:694/1990, IS 17048 specifications for Copper cable. | Rmt | 145 | 8000 | 122.8814 | 1160000 | 8000 | 1160000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 8000 | 1160000 | 8000 | 1160000 | 0 | 0 | 8000 | 1160000 | 0 | 0
69 | 60 | SOTC070 | Supply and Run of 3 runs of 4.0 sq mm (phase neutral and earth) FRLSH / HFFR PVC insulated 1100V grade as per IS:694/1990, IS 17048 specifications for Copper cable. | Rmt | 230 | 5000 | 194.9153 | 1150000 | 5000 | 1150000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 5000 | 1150000 | 5000 | 1150000 | 0 | 0 | 5000 | 1150000 | 0 | 0
70 | 61 | SOTC071 | Supply and Run of 3 of 6.0 Sq.mm FRLSH / HFFR PVC insulated 1100V grade as per IS:694/1990, IS 17048 specifications for Copper cable. | Rmt | 325 | 300 | 275.4237 | 97500 | 300 | 97500 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 300 | 97500 | 300 | 97500 | 0 | 0 | 300 | 97500 | 0 | 0
71 | 62 | SOTC072 | Supply and Run of 5 of 6.0 Sq.mm FRLSH / HFFR PVC insulated 1100V grade as per IS:694/1990, IS 17048 specifications for Copper cable. | Rmt | 545 | 300 | 461.8644 | 163500 | 300 | 163500 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 300 | 163500 | 300 | 163500 | 0 | 0 | 300 | 163500 | 0 | 0
72 | 63 | SOTC073 | Supply and Run of 5 of 10.0 Sq.mm FRLSH / HFFR PVC insulated 1100V grade as per IS:694/1990, IS 17048 specifications for Copper cable. | Rmt | 850 | 500 | 720.339 | 425000 | 500 | 425000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 500 | 425000 | 500 | 425000 | 0 | 0 | 500 | 425000 | 0 | 0
73 | 64 | SOTC074 | Supply and fixing of DP Metal Enclosure with IP 20 Protection DB Make with 1 No 20A, 10 KA DP MCB | Nos | 1800 | 8 | 1525.4237 | 14400 | 8 | 14400 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 8 | 14400 | 8 | 14400 | 0 | 0 | 8 | 14400 | 0 | 0
74 | 65 | SOTC075 | Supply and fixing of 4 Way TPN DB Horizontal with IP 43 Protection as per IS:13032 (For Lighting DBs) | Nos | 13000 | 10 | 11016.9492 | 130000 | 10 | 130000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 10 | 130000 | 10 | 130000 | 0 | 0 | 10 | 130000 | 0 | 0
75 | 230 | SOTC076 | Supply and fixing of 4 Way TPN DB Horizontal with IP 43 Protection as per IS:13032 (For Power DB's) | Nos | 13000 | 14 | 11016.9492 | 182000 | 14 | 182000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 14 | 182000 | 14 | 182000 | 0 | 0 | 14 | 182000 | 0 | 0
76 | 66 | SOTC077 | Supply and fixing of 8 Way VTPN DB with IP 43 Protection as per IS:13032 | Nos | 50000 | 5 | 42372.8814 | 250000 | 5 | 250000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 5 | 250000 | 5 | 250000 | 0 | 0 | 5 | 250000 | 0 | 0
77 | 67 | SOTC078 | Supply and fixing of cable adopteres box with cover for DBs including, massanory work etc., complete., | Nos | 6000 | 10 | 5084.7458 | 60000 | 10 | 60000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 10 | 60000 | 10 | 60000 | 0 | 0 | 10 | 60000 | 0 | 0
78 | 206 | SOTC079 | Providing independent earthing for Important equipment with 40mm dia 'B' class 2.5m long G.I pipe (GI Earthing) | Nos | 22500 | 18 | 19067.7966 | 405000 | 18 | 405000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 18 | 405000 | 18 | 405000 | 0 | 0 | 18 | 405000 | 0 | 0
79 | 68 | SOTC080 | Providing independent earthing by exacavating a pit to a depth of 2.25Mtr in all soils as per size specified in the data for Sophisticated Electronic equipment (Copper Earthing) | Nos | 54000 | 18 | 45762.7119 | 972000 | 18 | 972000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 18 | 972000 | 18 | 972000 | 0 | 0 | 18 | 972000 | 0 | 0
80 | 69 | SOTC081 | Providing independent earthing for Important equipment with 100mm dia Heavy gauge C.I Earthing | Nos | 25000 | 6 | 21186.4407 | 150000 | 6 | 150000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 6 | 150000 | 6 | 150000 | 0 | 0 | 6 | 150000 | 0 | 0
81 | 70 | SOTC082 | Supply and Run of 50mm x 6mm G.I Strip | Rmt | 450 | 400 | 381.3559 | 180000 | 400 | 180000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 400 | 180000 | 400 | 180000 | 0 | 0 | 400 | 180000 | 0 | 0
82 | 71 | SOTC083 | Supply and Run of 25mm x 3mm copper strip | Rmt | 300 | 400 | 254.2373 | 120000 | 400 | 120000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 400 | 120000 | 400 | 120000 | 0 | 0 | 400 | 120000 | 0 | 0
83 | 207 | SOTC084 | Supply, transportation and fixing of 22W +/ 10% , >/ 2300 lumens, 1200mm length LED light | Nos | 4800 | 20 | 4067.7966 | 96000 | 20 | 96000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 20 | 96000 | 20 | 96000 | 0 | 0 | 20 | 96000 | 0 | 0
84 | 208 | SOTC085 | Supply, transportation and fixing 32-36W (>=3600 Lumens), 2' x2' (600mm x 600mm) slim panel LED luminaire | Nos | 4000 | 60 | 3389.8305 | 240000 | 60 | 240000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 60 | 240000 | 60 | 240000 | 0 | 0 | 60 | 240000 | 0 | 0
85 | 209 | SOTC086 | Supply, transportation and fixing 12 W +/-10% (>= 1200 Lumens) Down lighter back lit LED Down Light Recessed / Surface | Nos | 1400 | 215 | 1186.4407 | 301000 | 215 | 301000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 215 | 301000 | 215 | 301000 | 0 | 0 | 215 | 301000 | 0 | 0
86 | 210 | SOTC087 | Supply, transportation and fixing 18 W +/-10% (>= 1800 Lumens) Down lighter back lit LED Down Light | Nos | 1800 | 95 | 1525.4237 | 171000 | 95 | 171000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 95 | 171000 | 95 | 171000 | 0 | 0 | 95 | 171000 | 0 | 0
87 | 72 | SOTC088 | Supply, transportation and fixing ISI mark batten holder / slanting holder | Nos | 160 | 8 | 135.5932 | 1280 | 8 | 1280 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 8 | 1280 | 8 | 1280 | 0 | 0 | 8 | 1280 | 0 | 0
88 | 231 | SOTC089 | Supply, Transportation of energy efficient fan, 1200 mm sweep, aluminium body, consuming 28 W, BEE 5 star rated, ceiling fan | Nos | 3700 | 40 | 3135.5932 | 148000 | 40 | 148000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 40 | 148000 | 40 | 148000 | 0 | 0 | 40 | 148000 | 0 | 0
89 | 73 | SOTC090 | Supply and fixing of Modular type Stepped electronic regulator. | Nos | 1000 | 40 | 847.4576 | 40000 | 40 | 40000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 40 | 40000 | 40 | 40000 | 0 | 0 | 40 | 40000 | 0 | 0
90 | 74 | SOTC091 | Labour charges for fixing of ceiling fan and regulator | Nos | 210 | 40 | 177.9661 | 8400 | 40 | 8400 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 40 | 8400 | 40 | 8400 | 0 | 0 | 40 | 8400 | 0 | 0
91 | 75 | SOTC092 | Supply and erecting 19/20mm steel tube down rod of one meter length | Nos | 600 | 40 | 508.4746 | 24000 | 40 | 24000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 40 | 24000 | 40 | 24000 | 0 | 0 | 40 | 24000 | 0 | 0
92 | 211 | SOTC093 | Supply of 12" (300mm) Light duty exhaust fan | Nos | 3000 | 5 | 2542.3729 | 15000 | 5 | 15000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 5 | 15000 | 5 | 15000 | 0 | 0 | 5 | 15000 | 0 | 0
93 | 212 | SOTC094 | Supply,Transportation of 12" (300mm) ISI, 900 RPM Heavy duty exhaust fan | Nos | 4900 | 10 | 4152.5424 | 49000 | 10 | 49000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 10 | 49000 | 10 | 49000 | 0 | 0 | 10 | 49000 | 0 | 0
94 | 76 | SOTC095 | Labour charges for fixing the exhaust fan in wall with necessary connections | Nos | 900 | 15 | 762.7119 | 13500 | 15 | 13500 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 15 | 13500 | 15 | 13500 | 0 | 0 | 15 | 13500 | 0 | 0
95 | 77 | SOTC096 | Supply and fixing of GI louver shutter including GI mesh | Nos | 3200 | 15 | 2711.8644 | 48000 | 15 | 48000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 15 | 48000 | 15 | 48000 | 0 | 0 | 15 | 48000 | 0 | 0
96 | 213 | SOTC097 | Main Power Panel with 1000A 4 Pole ACB as incomer - 1 No and out goings 800 A 4P MCCB - 1 No., 630 A 4P MCCB - 1 No., 400A 4P MCCB - 4 Nos & 250A 4P MCCB - 3 No's with required Digital Ammeter and Voltmer, LED Indicators | Nos | 1315000 | 1 | 1114406.7797 | 1315000 | 1 | 1315000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 1315000 | 1 | 1315000 | 0 | 0 | 1 | 1315000 | 0 | 0
97 | 214 | SOTC098 | Floor Power Panel : Incomer: 630A 4 Pole MCCB,- 1 No Outgoings 250 A 4P MCCB - 4 No's 125 A 4P MCCB - 10 No's, 63 A 4P MCCB - 4 No's with required Digital Ammeter and Voltmer, LED Indicators | Nos | 875000 | 1 | 741525.4237 | 875000 | 1 | 875000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 875000 | 1 | 875000 | 0 | 0 | 1 | 875000 | 0 | 0
98 | 215 | SOTC099 | Electrical Lighting Panels : Incomer: 250 A 4 Pole MCCB - 1 No, Out Goings 125 A 4P MCCB - 4 No's 63 A 4P MCCB - 3 No's with required Digital Ammeter and Voltmer, LED Indicators | Nos | 370000 | 2 | 313559.322 | 740000 | 2 | 740000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 2 | 740000 | 2 | 740000 | 0 | 0 | 2 | 740000 | 0 | 0
99 | 78 | SOTC100 | 130KVAR Out Door Capacitor panel : Incomer: 250A FP MCCB - 1 No, 63A 10KA TP MCB - 9 Nos. 20 KVAR Capacitor Duty contactors - 5 Nos., 10 KVAR Capacitor Duty contactors - 2 Nos, .5 KVAR Capacitor Duty contactors - 2 Nos. 12 stage APFC Relay - 1 No | Nos | 450000 | 1 | 381355.9322 | 450000 | 1 | 450000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 450000 | 1 | 450000 | 0 | 0 | 1 | 450000 | 0 | 0
100 | 232 | SOTC101 | 630 KVA Transformer OLTC for transformers with RTCC: Supply, Transportation, Installation, Testing and Commissioning of 630 KVA TRANSFORMER with all test reports. The Transformer shall be designed and manufactured as per IS:1180 OLTC with level-II with initial filling of oil as per IS 335-1993. 1000 A LT Breaker Kiosk - 01 No.The basic details of the Transformer are as under. Makes: Kirloskar / PETE / Esennar / Voltamp / Crompton / ABB / Schneider. | Nos | 4000000 | 1 | 3389830.5085 | 4000000 | 0 | 0 | 0 | 4000000 |  | 0 |  | 0 | 0 | 0 | 1 | 4000000 | 0 | 0 | 0 | 4000000 | 0 | 0 | 0 | 4000000
101 | 79 | SOTC102 | Supply of 25 Sqmm 3.5 Core XLPE insulated UG Cable. | Rmt | 300 | 200 | 254.2373 | 60000 | 200 | 60000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 200 | 60000 | 200 | 60000 | 0 | 0 | 200 | 60000 | 0 | 0
102 | 80 | SOTC103 | Supply of 50 Sqmm 3.5 Core XLPE insulated UG Cable. | Rmt | 560 | 200 | 474.5763 | 112000 | 200 | 112000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 200 | 112000 | 200 | 112000 | 0 | 0 | 200 | 112000 | 0 | 0
103 | 81 | SOTC104 | Supply of 70 Sqmm 3.5 Core XLPE insulated UG Cable. | Rmt | 750 | 75 | 635.5932 | 56250 | 75 | 56250 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 75 | 56250 | 75 | 56250 | 0 | 0 | 75 | 56250 | 0 | 0
104 | 82 | SOTC105 | Supply of 120 Sqmm 3.5 Core XLPE insulated UG Cable. | Rmt | 1050 | 50 | 889.8305 | 52500 | 50 | 52500 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 50 | 52500 | 50 | 52500 | 0 | 0 | 50 | 52500 | 0 | 0
105 | 83 | SOTC106 | Supply of 185 Sqmm 3.5 Core XLPE insulated UG Cable. | Rmt | 1500 | 50 | 1271.1864 | 75000 | 50 | 75000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 50 | 75000 | 50 | 75000 | 0 | 0 | 50 | 75000 | 0 | 0
106 | 84 | SOTC107 | Supply of 240 Sqmm 3.5 Core XLPE insulated UG Cable. | Rmt | 1900 | 100 | 1610.1695 | 190000 | 100 | 190000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 100 | 190000 | 100 | 190000 | 0 | 0 | 100 | 190000 | 0 | 0
107 | 85 | SOTC108 | Supply of 300 Sqmm 3.5 Core XLPE insulated UG Cable. | Rmt | 2400 | 500 | 2033.8983 | 1200000 | 500 | 1200000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 500 | 1200000 | 500 | 1200000 | 0 | 0 | 500 | 1200000 | 0 | 0
108 | 86 | SOTC109 | Termination of UG cables of 3.5 core 25 Sq.mm | Nos | 850 | 8 | 720.339 | 6800 | 8 | 6800 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 8 | 6800 | 8 | 6800 | 0 | 0 | 8 | 6800 | 0 | 0
109 | 87 | SOTC110 | Termination of UG cables of 3.5 core 50 Sq.mm | Nos | 1200 | 8 | 1016.9492 | 9600 | 8 | 9600 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 8 | 9600 | 8 | 9600 | 0 | 0 | 8 | 9600 | 0 | 0
110 | 88 | SOTC111 | Termination of UG cables of 3.5 core 70 Sq.mm | Nos | 1500 | 8 | 1271.1864 | 12000 | 8 | 12000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 8 | 12000 | 8 | 12000 | 0 | 0 | 8 | 12000 | 0 | 0
111 | 89 | SOTC112 | Termination of UG cables of 3.5 core 120 Sq.mm | Nos | 1900 | 4 | 1610.1695 | 7600 | 4 | 7600 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 4 | 7600 | 4 | 7600 | 0 | 0 | 4 | 7600 | 0 | 0
112 | 90 | SOTC113 | Termination of UG cables of 3.5 core 185 Sq.mm | Nos | 2500 | 4 | 2118.6441 | 10000 | 4 | 10000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 4 | 10000 | 4 | 10000 | 0 | 0 | 4 | 10000 | 0 | 0
113 | 91 | SOTC114 | Termination of UG cables of 3.5 core 240 Sq.mm | Nos | 3500 | 4 | 2966.1017 | 14000 | 4 | 14000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 4 | 14000 | 4 | 14000 | 0 | 0 | 4 | 14000 | 0 | 0
114 | 92 | SOTC115 | Termination of UG cables of 3.5 core 300 Sq.mm | Nos | 4000 | 12 | 3389.8305 | 48000 | 12 | 48000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 12 | 48000 | 12 | 48000 | 0 | 0 | 12 | 48000 | 0 | 0
115 | 93 | SOTC116 | Earth work excavation of Trench laying of U.G cables up to 70 sqmm | Rmt | 1100 | 100 | 932.2034 | 110000 | 100 | 110000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 100 | 110000 | 100 | 110000 | 0 | 0 | 100 | 110000 | 0 | 0
116 | 94 | SOTC117 | Earth work excavation of Trench laying of U.G cables from 95 Sqmm | Rmt | 1150 | 100 | 974.5763 | 115000 | 100 | 115000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 100 | 115000 | 100 | 115000 | 0 | 0 | 100 | 115000 | 0 | 0
117 | 95 | SOTC118 | Laying of PVC armoured under ground cable up to 95 Sqmm on wall | Rmt | 125 | 200 | 105.9322 | 25000 | 200 | 25000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 200 | 25000 | 200 | 25000 | 0 | 0 | 200 | 25000 | 0 | 0
118 | 96 | SOTC119 | Laying of PVC armoured under ground cable from 120 Sq.mm to 400 Sqmm saddles on wall | Rmt | 270 | 700 | 228.8136 | 189000 | 700 | 189000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 700 | 189000 | 700 | 189000 | 0 | 0 | 700 | 189000 | 0 | 0
119 | 97 | SOTC120 | Supply, Transportation and Installation of 150mm x 50mm x 2mm thick hot dip GI perforated cable tray | Rmt | 1295 | 200 | 1097.4576 | 259000 | 200 | 259000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 200 | 259000 | 200 | 259000 | 0 | 0 | 200 | 259000 | 0 | 0
120 | 98 | SOTC121 | Supply, Transportation and Installation of 300mm x 50mm x 2mm thick thick hot dip GI perforated cable tray | Rmt | 4500 | 100 | 3813.5593 | 450000 | 100 | 450000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 100 | 450000 | 100 | 450000 | 0 | 0 | 100 | 450000 | 0 | 0
121 | 99 | SOTC122 | Supply, Transportation and installation of 10KVA / 312V DC on line UPS system | Nos | 400000 | 7 | 338983.0508 | 2800000 | 11 | 4400000 | 1600000 | 0 | 2 | 800000 | 2 | 800000 | 0 | 0 | 9 | 3600000 | 13 | 5200000 | 1600000 | 0 | 10 | 4000000 | 400000 | 0
122 | 100 | SOTC123 | Supply and fixing of 12V, 150 AH MF battery | Nos | 25000 | 182 | 21186.4407 | 4550000 | 286 | 7150000 | 2600000 | 0 | 52 | 1300000 | 52 | 1300000 | 0 | 0 | 234 | 5850000 | 338 | 8450000 | 2600000 | 0 | 384 | 9600000 | 3750000 | 0
123 | 101 | SOTC124 | Supply and providing of UPS cum battery rack 20 batteries | Nos | 30000 | 7 | 25423.7288 | 210000 | 11 | 330000 | 120000 | 0 | 2 | 60000 | 2 | 60000 | 0 | 0 | 9 | 270000 | 13 | 390000 | 120000 | 0 | 12 | 360000 | 90000 | 0
124 | 102 | SOTC125 | Supply, Transportation, Installation, Testing and commissioning of storage / Pressure type 5 Star rated water heater with ABS plastic body of 15 Ltrs | Nos | 16000 | 7 | 13559.322 | 112000 | 12 | 192000 | 80000 | 0 |  | 0 |  | 0 | 0 | 0 | 7 | 112000 | 11 | 176000 | 64000 | 0 | 11 | 176000 | 64000 | 0
125 | 103 | SOTC126 | 26 persons ICU bed cum passenger lift (1768 Kgs) G+8 Floors, 9 stops,9 Openings (Cost Includes amount for Construction of Shaft / Cladding from Ground to 8th Floor) | Nos | 10495000 | 1 | 8894067.7966 | 10495000 | 1 | 10495000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 10495000 | 1 | 10495000 | 0 | 0 | 1 | 10495000 | 0 | 0
126 | 104 | SOTC127 | 1.50 TR with , 18000 BTU/Hr High Wall mount Split Air Conditioners | Nos | 150000 | 6 | 127118.6441 | 900000 | 6 | 900000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 6 | 900000 | 6 | 900000 | 0 | 0 | 7 | 1050000 | 150000 | 0
127 | 105 | SOTC128 | 2.0 TR with , 24000 BTU/Hr High Wall mount Split Air Conditioners | Nos | 210000 | 2 | 177966.1017 | 420000 | 6 | 1260000 | 840000 | 0 |  | 0 |  | 0 | 0 | 0 | 2 | 420000 | 6 | 1260000 | 840000 | 0 | 6 | 1260000 | 840000 | 0
128 | 106 | SOTC129 | Voltage stabilizer for 4 KVA maximum load | Nos | 7000 | 6 | 5932.2034 | 42000 | 6 | 42000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 6 | 42000 | 6 | 42000 | 0 | 0 | 7 | 49000 | 7000 | 0
129 | 107 | SOTC130 | Voltage stabilizer for 5 KVA maximum load | Nos | 8500 | 2 | 7203.3898 | 17000 | 6 | 51000 | 34000 | 0 |  | 0 |  | 0 | 0 | 0 | 2 | 17000 | 6 | 51000 | 34000 | 0 | 6 | 51000 | 34000 | 0
130 | 216 | SOTC131 | Ductable Air Conditioners 11.0 TR with ISEER ≥ 4 | Nos | 1200000 | 1 | 1016949.1525 | 1200000 | 1 | 1200000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 1200000 | 1 | 1200000 | 0 | 0 | 1 | 1200000 | 0 | 0
131 | 217 | SOTC132 | Ductable Air Conditioners 8.5 TR with ISEER ≥ 4 | Nos | 1000000 | 2 | 847457.6271 | 2000000 | 2 | 2000000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 2 | 2000000 | 2 | 2000000 | 0 | 0 | 4 | 4000000 | 2000000 | 0
132 | 218 | SOTC133 | Ductable Air Conditioners 5.5 TR with ISEER ≥ 4 | Nos | 900000 | 1 | 762711.8644 | 900000 | 3 | 2700000 | 1800000 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 900000 | 3 | 2700000 | 1800000 | 0 | 3 | 2700000 | 1800000 | 0
133 | 108 | SOTC134 | Automatic Smoke Detection System | Job | 1425000 | 1 | 1207627.1186 | 1425000 | 1 | 1425000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 1425000 | 1 | 1425000 | 0 | 0 | 1 | 1425000 | 0 | 0
134 | 109 | SOTC135 | Automatic Fire Alarm System | Job | 1400000 | 1 | 1186440.678 | 1400000 | 1 | 1400000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 1400000 | 1 | 1400000 | 0 | 0 | 1 | 1400000 | 0 | 0
135 | 219 | SOTC136 | Supply & Fixing of 4.5Kg, CO2 Type Fire Extinguisher. | Nos | 27000 | 6 | 22881.3559 | 162000 | 6 | 162000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 6 | 162000 | 6 | 162000 | 0 | 0 | 6 | 162000 | 0 | 0
136 | 110 | SOTC137 | Supply and fixing of ABC stored pressure squeeze grip type fire extinguishers, 9 kg capacity. | Nos | 16000 | 6 | 13559.322 | 96000 | 6 | 96000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 6 | 96000 | 6 | 96000 | 0 | 0 | 6 | 96000 | 0 | 0
137 | 111 | SOTC138 | Supply and fixing of ABC Powder MAP 4 Kg Fire extinguisher | Nos | 11000 | 10 | 9322.0339 | 110000 | 10 | 110000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 10 | 110000 | 10 | 110000 | 0 | 0 | 10 | 110000 | 0 | 0
138 | 112 | SOTC139 | Supply and fixing of 2 Kg Fire extinguisher Clean Agent | Nos | 22500 | 10 | 19067.7966 | 225000 | 10 | 225000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 10 | 225000 | 10 | 225000 | 0 | 0 | 10 | 225000 | 0 | 0
139 | 113 | SOTC140 | Supply and fixing of Escape signage boards in Rigid Photo luminescent based glow | Nos | 2000 | 150 | 1694.9153 | 300000 | 150 | 300000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 150 | 300000 | 150 | 300000 | 0 | 0 | 150 | 300000 | 0 | 0
140 | 220 | SOTC141 | Supply & Fixing of Powder Coated Fire Rated doors. | Sqm | 29000 | 6 | 24576.2712 | 174000 | 3 | 87000 | 0 | 87000 |  | 0 |  | 0 | 0 | 0 | 6 | 174000 | 3 | 87000 | 0 | 87000 | 13.8 | 400200 | 226200 | 0
141 | 221 | SOTC142 | Telephone & EPABX System | Job | 1000000 | 1 | 847457.6271 | 1000000 | 1 | 1000000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 1000000 | 1 | 1000000 | 0 | 0 | 1 | 1000000 | 0 | 0
142 | 114 | SOTC143 | Local Area Network (LAN) System | Job | 1250000 | 1 | 1059322.0339 | 1250000 | 1 | 1250000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 1250000 | 1 | 1250000 | 0 | 0 | 1 | 1250000 | 0 | 0
143 | 115 | SOTC144 | Biometric Access Control System | Nos | 300000 | 2 | 254237.2881 | 600000 | 3 | 900000 | 300000 | 0 |  | 0 |  | 0 | 0 | 0 | 2 | 600000 | 3 | 900000 | 300000 | 0 | 3 | 900000 | 300000 | 0
144 | 116 | SOTC145 | Dismantling, clearing away and carefully stacking useful materials for re-use and disposal of unserviceable materials with 100m lead as directed by Engineer-in-Charge duly taking actual premeasurements before dismantling including all charges complete (Reinforced cement concrete) | Cum | 5400 | 10 | 4576.2712 | 54000 | 5.95 | 32130 | 0 | 21870 |  | 0 |  | 0 | 0 | 0 | 10 | 54000 | 5.95 | 32130 | 0 | 21870 | 10 | 54000 | 0 | 0
145 | 117 | SOTC146 | Dismantling, clearing away and carefully stacking useful materials for re-use and disposal of unserviceable materials with 100m lead as directed by Engineer-in-Charge duly taking actual premeasurements before dismantling including all charges complete (Unreinforced cement concrete) | Cum | 4500 | 1.5 | 3813.5593 | 6750 | 49.43 | 222435 | 215685 | 0 |  | 0 |  | 0 | 0 | 0 | 1.5 | 6750 | 49.43 | 222435 | 215685 | 0 | 51.9015 | 233556.75 | 226806.75 | 0
146 | 118 | SOTC147 | Dismantling, clearing away and carefully stacking useful materials for re-use and disposal of unserviceable materials with 100m lead as directed by Engineer-in-Charge duly taking actual premeasurements before dismantling including all charges complete (Brick Masonary) | Cum | 900 | 118 | 762.7119 | 106200 | 145.42 | 130878 | 24678 | 0 |  | 0 |  | 0 | 0 | 0 | 118 | 106200 | 145.42 | 130878 | 24678 | 0 | 152.691 | 137421.9 | 31221.9 | 0
147 | 119 | SOTC148 | Dismantling, clearing away and carefully stacking useful materials for re-use and disposal of unserviceable materials with 100m lead as directed by Engineer-in-Charge duly taking actual premeasurements before dismantling including all charges complete (Kadapa slabs or shahabad stone slabs on sand bed) | Sqm | 630 | 25 | 533.8983 | 15750 | 659.93 | 415755.9 | 400005.9 | 0 |  | 0 |  | 0 | 0 | 0 | 25 | 15750 | 659.93 | 415755.9 | 400005.9 | 0 | 692.9265 | 436543.695 | 420793.695 | 0
148 | 120 | SOTC149 | Dismantling doors, windows and clear storey windows, Ventilators etc., (wood or steel) shutters including Chowkhats, architraves,hold fasts and other attachments etc., and stacking them within 100m lead including charge etc., complete for finished item of work. (Not exceeding 3 sqm in area) | Nos | 1800 | 57 | 1525.4237 | 102600 | 203 | 365400 | 262800 | 0 |  | 0 |  | 0 | 0 | 0 | 57 | 102600 | 203 | 365400 | 262800 | 0 | 203 | 365400 | 262800 | 0
149 | 121 | SOTC150 | Conveyance of un-useful excavated earth to a distance of 16 KM for disposal including hire charges of T and P, labour charges etc., complete for finished item of work. | Cum | 900 | 250 | 762.7119 | 225000 | 299.78 | 269802 | 44802 | 0 |  | 0 |  | 0 | 0 | 0 | 250 | 225000 | 299.78 | 269802 | 44802 | 0 | 314.769 | 283292.1 | 58292.1 | 0
150 | 122 | SOTC151 | RCC M 25 grade design mix (For lintels) | Cum | 18900 | 3 | 16016.9492 | 56700 | 3.02 | 57078 | 378 | 0 |  | 0 |  | 0 | 0 | 0 | 3 | 56700 | 3.02 | 57078 | 378 | 0 | 3.171 | 59931.9 | 3231.9 | 0
151 | 123 | SOTC152 | RCC M 20 grade design mix (50mm thick platforms) | Sqm | 1170 | 12 | 991.5254 | 14040 | 0 | 0 | 0 | 14040 |  | 0 |  | 0 | 0 | 0 | 12 | 14040 | 0 | 0 | 0 | 14040 | 0 | 0 | 0 | 14040
152 | 124 | SOTC153 | RCC M 20 grade design mix (25 mm thick Shelves) | Sqm | 900 | 12 | 762.7119 | 10800 | 0 | 0 | 0 | 10800 |  | 0 |  | 0 | 0 | 0 | 12 | 10800 | 0 | 0 | 0 | 10800 | 0 | 0 | 0 | 10800
153 | 125 | SOTC154 | Brick Masonry work in CM (1:6) prop in superstructure | Cum | 15300 | 3 | 12966.1017 | 45900 | 106.62 | 1631286 | 1585386 | 0 |  | 0 |  | 0 | 0 | 0 | 3 | 45900 | 106.62 | 1631286 | 1585386 | 0 | 111.951 | 1712850.3 | 1666950.3 | 0
154 | 126 | SOTC155 | Reinforced Masonry for partition walls (100 mm thick) in CM (1:4) | Sqm | 2700 | 500 | 2288.1356 | 1350000 | 385.65 | 1041255 | 0 | 308745 |  | 0 |  | 0 | 0 | 0 | 500 | 1350000 | 385.65 | 1041255 | 0 | 308745 | 404.9325 | 1093317.75 | 0 | 256682.25
155 | 127 | SOTC156 | PCC (1:3:6) nominal mix using 20mm size graded m/c (For bed blocks and hold fasts) (OTs screed) | Cum | 9000 | 1.5 | 7627.1186 | 13500 | 0 | 0 | 0 | 13500 |  | 0 |  | 0 | 0 | 0 | 1.5 | 13500 | 0 | 0 | 0 | 13500 | 0 | 0 | 0 | 13500
156 | 128 | SOTC157 | Filling with light weight concrete in Cement Concrete (1:5:10) proportion using brick jelly for low roofs | Cum | 7200 | 23 | 6101.6949 | 165600 | 16.062 | 115646.4 | 0 | 49953.6 |  | 0 |  | 0 | 0 | 0 | 23 | 165600 | 16.062 | 115646.4 | 0 | 49953.6 | 16.8651 | 121428.72 | 0 | 44171.28
157 | 129 | SOTC158 | Thermo Mechanically Treated (Fe -500/500D/550D) for RCC works | MT | 126000 | 1.25 | 106779.661 | 157500 | 0.732 | 92232 | 0 | 65268 |  | 0 |  | 0 | 0 | 0 | 1.25 | 157500 | 0.732 | 92232 | 0 | 65268 | 0.7686 | 96843.6 | 0 | 60656.4
158 | 130 | SOTC159 | Plastering 12mm thick in two coats with base coat of 8mm thick in CM (1:6) and top coat of 4mm thick in CM (1:4). for Internal walls. | Sqm | 1224 | 1600 | 1037.2881 | 1958400 | 2046.48 | 2504891.52 | 546491.52 | 0 |  | 0 |  | 0 | 0 | 0 | 1600 | 1958400 | 2046.48 | 2504891.52 | 546491.52 | 0 | 2148.804 | 2630136.096 | 671736.096 | 0
159 | 131 | SOTC160 | Impervious coat to exposed RCC roof slab surfaces (APSS No. 901 and 903) For Toilets | Sqm | 360 | 77.78 | 305.0847 | 28000.8 | 41 | 14760 | 0 | 13240.8 |  | 0 |  | 0 | 0 | 0 | 77.78 | 28000.8 | 41 | 14760 | 0 | 13240.8 | 43.05 | 15498 | 0 | 12502.8
160 | 222 | SOTC161 | Providing and applying Wall putty of White Cement or Polymer or Cement based of average 1 to 2 mm thickness over plastered surface to prepare the surface even and smooth after thoroughly brushing the surface to remove all dirt and remains of loose powdered materials, applying emery paper, Sand the surface, clean & wipe off loose dust, applying knifing paste filler by putty knife / muslin pad, air dry for 2 - 3 | Sqm | 270 | 4447 | 228.8136 | 1200690 | 1725.27 | 465822.9 | 0 | 734867.1 |  | 0 |  | 0 | 0 | 0 | 4447 | 1200690 | 1725.27 | 465822.9 | 0 | 734867.1 | 1811.5335 | 489114.045 | 0 | 711575.955
161 | 132 | SOTC162 | Flooring with non-skid full body ceramic floor tiles | Sqm | 1710 | 85 | 1449.1525 | 145350 | 93.41 | 159731.1 | 14381.1 | 0 |  | 0 |  | 0 | 0 | 0 | 85 | 145350 | 93.41 | 159731.1 | 14381.1 | 0 | 98.0805 | 167717.655 | 22367.655 | 0
162 | 133 | SOTC163 | Dadooing to walls with glazed full body Porcelain wall tiles | Sqm | 1440 | 225 | 1220.339 | 324000 | 372.89 | 536961.6 | 212961.6 | 0 |  | 0 |  | 0 | 0 | 0 | 225 | 324000 | 372.89 | 536961.6 | 212961.6 | 0 | 391.5345 | 563809.68 | 239809.68 | 0
163 | 134 | SOTC164 | Dadooing to walls with glazed full body Ceramic tiles | Sqm | 1440 | 350 | 1220.339 | 504000 | 257.35 | 370584 | 0 | 133416 |  | 0 |  | 0 | 0 | 0 | 350 | 504000 | 257.35 | 370584 | 0 | 133416 | 270.2175 | 389113.2 | 0 | 114886.8
164 | 135 | SOTC165 | Painting one coat water based cement primer of interior grade I and two coats of acrylic emulsion paint for ceiling and Walls | Sqm | 360 | 4447 | 305.0847 | 1600920 | 1306.68 | 470404.8 | 0 | 1130515.2 |  | 0 |  | 0 | 0 | 0 | 4447 | 1600920 | 1306.68 | 470404.8 | 0 | 1130515.2 | 1372.014 | 493925.04 | 0 | 1106994.96
165 | 136 | SOTC166 | Painting to new wood work | Sqm | 360 | 313 | 305.0847 | 112680 | 60 | 21600 | 0 | 91080 |  | 0 |  | 0 | 0 | 0 | 313 | 112680 | 60 | 21600 | 0 | 91080 | 75 | 27000 | 0 | 85680
166 | 137 | SOTC167 | Painting to new iron work | Sqm | 270 | 88 | 228.8136 | 23760 | 120.4 | 32508 | 8748 | 0 |  | 0 |  | 0 | 0 | 0 | 88 | 23760 | 120.4 | 32508 | 8748 | 0 | 126.42 | 34133.4 | 10373.4 | 0
167 | 138 | SOTC168 | Two shutter cupboards | Sqm | 9000 | 100 | 7627.1186 | 900000 | 0 | 0 | 0 | 900000 |  | 0 |  | 0 | 0 | 0 | 100 | 900000 | 0 | 0 | 0 | 900000 | 0 | 0 | 0 | 900000
168 | 139 | SOTC169 | UPVC Fixed Louvered Ventilator | Sqm | 12000 | 7 | 10169.4915 | 84000 | 15.73 | 188760 | 104760 | 0 |  | 0 |  | 0 | 0 | 0 | 7 | 84000 | 15.73 | 188760 | 104760 | 0 | 16.5165 | 198198 | 114198 | 0
169 | 140 | SOTC170 | UPVC 3 track Sliding Windows | Sqm | 9000 | 15 | 7627.1186 | 135000 | 43.12 | 388080 | 253080 | 0 |  | 0 |  | 0 | 0 | 0 | 15 | 135000 | 43.12 | 388080 | 253080 | 0 | 45.276 | 407484 | 272484 | 0
170 | 141 | SOTC171 | MS Grills to Windows | Sqm | 1800 | 150 | 1525.4237 | 270000 | 120.4 | 216720 | 0 | 53280 |  | 0 |  | 0 | 0 | 0 | 150 | 270000 | 120.4 | 216720 | 0 | 53280 | 126.42 | 227556 | 0 | 42444
171 | 142 | SOTC172 | Flooring with 16 to 18 mm thick high polished granite stone slabs black colour for platforms (S.S.701 and special) | Sqm | 6300 | 50 | 5338.9831 | 315000 | 402.07 | 2533041 | 2218041 | 0 |  | 0 |  | 0 | 0 | 0 | 50 | 315000 | 402.07 | 2533041 | 2218041 | 0 | 422.1735 | 2659693.05 | 2344693.05 | 0
172 | 143 | SOTC173 | Doors as per approved drawings with medium teak wood frame (1500mm x 2600mm) | Sqm | 6300 | 50 | 5338.9831 | 315000 | 14.16 | 89208 | 0 | 225792 |  | 0 |  | 0 | 0 | 0 | 50 | 315000 | 14.16 | 89208 | 0 | 225792 | 15.4 | 97020 | 0 | 217980
173 | 144 | SOTC174 | Doors as per approved drawings with medium teak wood frame (1000mm x 2100mm) | Sqm | 7400 | 45 | 6271.1864 | 333000 | 8.98 | 66452 | 0 | 266548 |  | 0 |  | 0 | 0 | 0 | 45 | 333000 | 8.98 | 66452 | 0 | 266548 | 17.2 | 127280 | 0 | 205720
174 | 145 | SOTC175 | Doors Shutters WPC(800mm x 2100mm) | Sqm | 5400 | 40 | 4576.2712 | 216000 | 31.79 | 171666 | 0 | 44334 |  | 0 |  | 0 | 0 | 0 | 40 | 216000 | 31.79 | 171666 | 0 | 44334 | 33.3795 | 180249.3 | 0 | 35750.7
175 | 146 | SOTC176 | Scientific Doors with metal door frames and door shutters made of galvanize steel | Sqm | 18000 | 45 | 15254.2373 | 810000 | 78.72 | 1416960 | 606960 | 0 |  | 0 |  | 0 | 0 | 0 | 45 | 810000 | 78.72 | 1416960 | 606960 | 0 | 77.65 | 1397700 | 587700 | 0
176 | 147 | SOTC177 | False ceiling as per Technical specification | Sqm | 1800 | 1400 | 1525.4237 | 2520000 | 825.4 | 1485720 | 0 | 1034280 |  | 0 |  | 0 | 0 | 0 | 1400 | 2520000 | 825.4 | 1485720 | 0 | 1034280 | 866.67 | 1560006 | 0 | 959994
177 | 148 | SOTC178 | Vinyl flooring | Sqm | 3000 | 500 | 2542.3729 | 1500000 | 691 | 2073000 | 573000 | 0 |  | 0 |  | 0 | 0 | 0 | 500 | 1500000 | 691 | 2073000 | 573000 | 0 | 725.55 | 2176650 | 676650 | 0
178 | 149 | SOTC179 | Impervious coat to exposed RCC roof slab surfacesof 20mm thick (APSS No. 901 and 903) | Sqm | 1260 | 350 | 1067.7966 | 441000 | 0 | 0 | 0 | 441000 |  | 0 |  | 0 | 0 | 0 | 350 | 441000 | 0 | 0 | 0 | 441000 | 0 | 0 | 0 | 441000
179 | 233 | SOTC180 | Fixed Glass Window – 1200 x 1200 | Sqm | 5400 | 53.55 | 4576.2712 | 289170 | 60.51 | 326754 | 37584 | 0 |  | 0 |  | 0 | 0 | 0 | 53.55 | 289170 | 60.51 | 326754 | 37584 | 0 | 61.01 | 329454 | 40284 | 0
180 | 223 | SOTC181 | Grouting the holes with neat cement slurry of 20mm dia with all required accessories of all materials etc., including cost & Conveyance of all labour Charges etc., complete finished item of work (*As per SSR2021-22 of S.NO:-8) | Nos | 180 | 500 | 152.5424 | 90000 | 0 | 0 | 0 | 90000 |  | 0 |  | 0 | 0 | 0 | 500 | 90000 | 0 | 0 | 0 | 90000 | 0 | 0 | 0 | 90000
181 | 224 | SOTC182 | Pressure grouting the drilled holes with neat cement slurry or with approved grout admixture using pump - excluding cost of drilling holes after fixing nozzles as technical specification approved by the department etc., including cost & Conveyance of all labour charges etc., complete finished item of work | Nos | 630 | 500 | 533.8983 | 315000 | 1084 | 682920 | 367920 | 0 |  | 0 |  | 0 | 0 | 0 | 500 | 315000 | 1084 | 682920 | 367920 | 0 | 1132 | 713160 | 398160 | 0
182 | 234 | SOTC183 | Supply and fabricating,erecting and fixing inposition trusses of approved design with structural steel other than MS. | Kgs | 180 | 6500 | 152.5424 | 1170000 | 6500 | 1170000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 6500 | 1170000 | 6500 | 1170000 | 0 | 0 | 6500 | 1170000 | 0 | 0
183 | 150 | SOTC184 | Supply and fixing of pre painted Galvalume Trapezoidal Profile Roofing with 0.50mm Thickness. | Sqm | 1080 | 65 | 915.2542 | 70200 | 65 | 70200 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 65 | 70200 | 65 | 70200 | 0 | 0 | 65 | 70200 | 0 | 0
184 | 225 | SOTC185 | 4" (101.6mm) multi floor trap with jali - UPVC/SWR | Nos | 270 | 25 | 228.8136 | 6750 | 44 | 11880 | 5130 | 0 |  | 0 |  | 0 | 0 | 0 | 25 | 6750 | 44 | 11880 | 5130 | 0 | 44 | 11880 | 5130 | 0
185 | 151 | SOTC186 | 580mm x 440mm long Orissa pan white glazed Water Closet | Nos | 5400 | 4 | 4576.2712 | 21600 | 4 | 21600 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 4 | 21600 | 4 | 21600 | 0 | 0 | 4 | 21600 | 0 | 0
186 | 152 | SOTC187 | European Water Closet of 1st quality | Nos | 6300 | 9 | 5338.9831 | 56700 | 9 | 56700 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 9 | 56700 | 9 | 56700 | 0 | 0 | 9 | 56700 | 0 | 0
187 | 153 | SOTC188 | Indian make Flat Back Wash Hand Basin 1st quality | Nos | 3600 | 16 | 3050.8475 | 57600 | 15 | 54000 | 0 | 3600 |  | 0 |  | 0 | 0 | 0 | 16 | 57600 | 15 | 54000 | 0 | 3600 | 15 | 54000 | 0 | 3600
188 | 154 | SOTC189 | CP finish brass soap dish | Nos | 1100 | 21 | 932.2034 | 23100 | 21 | 23100 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 21 | 23100 | 21 | 23100 | 0 | 0 | 21 | 23100 | 0 | 0
189 | 155 | SOTC190 | TV shape mirror with plastic frame of size 609.6mm x 457.2mm | Nos | 630 | 25 | 533.8983 | 15750 | 15 | 9450 | 0 | 6300 |  | 0 |  | 0 | 0 | 0 | 25 | 15750 | 15 | 9450 | 0 | 6300 | 15 | 9450 | 0 | 6300
190 | 156 | SOTC191 | 25.4mm dia , 609.6mm long aluminium anodized towel rods | Nos | 540 | 36 | 457.6271 | 19440 | 21 | 11340 | 0 | 8100 |  | 0 |  | 0 | 0 | 0 | 36 | 19440 | 21 | 11340 | 0 | 8100 | 21 | 11340 | 0 | 8100
191 | 156 | SOTC192 | 15 mm brass body CP finish bib tap of not less than 300 grams weight | Nos | 540 | 25 | 457.6271 | 13500 | 14 | 7560 | 0 | 5940 |  | 0 |  | 0 | 0 | 0 | 25 | 13500 | 14 | 7560 | 0 | 5940 | 14 | 7560 | 0 | 5940
192 | 158 | SOTC193 | Self Closing Tap - Push Type | Nos | 720 | 25 | 610.1695 | 18000 | 15 | 10800 | 0 | 7200 |  | 0 |  | 0 | 0 | 0 | 25 | 18000 | 15 | 10800 | 0 | 7200 | 15 | 10800 | 0 | 7200
193 | 159 | SOTC194 | Chromium plated finish brass body quarter turn Bibcock cum Health Faucet | Nos | 3600 | 12 | 3050.8475 | 43200 | 24 | 86400 | 43200 | 0 |  | 0 |  | 0 | 0 | 0 | 12 | 43200 | 24 | 86400 | 43200 | 0 | 24 | 86400 | 43200 | 0
194 | 160 | SOTC195 | Ashirvad/ Ajay/ Astral Flowguard or equivalent CPVC Pipes and Fittings - 15.90mm OD pipe | Rmt | 270 | 55 | 228.8136 | 14850 | 103.08 | 27831.6 | 12981.6 | 0 |  | 0 |  | 0 | 0 | 0 | 55 | 14850 | 103.08 | 27831.6 | 12981.6 | 0 | 108.234 | 29223.18 | 14373.18 | 0
195 | 161 | SOTC196 | Ashirvad/Ajay/Astral Flowguard or equivalent CPVC Pipes and Fittings - 22.20mm OD pipe | Rmt | 360 | 115 | 305.0847 | 41400 | 123.53 | 44470.8 | 3070.8 | 0 |  | 0 |  | 0 | 0 | 0 | 115 | 41400 | 123.53 | 44470.8 | 3070.8 | 0 | 129.7065 | 46694.34 | 5294.34 | 0
196 | 162 | SOTC197 | Ashirvad/ Ajay/ Astral Flowguard or equivalent CPVC Pipes and Fittings -28.60mm OD pipe | Rmt | 450 | 143 | 381.3559 | 64350 | 110 | 49500 | 0 | 14850 |  | 0 |  | 0 | 0 | 0 | 143 | 64350 | 110 | 49500 | 0 | 14850 | 115.5 | 51975 | 0 | 12375
197 | 163 | SOTC198 | Bronze Gate/ Globe valve - 25mm Nominal bore | Nos | 1440 | 15 | 1220.339 | 21600 | 20 | 28800 | 7200 | 0 |  | 0 |  | 0 | 0 | 0 | 15 | 21600 | 20 | 28800 | 7200 | 0 | 20 | 28800 | 7200 | 0
198 | 164 | SOTC199 | SWR PVC pipes (Prince/ Sudhakar/ Kisan/ Supreme or any ISI brand) 4 Kg/Sq.cm. - 75mmdia | Rmt | 450 | 145 | 381.3559 | 65250 | 80 | 36000 | 0 | 29250 |  | 0 |  | 0 | 0 | 0 | 145 | 65250 | 80 | 36000 | 0 | 29250 | 84 | 37800 | 0 | 27450
199 | 165 | SOTC200 | SWR PVC pipes (Prince/ Sudhakar/ Kisan/ Supreme or any ISI brand) 4 Kg/Sq.cm. -110mmdia | Rmt | 540 | 145 | 457.6271 | 78300 | 65 | 35100 | 0 | 43200 |  | 0 |  | 0 | 0 | 0 | 145 | 78300 | 65 | 35100 | 0 | 43200 | 68.25 | 36855 | 0 | 41445
200 | 226 | SOTC201 | Supplying and fixing15 mm nominal size 152.0 mm CP finish iron body shower rose 1st quality including cost and conveyance of all materials, labour charges , overheads & contractors profit for finished item of work in all floors. | Nos | 630 | 5 | 533.8983 | 3150 | 6 | 3780 | 630 | 0 |  | 0 |  | 0 | 0 | 0 | 5 | 3150 | 6 | 3780 | 630 | 0 | 630 | 396900 | 393750 | 0
201 | 166 | SOTC202 | Supply and Fixing of white glazed flat back bowl urinals | Nos | 2700 | 4 | 2288.1356 | 10800 | 0 | 0 | 0 | 10800 |  | 0 |  | 0 | 0 | 0 | 4 | 10800 | 0 | 0 | 0 | 10800 | 0 | 0 | 0 | 10800
202 | 227 | SOTC203 | Supply and fixing of 16mm to 20 mm thick ploished marbles slab partitions of size 4'0"*2'0" | Nos | 3600 | 10 | 3050.8475 | 36000 | 0 | 0 | 0 | 36000 |  | 0 |  | 0 | 0 | 0 | 10 | 36000 | 0 | 0 | 0 | 36000 | 0 | 0 | 0 | 36000
203 | 167 | SOTC204 | 28 mm dia. and 0.90 mm thick Copper Pipe Lines for Main lines | Rmt | 1750 | 700 | 1483.0508 | 1225000 | 832 | 1456000 | 231000 | 0 |  | 0 |  | 0 | 0 | 0 | 700 | 1225000 | 832 | 1456000 | 231000 | 0 | 833 | 1457750 | 232750 | 0
204 | 168 | SOTC205 | 42 mm dia. and 1.20 mm thick Copper Pipe Lines for Main lines | Rmt | 2250 | 200 | 1906.7797 | 450000 | 226 | 508500 | 58500 | 0 |  | 0 |  | 0 | 0 | 0 | 200 | 450000 | 226 | 508500 | 58500 | 0 | 227 | 510750 | 60750 | 0
205 | 169 | SOTC206 | 54 mm dia. and 1.20 mm thick Copper Pipe Lines for Main lines | Rmt | 2950 | 550 | 2500 | 1622500 | 550 | 1622500 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 550 | 1622500 | 550 | 1622500 | 0 | 0 | 564 | 1663800 | 41300 | 0
206 | 170 | SOTC207 | 12 mm dia. and 0.70 mm thick Copper Pipe Lines for distribution lines | Rmt | 650 | 320 | 550.8475 | 208000 | 591 | 384150 | 176150 | 0 |  | 0 |  | 0 | 0 | 0 | 320 | 208000 | 591 | 384150 | 176150 | 0 | 544 | 353600 | 145600 | 0
207 | 171 | SOTC208 | 15 mm dia. and 0.90 mm thick Copper Pipe Lines for distribution lines | Rmt | 950 | 525 | 805.0847 | 498750 | 838 | 796100 | 297350 | 0 |  | 0 |  | 0 | 0 | 0 | 525 | 498750 | 838 | 796100 | 297350 | 0 | 757 | 719150 | 220400 | 0
208 | 172 | SOTC209 | 22 mm dia. and 0.90 mm thick Copper Pipe Lines for distribution lines | Rmt | 1450 | 530 | 1228.8136 | 768500 | 636 | 922200 | 153700 | 0 |  | 0 |  | 0 | 0 | 0 | 530 | 768500 | 636 | 922200 | 153700 | 0 | 595 | 862750 | 94250 | 0
209 | 228 | SOTC210 | 15 mm (1/2") Isolation Valves | Nos | 1500 | 40 | 1271.1864 | 60000 | 35 | 52500 | 0 | 7500 |  | 0 |  | 0 | 0 | 0 | 40 | 60000 | 35 | 52500 | 0 | 7500 | 31 | 46500 | 0 | 13500
210 | 229 | SOTC211 | 22 mm (3/4") Isolation Valves | Nos | 2500 | 15 | 2118.6441 | 37500 | 13 | 32500 | 0 | 5000 |  | 0 |  | 0 | 0 | 0 | 15 | 37500 | 13 | 32500 | 0 | 5000 | 14 | 35000 | 0 | 2500
211 | 173 | SOTC212 | 28 mm Isolation Valves | Nos | 3500 | 3 | 2966.1017 | 10500 | 7 | 24500 | 14000 | 0 | 2 | 7000 | 2 | 7000 | 0 | 0 | 5 | 17500 | 9 | 31500 | 14000 | 0 | 9 | 31500 | 14000 | 0
212 | 174 | SOTC213 | 42 mm Isolation Valves | Nos | 4500 | 2 | 3813.5593 | 9000 | 2 | 9000 | 0 | 0 | 3 | 13500 | 2 | 9000 | 0 | 4500 | 5 | 22500 | 4 | 18000 | 0 | 4500 | 4 | 18000 | 0 | 4500
213 | 175 | SOTC214 | 54 mm Isolation Valves | Nos | 5500 | 2 | 4661.0169 | 11000 | 5 | 27500 | 16500 | 0 | 1 | 5500 | 1 | 5500 | 0 | 0 | 3 | 16500 | 6 | 33000 | 16500 | 0 | 10 | 55000 | 38500 | 0
214 | 176 | SOTC215 | Gas Outlet Points with probes for Oxygen with S Brackets | Nos | 2850 | 189 | 2415.2542 | 538650 | 231 | 658350 | 119700 | 0 |  | 0 |  | 0 | 0 | 0 | 189 | 538650 | 231 | 658350 | 119700 | 0 | 206 | 587100 | 48450 | 0
215 | 177 | SOTC216 | 2 Gas Digital Area Alarm Panels | Nos | 25000 | 2 | 21186.4407 | 50000 | 0 | 0 | 0 | 50000 |  | 0 |  | 0 | 0 | 0 | 2 | 50000 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 50000
216 | 178 | SOTC217 | 3 Gas Digital Area Alarm Panels | Nos | 30000 | 4 | 25423.7288 | 120000 | 5 | 150000 | 30000 | 0 |  | 0 |  | 0 | 0 | 0 | 4 | 120000 | 5 | 150000 | 30000 | 0 | 5 | 150000 | 30000 | 0
217 | 179 | SOTC218 | 5 Gas Digital Area Alarm Panels | Nos | 40000 | 5 | 33898.3051 | 200000 | 0 | 0 | 0 | 200000 | 1 | 40000 | 0 | 0 | 0 | 40000 | 6 | 240000 | 0 | 0 | 0 | 240000 | 0 | 0 | 0 | 240000
218 | 180 | SOTC219 | Master Digital Alarm Panels | Nos | 50000 | 1 | 42372.8814 | 50000 | 1 | 50000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 50000 | 1 | 50000 | 0 | 0 | 1 | 50000 | 0 | 0
219 | 181 | SOTC220 | BPC Flow meter with Humidifier bottle and L adapter | Nos | 2250 | 27 | 1906.7797 | 60750 | 43 | 96750 | 36000 | 0 |  | 0 |  | 0 | 0 | 0 | 27 | 60750 | 43 | 96750 | 36000 | 0 | 43 | 96750 | 36000 | 0
220 | 182 | SOTC221 | L Type Adapter for Oxygen Flow meters | Nos | 1250 | 27 | 1059.322 | 33750 | 27 | 33750 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 27 | 33750 | 27 | 33750 | 0 | 0 | 27 | 33750 | 0 | 0
221 | 183 | SOTC222 | Kit for conversion of Oxygen | Nos | 1650 | 27 | 1398.3051 | 44550 | 18 | 29700 | 0 | 14850 |  | 0 |  | 0 | 0 | 0 | 27 | 44550 | 18 | 29700 | 0 | 14850 | 18 | 29700 | 0 | 14850
222 | 184 | SOTC223 | Suction Jars of 600 ml capacity | Nos | 3450 | 27 | 2923.7288 | 93150 | 37 | 127650 | 34500 | 0 |  | 0 |  | 0 | 0 | 0 | 27 | 93150 | 37 | 127650 | 34500 | 0 | 46 | 158700 | 65550 | 0
223 | 185 | SOTC224 | Adapters for Vacuum | Nos | 750 | 27 | 635.5932 | 20250 | 27 | 20250 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 27 | 20250 | 27 | 20250 | 0 | 0 | 27 | 20250 | 0 | 0
224 | 186 | SOTC225 | Adapters for Air | Nos | 750 | 27 | 635.5932 | 20250 | 27 | 20250 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 27 | 20250 | 27 | 20250 | 0 | 0 | 27 | 20250 | 0 | 0
225 | 187 | SOTC226 | Adapters for Nitrous Oxide | Nos | 750 | 15 | 635.5932 | 11250 | 15 | 11250 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 15 | 11250 | 15 | 11250 | 0 | 0 | 15 | 11250 | 0 | 0
226 | 188 | SOTC227 | Vacuum Tube | Nos | 550 | 27 | 466.1017 | 14850 | 32 | 17600 | 2750 | 0 | 58 | 31900 | 5 | 2750 | 0 | 29150 | 85 | 46750 | 37 | 20350 | 0 | 26400 | 115 | 63250 | 16500 | 0
227 | 189 | SOTC228 | Bed Head wall panel horizontal 1500 mm long single railing | Nos | 35000 | 27 | 29661.0169 | 945000 | 31 | 1085000 | 140000 | 0 |  | 0 |  | 0 | 0 | 0 | 27 | 945000 | 31 | 1085000 | 140000 | 0 | 31 | 1085000 | 140000 | 0
228 | 190 | SOTC229 | Valve box -2 services | Nos | 9500 | 1 | 8050.8475 | 9500 | 0 | 0 | 0 | 9500 |  | 0 |  | 0 | 0 | 0 | 1 | 9500 | 0 | 0 | 0 | 9500 | 0 | 0 | 0 | 9500
229 | 191 | SOTC230 | Valve box -3 services | Nos | 14500 | 3 | 12288.1356 | 43500 | 5 | 72500 | 29000 | 0 |  | 0 |  | 0 | 0 | 0 | 3 | 43500 | 5 | 72500 | 29000 | 0 | 5 | 72500 | 29000 | 0
230 | 192 | SOTC231 | Valve box -6 services | Nos | 22500 | 1 | 19067.7966 | 22500 | 2 | 45000 | 22500 | 0 | 5 | 112500 | 5 | 112500 | 0 | 0 | 6 | 135000 | 7 | 157500 | 22500 | 0 | 6 | 135000 | 0 | 0
231 | 193 | SOTC232 | 4 + 4 size of CO2 manifold System | Job | 40000 | 1 | 33898.3051 | 40000 | 1 | 40000 | 0 | 0 | 1 | 40000 | 1 | 40000 | 0 | 0 | 2 | 80000 | 2 | 80000 | 0 | 0 | 3 | 120000 | 40000 | 0
232 | 194 | SOTC233 | 2 cylinder emergency manifold CO2 | Job | 14500 | 1 | 12288.1356 | 14500 | 1 | 14500 | 0 | 0 | 1 | 14500 | 1 | 14500 | 0 | 0 | 2 | 29000 | 2 | 29000 | 0 | 0 | 2 | 29000 | 0 | 0
233 | 195 | SOTC234 | Fully Automatic CO2 Control System | Job | 185000 | 1 | 156779.661 | 185000 | 1 | 185000 | 0 | 0 | 1 | 185000 | 1 | 185000 | 0 | 0 | 2 | 370000 | 2 | 370000 | 0 | 0 | 2 | 370000 | 0 | 0
234 | 237 | SOTC235 | Aneste Iwata Make TFS 150 C9 Model, Compresso Two stage, Motor 15 HP & 57.18 CFM, 60 CFM Air Dryer with 2000 Ltrs Receiver Twin System (For Air4, Air7) | Job | 1895000 | 1 | 1605932.2034 | 1895000 | 1 | 1895000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 1895000 | 1 | 1895000 | 0 | 0 | 1 | 1895000 | 0 | 0
235 | 196 | SOTC236 | Supporting structure for MGPS lines with Ismb Columns, beams, MS angles, Flats and square rods | Job | 795000 | 1 | 673728.8136 | 795000 | 1 | 795000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 795000 | 1 | 795000 | 0 | 0 | 1 | 795000 | 0 | 0
236 | 197 | SOTC237 | 2x20 Oxygen Main manifold System | Job | 95000 | 1 | 80508.4746 | 95000 | 1 | 95000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 95000 | 1 | 95000 | 0 | 0 | 1 | 95000 | 0 | 0
237 | 198 | SOTC238 | Electrical Control Panel for MGPS | Job | 145000 | 1 | 122881.3559 | 145000 | 1 | 145000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 145000 | 1 | 145000 | 0 | 0 | 1 | 145000 | 0 | 0
238 | 238 | SOTC239 | Vaccum system Ingersoll Rand Make Model 15V x 10 Model with 5 HP Motor with 1000 Liters Reciever, Filters, Electricals, Etc Secretion Trap and Bacteria Filter | Job | 1495000 | 2 | 1266949.1525 | 2990000 | 2 | 2990000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 2 | 2990000 | 2 | 2990000 | 0 | 0 | 2 | 2990000 | 0 | 0
239 | 235 | SOTC240 | Validation By Third Party Agency Charges per Each MOT | Each | 100000 | 4 | 84745.7627 | 400000 | 4 | 400000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 4 | 400000 | 4 | 400000 | 0 | 0 | 9 | 900000 | 500000 | 0
240 | 236 | SOTC241 | Anesthetic Gas Scavenging System (AGSS) | Job | 1213000 | 1 | 1027966.1017 | 1213000 | 1 | 1213000 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 1 | 1213000 | 1 | 1213000 | 0 | 0 | 1 | 1213000 | 0 | 0
242 |  |  | Double Arm Surgical Pendants (Imported) | Nos | 1195000 | 0 |  | 0 | 0 | 0 | 0 | 0 | 6 | 7170000 | 6 | 7170000 | 0 | 0 | 6 | 7170000 | 6 | 7170000 | 0 | 0 | 6 | 7170000 | 0 | 0
[5 empty] | 742795.0127 |  |  | 175773220.8 |  |  |  | #REF! |  | 39441980 |  |  | 535753.7 | #REF! |  | 215215200.8 |  | #REF! |  |  |  | 219738485.591 | 24274756.314 | 19751471.523
[15 empty] | #REF! | [6 empty] | #REF! |  |  | Excess | 4523284.791
Supplemental Items
Sl.No |  |  | Item Description | UOM | Unit Rate (Rs.) |  |  |  | QTY | Amount (Rs.) | [10 empty] | QTY | Amount (Rs.) |  |  | QTY | Amount (Rs.)
1 |  |  | Supply and installation of Under-deck Thermocol insulation sheets of 40 mm thick having more than 30 Kg/m3 density to ceiling by brush application of bituminous adhesive to the sheets and secured with screw along with washer at the centre of the sheet supported with GI wire running diagonally to the sheet of 2mm dia. | Sqm | 1014 |  |  |  | 262.74 | 266418.36 | [10 empty] | 262.74 | 266418.36 |  |  | 262.74 | 266418.36
2 |  |  | Supply and placing of the Design Mix Plain Cement Concrete of M 25 grade corresponding to IS 456 with minimum cement content of 380 kgs per 1 cum of concrete using Concrete Batching Plant with 20mm size graded machine crushed hard granite metal (coarse aggregate - as per IS 383 - 1970 and IS 2386 Part 1 to Part 8) including cost and conveyance of all materials like cement, fine aggregate (sand) coarse aggregate, water etc., to site and sales & other taxes on all materials. | Cum | 11740 |  |  |  | 28.01 | 328837.4 | [10 empty] | 28.01 | 328837.4 |  |  | 28.01 | 328837.4 |  |  | As per SSR
3 |  |  | Supply and Laying of Floor leveller compund (self smoothing mortar) to level the surface, having bulk density not less than 2 Kg/l for a fresh mortor, compressive strength not less than 20 N/mm2, initial setting time not more than 40 minutes and offer a 25 minutes working time, The surface should be walkabe after 30 min of laying. (ICUs) | Sqm | 1460 |  |  |  | 636.23 | 928895.8 | [10 empty] | 636.23 | 928895.8 |  |  | 725.55 | 1059303
4 |  |  | 800 KVA Transformer OLTC for transformers with RTCC: Supply, Transportation, Installation, Testing and Commissioning of 800 KVA TRANSFORMER with all test reports. The Transformer shall be designed and manufactured as per IS:1180 OLTC with level-II with initial filling of oil as per IS 335-1993. 1000 A LT Breaker Kiosk - 01 No.The basic details of the Transformer are as under. Makes: Kirloskar / PETE / Esennar / Voltamp / Crompton / ABB / Schneider. | Nos | 5086347 |  |  |  | 1 | 5086347 | [10 empty] | 1 | 5086347 |  |  | 1 | 5086347
5 |  |  | 4 Gas Digital Alarm Panels | Nos | 35000 |  |  | 21755.5025 | 1 | 35000 | [10 empty] | 1 | 35000 |  |  | 1 | 35000
6 |  |  | 6 Gas Digital Alarm Panels | Nos | 50000 |  |  | 31079.2892 | 7 | 350000 | [10 empty] | 7 | 350000 |  |  | 6 | 300000
7 |  |  | Valve box 4 series | Nos | 18500 |  |  | 11499.337 | 1 | 18500 | [10 empty] | 1 | 18500 |  |  | 1 | 18500
8 |  |  | 4 + 4 O2 manifold system | Job | 40000 |  |  | 24863.4314 | 1 | 40000 | [10 empty] | 1 | 40000 |  |  | 1 | 40000
9 |  |  | Fully automatic O2 control system | Job | 185000 |  |  | 114993.3702 | 1 | 185000 | [10 empty] | 1 | 185000 |  |  | 1 | 185000
10 |  |  | Supply and installation of 50mm thick double skin modular wall Panels made of 0.8 mm thick powder coated GI on both the sides, with 40 plus or minus 2 kg/m3 density PUF as infill, GI profiles all along the periphery, flush on both sides with maximum allowable gap of 3- 4mm filled with food grade silicon sealant and placed on cold rolled galvanised bottom tracks with a recess to provide floor to wall coving flush with the wall panel. This includes all required harware for completion Panels to be covered with a protective film to avoid any damages during transportation and installation | Sqm | 7450 |  |  |  | 297.52 | 2216524 | [10 empty] | 297.52 | 2216524 |  |  | 312.396 | 2327350.2
11 |  |  | Supply and installation of 50mm thick double skin ceiling system made of 0.8 mm thick Powder Coated GI sheets on both sides, 40 plus or minus 2 kg/m3 density PUF as infill, GI profiles all along the periphery, panels flush towards room side with maximum allowable gap of 3-4mm at panel to panel joints filled with silicon sealant. Ceiling panels are suspended from the RCC slab by using concealed AL ceiling grid with tie rod and adjustable turn buckle arrangement etc. This includes all required hardware for completion. Panels to be covered with a protective film to avoid any damages during transportation and installation | Sqm | 7450 |  |  |  | 163.08 | 1214946 | [10 empty] | 163.08 | 1214946 |  |  | 171.234 | 1275693.3
12 |  |  | Providing dadooing to walls with glazed full body ceramic wall tiles of size 800 x 1600 mm with any type of design texture such as marble finish, wooden, bamboo, stone finishes etc., scratch less, stain free and thickness between 6-8 mm 1st quality conforming to IS:13711, IS:13712, IS:13630 Parts 1 to 15 of any colour and finish in all shades and designs with borders as approved by Engineer-in-Charge set over base coat of CM1:5 12 mm thick using screened sand with cement slurry of honey like consistency spread at the rate of 3.30 kgs per sqm and jointing with white cement paste mixed with pigment of matching shade to full depth, including cost of all materials like tiles, cement, sand and water etc., complete for finished item of work. | Sqm | 4665 | [15 empty] | 113.7 | 530410.5 |  |  | 119.385 | 556931.025
13 |  |  | Glass Sliding Doors in TIR-2 & TIR-3 | Nos | 225000 |  |  | 139856.8016 | [12 empty] | 20 | 4500000 |  |  | 2 | 450000
14 |  |  | Monitor Stand beside Bed in ICUs & TIRs | Nos | 6176 | [15 empty] | 31 | 191456 |  |  | 31 | 191456
15 |  |  | Recording in counselling room | Job | 155378 | [15 empty] | 1 | 155378 |  |  | 1 | 155378
16 |  |  | Removal of old Cement Mortor of Wall cladding | Sqm | 18 | [15 empty] | 543.3 | 9779.4 |  |  | 543.3 | 9779.4
17 |  |  | Local Area Network (LAN) System | Job | 460242 | [19 empty] | 1 | 460242
18 |  |  | Supply, Transportation and installation of 20KVA / 312V DC on line UPS system | Nos | 629358 | [19 empty] | 2 | 1258716
19 |  |  | V-Board Partitions on top of false ceiling for partitioning of sterile corridor and non-sterile corridor | Sqm | 3640 | [19 empty] | 16 | 58240
20 |  |  | Manual Hermetically Sealed Sliding Door (1.20mt x 2.10 mt) | Nos | 554600 |  |  | 344731.4762 | [16 empty] | 1 | 554600
21 |  |  | 4 + 4 size of N2O manifold System | Job | 40000 |  |  | 24863.4314 | [16 empty] | 1 | 40000
22 |  |  | 2 cylinder emergency manifold N2O | Job | 14500 |  |  | 9012.9939 | [16 empty] | 1 | 14500
23 |  |  | Fully Automatic N2O Control System | Job | 185000 |  |  | 114993.3702 | [16 empty] | 1 | 185000
14857291.685
19380576.476
21 |  |  | Water Proofing of roof and peripheral walls of south west block, 8th floor, Gandhi Hospital which includes Dismantling of existing screed and lifting of debris to ground floor, Surface preparation and cracks treatment, Providing Angle fillet/taper of 75mm X 75mm with polymer modified mortor in the ratio of cement:sand:admixture (1:1.5:1.5) (Forsoc Nitobond SBR/M-Crete PC Bond @ 10% by weight of cement), Applying 1 coat of Forsoc Nitoproof WB Primer, Application of 2 coats of pitch free based liquid applied single component elastomeric waterproofing membrane (Forsoc Nito proof 600PF/BASF HLM5000), Laying 200 GSM Geotextile Fabric, Laying of 125mm Fiber Reinforced M20 grade protective concrete screed on terrace, Control joints treatment and External walls repair with window Frame-walls joints/Gaps treatment. (Considered 7th floor peripheral walls also for water proofing) | Job | 28493405 | [19 empty] | 1 | 28493405
13 |  |  | Supply and installation of double pass RO system with raw water tank capacity of 5000 ltr plastic tank having 2 nos feed pumps of 1.5 HP with max flow of 9000 ltr/hr including construction of sand filter of dimensions (H=1665 mm, D=325 mm) with filter media as Quartz sand of SS vessel construction and Activated Carbon filter of dimensions (H= 1665mm) with filter media as Activated carbon (IV-600) of SS vessel construction, with 4 nos of spiral wound RO membrane of size 8 inch dia x 1 m length of make G.E OSMONICS (or) HYDRAUNAUTICS, 4 nos UV system with service flow of 1000 ltr/hr (Before Snd filter and after SS tank out-let) for supply for 10 beds in Post ICU, 4 beds in Transplant ICU and 1 for each TIR with drinage system for used water.) | Nos | 5919000 | [15 empty] | 1 | 5919000 |  |  | 1 | 5919000
80
24.1
827.13
1
7
1
1
1
1
1
1
1
470
88.5
61.5
147
534.3
[21 empty] | 0 | 0

## Sheet1
SUPPLEMENTAL ITEM NO : 01 UNDER DECK INSULATION
SUPPLEMENTAL ITEM NO : 03 FLOOR LEVELLING COMPOUND (SELF SMOOTHING MORTOR)
SUPPLEMENTAL ITEM NO : 04 800 KVA TRANSFORMER
SUPPLEMENTAL ITEM NO : 5 4 GAS DIGITAL ALARM PANELS
SUPPLEMENTAL ITEM NO : 06 6 GAS DIGITAL ALARM PANEL
SUPPLEMENTAL ITEM NO : 07 VALVE BOX 4 SERIES
SUPPLEMENTAL ITEM NO : 08 4+4 O2 MANIFOLD SYSTEM
SUPPLEMENTAL ITEM NO : 09 FULLY AUTOMATIC CO2 CONTROL SYSTEM
SUPPLEMENTAL ITEM NO : 10,11 PCGI PANELING (WALL & CEILING)
SUPPLEMENTAL ITEM NO : 12 ENTRANCE WALL DADO
SUPPLEMENTAL ITEM NO : 14 MONITOR STAND
SUPPLEMENTAL ITEM NO : 15 RECORDING IN COUNSELLING ROOM
SUPPLEMENTAL ITEM NO : 17 LAN
SUPPLEMENTAL ITEM NO : 18 20 KVA UPS
SUPPLEMENTAL ITEM NO : 19 V-BOARD PARTITION
SUPPLEMENTAL ITEM NO : 20 MANUAL HERMATICALLY SEALED SLIDING DOOR
RO SYSTEM
WATER PROOFING
SUPPLEMENTAL ITEM NO : 13 GLASS SLIDING DOOR
SUPPLEMENTAL ITEM NO :21 4+4 N2O MANIFOLD SYSTEM
SUPPLEMENTAL ITEM NO : 22 2 CYLINDER N2O MANIFOLD SYSTEM
SUPPLEMENTAL ITEM NO : 23 FULLY AUTOMATIC N2O CONTROL SYSTEM