## Sheet1
TSMSIDC, Hyderabad Division - I & Ranga Reddy Division
Report on IVF Centresas on 31.08.2023
S.No. | Name Of The Work | Reference to AS | Estimate Cost | Name of the Agency | Stage of the work | Remarks
1 | Design, Fabrication, establishing and Commissioning of In - Vitro Fertility Centre (IVFCs) along with allied services on Turnkey basis at MGMH Petlaburj,Hyderabad | G.O.Rt.No: 10 Dt: 22.02.2023 of the HM & FW (C2) Department | RS. 5.50 Crores | Asta Vardaman Consortium | Brick Work Completed, Plastring Work In Progress, electrical tray Fixing And ELV Work In Progress
2 | Design, Fabrication, establishing and Commissioning of In - Vitro Fertility Centre (IVFCs) along with allied services on Turnkey basis at Gandhi Hospital Secunderabad |  |  |  | All Civil Work is Completed, Water Connection Work is in Progress, and Electrical work in Progres, HVAC Ducting Work In Progress.
| Deputy Executive Engineer, | Deputy Executive Engineer, |  |  | Executive Engineer,
| Hyderabad Divison-I | Ranga Reddy Divison |  |  | Hyderabad Division-I & Ranga Reddy Division
| TSMSIDC | TSMSIDC |  |  | TSMSIDC